## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 46694R301 - ITP - LEVEL 05 - Installation of RIS Anchor Points SA312, SA322, SA332, SA342, SA352, SA362 | itp |  |  |  |  | 46694R301 - ITP - LEVEL 05 - Installation of RIS Anchor Points SA312, SA322, SA332, SA342, SA352, SA362
section | INSPECTION TEST PLAN
checkpoint | Access point location(s)
label | CHARACTERISTICS - AS5532 7.3 (h) AS1891.4 3.2.2
label | STAGE/FREQUENCY - Prestart installation work
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Roof profile match
label | CHARACTERISTICS - AS5532 6.3.1.3 (a)
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Roof profile minimum sheet width
label | CHARACTERISTICS - AS5532 6.3.1.3 (iii)
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Roof profile minimum length
label | CHARACTERISTICS - AS5532 6.3.1.3 (v)
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Roof profile minimum fixings and type
label | CHARACTERISTICS - AS5532 6.3.1.3 c
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Position and orientation of anchor point to roof
label | CHARACTERISTICS - AS5532 6.3.1.3 (v)
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Additional pendulum fixing points to roof to allow safe transition and access
label | CHARACTERISTICS - AS1891.4 Table 2.1 restraint technique
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Number of fixing and location of fixing to anchor point
label | CHARACTERISTICS - AS5532 6.3.1.3 ©
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Prevention of corrosion
label | CHARACTERISTICS - AS5532 5.1
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Visual
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Product marking and signage
label | CHARACTERISTICS - AS5532 7.2.3 a, b & c
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Visual
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Instructions for general use
label | CHARACTERISTICS - AS5532 7.1 a, b, c, d, e, f & g
label | STAGE/FREQUENCY - On Completion
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Completion Handover
label | INSTALLER -
label | INSTALL SUPERVISOR - H
label | CLIENT - H
holdpoint | HOLD POINT
section | CHECKLIST - Installation (Refer to Installation Instructions)
checkpoint | Access point location(s)
label | REFERENCE - Systems can be accessed safely by trained persons without the risk of an uncontrolled fall
checkpoint | Roof profile installation
label | REFERENCE - Roof sheet is installed as per manufacturing instructions and guidelines
checkpoint | Minimum roof sheet width and length
label | REFERENCE - 3 x normal lapped roof sheets wide and crossing a minimum of three purlins or battens
checkpoint | Minimum structural requirements
label | REFERENCE - Purlin connected by M12 bolts each end of purlin, purlin details: C/Z15015 minimum size for attachment of anchor
checkpoint | Applications with roof raiser/Top hat section/rack systems for insulation integrity
label | REFERENCE - Custom made anchor with longer M12 thread to enable fixing to the purlin. The use of a RIS spacer is required to bridge the gap from the top of the purlin to the underside of the sheet.
textbox | COMMENTS - Nominate the type of structure utilized for this application:
checkpoint | Penetration of roof is not over sized
label | REFERENCE - Maximum 29mm hole sizes for top fixed anchors and 13mm hole used for anchors fixed with access underneath the roof.
checkpoint | Position and orientation of anchor point to roof
label | REFERENCE - Anchor sits flat and is at 90 degrees with the roof. Eye bolt is orientated towards the intended access point.
checkpoint | Anchor points to roof to prevent lateral swing fall are installed or mitigation agreed
label | REFERENCE - The distance to the next anchor is less than the length to the closest edge, unless mitigated by other means.
checkpoint | Anchor at entry point with a stainless steel Strop
label | REFERENCE - Anchor strop must be positioned to enable user to reach and connect to.
label | ○ Strop is marked and rated to 15kN.
label | ○ Mallion/Quicklink connection to roof anchor point is secured and mechanically tightened or chemically set with loctite.
label | COMMENTS - Not applicable as anchor is not within the Fall Zone.
bool | Tick if is not applicable
checkpoint | Corrosion prevention
label | REFERENCE - Dissimilar metals are separated by EPDM barrier or sealant.
checkpoint | Water proofing
label | REFERENCE - Anchor sealed and inspected for water tight fit.
checkpoint | Site clean up and picture evidence if handover is not possible
label | REFERENCE - Site has been cleared of swarf or other debris installation inspection completed and witnessed by the customers representative. Where a client cannot sign for handover, clear high resolution pictures have been taken of each anchor point.
checkpoint | Anchor systems installation completion action
label | REFERENCE - Anchor fit for use sticker/tag filled in and attached to the anchor point, mark with confirmed rating. Entry point signage updated and installed.
section | Project Completion
checkpoint | Handover operating and systems documentation issued
checkpoint | I have carried out all necessary inspections and verify that the above items/activities conform to the contract specification/documents
textbox | Name:
date | Date:
holdpoint | Signature:
checklist | 46694R301 - ITP - LEVEL 29 - VERTICAL FACE STEEL BEAM - Installation of RIS Anchor Points SA312, SA322, SA332, SA342, SA352, SA362 | itp |  |  |  |  | 46694R301 - ITP - LEVEL 29 - VERTICAL FACE STEEL BEAM - Installation of RIS Anchor Points SA312, SA322, SA332, SA342, SA352, SA362
section | INSPECTION TEST PLAN
checkpoint | Access point location(s)
label | CHARACTERISTICS - AS5532 7.3 (h) AS1891.4 3.2.2
label | STAGE/FREQUENCY - Prestart installation work
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Roof profile match
label | CHARACTERISTICS - AS5532 6.3.1.3 (a)
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Roof profile minimum sheet width
label | CHARACTERISTICS - AS5532 6.3.1.3 (iii)
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Roof profile minimum length
label | CHARACTERISTICS - AS5532 6.3.1.3 (v)
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Roof profile minimum fixings and type
label | CHARACTERISTICS - AS5532 6.3.1.3 c
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Position and orientation of anchor point to roof
label | CHARACTERISTICS - AS5532 6.3.1.3 (v)
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Additional pendulum fixing points to roof to allow safe transition and access
label | CHARACTERISTICS - AS1891.4 Table 2.1 restraint technique
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Number of fixing and location of fixing to anchor point
label | CHARACTERISTICS - AS5532 6.3.1.3 ©
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Prevention of corrosion
label | CHARACTERISTICS - AS5532 5.1
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Visual
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Product marking and signage
label | CHARACTERISTICS - AS5532 7.2.3 a, b & c
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Visual
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Instructions for general use
label | CHARACTERISTICS - AS5532 7.1 a, b, c, d, e, f & g
label | STAGE/FREQUENCY - On Completion
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Completion Handover
label | INSTALLER -
label | INSTALL SUPERVISOR - H
label | CLIENT - H
holdpoint | HOLD POINT
section | CHECKLIST - Installation (Refer to Installation Instructions)
checkpoint | Access point location(s)
label | REFERENCE - Systems can be accessed safely by trained persons without the risk of an uncontrolled fall
checkpoint | Roof profile installation
label | REFERENCE - Roof sheet is installed as per manufacturing instructions and guidelines
checkpoint | Minimum roof sheet width and length
label | REFERENCE - 3 x normal lapped roof sheets wide and crossing a minimum of three purlins or battens
checkpoint | Minimum structural requirements
label | REFERENCE - Purlin connected by M12 bolts each end of purlin, purlin details: C/Z15015 minimum size for attachment of anchor
checkpoint | Applications with roof raiser/Top hat section/rack systems for insulation integrity
label | REFERENCE - Custom made anchor with longer M12 thread to enable fixing to the purlin. The use of a RIS spacer is required to bridge the gap from the top of the purlin to the underside of the sheet.
textbox | COMMENTS - Nominate the type of structure utilized for this application:
checkpoint | Penetration of roof is not over sized
label | REFERENCE - Maximum 29mm hole sizes for top fixed anchors and 13mm hole used for anchors fixed with access underneath the roof.
checkpoint | Position and orientation of anchor point to roof
label | REFERENCE - Anchor sits flat and is at 90 degrees with the roof. Eye bolt is orientated towards the intended access point.
checkpoint | Anchor points to roof to prevent lateral swing fall are installed or mitigation agreed
label | REFERENCE - The distance to the next anchor is less than the length to the closest edge, unless mitigated by other means.
checkpoint | Anchor at entry point with a stainless steel Strop
label | REFERENCE - Anchor strop must be positioned to enable user to reach and connect to.
label | ○ Strop is marked and rated to 15kN.
label | ○ Mallion/Quicklink connection to roof anchor point is secured and mechanically tightened or chemically set with loctite.
label | COMMENTS - Not applicable as anchor is not within the Fall Zone.
bool | Tick if is not applicable
checkpoint | Corrosion prevention
label | REFERENCE - Dissimilar metals are separated by EPDM barrier or sealant.
checkpoint | Water proofing
label | REFERENCE - Anchor sealed and inspected for water tight fit.
checkpoint | Site clean up and picture evidence if handover is not possible
label | REFERENCE - Site has been cleared of swarf or other debris installation inspection completed and witnessed by the customers representative. Where a client cannot sign for handover, clear high resolution pictures have been taken of each anchor point.
checkpoint | Anchor systems installation completion action
label | REFERENCE - Anchor fit for use sticker/tag filled in and attached to the anchor point, mark with confirmed rating. Entry point signage updated and installed.
section | Project Completion
checkpoint | Handover operating and systems documentation issued
checkpoint | I have carried out all necessary inspections and verify that the above items/activities conform to the contract specification/documents
textbox | Name:
date | Date:
holdpoint | Signature: