## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 46694R302 - ITP - LEVEL 05 - Installation of RIS Anchor Points SA412 | itp |  |  |  |  | 46694R302 - ITP - LEVEL 05 - Installation of RIS Anchor Points SA412
section | INSPECTION TEST PLAN
checkpoint | Access point location (s)
label | CHARACTERISTICS - AS5532 7.3 (h) AS1891.4 3.2.2
label | STAGE/FREQUENCY - Prestart installation work
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Position and orientation of anchor point to roof/structure
label | CHARACTERISTICS - AS5532 6.3.1.3 (v), AS1891.4 - 3.1.2 (g) Single point anchorages suitable for direct connection of personal fall-arrest
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Additional pendulum fixing points to roof to allow safe transition and access
label | CHARACTERISTICS - AS1891.4 Table 2.1 restraint technique AS4488 5.3 a
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Load Testing
label | CHARACTERISTICS - AS1891.4 - 3.1.2 (g) Single point anchorages suitable for direct connection of personal fall-arrest AS5532 7.3 (f)
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Load Test
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Prevention of corrosion
label | CHARACTERISTICS - AS5532 5.1
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Visual
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Product marking and signage
label | CHARACTERISTICS - AS5532 7.2.3 a, b & c
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Visual
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Instructions for general use
label | CHARACTERISTICS - AS5532 7.1 a, b, c, d, e, f & g
label | STAGE/FREQUENCY - On Completion
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Completion Handover
label | INSTALLER -
label | INSTALL SUPERVISOR - H
label | CLIENT - H
holdpoint | HOLD POINT
section | CHECKLIST - Installation (Refer to Installation Instructions)
checkpoint | Access point location(s)
label | REFERENCE - Systems can be accessed safely by trained persons without the risk of an uncontrolled fall
checkpoint | Position and orientation of anchor point to roof
label | REFERENCE - Eye bolt to run 90 degrees to the primary work area. Friction anchorages shall be placed so that the shear load and the pull angle must not exceed 20° to the surface in which the bolt is installed.
checkpoint | Mechanical anchor fitting per anchor/bolt
label | REFERENCE - Drill bit for 12mm thread = 18mm (complete the hole that you start to the correct depth of 131 mm and ensure that the hole is cleaned appropriately)
label | ○ For cleaning holes, torque wrench tensioned EXACTLY 80Nm Minimum edge distance: 105mm
label | ○ Minimum spacing distance: 265mm Minimum concrete thickness: 185mm
checkpoint | Anchor points to roof to prevent lateral swing fall are installed or mitigation agreed
label | REFERENCE - The distance to the next anchor is less than the length to the closest edge, unless mitigated by other means
checkpoint | Load test each anchor with calibrated pull tester. Last calibration date must not exceed 12 months
label | REFERENCE - Each individual friction anchor is tested to 50% of the required design load
label | ○ 12kn tested to 6kN
label | ○ 15kN tested to 7.5kN
label | ○ 21kN tested to 10.5kN
textbox | COMMENTS - Nominate the kN rating that you tested each anchor to:
checkpoint | Anchor at entry point with a stainless steel Strop
label | REFERENCE - Anchor strop must be positioned to enable user to reach and connect to.
label | ○ Strop is marked and rated to 15kN.
label | ○ Mallion/Quicklink connection to roof anchor point is secured and mechanically tightened or chemically set with loctite.
label | COMMENTS - Not applicable as anchor is not within the Fall Zone.
bool | Tick if is not applicable
checkpoint | Corrosion prevention
label | REFERENCE - Dissimilar metals are separated by EPDM barrier or sealant
checkpoint | Site clean up and picture evidence if handover is not possible
label | REFERENCE - Site has been cleared of swarf or other debris installation inspection completed and witnessed by the customers representative. Where a client cannot sign for handover, clear high resolution pictures have been taken of each anchor point.
checkpoint | Anchor systems installation completion action
label | REFERENCE - Anchor fit for use sticker/tag filled in and attached to the anchor point, mark with confirmed rating. Entry point signage updated and installed.
section | Project Completion
checkpoint | Handover operating and systems documentation issued
checkpoint | I have carried out all necessary inspections and verify that the above items/activities conform to the contract specification/documents
textbox | Name:
date | Date:
holdpoint | Signature:
checklist | 46694R301 - ITP - LEVEL 28 - Installation of RIS Anchor Points SA412 | itp |  |  |  |  | 46694R301 - ITP - LEVEL 28 - Installation of RIS Anchor Points SA412
section | INSPECTION TEST PLAN
checkpoint | Access point location (s)
label | CHARACTERISTICS - AS5532 7.3 (h) AS1891.4 3.2.2
label | STAGE/FREQUENCY - Prestart installation work
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Position and orientation of anchor point to roof/structure
label | CHARACTERISTICS - AS5532 6.3.1.3 (v), AS1891.4 - 3.1.2 (g) Single point anchorages suitable for direct connection of personal fall-arrest
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Additional pendulum fixing points to roof to allow safe transition and access
label | CHARACTERISTICS - AS1891.4 Table 2.1 restraint technique AS4488 5.3 a
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Load Testing
label | CHARACTERISTICS - AS1891.4 - 3.1.2 (g) Single point anchorages suitable for direct connection of personal fall-arrest AS5532 7.3 (f)
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Load Test
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Prevention of corrosion
label | CHARACTERISTICS - AS5532 5.1
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Visual
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Product marking and signage
label | CHARACTERISTICS - AS5532 7.2.3 a, b & c
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Visual
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Instructions for general use
label | CHARACTERISTICS - AS5532 7.1 a, b, c, d, e, f & g
label | STAGE/FREQUENCY - On Completion
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Completion Handover
label | INSTALLER -
label | INSTALL SUPERVISOR - H
label | CLIENT - H
holdpoint | HOLD POINT
section | CHECKLIST - Installation (Refer to Installation Instructions)
checkpoint | Access point location(s)
label | REFERENCE - Systems can be accessed safely by trained persons without the risk of an uncontrolled fall
checkpoint | Position and orientation of anchor point to roof
label | REFERENCE - Eye bolt to run 90 degrees to the primary work area. Friction anchorages shall be placed so that the shear load and the pull angle must not exceed 20° to the surface in which the bolt is installed.
checkpoint | Mechanical anchor fitting per anchor/bolt
label | REFERENCE - Drill bit for 12mm thread = 18mm (complete the hole that you start to the correct depth of 131 mm and ensure that the hole is cleaned appropriately)
label | ○ For cleaning holes, torque wrench tensioned EXACTLY 80Nm Minimum edge distance: 105mm
label | ○ Minimum spacing distance: 265mm Minimum concrete thickness: 185mm
checkpoint | Anchor points to roof to prevent lateral swing fall are installed or mitigation agreed
label | REFERENCE - The distance to the next anchor is less than the length to the closest edge, unless mitigated by other means
checkpoint | Load test each anchor with calibrated pull tester. Last calibration date must not exceed 12 months
label | REFERENCE - Each individual friction anchor is tested to 50% of the required design load
label | ○ 12kn tested to 6kN
label | ○ 15kN tested to 7.5kN
label | ○ 21kN tested to 10.5kN
textbox | COMMENTS - Nominate the kN rating that you tested each anchor to:
checkpoint | Anchor at entry point with a stainless steel Strop
label | REFERENCE - Anchor strop must be positioned to enable user to reach and connect to.
label | ○ Strop is marked and rated to 15kN.
label | ○ Mallion/Quicklink connection to roof anchor point is secured and mechanically tightened or chemically set with loctite.
label | COMMENTS - Not applicable as anchor is not within the Fall Zone.
bool | Tick if is not applicable
checkpoint | Corrosion prevention
label | REFERENCE - Dissimilar metals are separated by EPDM barrier or sealant
checkpoint | Site clean up and picture evidence if handover is not possible
label | REFERENCE - Site has been cleared of swarf or other debris installation inspection completed and witnessed by the customers representative. Where a client cannot sign for handover, clear high resolution pictures have been taken of each anchor point.
checkpoint | Anchor systems installation completion action
label | REFERENCE - Anchor fit for use sticker/tag filled in and attached to the anchor point, mark with confirmed rating. Entry point signage updated and installed.
section | Project Completion
checkpoint | Handover operating and systems documentation issued
checkpoint | I have carried out all necessary inspections and verify that the above items/activities conform to the contract specification/documents
textbox | Name:
date | Date:
holdpoint | Signature:
checklist | 46694R301 - ITP - LEVEL 29 - VERTICAL FACE OF PARAPET - Installation of RIS Anchor Points SA412 | itp |  |  |  |  | 46694R301 - ITP - LEVEL 29 - VERTICAL FACE OF PARAPET - Installation of RIS Anchor Points SA412
section | INSPECTION TEST PLAN
checkpoint | Access point location (s)
label | CHARACTERISTICS - AS5532 7.3 (h) AS1891.4 3.2.2
label | STAGE/FREQUENCY - Prestart installation work
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Position and orientation of anchor point to roof/structure
label | CHARACTERISTICS - AS5532 6.3.1.3 (v), AS1891.4 - 3.1.2 (g) Single point anchorages suitable for direct connection of personal fall-arrest
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Additional pendulum fixing points to roof to allow safe transition and access
label | CHARACTERISTICS - AS1891.4 Table 2.1 restraint technique AS4488 5.3 a
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Load Testing
label | CHARACTERISTICS - AS1891.4 - 3.1.2 (g) Single point anchorages suitable for direct connection of personal fall-arrest AS5532 7.3 (f)
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Load Test
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Prevention of corrosion
label | CHARACTERISTICS - AS5532 5.1
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Visual
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Product marking and signage
label | CHARACTERISTICS - AS5532 7.2.3 a, b & c
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Visual
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Instructions for general use
label | CHARACTERISTICS - AS5532 7.1 a, b, c, d, e, f & g
label | STAGE/FREQUENCY - On Completion
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Completion Handover
label | INSTALLER -
label | INSTALL SUPERVISOR - H
label | CLIENT - H
holdpoint | HOLD POINT
section | CHECKLIST - Installation (Refer to Installation Instructions)
checkpoint | Access point location(s)
label | REFERENCE - Systems can be accessed safely by trained persons without the risk of an uncontrolled fall
checkpoint | Position and orientation of anchor point to roof
label | REFERENCE - Eye bolt to run 90 degrees to the primary work area. Friction anchorages shall be placed so that the shear load and the pull angle must not exceed 20° to the surface in which the bolt is installed.
checkpoint | Mechanical anchor fitting per anchor/bolt
label | REFERENCE - Drill bit for 12mm thread = 18mm (complete the hole that you start to the correct depth of 131 mm and ensure that the hole is cleaned appropriately)
label | ○ For cleaning holes, torque wrench tensioned EXACTLY 80Nm Minimum edge distance: 105mm
label | ○ Minimum spacing distance: 265mm Minimum concrete thickness: 185mm
checkpoint | Anchor points to roof to prevent lateral swing fall are installed or mitigation agreed
label | REFERENCE - The distance to the next anchor is less than the length to the closest edge, unless mitigated by other means
checkpoint | Load test each anchor with calibrated pull tester. Last calibration date must not exceed 12 months
label | REFERENCE - Each individual friction anchor is tested to 50% of the required design load
label | ○ 12kn tested to 6kN
label | ○ 15kN tested to 7.5kN
label | ○ 21kN tested to 10.5kN
textbox | COMMENTS - Nominate the kN rating that you tested each anchor to:
checkpoint | Anchor at entry point with a stainless steel Strop
label | REFERENCE - Anchor strop must be positioned to enable user to reach and connect to.
label | ○ Strop is marked and rated to 15kN.
label | ○ Mallion/Quicklink connection to roof anchor point is secured and mechanically tightened or chemically set with loctite.
label | COMMENTS - Not applicable as anchor is not within the Fall Zone.
bool | Tick if is not applicable
checkpoint | Corrosion prevention
label | REFERENCE - Dissimilar metals are separated by EPDM barrier or sealant
checkpoint | Site clean up and picture evidence if handover is not possible
label | REFERENCE - Site has been cleared of swarf or other debris installation inspection completed and witnessed by the customers representative. Where a client cannot sign for handover, clear high resolution pictures have been taken of each anchor point.
checkpoint | Anchor systems installation completion action
label | REFERENCE - Anchor fit for use sticker/tag filled in and attached to the anchor point, mark with confirmed rating. Entry point signage updated and installed.
section | Project Completion
checkpoint | Handover operating and systems documentation issued
checkpoint | I have carried out all necessary inspections and verify that the above items/activities conform to the contract specification/documents
textbox | Name:
date | Date:
holdpoint | Signature:
checklist | 46694R303 - ITP - LEVEL 29 - Installation of RIS Anchor Points SA412 | itp |  |  |  |  | 46694R303 - ITP - LEVEL 29 - Installation of RIS Anchor Points SA412
section | INSPECTION TEST PLAN
checkpoint | Access point location (s)
label | CHARACTERISTICS - AS5532 7.3 (h) AS1891.4 3.2.2
label | STAGE/FREQUENCY - Prestart installation work
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Position and orientation of anchor point to roof/structure
label | CHARACTERISTICS - AS5532 6.3.1.3 (v), AS1891.4 - 3.1.2 (g) Single point anchorages suitable for direct connection of personal fall-arrest
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Additional pendulum fixing points to roof to allow safe transition and access
label | CHARACTERISTICS - AS1891.4 Table 2.1 restraint technique AS4488 5.3 a
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Load Testing
label | CHARACTERISTICS - AS1891.4 - 3.1.2 (g) Single point anchorages suitable for direct connection of personal fall-arrest AS5532 7.3 (f)
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Load Test
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Prevention of corrosion
label | CHARACTERISTICS - AS5532 5.1
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Visual
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Product marking and signage
label | CHARACTERISTICS - AS5532 7.2.3 a, b & c
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Visual
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Instructions for general use
label | CHARACTERISTICS - AS5532 7.1 a, b, c, d, e, f & g
label | STAGE/FREQUENCY - On Completion
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Completion Handover
label | INSTALLER -
label | INSTALL SUPERVISOR - H
label | CLIENT - H
holdpoint | HOLD POINT
section | CHECKLIST - Installation (Refer to Installation Instructions)
checkpoint | Access point location(s)
label | REFERENCE - Systems can be accessed safely by trained persons without the risk of an uncontrolled fall
checkpoint | Position and orientation of anchor point to roof
label | REFERENCE - Eye bolt to run 90 degrees to the primary work area. Friction anchorages shall be placed so that the shear load and the pull angle must not exceed 20° to the surface in which the bolt is installed.
checkpoint | Mechanical anchor fitting per anchor/bolt
label | REFERENCE - Drill bit for 12mm thread = 18mm (complete the hole that you start to the correct depth of 131 mm and ensure that the hole is cleaned appropriately)
label | ○ For cleaning holes, torque wrench tensioned EXACTLY 80Nm Minimum edge distance: 105mm
label | ○ Minimum spacing distance: 265mm Minimum concrete thickness: 185mm
checkpoint | Anchor points to roof to prevent lateral swing fall are installed or mitigation agreed
label | REFERENCE - The distance to the next anchor is less than the length to the closest edge, unless mitigated by other means
checkpoint | Load test each anchor with calibrated pull tester. Last calibration date must not exceed 12 months
label | REFERENCE - Each individual friction anchor is tested to 50% of the required design load
label | ○ 12kn tested to 6kN
label | ○ 15kN tested to 7.5kN
label | ○ 21kN tested to 10.5kN
textbox | COMMENTS - Nominate the kN rating that you tested each anchor to:
checkpoint | Anchor at entry point with a stainless steel Strop
label | REFERENCE - Anchor strop must be positioned to enable user to reach and connect to.
label | ○ Strop is marked and rated to 15kN.
label | ○ Mallion/Quicklink connection to roof anchor point is secured and mechanically tightened or chemically set with loctite.
label | COMMENTS - Not applicable as anchor is not within the Fall Zone.
bool | Tick if is not applicable
checkpoint | Corrosion prevention
label | REFERENCE - Dissimilar metals are separated by EPDM barrier or sealant
checkpoint | Site clean up and picture evidence if handover is not possible
label | REFERENCE - Site has been cleared of swarf or other debris installation inspection completed and witnessed by the customers representative. Where a client cannot sign for handover, clear high resolution pictures have been taken of each anchor point.
checkpoint | Anchor systems installation completion action
label | REFERENCE - Anchor fit for use sticker/tag filled in and attached to the anchor point, mark with confirmed rating. Entry point signage updated and installed.
section | Project Completion
checkpoint | Handover operating and systems documentation issued
checkpoint | I have carried out all necessary inspections and verify that the above items/activities conform to the contract specification/documents
textbox | Name:
date | Date:
holdpoint | Signature: