## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 46694R301 - ITP - LEVEL 01 - Installation of RIS HL200 Lifelines | itp |  |  |  |  | 46694R301 - ITP - LEVEL 01 - Installation of RIS HL200 Lifelines
section | INSPECTION TEST PLAN
checkpoint | Access point location(s)
label | CHARACTERISTICS - AS1891.2 1.4 System Acceptance Criteria a. AS5532 7.3 (h) AS1891.4 3.2.2. RIS HL200 Installation requirement
label | STAGE/FREQUENCY - Prestart installation work
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Manufacturer recommendation
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Structure location compatibility match
label | CHARACTERISTICS - AS1891.2 1.4 System Acceptance Criteria a. RIS HL200 Installation requirement
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Position of line to fall zone
label | CHARACTERISTICS - AS1891.2 1.4 System Acceptance Criteria a. RIS HL200 Installation requirement
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Fall clearance
label | CHARACTERISTICS - AS1891.2 1.4 System Acceptance Criteria a. 1891.4:2009 Section 7
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Lifeline connections and swaging
label | CHARACTERISTICS - AS1891.2 1.4 System Acceptance Criteria a. RIS HL200 Installation requirement
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Maximum loading angle
label | CHARACTERISTICS - AS1891.2 1.4 System Acceptance Criteria a. AS1891.2.5.3 Drilled-in anchorages. RIS HL200 Installation requirement
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Additional pendulum fixing points to roof allow safe transition and access
label | CHARACTERISTICS - AS1891.2 1.4 System Acceptance Criteria a. RIS HL200 Installation requirement
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Prevention of corrosion
label | CHARACTERISTICS - AS1891.2 1.4 System Acceptance Criteria a. RIS HL200 Installation requirement
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Product marking and signage
label | CHARACTERISTICS - AS1891.2 1.4 System Acceptance Criteria a. RIS HL200 Installation requirement
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Instructions for general use
label | CHARACTERISTICS - AS1891.2 1.4 System Acceptance Criteria a. AS/NZS 1891.4.2009 Section (9). RIS HL200 Installation requirement
label | STAGE/FREQUENCY - On Completion
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Completion Handover
label | INSTALLER -
label | INSTALL SUPERVISOR - H
label | CLIENT - H
holdpoint | HOLD POINT
section | CHECKLIST - Installation (Refer to Installation Instructions)
checkpoint | Access point location(s)
label | REFERENCE - Systems can be accessed safely by trained persons without the risk of an uncontrolled fall.
checkpoint | Structure location compatibility match
label | REFERENCE - Purlin connected by minimum M12 bolts each end of purlin. Purlin details: C/Z15015 minimum size for attachment of anchor.
checkpoint | Lifeline length, Inline connection and swaging
label | REFERENCE - 8mm cable with minimum static line length of 4m. End anchors installed with a minimum 2 x M12 bolts supporting the end termination Jaw Jaw or fork swage or quicklinks if applicable. Intermediate anchors have a minimum of 1 x M12 bolt supporting the static line to the structure.
label | ○ Each swage termination has 5 crimps equally spaced over 85mm.
label | ○ Joiner requires 10 crimps with 5 crimps either side of the central point.
label | ○ Intermediate corners to be single crimped to form radius.
checkpoint | Terminations position, Connections, Tensioning and Spans
label | REFERENCE - End anchor static line assemblies that terminate closer than 2m to a fall zone have an inline stopper fitted a minimum of 2m from fall zone.
label | ○ Maximum anchor to anchor span without written exemption (from an RIS manager or engineer) is 8m.
label | ○ Systems under 20m include an inline shock absorbing assembly.
label | ○ Locking pins are installed and split pins/rings secured on the tensioner and the fork ends.
checkpoint | Steel fixed configuration
label | REFERENCE - M12 stainless steel bolts with nyloc nuts and washers. Drill bit for 12mm thread = 14mm hole, torque wrench tensioned to 80Nm. Minimum edge distance on structural steel is 25mm
textbox | COMMENTS - Nominate the type of structure utilized for this application:
checkpoint | Applications with roof raiser/Top hat section/rack systems for insulation integrity
label | REFERENCE - Custom made anchor with longer M12 thread to enable fixing to the purlin. The use of a RIS spacer is required to bridge the gap from the top of the purlin to the underside of the sheet.
checkpoint | Penetration of roof is not over sized
label | REFERENCE - Maximum 29mm hole sizes for top fixed anchors.
checkpoint | Maximum loading angle and corner radiuses
label | REFERENCE - 20 degrees from the structural surface. 500mm radius.
checkpoint | Anchor points to structure to prevent lateral swing fall are installed or mitigation agreed
label | REFERENCE - Corners and changes of shape have additional pendulum anchor points installed to allow access and prevent swing fall.
checkpoint | Anchor at entry point with a stainless steel Strop
label | REFERENCE - Anchor strop must be positioned to enable user to reach and connect to.
label | ○ Strop is marked and rated to 15kN.
label | ○ Mallion/Quicklink connection to roof anchor point is secured and mechanically tightened or chemically set with loctite.
label | COMMENTS - Not applicable as anchor is not within the Fall Zone.
bool | Tick if is not applicable
checkpoint | Prevention of corrosion
label | REFERENCE - Dissimilar metals are separated by foam, tape, EPDM barrier or sealant.
checkpoint | Site clean up and picture evidence if handover is not possible
label | REFERENCE - Site has been cleared of swarf or other debris installation inspection completed and witnessed by the customers representative. Where a client cannot sign for handover, clear high resolution pictures have been taken of the installed product.
checkpoint | Systems installation completion action
label | REFERENCE - Fit for use sticker/tag filled in and attached to each static line anchor point, mark with confirmed rating and install dates. Entry point signage updated and installed.
section | Project Completion
checkpoint | Handover operating and systems documentation issued and maximum lanyard length nominated in manual which prevents access to a fall arrest event.
checkpoint | I have carried out all necessary inspections and verify that the above items/activities conform to the contract specification/documents
textbox | Name:
date | Date:
holdpoint | Signature:
checklist | 46694R301 - ITP - LEVEL 04 - Installation of RIS HL200 Lifelines | itp |  |  |  |  | 46694R301 - ITP - LEVEL 04 - Installation of RIS HL200 Lifelines
section | INSPECTION TEST PLAN
checkpoint | Access point location(s)
label | CHARACTERISTICS - AS1891.2 1.4 System Acceptance Criteria a. AS5532 7.3 (h) AS1891.4 3.2.2. RIS HL200 Installation requirement
label | STAGE/FREQUENCY - Prestart installation work
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Manufacturer recommendation
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Structure location compatibility match
label | CHARACTERISTICS - AS1891.2 1.4 System Acceptance Criteria a. RIS HL200 Installation requirement
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Position of line to fall zone
label | CHARACTERISTICS - AS1891.2 1.4 System Acceptance Criteria a. RIS HL200 Installation requirement
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Fall clearance
label | CHARACTERISTICS - AS1891.2 1.4 System Acceptance Criteria a. 1891.4:2009 Section 7
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Lifeline connections and swaging
label | CHARACTERISTICS - AS1891.2 1.4 System Acceptance Criteria a. RIS HL200 Installation requirement
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Maximum loading angle
label | CHARACTERISTICS - AS1891.2 1.4 System Acceptance Criteria a. AS1891.2.5.3 Drilled-in anchorages. RIS HL200 Installation requirement
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Additional pendulum fixing points to roof allow safe transition and access
label | CHARACTERISTICS - AS1891.2 1.4 System Acceptance Criteria a. RIS HL200 Installation requirement
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Prevention of corrosion
label | CHARACTERISTICS - AS1891.2 1.4 System Acceptance Criteria a. RIS HL200 Installation requirement
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Product marking and signage
label | CHARACTERISTICS - AS1891.2 1.4 System Acceptance Criteria a. RIS HL200 Installation requirement
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Instructions for general use
label | CHARACTERISTICS - AS1891.2 1.4 System Acceptance Criteria a. AS/NZS 1891.4.2009 Section (9). RIS HL200 Installation requirement
label | STAGE/FREQUENCY - On Completion
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Completion Handover
label | INSTALLER -
label | INSTALL SUPERVISOR - H
label | CLIENT - H
holdpoint | HOLD POINT
section | CHECKLIST - Installation (Refer to Installation Instructions)
checkpoint | Access point location(s)
label | REFERENCE - Systems can be accessed safely by trained persons without the risk of an uncontrolled fall.
checkpoint | Structure location compatibility match
label | REFERENCE - Purlin connected by minimum M12 bolts each end of purlin. Purlin details: C/Z15015 minimum size for attachment of anchor.
checkpoint | Lifeline length, Inline connection and swaging
label | REFERENCE - 8mm cable with minimum static line length of 4m. End anchors installed with a minimum 2 x M12 bolts supporting the end termination Jaw Jaw or fork swage or quicklinks if applicable. Intermediate anchors have a minimum of 1 x M12 bolt supporting the static line to the structure.
label | ○ Each swage termination has 5 crimps equally spaced over 85mm.
label | ○ Joiner requires 10 crimps with 5 crimps either side of the central point.
label | ○ Intermediate corners to be single crimped to form radius.
checkpoint | Terminations position, Connections, Tensioning and Spans
label | REFERENCE - End anchor static line assemblies that terminate closer than 2m to a fall zone have an inline stopper fitted a minimum of 2m from fall zone.
label | ○ Maximum anchor to anchor span without written exemption (from an RIS manager or engineer) is 8m.
label | ○ Systems under 20m include an inline shock absorbing assembly.
label | ○ Locking pins are installed and split pins/rings secured on the tensioner and the fork ends.
checkpoint | Steel fixed configuration
label | REFERENCE - M12 stainless steel bolts with nyloc nuts and washers. Drill bit for 12mm thread = 14mm hole, torque wrench tensioned to 80Nm. Minimum edge distance on structural steel is 25mm
textbox | COMMENTS - Nominate the type of structure utilized for this application:
checkpoint | Applications with roof raiser/Top hat section/rack systems for insulation integrity
label | REFERENCE - Custom made anchor with longer M12 thread to enable fixing to the purlin. The use of a RIS spacer is required to bridge the gap from the top of the purlin to the underside of the sheet.
checkpoint | Penetration of roof is not over sized
label | REFERENCE - Maximum 29mm hole sizes for top fixed anchors.
checkpoint | Maximum loading angle and corner radiuses
label | REFERENCE - 20 degrees from the structural surface. 500mm radius.
checkpoint | Anchor points to structure to prevent lateral swing fall are installed or mitigation agreed
label | REFERENCE - Corners and changes of shape have additional pendulum anchor points installed to allow access and prevent swing fall.
checkpoint | Anchor at entry point with a stainless steel Strop
label | REFERENCE - Anchor strop must be positioned to enable user to reach and connect to.
label | ○ Strop is marked and rated to 15kN.
label | ○ Mallion/Quicklink connection to roof anchor point is secured and mechanically tightened or chemically set with loctite.
label | COMMENTS - Not applicable as anchor is not within the Fall Zone.
bool | Tick if is not applicable
checkpoint | Prevention of corrosion
label | REFERENCE - Dissimilar metals are separated by foam, tape, EPDM barrier or sealant.
checkpoint | Site clean up and picture evidence if handover is not possible
label | REFERENCE - Site has been cleared of swarf or other debris installation inspection completed and witnessed by the customers representative. Where a client cannot sign for handover, clear high resolution pictures have been taken of the installed product.
checkpoint | Systems installation completion action
label | REFERENCE - Fit for use sticker/tag filled in and attached to each static line anchor point, mark with confirmed rating and install dates. Entry point signage updated and installed.
section | Project Completion
checkpoint | Handover operating and systems documentation issued and maximum lanyard length nominated in manual which prevents access to a fall arrest event.
checkpoint | I have carried out all necessary inspections and verify that the above items/activities conform to the contract specification/documents
textbox | Name:
date | Date:
holdpoint | Signature:
checklist | 46694R306 - ITP - LEVEL 05 - Installation of RIS HL200 Lifelines | itp |  |  |  |  | 46694R306 - ITP - LEVEL 05 - Installation of RIS HL200 Lifelines
section | INSPECTION TEST PLAN
checkpoint | Access point location(s)
label | CHARACTERISTICS - AS1891.2 1.4 System Acceptance Criteria a. AS5532 7.3 (h) AS1891.4 3.2.2. RIS HL200 Installation requirement
label | STAGE/FREQUENCY - Prestart installation work
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Manufacturer recommendation
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Structure location compatibility match
label | CHARACTERISTICS - AS1891.2 1.4 System Acceptance Criteria a. RIS HL200 Installation requirement
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Position of line to fall zone
label | CHARACTERISTICS - AS1891.2 1.4 System Acceptance Criteria a. RIS HL200 Installation requirement
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Fall clearance
label | CHARACTERISTICS - AS1891.2 1.4 System Acceptance Criteria a. 1891.4:2009 Section 7
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Lifeline connections and swaging
label | CHARACTERISTICS - AS1891.2 1.4 System Acceptance Criteria a. RIS HL200 Installation requirement
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Maximum loading angle
label | CHARACTERISTICS - AS1891.2 1.4 System Acceptance Criteria a. AS1891.2.5.3 Drilled-in anchorages. RIS HL200 Installation requirement
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Additional pendulum fixing points to roof allow safe transition and access
label | CHARACTERISTICS - AS1891.2 1.4 System Acceptance Criteria a. RIS HL200 Installation requirement
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Prevention of corrosion
label | CHARACTERISTICS - AS1891.2 1.4 System Acceptance Criteria a. RIS HL200 Installation requirement
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Product marking and signage
label | CHARACTERISTICS - AS1891.2 1.4 System Acceptance Criteria a. RIS HL200 Installation requirement
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Instructions for general use
label | CHARACTERISTICS - AS1891.2 1.4 System Acceptance Criteria a. AS/NZS 1891.4.2009 Section (9). RIS HL200 Installation requirement
label | STAGE/FREQUENCY - On Completion
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Completion Handover
label | INSTALLER -
label | INSTALL SUPERVISOR - H
label | CLIENT - H
holdpoint | HOLD POINT
section | CHECKLIST - Installation (Refer to Installation Instructions)
checkpoint | Access point location(s)
label | REFERENCE - Systems can be accessed safely by trained persons without the risk of an uncontrolled fall.
checkpoint | Structure location compatibility match
label | REFERENCE - Purlin connected by minimum M12 bolts each end of purlin. Purlin details: C/Z15015 minimum size for attachment of anchor.
checkpoint | Lifeline length, Inline connection and swaging
label | REFERENCE - 8mm cable with minimum static line length of 4m. End anchors installed with a minimum 2 x M12 bolts supporting the end termination Jaw Jaw or fork swage or quicklinks if applicable. Intermediate anchors have a minimum of 1 x M12 bolt supporting the static line to the structure.
label | ○ Each swage termination has 5 crimps equally spaced over 85mm.
label | ○ Joiner requires 10 crimps with 5 crimps either side of the central point.
label | ○ Intermediate corners to be single crimped to form radius.
checkpoint | Terminations position, Connections, Tensioning and Spans
label | REFERENCE - End anchor static line assemblies that terminate closer than 2m to a fall zone have an inline stopper fitted a minimum of 2m from fall zone.
label | ○ Maximum anchor to anchor span without written exemption (from an RIS manager or engineer) is 8m.
label | ○ Systems under 20m include an inline shock absorbing assembly.
label | ○ Locking pins are installed and split pins/rings secured on the tensioner and the fork ends.
checkpoint | Steel fixed configuration
label | REFERENCE - M12 stainless steel bolts with nyloc nuts and washers. Drill bit for 12mm thread = 14mm hole, torque wrench tensioned to 80Nm. Minimum edge distance on structural steel is 25mm
textbox | COMMENTS - Nominate the type of structure utilized for this application:
checkpoint | Applications with roof raiser/Top hat section/rack systems for insulation integrity
label | REFERENCE - Custom made anchor with longer M12 thread to enable fixing to the purlin. The use of a RIS spacer is required to bridge the gap from the top of the purlin to the underside of the sheet.
checkpoint | Penetration of roof is not over sized
label | REFERENCE - Maximum 29mm hole sizes for top fixed anchors.
checkpoint | Maximum loading angle and corner radiuses
label | REFERENCE - 20 degrees from the structural surface. 500mm radius.
checkpoint | Anchor points to structure to prevent lateral swing fall are installed or mitigation agreed
label | REFERENCE - Corners and changes of shape have additional pendulum anchor points installed to allow access and prevent swing fall.
checkpoint | Anchor at entry point with a stainless steel Strop
label | REFERENCE - Anchor strop must be positioned to enable user to reach and connect to.
label | ○ Strop is marked and rated to 15kN.
label | ○ Mallion/Quicklink connection to roof anchor point is secured and mechanically tightened or chemically set with loctite.
label | COMMENTS - Not applicable as anchor is not within the Fall Zone.
bool | Tick if is not applicable
checkpoint | Prevention of corrosion
label | REFERENCE - Dissimilar metals are separated by foam, tape, EPDM barrier or sealant.
checkpoint | Site clean up and picture evidence if handover is not possible
label | REFERENCE - Site has been cleared of swarf or other debris installation inspection completed and witnessed by the customers representative. Where a client cannot sign for handover, clear high resolution pictures have been taken of the installed product.
checkpoint | Systems installation completion action
label | REFERENCE - Fit for use sticker/tag filled in and attached to each static line anchor point, mark with confirmed rating and install dates. Entry point signage updated and installed.
section | Project Completion
checkpoint | Handover operating and systems documentation issued and maximum lanyard length nominated in manual which prevents access to a fall arrest event.
checkpoint | I have carried out all necessary inspections and verify that the above items/activities conform to the contract specification/documents
textbox | Name:
date | Date:
holdpoint | Signature: