## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 46694R302 - ITP - LEVEL 01 - Installation of RIS Ladder Bracket | itp |  |  |  |  | 46694R302 - ITP - LEVEL 01 - Installation of RIS Ladder Bracket
section | INSPECTION TEST PLAN
checkpoint | Access point location(s)
label | CHARACTERISTICS - AS5532 7.3 (h) AS1891.4 3.2.2
label | STAGE/FREQUENCY - Prestart installation work
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Manufacturer recommendation
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Safe transition to roof
label | CHARACTERISTICS - AS1891.6.2.2, (e) Other selection criteria
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Ladder bracket connection to the structure
label | CHARACTERISTICS - RIS Ladder Bracket Installation Requirement
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Ladder bracket location
label | CHARACTERISTICS - RIS Ladder Bracket Installation Requirement
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Transfer strop location
label | CHARACTERISTICS - RIS Ladder Bracket Installation Requirement
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Transfer anchor location
label | CHARACTERISTICS - RIS Ladder Bracket Installation Requirement
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Number of fixings, location of fixings
label | CHARACTERISTICS - RIS Ladder Bracket Installation Requirement
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Prevention of corrosion
label | CHARACTERISTICS - RIS Ladder Bracket Installation Requirement
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Product marking and signage
label | CHARACTERISTICS - RIS Ladder Bracket Installation Requirement
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Instructions for general use
label | CHARACTERISTICS - AS1891.2 1.4 System Acceptance Criteria a. AS/NZS 1891.4.2009 Section (9). RIS Ladder Bracket Installation Requirement.
label | STAGE/FREQUENCY - On Completion
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Completion Handover
label | INSTALL SUPERVISOR - H
label | CLIENT - H
holdpoint | HOLD POINT
section | CHECKLIST - Installation (Refer to Installation Instructions)
checkpoint | Access point location(s)
label | REFERENCE - Installed equipment is positioned so it can be accessed in a secure and safe manner using normal ladder safety protocols. e.g. 3 points of contact, tie off, 4 to 1 angle and 1m past step of point. Maximum of 6m allowable height of a ladder bracket off the ground.
checkpoint | Safe transition from ladder to roof
label | REFERENCE - Ladder bracket is installed with entry point anchor assembly to allow connection or transition to a safe position away from the roof edge.
checkpoint | Ladder bracket connection to the structure
label | REFERENCE - Bracket must connect to the structure with one of the following methods:
label | ○ 3 x 8mm Bulb Tite Rivets. or
label | ○ 3 x 12x14x50 metal/timber screw. or
label | ○ 3 x HSA R M8 x 55 5/-/-, Drill bit for 8mm thread = 8mm hole.
textbox | COMMENTS - Nominate the fixing method used:
checkpoint | Ladder bracket location
label | REFERENCE - Ladder bracket is installed with entry point anchor assembly to allow connection or transition to a safe position away from the roof edge.
checkpoint | Transfer strop location
label | REFERENCE - Strop must be positioned to enable user to reach and connect without falling.
bool | Tick if is not applicable
checkpoint | Transfer anchor location
label | REFERENCE - Entry anchor that do not have strops are positioned to enable user to reach and connect without falling or leaning out from ladder.
bool | Tick if is not applicable
checkpoint | Prevention of Corrosion
label | REFERENCE - Dissimilar metals are separated by EPDM barrier or sealant.
label | NOTE: It's acceptable to have some paper remain on the FOAM during installation.
checkpoint | Site clean up and picture evidence if handover is not possible
label | REFERENCE - Site has been cleared of swarf or other debris installation inspection completed and witnessed by the customers representative. Where a client cannot sign for handover, clear high resolution pictures have been taken of the installed product.
checkpoint | Systems installation completion action
label | REFERENCE - Entry point signage updated and installed.
section | Project Completion
checkpoint | Handover operating and systems documentation issued and maximum lanyard length nominated in manual for fall arrest/restraint systems.
checkpoint | I have carried out all necessary inspections and verify that the above items/activities conform to the contract specification/documents
textbox | Name:
date | Date:
holdpoint | Signature:
checklist | 46694R307 - ITP - LEVEL 05 - Installation of RIS Ladder Bracket | itp |  |  |  |  | 46694R307 - ITP - LEVEL 05 - Installation of RIS Ladder Bracket
section | INSPECTION TEST PLAN
checkpoint | Access point location(s)
label | CHARACTERISTICS - AS5532 7.3 (h) AS1891.4 3.2.2
label | STAGE/FREQUENCY - Prestart installation work
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Manufacturer recommendation
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Safe transition to roof
label | CHARACTERISTICS - AS1891.6.2.2, (e) Other selection criteria
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Ladder bracket connection to the structure
label | CHARACTERISTICS - RIS Ladder Bracket Installation Requirement
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Ladder bracket location
label | CHARACTERISTICS - RIS Ladder Bracket Installation Requirement
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Transfer strop location
label | CHARACTERISTICS - RIS Ladder Bracket Installation Requirement
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Transfer anchor location
label | CHARACTERISTICS - RIS Ladder Bracket Installation Requirement
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Number of fixings, location of fixings
label | CHARACTERISTICS - RIS Ladder Bracket Installation Requirement
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Prevention of corrosion
label | CHARACTERISTICS - RIS Ladder Bracket Installation Requirement
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Product marking and signage
label | CHARACTERISTICS - RIS Ladder Bracket Installation Requirement
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - x
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Instructions for general use
label | CHARACTERISTICS - AS1891.2 1.4 System Acceptance Criteria a. AS/NZS 1891.4.2009 Section (9). RIS Ladder Bracket Installation Requirement.
label | STAGE/FREQUENCY - On Completion
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Completion Handover
label | INSTALL SUPERVISOR - H
label | CLIENT - H
holdpoint | HOLD POINT
section | CHECKLIST - Installation (Refer to Installation Instructions)
checkpoint | Access point location(s)
label | REFERENCE - Installed equipment is positioned so it can be accessed in a secure and safe manner using normal ladder safety protocols. e.g. 3 points of contact, tie off, 4 to 1 angle and 1m past step of point. Maximum of 6m allowable height of a ladder bracket off the ground.
checkpoint | Safe transition from ladder to roof
label | REFERENCE - Ladder bracket is installed with entry point anchor assembly to allow connection or transition to a safe position away from the roof edge.
checkpoint | Ladder bracket connection to the structure
label | REFERENCE - Bracket must connect to the structure with one of the following methods:
label | ○ 3 x 8mm Bulb Tite Rivets. or
label | ○ 3 x 12x14x50 metal/timber screw. or
label | ○ 3 x HSA R M8 x 55 5/-/-, Drill bit for 8mm thread = 8mm hole.
textbox | COMMENTS - Nominate the fixing method used:
checkpoint | Ladder bracket location
label | REFERENCE - Ladder bracket is installed with entry point anchor assembly to allow connection or transition to a safe position away from the roof edge.
checkpoint | Transfer strop location
label | REFERENCE - Strop must be positioned to enable user to reach and connect without falling.
bool | Tick if is not applicable
checkpoint | Transfer anchor location
label | REFERENCE - Entry anchor that do not have strops are positioned to enable user to reach and connect without falling or leaning out from ladder.
bool | Tick if is not applicable
checkpoint | Prevention of Corrosion
label | REFERENCE - Dissimilar metals are separated by EPDM barrier or sealant.
label | NOTE: It's acceptable to have some paper remain on the FOAM during installation.
checkpoint | Site clean up and picture evidence if handover is not possible
label | REFERENCE - Site has been cleared of swarf or other debris installation inspection completed and witnessed by the customers representative. Where a client cannot sign for handover, clear high resolution pictures have been taken of the installed product.
checkpoint | Systems installation completion action
label | REFERENCE - Entry point signage updated and installed.
section | Project Completion
checkpoint | Handover operating and systems documentation issued and maximum lanyard length nominated in manual for fall arrest/restraint systems.
checkpoint | I have carried out all necessary inspections and verify that the above items/activities conform to the contract specification/documents
textbox | Name:
date | Date:
holdpoint | Signature: