## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 46694R304 - ITP - LEVEL 05 - Installation of RIS Single Sided Handrail only | itp |  |  |  |  | 46694R304 - ITP - LEVEL 05 - Installation of RIS Single Sided Handrail only
section | INSPECTION TEST PLAN
checkpoint | Access point location(s)
label | CHARACTERISTICS - AS1657 J2.2, 5.4.1 & G5
label | STAGE/FREQUENCY - Prestart installation work
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Labelling of Installation
label | CHARACTERISTICS - AS1657 8.2 Labelling of Installation
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Material
label | CHARACTERISTICS - AS/NZS 1664.1 & AS/NZS 1664.2
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Headroom
label | CHARACTERISTICS - AS1657 3.1.5
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Safety below access areas
label | CHARACTERISTICS - AS1657 4.5 & 4.6
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Provision of a barrier
label | CHARACTERISTICS - AS1657 5.4.1
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Stability and structural capacity
label | CHARACTERISTICS - AS1657 6.1.1
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Finished surfaces, height and hand clearance
label | CHARACTERISTICS - AS1657 5.6.1, 5.6.2 & 5.6.3
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Documentation to be supplied
label | CHARACTERISTICS - AS1657 8.3
label | STAGE/FREQUENCY - On completion
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Visual
label | INSTALL SUPERVISOR - H
label | CLIENT - S
holdpoint | HOLD POINT
section | CHECKLIST - Installation (Refer to Installation Instructions)
checkpoint | Access point location(s)
label | REFERENCE - Systems can be accessed safely by trained persons without the risk of an uncontrolled fall
checkpoint | Material
label | REFERENCE - All materials installed are from tested and pre-fabricated RIS Stock
checkpoint | Obstructions and headroom
label | REFERENCE - Pathways allow 2m of clearance in proximity to the handrail systems installed
checkpoint | Safety below access areas
label | REFERENCE - Kickboards installed to areas that require dropped object protections. Gaps between kickboard and standing surface do not exceed 10mm.
checkpoint | Provision of guard railing
label | REFERENCE - Guard railing extends to the agreed zones and provides effective fall prevention
checkpoint | Structural stability and fixing metal roof mounted systems
label | REFERENCE - Roof materials minimum .42 BMT, 1 Handrail post, 1 Post Brace, Base Support Channel, 12x 4.8mm SS Rivets, 2 x 6mm Aluminimum Rivet, 2 x EPDM Rubber Washer.
label | ○ Maximum corner post spacing 500mm. Maximum span between posts 1500mm
checkpoint | Structural stability and fixings concrete/steel systems
label | REFERENCE - 1 Handrail post, 1 base spigot, 8x 4.8mm SS Rivets, Maximum corner post spacing 500mm.
label | Maximum span between posts 1500mm Mechanical Fixings:
label | ○ 2 x HSA R M12 x 100 20/5, drill bit for 12mm thread = 12mm hole x 2, torque wrench tensioned EXACTLY 50Nm
label | Chemical Fixings:
label | ○ 2 x Stainless M12 with minimum 110mm embedment, Drill bit for 12mm thread = 2 x14mm hole, Hilti Chemical Set product code HIT 200 R, Nut is torque wrench tensioned to EXACTLY 40Nm
label | Steel Fixings:
label | ○ 2 x M12 stainless steel bolts with nyloc nuts and washers, Drill bit for 12mm thread = 2 x 13mm hole, torque wrench tensioned to 80Nm
label | ○ Minimum edge distance to fixing steel: 25mm
textbox | COMMENTS - Nominate the fixing method that you have used on site:
checkpoint | Structural stability and fixing for handrails, midrail, corners, end caps and kickboard
label | REFERENCE - Joins in Hand and Mid Rails, End caps, Kickboards and Corners have 2 x 4.8mm SS Rivets per side.
label | ○ Closure bends have 6 x 4.8mm SS Rivets per bend. Handrail bracing is installed at every corner, every 15m for straight runs, at the start and end of each system.
checkpoint | Finished surfaces, height and hand clearance
label | REFERENCE - Handrail finished surfaces are free from sharp edges, burs and other conditions. Hand clearance between handrails and other adjacent structures is not less than 50mm.
checkpoint | Site clean up and picture evidence if handover is not possible
label | REFERENCE - Site has been cleared of swarf or other debris installation inspection completed and witnessed by the customers representative. Where a client cannot sign for handover, clear high resolution pictures have been taken of the installed product.
checkpoint | Systems installation completion action
label | REFERENCE - Fit for use sticker/tag filled in and attached to the handrail, mark with confirmed rating. Entry point signage updated and installed.
section | Project Completion
checkpoint | Handover operating and systems documentation issued
checkpoint | I have carried out all necessary inspections and verify that the above items/activities conform to the contract specification/documents
textbox | Name:
date | Date:
holdpoint | Signature: