## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 46694V1 - ITP | itp |  |  |  |  | 46694V1 - ITP
section | INSPECTION TEST PLAN AND CHECKLIST
checkpoint | 1 - Tender and Testing conformance
label | CHARACTERISTICS - Review specifications and performance standard requirements for project
label | STAGE/FREQUENCY - Pre-contract signing
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Confirm product is tested and designed to required project performance, international or national standards detailed in specifications at time of tender.
label | ACCEPTANCE CRITERIA - Tested to specification requirements ITP Checklist is relevant to product required
label | INSTALL SUPERVISOR - H
holdpoint | HOLD POINT
checkpoint | 2 - Preliminary activities (requiring Principal’s notification)
label | CHARACTERISTICS - Notification provided of any changes in design or structures that effect products to be used
label | STAGE/FREQUENCY - Before ordering products and beginning installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Specification, drawings remain unchanged since tender was accepted and contract signed or new plans and specifications are issued and reviewed, changes are accepted by client
label | ACCEPTANCE CRITERIA - Reviewed and changes do not alter quantities and types of products to be installed
label | INSPECTION/TEST PROCEDURE - Submit details of changes to client and agree to changes in scope or products to be used
label | INSTALL SUPERVISOR - H
label | CLIENT - S
holdpoint | HOLD POINT
checkpoint | 3 - Preliminary activities (requiring Contractor’s acceptance)
label | CHARACTERISTICS - Approvals required obtained or safety documentation is supplied and induction requirements outlined
label | STAGE/FREQUENCY - Before ordering products and beginning installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - variations requested if required, SWMS sent for review and inductions organised.
label | ACCEPTANCE CRITERIA - Change of design or quantities is agreed to and variations issued is SWMS and Induction accepted and conducted
label | INSPECTION/TEST PROCEDURE - Documents sent and acceptance confirmed with Client
label | INSTALL SUPERVISOR - H
label | CLIENT - W
holdpoint | HOLD POINT
checkpoint | 4 - Pre installation site investigation/measur e up completed confirmed.
label | CHARACTERISTICS - Progress of work and condition of the structure is confirmed, visual inspection where required is completed for compatibility and suitability
label | STAGE/FREQUENCY - Before installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - structures match and conditions on site are suitable for installation to begin
label | ACCEPTANCE CRITERIA - Structural and physical characteristics match
label | INSPECTION/TEST PROCEDURE - Job pack issued to Installer with relevant ITP Checklist included
label | INSTALL SUPERVISOR - H
label | CLIENT - S
holdpoint | HOLD POINT
section | Pre-Start/Installation
checkpoint | Plans and specifications have been reviewed and are current. Existing ITP checklists are suitable for project. Contract is signed.
checkpoint | SWMS and any other documents have been provided, reviewed and accepted by the client
checkpoint | Variations outlined and agreed, no changes or additions are required, job pack and ITP are included to project file.
checkpoint | Site inspected or reviewed, structural match confirmed with materials ordered, instation surface condition is undamaged and installation ready
checkpoint | I have carried out all necessary inspections and verify that the above items/activities conform to the contract specification/documents
textbox | Name:
date | Date:
holdpoint | Signature:
checklist | 46694V101 - ITP - Installation of RIS Single Sided Handrail only | itp |  |  |  |  | 46694V101 - ITP - Installation of RIS Single Sided Handrail only
section | INSPECTION TEST PLAN AND CHECKLIST
checkpoint | Access point location(s)
label | CHARACTERISTICS - AS1657 J2.2, 5.4.1 & G5
label | STAGE/FREQUENCY - Prestart installation work
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Labelling of Installation
label | CHARACTERISTICS - AS1657 8.2 Labelling of Installation
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Material
label | CHARACTERISTICS - AS/NZS 1664.1 & AS/NZS 1664.2
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Headroom
label | CHARACTERISTICS - AS1657 3.1.5
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Safety below access areas
label | CHARACTERISTICS - AS1657 4.5 & 4.6
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Provision of a barrier
label | CHARACTERISTICS - AS1657 5.4.1
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Stability and structural capacity
label | CHARACTERISTICS - AS1657 6.1.1
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Finished surfaces, height and hand clearance
label | CHARACTERISTICS - AS1657 5.6.1, 5.6.2 & 5.6.3
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Documentation to be supplied
label | CHARACTERISTICS - AS1657 8.3
label | STAGE/FREQUENCY - On completion
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Visual
label | INSTALL SUPERVISOR - H
label | CLIENT - S
holdpoint | HOLD POINT
section | CHECKLIST - Installation (Refer to Installation Instructions)
checkpoint | Access point location(s)
label | REFERENCE - Systems can be accessed safely by trained persons without the risk of an uncontrolled fall
checkpoint | Material
label | REFERENCE - All materials installed are from tested and pre-fabricated RIS Stock
checkpoint | Obstructions and headroom
label | REFERENCE - Pathways allow 2m of clearance in proximity to the handrail systems installed
checkpoint | Safety below access areas
label | REFERENCE - Kickboards installed to areas that require dropped object protections. Gaps between kickboard and standing surface do not exceed 10mm.
checkpoint | Provision of guard railing
label | REFERENCE - Guard railing extends to the agreed zones and provides effective fall prevention
checkpoint | Structural stability and fixing metal roof mounted systems
label | REFERENCE - Roof materials minimum .42 BMT, 1 Handrail post, 1 Post Brace, Base Support Channel, 12x 4.8mm SS Rivets, 2 x 6mm Aluminimum Rivet, 2 x EPDM Rubber Washer.
label | ○ Maximum corner post spacing 500mm.
label | ○ Maximum span between posts 1500mm
checkpoint | Structural stability and fixings concrete/steel systems
label | ○ 1 Handrail post, 1 base spigot, 8x 4.8mm SS Rivets, Maximum corner post spacing 500mm. Maximum span between posts 1500mm.
label | Mechanical Fixings:
label | ○ 2 x HSA R M12 x 100 20/5, drill bit for 12mm thread = 12mm hole x 2, torque wrench tensioned EXACTLY 50Nm
label | Chemical Fixings:
label | ○ 2 x Stainless M12 with minimum 110mm embedment, Drill bit for 12mm thread = 2 x14mm hole, Hilti Chemical Set product code HIT 200 R, Nut is torque wrench tensioned to EXACTLY 40Nm
label | Steel Fixings:
label | ○ 2 x M12 stainless steel bolts with nyloc nuts and washers, Drill bit for 12mm thread = 2 x 13mm hole, torque wrench tensioned to 80Nm
label | ○ Minimum edge distance to fixing steel: 25mm
textbox | COMMENTS - Nominate the fixing method that you have used on site:
checkpoint | Structural stability and fixing for handrails, midrail, corners, end caps and kickboard
label | ○ Joins in Hand and Mid Rails, End caps, Kickboards and Corners have 2 x 4.8mm SS Rivets per side.
label | ○ Closure bends have 6 x 4.8mm SS Rivets per bend. Handrail bracing is installed at every corner, every 15m for straight runs, at the start and end of each system.
checkpoint | Finished surfaces, height and hand clearance
label | ○ Handrail finished surfaces are free from sharp edges, burs and other conditions. Hand clearance between handrails and other adjacent structures is not less than 50mm.
checkpoint | Site clean up and picture evidence if handover is not possible
label | ○ Site has been cleared of swarf or other debris installation inspection completed and witnessed by the customers representative. Where a client cannot sign for handover, clear high resolution pictures have been taken of the installed product.
checkpoint | Systems installation completion action
label | ○ Fit for use sticker/tag filled in and attached to the handrail, mark with confirmed rating. Entry point signage updated and installed.
section | Project Completion
checkpoint | Handover operating and systems documentation issued
checkpoint | I have carried out all necessary inspections and verify that the above items/activities conform to the contract specification/documents
textbox | Name:
date | Date:
holdpoint | Signature:
checklist | 46694V101 - ITP - Installation of RIS Aluminium Platforms | itp |  |  |  |  | 46694V101 - ITP - Installation of RIS Aluminium Platforms
section | INSPECTION TEST PLAN AND CHECKLIST
checkpoint | Access point location(s)
label | CHARACTERISTICS - AS1657 J2.2, 5.4.1 & G5
label | STAGE/FREQUENCY - Prestart installation work
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Labelling of Installation
label | CHARACTERISTICS - AS1657 8.2 Labelling of Installation
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Visual
label | INSTALLER - H
label | INSTALL SUPERVISOR - S
label | CLIENT - S
holdpoint | HOLD POINT
checkpoint | Material
label | CHARACTERISTICS - AS/NZS 1664.1 & AS/NZS 1664.2
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Visual
label | INSTALLER - H
label | INSTALL SUPERVISOR - S
label | CLIENT - S
holdpoint | HOLD POINT
checkpoint | Welding
label | CHARACTERISTICS - AS/NZS 1554.1, AS/NZS 1554.6 or AS/NZS 1665
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Visual
label | INSTALLER - H
label | INSTALL SUPERVISOR - S
label | CLIENT - S
holdpoint | HOLD POINT
checkpoint | Headroom
label | CHARACTERISTICS - AS1657 3.1.5
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - H
label | INSTALL SUPERVISOR - S
label | CLIENT - S
holdpoint | HOLD POINT
checkpoint | Level access, change and slip resistance and footing
label | CHARACTERISTICS - AS1657 5.1.1, 3.1.4, 3.1.3 & 5.3.3
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - H
label | INSTALL SUPERVISOR - S
label | CLIENT - S
holdpoint | HOLD POINT
checkpoint | Safety below the platform
label | CHARACTERISTICS - AS1657 4.5 & 4.6
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - H
label | INSTALL SUPERVISOR - S
label | CLIENT - S
holdpoint | HOLD POINT
checkpoint | Provision of barriers to the platform
label | CHARACTERISTICS - AS1657 5.4.1 c) I, ii, iii
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - H
label | INSTALL SUPERVISOR - S
label | CLIENT - S
holdpoint | HOLD POINT
checkpoint | Stability and structural capacity
label | CHARACTERISTICS - AS1657 7.1.2
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - H
label | INSTALL SUPERVISOR - S
label | CLIENT - S
holdpoint | HOLD POINT
section | CHECKLIST - Installation (Refer to Installation Instructions)
checkpoint | Access point location(s)
label | REFERENCE - Systems can be accessed safely by trained persons without the risk of an uncontrolled fall.
checkpoint | Material and off site fabrication
label | REFERENCE - All materials installed are from tested and pre-fabricated RIS Stock.
checkpoint | Obstructions and Headroom
label | REFERENCE - Pathways to and from the ladder allow 2m of head clearance to access the platform.
checkpoint | Level access, change and slip resistance and footing
label | REFERENCE - Platform is within 3 degrees and all walking surfaces are level with the step on and off points to the platform. The maximum gap between the platform and adjacent access ladder is between 50mm and 100mm.
checkpoint | Safety below the step ladder platform
label | REFERENCE - Toe boarding or infill barrier is applied to areas that require direct access under the platform, other than the entry point where people are exposed to dropped objects.
checkpoint | Provision of handrails
label | REFERENCE - Handrail and kick boarding are installed to the platform perimeter on all sides other than at entry points and exit points for platforms over 300mm.
checkpoint | Stability and structural capacity
label | REFERENCE - Platform has been fixed into place following RIS engineer and fixing instruction.
checkpoint | Finished surfaces, height and hand clearance
label | REFERENCE - Surfaces and finishes are free from sharp edges, burs and other unsafe conditions. 50mm clearance where they meet adjacent structures.
checkpoint | Site clean up and picture evidence if handover is not possible
label | REFERENCE - Site has been cleared of swarf or other debris installation inspection completed and witnessed by the customers representative. Where a client cannot sign for handover, clear high resolution pictures have been taken of the installed product.
checkpoint | Systems installation completion action
label | REFERENCE - Fit for use sticker/tag filled in and attached to the system, mark with confirmed rating. Entry point signage updated and installed.
section | Project Completion
checkpoint | Handover operating and systems documentation issued
checkpoint | I have carried out all necessary inspections and verify that the above items/activities conform to the contract specification/documents
textbox | Name:
date | Date:
holdpoint | Signature: