## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 46694V2 - ITP | itp |  |  |  |  | 46694V2 - ITP
section | INSPECTION TEST PLAN AND CHECKLIST
checkpoint | 1 - Tender and Testing conformance
label | CHARACTERISTICS - Review specifications and performance standard requirements for project
label | STAGE/FREQUENCY - Pre-contract signing
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Confirm product is tested and designed to required project performance, international or national standards detailed in specifications at time of tender.
label | ACCEPTANCE CRITERIA - Tested to specification requirements ITP Checklist is relevant to product required
label | INSTALL SUPERVISOR - H
holdpoint | HOLD POINT
checkpoint | 2 - Preliminary activities (requiring Principal’s notification)
label | CHARACTERISTICS - Notification provided of any changes in design or structures that effect products to be used
label | STAGE/FREQUENCY - Before ordering products and beginning installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Specification, drawings remain unchanged since tender was accepted and contract signed or new plans and specifications are issued and reviewed, changes are accepted by client
label | ACCEPTANCE CRITERIA - Reviewed and changes do not alter quantities and types of products to be installed
label | INSPECTION/TEST PROCEDURE - Submit details of changes to client and agree to changes in scope or products to be used
label | INSTALL SUPERVISOR - H
label | CLIENT - S
holdpoint | HOLD POINT
checkpoint | 3 - Preliminary activities (requiring Contractor’s acceptance)
label | CHARACTERISTICS - Approvals required obtained or safety documentation is supplied and induction requirements outlined
label | STAGE/FREQUENCY - Before ordering products and beginning installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - variations requested if required, SWMS sent for review and inductions organised.
label | ACCEPTANCE CRITERIA - Change of design or quantities is agreed to and variations issued is SWMS and Induction accepted and conducted
label | INSPECTION/TEST PROCEDURE - Documents sent and acceptance confirmed with Client
label | INSTALL SUPERVISOR - H
label | CLIENT - W
holdpoint | HOLD POINT
checkpoint | 4 - Pre installation site investigation/measur e up completed confirmed.
label | CHARACTERISTICS - Progress of work and condition of the structure is confirmed, visual inspection where required is completed for compatibility and suitability
label | STAGE/FREQUENCY - Before
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - structures match and conditions on site are suitable for installation to begin
label | ACCEPTANCE CRITERIA - Structural and physical characteristics match
label | INSPECTION/TEST PROCEDURE - Job pack issued to Installer with relevant ITP Checklist included
label | INSTALL SUPERVISOR - H
label | CLIENT - S
holdpoint | HOLD POINT
section | Pre-Start/Installation
checkpoint | Plans and specifications have been reviewed and are current. Existing ITP checklists are suitable for project. Contract is signed
checkpoint | SWMS and any other documents have been provided, reviewed and accepted by the client
checkpoint | Variations outlined and agreed, no changes or additions are required, job pack and ITP are included to project file.
checkpoint | Site inspected or reviewed, structural match confirmed with materials ordered, instation surface condition is undamaged and installation ready
checkpoint | I have carried out all necessary inspections and verify that the above items/activities conform to the contract specification/documents
textbox | Name:
date | Date:
holdpoint | Signature:
checklist | 46694V201 - ITP - LEVEL 5 - MAIN BUILDING - Installation of RIS Anchor Points SA711 thru SA723 | itp |  |  |  |  | 46694V201 - ITP - LEVEL 5 - MAIN BUILDING - Installation of RIS Anchor Points SA711 thru SA723
section | INSPECTION TEST PLAN
checkpoint | Access point location (s)
label | CHARACTERISTICS - AS5532 7.3 (h) AS1891.4 3.2.2
label | STAGE/FREQUENCY - Prestart installation work
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Position and orientation of anchor point to roof/structure
label | CHARACTERISTICS - AS5532 6.3.1.3 (v) AS1891.4 - 3.1.2 (g) Single point anchorages suitable for direct connection of personal fall-arrest
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Additional Pendulum fixing points to roof/wall/structure to allow safe transition and access
label | CHARACTERISTICS - AS1891.4 Table 2.1 restraint technique AS4488 5.3 a
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Load Testing
label | CHARACTERISTICS - AS1891.4 - 3.1.2 (g) Single point anchorages suitable for direct connection of personal fall-arrest AS5532 7.3 (f)
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Load Test
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Product marking and signage
label | CHARACTERISTICS - AS5532 7.2.3 a, b & c
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Instructions for general use
label | CHARACTERISTICS - AS5532 7.1 a, b, c, d, e, f & g
label | STAGE/FREQUENCY - On Completion
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Completion Handover
label | INSTALL SUPERVISOR - H
label | CLIENT - H
holdpoint | HOLD POINT
section | CHECKLIST - Installation (Refer to Installation Instructions)
checkpoint | Access point location(s)
label | REFERENCE - Systems can be accessed safely by trained persons without the risk of an uncontrolled fall
checkpoint | Position and orientation of anchor point to roof
label | REFERENCE - Eye of anchor to run 90 degrees to the primary work area.
label | ○ Glued-in anchorages shall be placed so that the shear load and the pull angle must not exceed 20° to the surface in which the bolt is installed.
label | ○ Minimum edge distance = 200mm
label | ○ Minimum spacing = 300mm
label | ○ Minimum concrete thickness = 150mm
checkpoint | SA711 - SA713 Chemical anchor fitting per anchor/bolt, SA721- SA723 Chemical anchor fitting per anchor/bolt
label | REFERENCE - Drill diameter = 30mm
label | ○ Drill diameter = 40mm
label | ○ Minimum depth of hole: 90mm (complete the hole that you start to the correct depth and the hole is cleaned appropriately)
label | ○ Clean drilled out hole, Hilti Chemical Set Product Code HIT200-R
textbox | COMMENTS - Confirm what size hole was drilled:
checkpoint | Anchor points to roof to prevent lateral swing fall are installed or mitigation agreed
label | REFERENCE - The distance to the next anchor is less than the length to the closest edge, unless mitigated by other means
checkpoint | Load Test each anchor with calibrated pull tester. Last calibration date must not exceed 12 months
label | REFERENCE - 15kN tested to 7.5kN. Test the anchor once the chem-set has cured fully.
checkpoint | Water proofing
label | REFERENCE - Anchor sealed and inspected for water tight fit
checkpoint | Anchor at entry point with a stainless steel Strop
label | REFERENCE - Anchor strop must be positioned to enable user to reach and connect to.
label | ○ Strop is marked and rated to 15kN.
label | ○ Mallion/Quicklink connection to roof anchor point is secured and mechanically tightened or chemically set with loctite.
label | COMMENTS - Not applicable as anchor is not within the Fall Zone.
bool | Tick if is not applicable
checkpoint | Site clean up and picture evidence if handover is not possible
label | REFERENCE - Site has been cleared of swarf or other debris installation inspection completed and witnessed by the customers representative. Where a client cannot sign for handover, clear high resolution pictures have been taken of each anchor point.
checkpoint | Anchor systems installation completion action
label | REFERENCE - Anchor fit for use sticker/tag filled in and attached to the anchor point, mark with confirmed rating. Entry point signage updated and installed.
section | Project Completion
checkpoint | Handover operating and systems documentation issued
checkpoint | I have carried out all necessary inspections and verify that the above items/activities conform to the contract specification/documents
textbox | Name:
date | Date:
holdpoint | Signature:
checklist | 46694V201 - ITP - LEVEL 28 - MAIN BUILDING - Installation of RIS Davit Arms | itp |  |  |  |  | 46694V201 - ITP - LEVEL 28 - MAIN BUILDING - Installation of RIS Davit Arms
section | INSPECTION TEST PLAN
checkpoint | Access point location(s)
label | CHARACTERISTICS - AS5532 7.3 (h) AS1891.4 3.2.2
label | STAGE/FREQUENCY - Prestart installation work
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Manufacturer recommendation
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Position and orientation of anchor point to roof/structure
label | CHARACTERISTICS - AS5532 6.3.1.3 (v)
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - H
label | INSTALL SUPERVISOR - S
label | CLIENT - S
holdpoint | HOLD POINT
checkpoint | Additional pendulum fixing points to roof/wall/structure to allow safe transition and access
label | CHARACTERISTICS - AS1891.4 Table 2.1 restraint technique AS4488 5.3 a
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - H
label | INSTALL SUPERVISOR - S
label | CLIENT - S
holdpoint | HOLD POINT
checkpoint | Load testing
label | CHARACTERISTICS - AS1891.4 - 3.1.2 (g) Single point anchorages suitable for direct connection of personal fall-arrest AS5532 7.3 (f)
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - H
label | INSTALL SUPERVISOR - S
label | CLIENT - S
holdpoint | HOLD POINT
checkpoint | Prevention of corrosion
label | CHARACTERISTICS - AS5532 5.1
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - H
label | INSTALL SUPERVISOR - S
label | CLIENT - S
holdpoint | HOLD POINT
checkpoint | Product marking and signage
label | CHARACTERISTICS - AS5532 7.2.3 a, b & c
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - H
label | INSTALL SUPERVISOR - S
label | CLIENT - S
holdpoint | HOLD POINT
section | CHECKLIST - Installation (Refer to Installation Instructions)
checkpoint | Access point location(s)
label | REFERENCE - Systems can be accessed safely by trained persons without the risk of an uncontrolled fall.
checkpoint | Floor or Wall Base: Mechanical anchor fitting per HAS anchor/bolt
label | REFERENCE - Drill bit for 16mm thread = 16mm (complete the hole that you start to the correct depth and the hole is cleaned appropriately)
label | ○ Torque wrench tensioned to 100Nm
label | ○ Minimum edge distance: 250mm
label | ○ Minimum of 4 x M16 fixings
label | ○ Minimum of 3 bolt threads above the nut:
label | COMMENTS - Nominate the fixing method used
checkpoint | Floor or Wall Base: Chemical anchor fitting per anchor/bolt
label | REFERENCE - Drill bit for 16mm thread = 18mm (complete the hole that you start to the correct depth and the hole is cleaned appropriately) Clean drilled out hole, Hilti Chemical Set Product Code HIT500 -R
label | ○ Minimum edge distance: 250mm
label | ○ Minimum of 4 x M16 fixings
label | ○ Minimum of 3 bolt threads above the nut:
label | COMMENTS - Nominate the fixing method used
checkpoint | Concealed Base retro fit:
label | REFERENCE - Core diameter 100mm hole, a minimum of 200mm deep and use 1 x 300ml tube of Hilti Hit 500 chem set. Core hole to be a minimum of 500mm from slab edge.
label | COMMENTS - Nominate the fixing method used
checkpoint | Concealed Base cast in:
label | REFERENCE - If using the aluminium design base, any exposed aluminium is covered with suitable material separator prior to concrete pour and the base is positioned 500mm from slab edge and secured into position prior to concrete pour. The stainless steel concealed base does not require material seperation.
label | COMMENTS - Nominate the fixing method used
checkpoint | Position and orientation of primary and secondary anchor point to structure. Load Test each anchor/bolt with calibrated pull tester, last calibration date must not exceed 12 months.
label | REFERENCE - Eye of anchor to run 90 degrees to the primary work area.
label | ○ Friction and glued-in anchorages shall be placed so that the shear load and the pull angle must not exceed 20° to the surface in which the bolt is installed.
label | ○ Minimum measured distance between the centre of the anchor and a edge of a structure is 200mm.
label | ○ Minimum spacing between anchors is 300mm.
label | ○ Primary and Secondary anchors 50% proof tested to 7.5kN
checkpoint | Anchor points to structure to prevent lateral swing fall are installed or mitigation agreed
label | REFERENCE - The distance to the next anchor is less than the length to the closest edge, unless mitigated by other means.
checkpoint | Floor Mount and Wall Mount Davit base load Test each anchor/bolt with calibrated pull tester, last calibration date must not exceed 12 months. Concealed Base testing not required.
label | REFERENCE - Each individual friction or glued in bolt is tested to 50% of the required design load: 21kN tested to 10.5kN
checkpoint | Water proofing
label | REFERENCE - Sealed and inspected for water tight fit.
checkpoint | Corrosion prevention
label | REFERENCE - Dissimilar metals are separated by EPDM barrier or sealant.
checkpoint | Site clean up and picture evidence if handover is not possible
label | REFERENCE - Site has been cleared of swarf or other debris installation inspection completed and witnessed by the customers representative. Where a client cannot sign for handover, clear high resolution pictures have been taken of the installed product.
checkpoint | Systems Installation completion action
label | REFERENCE - Anchor fit for use sticker/tag filled in and attached to the anchor point, mark with confirmed rating. Entry point signage updated and installed
section | Project Completion
checkpoint | Handover operating and systems documentation issued
checkpoint | I have carried out all necessary inspections and verify that the above items/activities conform to the contract specification/documents
textbox | Name:
date | Date:
holdpoint | Signature:
checkpoint | I have carried out all necessary inspections and verify that the above work for this work area has been completed and conforms to the contract specification/documents
textbox | Name:
date | Date:
holdpoint | Signature: