## Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Add Daily Pre Start Checklist |  | Daily Pre Start Checklist | 36a7fc3e-c797-4b3f-86e4-3331c355e04e
| checkpoint | Daily Pre Start
a45310fd-4767-5c2f-9797-fc415a054aba | textbox | Site:
a2e2fef2-d464-5707-8596-214680fbf0b1 | textbox | Site Supervisor:
a985097d-7166-5679-8a08-b7235e6f2f6d | date | Date:
19f0a8fd-75e8-5a8f-8df9-deb44ffcbab9 | textbox | Weather forecast:
5a6ac46b-0697-5acd-aaf0-d4ab0eb255f2 | textbox | New site inductions:
2beeb06a-95de-5203-ac3d-29a69b0ecb4a | textbox | Safety concerns/reports from yesterdays work:
ebdff155-efaa-561c-97ae-ee5ee76f1255 | textbox | Changes to the site today:
| checkpoint | Any deliveries today?
29dbbe8b-de0e-53bf-a34a-b5a7a472ab25 | textbox | Details:
| checkpoint | All new workers inducted on to site and signed SWMS and Risk Assessments?
| checkpoint | Are all site specific permits filled out for today's activities? (Hot works, roof access, working at heights, confined space, excavation, etc)
| checkpoint | EWPs, Fall Protection and Electrical gear inspected, up to date, and safe for use?
| checkpoint | All workers have suitable PPE for all tasks to be performed today?
| checkpoint | All workers instructed in relation to today's work requirements?
| checkpoint | Are all other trades/public notified of relevant activities in their area?
| checkpoint | Daily assessment of work areas carried out?
| checkpoint | Weather conditions appropriate for commencement of works?
| checkpoint | Is there a SWMS in place for all specific activities commencing today?
| checkpoint | Work area safe to commence works?
| checkpoint-no-value | Work Area(s)
7be88f9b-9f55-59c4-8ccd-35e3cdfbcf90 | textbox | Work Area(s) today
0ea0261a-667d-506e-a061-8bd195481bcf | textbox | Planned Activities
fe367773-2047-554b-b234-a6d62d0d8343 | textbox | Safety Alerts/ Significant Hazards
| checkpoint-no-value | Attendees: Print Name & Sign
932f4ccd-0da7-5e75-92af-a8f29349ac8f | textbox | Name (1):
225cfd5d-016e-5ab4-ba29-2dd7e2923aad | textbox | Name (2):
70ca7fe4-9c47-54d7-a0ce-91a091677ed9 | textbox | Name (3):
f158b3f6-84c5-5e87-a873-87df540d498a | textbox | Name (4):
3a6afa6b-11e5-54bb-9617-36945e2dfae5 | textbox | Name (5):
38c4f16d-533c-5696-b345-cdc7562a4244 | textbox | Name (6):
71e4c3bd-6387-532e-b325-503066c5ba78 | textbox | Name (7):
e4a07f43-c58f-572f-aef2-cb2b2937e2e2 | textbox | Name (8):
2799a0f6-e244-5bab-a678-45e0891b25af | textbox | Name (9):
0bc82d95-145e-57c2-be91-c386ffbd213a | textbox | Name (10):
bfa1049f-a2e0-507a-b8f1-5bc24493b46d | textbox | Name (11):
f0b8bc45-f246-53e5-92bd-d9de170f0b96 | textbox | Name (12):
c3e778ef-84cc-5451-99d1-6ce7c51551e0 | textbox | Name (13):
f0f5f2f2-ffd8-5a4e-ad84-47b037bf230a | textbox | Name (14):
84029a2b-88ce-54b7-af79-bb45b5003983 | textbox | Name (15):
a1026297-ae03-5135-81f6-af348e6178ae | textbox | Name (16):
4c94d941-4798-59d5-9b5c-91efb17c8edd | textbox | Name (17):
80ef9cb4-dcaa-510e-b63c-b4d35e0431a3 | textbox | Name (18):
| checklist | Add New Document |  | Document Name: | 12b0f462-41f8-4bf1-a5e4-d7d7075ad300
| checkpoint | Upload document here, then press PASS
| checklist | Add Site Toolbox Meeting Checklist |  | Site Toolbox Meeting Checklist | 809bda39-3385-4e31-acec-7a15c4541566
| checkpoint | Site Toolbox Meeting
d3d42720-af78-5026-9ea8-a039d883f478 | textbox | Site:
c9317496-3321-5491-9092-812d21858512 | textbox | Site Foreman:
7769b16b-0f06-5d55-9ba1-43fdac01cf99 | date | Date:
ba4e1522-77d6-5abe-a9fc-5706b147639c | textbox | Time:
1a6dd70f-4412-5a2c-82c1-ceeb03c8ce4a | textbox | Weather forecast:
| checkpoint-no-value | Attendees
5f6f32f1-99a7-568b-8d7b-10ae9c02557e | textbox | Name (1):
19dbbb46-0af3-5a1b-ab5d-39fc4cf3dc2f | textbox | Name (2):
f3216882-0672-5b80-a682-cfd42bdf300d | textbox | Name (3):
9dcb7d4e-d145-5dbc-9b36-002f8aa82654 | textbox | Name (4):
0c2ea5c4-7fd3-5284-b37d-8ab6b438ca18 | textbox | Name (5):
3d85afaf-8d26-5e7a-83d2-fc92f5c4f6c8 | textbox | Name (6):
b1ec071e-b160-5a5e-99d6-c11352367b94 | textbox | Name (7):
4d926dfd-9821-56f2-9d2c-c86449cb23c0 | textbox | Name (8):
| checklist | Concrete Pour Checklist |  | Concrete Pour Checklist | cdc66c7a-0ceb-49cc-b7ab-47ad871e9c82
| section | Job Details
| checkpoint | Information
a8af6f2a-1f5c-5b23-9c4d-74db0d86651b | textbox | Pour Location
24e5fc6b-2c22-58e9-af0a-eac5a54891b7 | textbox | Placer
7bb1c572-9a3b-5959-a109-3bc54c1687a3 | textbox | Pour Date
dae689be-a7c5-5ecd-ba35-fffc75b42183 | textbox | Concrete Strength
358cdbda-f219-53c5-b8fc-07678fdd8a26 | textbox | Slump Required
841fd1e2-3265-5e60-8d17-5c5675754031 | textbox | Admixtures (if requested for VO purposes)
36cfa2a0-ca85-5d9b-9b0a-2e117a46455c | textbox | Finish
133e2b98-73f8-5393-b5f3-cfeee6a5cd76 | textbox | Tests ordered
1bbb5d6d-3da9-5c2e-8d00-ce1341112491 | textbox | Curing type required
| section | Pre Pour
| checkpoint | Pre Pour Inspection
9c771d66-003e-56bb-82ea-2a11336f14dd | tickbox | Formwork - check location, alignment, dimensions, plumb
85d3d207-2de2-5cfa-a987-8937d469fa25 | tickbox | Formwork - bracing, support, form ties, release agents
4d0b1376-cbe8-5f50-ba72-c8878bcbb3c8 | tickbox | Formwork - check position of fillets, chamfers
| checkpoint | Rebates
1dcf161a-d518-5023-8c84-fb325a45f0a1 | tickbox | Positions match arch plans
d5f7e45c-89c4-5a43-902c-4fbff8dabd76 | tickbox | Depths correct
| checkpoint | Set downs
4a876ea6-b1d1-56b7-95b5-00ebb91fa5c9 | tickbox | Positions match arch plans
fce94ab9-28bd-5bbf-b409-6c91a3b5d29f | tickbox | Depths correct
81a7a0ac-01f2-559c-9541-c291867cf9d2 | tickbox | Braced adequately
86373975-885c-5f54-9e5e-45f945e3fab8 | tickbox | Pre pour plan match up completed
| checkpoint | Items needing checking
86baf601-94c2-5669-9238-daa819b80ab6 | tickbox | HD Bolts Position
b608d310-1910-5f25-965c-a457df05ca27 | textbox | Final survey date
1a4905e8-5c5d-56f7-821c-d6ab00fab96d | tickbox | Share Keys installed
ff825fea-6e80-5b8c-8bc6-febdf4389d2f | tickbox | Block starters installed
11cfe5bc-544c-5258-9739-044bd1dfab47 | tickbox | Panel starters installed
c71b1eed-066f-5564-9ad9-90b95c7dc7ca | tickbox | Dross bach's installed
| checkpoint | Stop Ends
0bac858d-b905-56fb-ab66-e04298ff9ef4 | tickbox | Construction joints braced sufficiently Tied Top & Bottom
e7d23ba5-2da3-52cb-a8d7-145cb20adeac | tickbox | Location match as per pour plan
600ed00b-b410-5657-b695-80238e46094c | tickbox | Correct pours around mesh, adequate supervision required regarding concrete installation and vibration
f65de8ff-7753-525c-81dd-04264c083e70 | tickbox | Construction joints, control joints
cebaee6c-4092-5ac7-af95-33d557097673 | tickbox | Final survey point / levels check
11a07562-707e-527a-8783-be0ea6dfec79 | tickbox | Final clean out prior to pour
6494c9e1-2925-5c49-abb5-c538f61b9d29 | button | Are these stop ends a variation? | YES, NO
| checkpoint | M2 installed
| checkpoint | Pre pour discussion points
dc93c405-5443-5b3c-bf64-56dd173c5bf3 | tickbox | Emergency evacuation point discussed
abdf762e-061b-50e5-82c2-9ff046277681 | tickbox | Pour Methodology discussed & confirmed
3af66300-56df-5e22-b0f0-96e87319a318 | tickbox | Concrete pump locations discussed & confirmed
378ca1a7-95ad-5edd-9d1b-2d17fd4e9f17 | tickbox | Clear right of way for concrete trucks to deliver
a329c5f5-0560-517d-ac18-5aadae15f75e | tickbox | Turning circle for concrete trucks to be discussed & agreed
81ceb943-d4dc-580a-877b-6c34749ef283 | tickbox | Morning prestart location & time to be confirmed
| section | Post Pour
| checkpoint | Concrete pour final details/checks
6f32dd53-6a67-5376-a065-0b7193aafdb3 | tickbox | Curing organised
f32c1e51-3cd3-5992-96c7-eb79f1cd773d | tickbox | Concrete cutter organised
c3a49d4f-6aca-5338-b79a-f2f281447c6c | textbox | Start Time
2ff42a23-9891-5553-8aa2-24cb8e850b40 | textbox | Finish Time
915e782c-a8e8-5999-b7bf-3a2aa3b98131 | textbox | Weather
27aef37b-9111-5a3b-91cf-d4afb74ace1d | textbox | Pour Volume
2ae80dc6-0698-582c-96c8-96c5f940be1a | textbox | Rejected / Waste
| checkpoint | Post Pour Checks
ac7919de-efcf-54da-b5d3-6a7409885983 | tickbox | Concrete curing procedures in place
ee87740b-61bd-5d45-8374-d9a2155154db | tickbox | Confirm saw cut
8e793ab0-001c-5a5c-8e09-4fbf47f4b4d0 | tickbox | Mark saw cuts before water curing begins
93b4cdf9-438e-57e5-a908-a5bc296a9490 | tickbox | Concrete height check
eec3f085-b69c-565a-8a84-19eefd203fb3 | textbox | Formwork strip date
13b74186-277d-5427-ba52-e302df21b340 | tickbox | Hiab booked for pick up
d8554ca9-84dc-560f-865e-e714285d3d87 | tickbox | Strip formwork
9d839e65-4cf5-5d21-b7f8-0d79f6256c80 | tickbox | Repairs and patching
be8b1eab-c981-53e8-8266-e90d316959fb | tickbox | Floor height QA completed
| checkpoint | Concrete Dockets Attached/Sent
| checkpoint | Notes
e1b4793f-be2b-54c0-a0cf-5d98f1b7efc8 | textbox | Non-compliance
354c4ad6-acb8-5194-99b9-acfcb9116f89 | textbox | Action required
| checkpoint | Post Pour Actions
dbb57143-bac0-5680-97e6-1a0b442ed34b | tickbox | Saw cuts completed
4cc3616a-55e4-5530-a3ae-61c4bb9505c8 | tickbox | Curing completed
b4fb9c83-bd20-5f67-8ad2-6a5cf6faa268 | tickbox | Height check completed
728609d6-c1a4-5d9f-ac4a-f1600e955a88 | tickbox | Precast panels starters marked out
| checklist | In Situ Concrete Pour Checklist |  | In Situ: | 7ff23fb8-fd3f-448a-8614-f743e3a54c8c
| section | Job Details
| checkpoint | Information
e6ed6b54-525b-50f6-a452-007ca4d1a6d1 | textbox | Wall No
2c70ac19-1e17-5638-8ef9-e60e331abfc7 | textbox | Pour Location
39ae02fb-d420-5cc9-a36e-69253e5b3b59 | textbox | Placer
5aa36681-db99-50c9-be42-bcd36b011fc9 | textbox | Pour Date
4760c6ae-95fe-5176-b8cc-a1708f826a08 | textbox | Job Number
94bf21b9-82ff-540a-9d5a-e0b340d7453d | textbox | Concrete Strength
8857b6cd-804f-5311-b1c7-1be76cfc9c9d | textbox | Slump Required
b03cd0ed-e3ad-5bad-b624-d9402af60778 | textbox | Admixtures
0519aa17-b121-57a7-8afa-3ad4a4fdc34e | textbox | Max Aggregate Size
f511f295-73a1-544c-bcff-ba33b71b7b5a | textbox | Wall type / Finish
| checkpoint | Tests required
21e7a1ec-22fe-5a18-8d9f-3b57e63e73a6 | button | Cylinders | YES, NO
6b2b143c-5930-5cfe-bf22-903ec0ec424c | button | Slump | YES, NO
7a8d5a44-f6f6-57b6-8c3c-d35eb1d4ec0e | tickbox | Drawing Check
b8e9ae08-344a-5bd0-b443-2e93e1fd4955 | tickbox | Checked architectural drawings and details
14b00842-b833-5bc9-9423-61ae5861c89c | tickbox | Checked structural drawings and details
51c88e21-7aef-5fef-b090-7b5098a593e8 | tickbox | Pre-Construction Approvals
3f396583-1a7d-54bc-9ba6-81a6ced9d7d8 | tickbox | Client/Engineer Inspection completed
5b11acda-9b51-52a2-ae34-79835feec07c | tickbox | Starter bars check location level, laps
| section | Pre Pour
| checkpoint | Pre Pour Inspection
40edd62e-8c36-573f-9638-1d61c1434d22 | tickbox | Formwork - check location, alignment, dimensions, plumb
b90d4add-9930-57f0-90a6-5c0c5cbc8677 | tickbox | Formwork - bracing, support, form ties, release agents
1b8f3c5e-8441-5658-aadb-87cbdc6c58aa | tickbox | Formwork - check position of fillets, chamfers
430937a5-189f-5a99-8fbf-c3ec27a135b1 | tickbox | Location match as per pour plan
4185fc78-1c74-571d-ae21-85459923fb67 | tickbox | Final survey point / levels check
1047e1f4-af70-5634-8636-005e054d852d | tickbox | Final clean out prior to pour
| checkpoint | Hold Down Bolts
04c9721e-85b5-5ebf-b622-bf5402b1aa44 | tickbox | Position correct
745e0d47-d91c-5a08-94eb-ea183453c711 | tickbox | Surveyed date
| checkpoint | Cast in items
ed765c4c-a22a-5357-9c2b-a595839937e0 | tickbox | Block outs - size, location
4075115d-03df-5018-a36d-6cfe760f875f | tickbox | Floor starters - size, location
e60d0ad9-a878-538e-b7fb-33fab5c8f7b0 | tickbox | Drossbach starters - size, location
| checkpoint | Set downs
c59efd41-f174-5752-883c-4c3c04e1aae1 | tickbox | Positions match arch plans
8430e092-9137-53c0-9691-3bbfc652504f | tickbox | Depths correct
1862ae17-f593-5025-828f-9cc576b0593e | tickbox | Braced adequately
| checkpoint | Pre pour discussion points
9e7878e5-d659-5721-a270-5c86b39ce8e1 | tickbox | Emergency evacuation point discussed
7d6c64e5-9884-56d4-ab75-2b65a67037d6 | tickbox | Pour Methodology discussed & confirmed
a2f96315-8d1a-5fcb-817a-08a39aa82541 | tickbox | Concrete pump locations discussed & confirmed
45aa9676-4867-547c-a845-b121c796b7bf | tickbox | Clear right of way for concrete trucks to deliver
a5e2456f-1590-511d-a743-297b43a56abf | tickbox | Turning circle for concrete trucks to be discussed & agreed
fb708c2f-a97e-5719-8708-ac4f0a5d4252 | tickbox | Morning prestart location & time to be confirmed
8a9f5258-862e-5619-a6a1-c0ae645df038 | note | Note All sections are to be completed prior to pouring concrete
| checkpoint | Final Approvals
6e3b6f8a-d76a-5b12-ac84-6d987c7b2282 | tickbox | FWL Company Foreman
47b1feb9-ba47-5c9d-af34-6f90da18a4f7 | tickbox | Main Contractor Rep
9f4d54dd-aa93-5764-a4d1-d389ab93f40a | tickbox | FWL Company Project Manager
| section | Post Pour
| checkpoint | Concrete Dockets Attached/Sent
712f5293-1256-51a4-aeef-4966e572d844 | textbox | Start Time
52567fad-e983-5d53-8f6e-4974b3f3861d | textbox | Finish Time
aa7d24ea-4c8a-5581-81b4-2a2c0ac08491 | textbox | Weather
fc5087bf-262c-55ba-a441-99d72f9c6d38 | textbox | Pour Volume
7855756d-723c-5aab-80c8-ecc6dc03cf17 | textbox | Rejected / Waste
| checkpoint | Post Pour Checks
5c4a68c8-88f3-5301-a4e3-a96753a5ec4a | tickbox | Strip formwork
b80692b1-2e04-5bb7-b55c-9b6fd9ecc130 | tickbox | Repairs and patching
f02142de-ebe0-5c7e-bf6a-e3a9d1f40327 | tickbox | Notes
536e4d9e-c0f6-5baa-8e52-e54dacb5b869 | textbox | Non-compliance
4c0df43d-00ed-5884-b26c-c33cbfcb05da | textbox | Action required
02158a58-7409-586a-b8cc-1f0e191b8abe | textbox | Comments
| checkpoint | Final Approvals
1622d337-b88b-57cc-bc88-40281216f82a | tickbox | FWL Company Foreman
b1a6209b-6592-56c9-9ca9-7bded106c66a | tickbox | Main Contractor Rep
6907e76b-e923-5229-8b5a-47b420e8b189 | tickbox | FWL Company Project Manager
| checklist | Reinforcing Inspection Checklist |  | Reinforcing Inspection Checklist | ebe9445f-f1cb-494d-9ae5-973b50f90983
| section | Details
| checkpoint-no-value | Details
07d86d62-4f04-5b1d-ae91-fcc4e33687eb | textbox | Job No:
9248367d-b33d-562b-ac3a-26ec6186e92e | textbox | Contract Name:
890adf0e-cb46-556c-9bad-5b910adeedd6 | date | Date:
0dd38ca1-69fe-52bc-bccf-38164c2442a8 | textbox | Trade:
22725cf0-fa0d-532e-a0a2-108ce7396bc3 | textbox | Subcontractor:
a669df7e-87fe-53e4-ba07-58924ba96498 | textbox | Foreman:
4713ba46-f1cb-595b-b3b1-b45f1d5592ff | textbox | Work Area:
efe93e5a-7c9f-524d-9343-a41d51e45866 | textbox | Inspection No:
74f43ae4-e910-50f1-a7e3-667ed09f7a09 | textbox | Drawings Ref:
c9ad97d2-ccde-5333-9c85-cc51bf7b733a | textbox | Project Specification Refs:
094b4874-bf1a-5800-9e1e-76c21ee60c1e | textbox | Code / Standard Specification Refs:
| checkpoint | Laps - length / position
| checkpoint | Stirrups - quantity, size, spacing correct
| checkpoint | Tied rigidly
| checkpoint | Spacing correct
| checkpoint | Caps on bars
| checkpoint | Starters
| checkpoint | Cover - ground / formwork
| checkpoint | Spacers / chairs
| checkpoint | Rebar clean
| checkpoint | Engineer‚Äôs inspection booked
| checkpoint | Release for under floor heating
| checkpoint | Clean up work area
| checkpoint | Any defects add to remedial list
| checkpoint | Final Approvals
8dfa87e1-072d-590b-b6ee-43fe28e1cc48 | textbox | Subcontractor Foreman:
e6f79caa-8769-55f1-9bef-6722eea04b17 | date | Date:
5dc09170-62c6-5aba-bd96-5efb7d3ba37c | textbox | Company QA Check Francis Ward Ltd:
2bcd16dc-da9e-52bf-8a80-4ab6d8f855cc | date | Date:
| checklist | Remedial Checklist |  | Remedial: | 947a6e1d-5b45-4ab2-a683-00ad10341bc8
| section | Job Details
| checkpoint | Information
9d4a28a5-6921-56f8-89d5-ea452e287f7c | textbox | Building No
a820f41e-8464-5101-973b-bb8892996ce8 | textbox | Pour Location
842756da-7c7a-513d-9abc-f615d4490722 | textbox | Placer
6bf6d99f-dd98-5d5f-a22f-546fb7892872 | textbox | Pour Date
c30c21bf-da88-5a19-b8e6-cb9eef99c697 | textbox | Job Number
36ec633d-388f-5334-9a15-df4ddbeed6df | textbox | Concrete Strength
c91c1b7d-68a8-50bc-9495-27d91e0fd42a | textbox | Slump Required
54dc81f6-ab98-5de6-affb-bb6d8a20fa37 | textbox | Admixtures
cccf22c3-3628-56f5-8bcc-a0edf2ce55ad | textbox | Max Aggregate Size
5a4dd96d-3b4b-55ad-bca8-341859e59221 | textbox | Finish
| checkpoint | Tests required
a6ceb60a-4633-5f32-a868-eeb7e78f1feb | button | Cylinders | YES, NO
a50c0341-ce73-5f3a-808c-bbcdc1a33059 | button | Slump | YES, NO
| checkpoint | Drawing Check
592dd4cd-3b37-5788-b638-51b9f79138b9 | tickbox | Checked architectural drawings and details
f8bf4fd4-88cb-5df1-a1fb-81ea1d2b558a | tickbox | Checked structural drawings and details
| checkpoint | Pre-Construction Approvals
e43bd19d-4ea0-5bf1-892a-13c87581895b | tickbox | Foundation inspection completed
1e9344b3-4ce6-5a1f-afb1-6d5f11eb2af8 | tickbox | In ground drainage completed and tested (see drainage check sheet QA)
587321fe-6db8-595b-9fc8-25f9cdd4cd6a | tickbox | In ground services completed and tested
8801e8ec-87a1-5165-8cd9-80260a13fc10 | tickbox | Starter bars check location level, laps
| section | Pre Pour
| checkpoint | Pre Pour Inspection
759875fb-58b0-5677-8760-e6617077b30d | tickbox | Formwork - check location, alignment, dimensions, plumb
8b869d0d-8b20-5aa6-9981-a5818b94154a | tickbox | Formwork - bracing, support, form ties, release agents
f31490af-96db-5179-9ff5-30a9e96a1c88 | tickbox | Formwork - check position of fillets, chamfers
| checkpoint | Rebates
55413f6b-3e3c-55db-9f0d-7255fed9c16b | tickbox | Positions match arch plans
ca1dbe58-a892-5508-be37-50c212af4884 | tickbox | Depths correct
| checkpoint | Cast in items
8a5826b3-e300-5596-8f15-bf4784635052 | tickbox | Block outs - size, location
6acd2a50-fd33-50d9-8d31-faac6575ea3b | tickbox | Floor starters - size, location
208c4441-4988-5da4-acb4-d651dc64e251 | tickbox | Drossbach starters - size, location
| checkpoint | Set downs
f67982a5-c5c1-5259-87ab-ae2b8d1c6c85 | tickbox | Positions match arch plans
1e3dcc73-582b-5b79-aa72-c60e78e29966 | tickbox | Depths correct
86de4c50-9248-5893-9ae0-2853a9639f94 | tickbox | Braced adequately
ebced031-5664-5e80-9c10-4469bb91301a | tickbox | Pre pour plan match up completed
| checkpoint | Hold Down Bolts /Shear Keys
404e4c19-4ef6-5290-9c55-caca8aadd6df | tickbox | Position correct
65066508-fc1c-5cb3-8912-7a51230972a9 | tickbox | Surveyed date
| checkpoint | Stop Ends
e56ad807-2585-5ed1-80f5-0201a0119cf8 | tickbox | Construction joints braced sufficiently Tied Top & Bottom
06b2a25c-efb9-5126-871b-12bd49b84f4f | tickbox | Location match as per pour plan
742d4459-602e-52d2-89e0-2a2bb54617ef | tickbox | Correct pours around mesh, adequate supervision required regarding concrete installation and vibration
328808c6-45d1-5c93-8dfe-8be020c43091 | tickbox | Construction joints, control joints
f9be21b1-a9c7-5f9b-9e9f-c545270bca18 | tickbox | Final survey point / levels check
75dab3dd-bb6b-51e3-9472-8f8e001f2873 | tickbox | Final clean out prior to pour
| checkpoint | Pre pour discussion points
accecc58-f274-58cb-8bb3-c9ec3d05124d | tickbox | Emergency evacuation point discussed
3249518b-99de-5dd7-a895-eab17b7f502a | tickbox | Pour Methodology discussed & confirmed
ab0c1bf3-1d6e-5bd9-9892-b2bf0648e775 | tickbox | Concrete pump locations discussed & confirmed
b14137c8-fbb7-5253-a4d9-70e0b959bc59 | tickbox | Clear right of way for concrete trucks to deliver
5dd0ec02-af52-5dd6-99ca-0129cf4f2474 | tickbox | Turning circle for concrete trucks to be discussed & agreed
12b5cce7-ac6f-549c-b769-1e3114329d2c | tickbox | Morning prestart location & time to be confirmed
| checkpoint | FWL Sign Off
65ce1337-cda5-5a28-88d7-e23b9bfcf9d2 | tickbox | Will Puketapu
6ed62a3c-0ac3-58e3-8a0d-48a4d89b1e36 | tickbox | Regan Howley
79cbede3-ee48-53d9-a91b-2794ef679179 | tickbox | Other Site Supervisor
4d326044-a473-5b1a-8ec2-851fbee8cfed | note | Note All sections are to be completed prior to pouring concrete
| section | Post Pour
| checkpoint | Concrete Dockets Attached/Sent
b19e4614-0669-5893-b7ff-aa6b0711159d | textbox | Start Time
04d3225b-2291-5de5-b964-dc52e8329702 | textbox | Finish Time
f55fa9f8-9404-5f41-828c-ed8e837716a2 | textbox | Weather
ef2bca2a-c63d-54eb-9d7f-6674c4e69f3b | textbox | Pour Volume
a2659077-803f-5b7c-b857-f4af478b9263 | textbox | Rejected / Waste
| checkpoint | Post Pour Checks
cfb07e55-4a66-57cf-b404-53db58f730b0 | tickbox | Concrete curing procedures in place
53cff4af-8b10-53ef-9af0-2fce432ee020 | tickbox | Confirm saw cut
fdb5c69b-4ad4-5df7-809f-867528441970 | tickbox | Strip formwork
150a3abf-4998-56bd-8803-90d24aadf553 | tickbox | Repairs and patching
c24be7df-498b-53fa-819d-cf9e9bb56219 | tickbox | Floor height QA completed
540b8ba8-2079-5a91-8a0e-ae2f15bb5b25 | tickbox | Notes
f6fb3987-155d-5fd9-8408-331f1bbb7bb9 | textbox | Non-compliance
7c9233e5-f2cb-5b70-a070-3c22337a6c5c | textbox | Action required
| checkpoint | Post Pour Actions
09455dff-e3f9-5c42-bd3d-b43cfdbcd9a5 | tickbox | Saw cuts completed
7359b982-af49-515d-84b1-b4a3c948970f | tickbox | Precast panels starters marked out
| checkpoint | Final Approvals
f1ba8f7d-29c3-55ab-906b-bf3608ec51ba | tickbox | FWL Company Foreman
cd029803-4df0-5fb8-ab09-414ace53733f | tickbox | Main Contractor Rep
f8105d82-d530-5668-b517-4b8a2dbee4bd | tickbox | FWL Company Project Manager
| checklist | Site Establishment Pre-start Checklist |  | Site Establishment Pre-start Checklist | 4dfee45c-9551-4325-9390-cd8a8b202a3a
| checkpoint | Details
b1619da3-2a0e-5595-be62-3857cbd2d854 | textbox | Site name & number:
1ce64e61-55b0-5fa4-aec1-9d26b8270289 | textbox | Completed by:
9768d9c4-2224-5bd2-91bd-4d8253863999 | textbox | Date:
| checkpoint | Have all staff undertaken an induction
e0846970-d2b4-5e02-8a1f-fdcf5f9fdb51 | button | Francis Ward Induction | Yes, No, N/A
a2f2b873-eb92-50f0-9acd-6f185edcc85c | button | Main Contractor Site Induction | Yes, No, N/A
| checkpoint | Have the following been covered in the SWMS/TA’s/Risk Assessments and Site plans
95398c67-ac2d-5992-b73c-ce20171b3b59 | button | Height Work | Yes, No, N/A
b6f0aca8-50b0-5e52-9116-24c846aa9cb1 | button | Confined Spaces | Yes, No, N/A
1aa99844-0448-5ab2-afee-111a311490e9 | button | Hot Work - Grinder | Yes, No, N/A
f9341bf9-eba3-57b8-b6a1-0ce1aa195b1b | button | Dust | Yes, No, N/A
3e6563e9-9d06-5ba4-9260-0bb9384ea56d | button | Vibration | Yes, No, N/A
323a29f5-b1de-586b-a857-3ac7eef65f59 | button | Waste | Yes, No, N/A
d01e2d37-a310-5090-af1d-3e6a5e6f3d19 | button | Noise | Yes, No, N/A
8f058c01-6944-56dd-af41-66fb0a7b405e | button | Existing Services | Yes, No, N/A
7c2eaefc-33dc-55aa-890f-eecf3ff4277c | button | Suspended Floors | Yes, No, N/A
98f84142-2222-5fd0-98a8-5b2ca0877ce9 | textbox | Others:
| checkpoint | Emergency procedures
6d67b716-f2ad-5897-8da4-589c44d7129d | textbox | Where are the First aid kits & fire extinguishers located
1ad2ea67-b408-5a53-b861-4a74d4f0d785 | button | Are all First aid kits and Fire extinguishers compliant | Yes, No, N/A
0e98f616-57ce-52db-a476-88982c60fe02 | button | Is there an Emergency plan in place | Yes, No, N/A
de2c3240-7b45-5609-ac52-513b80227679 | textbox | Where is the emergency evacuation point
| checkpoint | Other subcontractors on this site
b9e66f29-7013-543b-b44b-42d06a15a602 | textbox | Subcontractors:
88dd8c87-db21-587b-aba4-a2c7cecd5d69 | note | List the other subcontractors working on this site (separated by a comma)
| checkpoint | Site facilities
55f7bc3b-062a-5ab8-90ce-5c8feca18631 | button | Site shed clean / tidy | Yes, No, N/A
e784aae3-4afa-5463-aa64-8e24d2c37c12 | button | Toilets available / clean | Yes, No, N/A
e32c3232-9436-5b7b-b785-2711ec450b87 | button | Water available | Yes, No, N/A
3084bee4-acc4-5321-a162-027623fd1ef3 | button | Power supply | Yes, No, N/A
5acc755f-5acf-5431-bc9e-c79963e99185 | button | Site fencing in place | Yes, No, N/A
39d9cecf-6b59-5f15-ba63-4826a5dcf3a3 | button | Signage & hazard board in place | Yes, No, N/A
c6d256aa-880d-56d9-bcf6-954a57f9212d | button | Staff parking available | Yes, No, N/A
ddf7ade1-f21b-5701-aaa7-a8cf5b0c1372 | textbox | Parking location:
| checkpoint | Personal protective equipment
783e7168-8aa9-572a-8e71-3e1be9021927 | button | Steel cap safety boots | Compulsory, When Required
795a4d32-c625-54c7-818a-bdd7aab0debe | button | Hearing Protection | Compulsory, When Required
a09b4f67-cfeb-56c3-a071-a81f72e1d980 | button | Gloves | Compulsory, When Required
3c66442d-086e-5b82-b192-58df3501cf6f | button | Eye Protection | Compulsory, When Required
d33a75f5-f456-55fa-9bd8-dad7e6399182 | button | Hi Viz Clothing | Compulsory, When Required
530a525d-5cd2-5701-b297-a0745f73d608 | button | Safety Helmet | Compulsory, When Required
14c1d97b-bf40-57c6-a7ac-cfea09d192f3 | button | Respiratory Protection | Compulsory, When Required
| checkpoint | Final Signoff
| signoff | Person completing this checklist to sign here