## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | GT4-ITP-018 - ACO Drain Install | itp |  |  |  | Yes | GT4-ITP-018 - ACO Drain Install
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | Frequency: Prior to commencing any activity
label | Acceptance Criteria: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | Reference Documents: Drawings and drawing registers
label | Inspection / Test Method: Visual inspection
label | Record of conformity: ITP Signed
label | HP*
label | Responsibility: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency: Prior to commencing any activity
label | Acceptance Criteria: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | Reference Documents: PSP, EMP, TMP, SWMS, WP
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: ITP Signed
label | HP*
label | Responsibility: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.3 - Submission & Approval of Concrete Mix Design
label | Frequency: Prior to first concrete pour
label | Acceptance Criteria: The Contractor shall submit the concrete mix design details for review by the Superintendent not less than 4 weeks prior to the placement of concrete. Concrete shall not be placed until the mix design has been reviewed by the Superintendent
label | Reference Documents: 610.07(b)
label | Inspection / Test Method: Verify
label | Record of conformity: ITP Signed, Mix design approval
label | HP
label | Responsibility: Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Construction Works
checkpoint | 2.1 - Setting Out
label | Frequency: Prior to start
label | Acceptance Criteria: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
label | Reference Documents: 703.17
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP Signed
label | HP
label | Responsibility: Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Excavation Permit
label | Frequency: For Each Day of Activity
label | Acceptance Criteria: An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task.
label | ○ Excavation operations shall not disturb areas outside the limit of excavation
label | Reference Documents: Excavation permit
label | Inspection / Test Method: Verify
label | Record of conformity: ITP Signed
label | HP*
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 2.3 - Excavation
label | Frequency: Each Lot
label | Acceptance Criteria: Excavation completed to required depth to allow placement of the concrete blinding layer.
label | Reference Documents: 703.2
label | Inspection / Test Method: Verify
label | Record of conformity: ITP Signed
label | IP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 2.4 - Dowel
label | Frequency: Prior to concrete pour
label | Acceptance Criteria: 12mm Diamond dowel at X centres
label | Reference Documents:
label | Inspection / Test Method: Verify
label | Record of conformity: ITP Signed
label | IP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 2.5 - Bedding
label | Frequency: Before placement of ACO DRAIN sections
label | Acceptance Criteria: 150mm concrete blinding to base of proposed ACO DRAIN.
label | Reference Documents: Trench grate joint detail with concrete pavement
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: ITP Signed
label | IP
label | Responsibility: Site Foreman
date | Date Completed:
checkpoint | 2.6 - Formwork
label | Frequency: Each Lot
label | Acceptance Criteria: Formwork shall comply with the requirements of AS 3610 where required
label | Reference Documents: 703.12, AS 3610
label | Inspection / Test Method: Verify
label | Record of conformity: ITP Signed
label | IP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 2.6 - Expansion Joint
label | Frequency: Prior to concrete pour
label | Acceptance Criteria: 12mm Abelflex seal with approved sealant against existing and adjacent concrete pavements
label | Reference Documents: Trench grate joint detail with concrete pavement
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: ITP Signed
label | IP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 2.7 - ACO Drain placement
label | Frequency: Prior to concrete pour
label | Acceptance Criteria: ACO drain sections to be placed in trench with lid surface flush with adjacent pacement surfaces. Ensure a 150mm width either side of ACO DRAIN to existing pavements.
label | Reference Documents: Trench grate joint detail with concrete pavement
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: ITP Signed
label | IP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 2.7 - Concrete Encasement
label | Frequency: Each section of ACO trench
label | Acceptance Criteria: Concrete shall be thoroughly compacted via contious tamping and internal vibration. Where concrete is unformed it shall be hand tamped to a smooth surface and screeded in accordance with the construction drawings.
label | ○ Where fresh concrete is being placed against concrete which has taken initial set a properly formed construction joint must be used.
label | ○ N25 concrete as per installation drawing - ACO Drain
label | Reference Documents: SPECIFICATION CLAUSE KLASSIKDRAIN K200 - LOAD CLASS A-B
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: ITP Signed
label | IP
label | Responsibility: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.8 - Record location of each batch
label | Frequency: Each concrete pour
label | Acceptance Criteria: Batch location recorded on Load Batch Traceability Checklist
label | Reference Documents: 610.15, CL001D
label | Inspection / Test Method: Checklist
label | Record of conformity: This ITP Signed
label | IP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 2.9 - Surface Finish
label | Frequency: Each Lot
label | Acceptance Criteria: Concrete elements shall have a Class 3 surface finish for external surfaces and a Class 4 surface finish for permanently hidden surfaces in accordance with AS 3610.
label | ○ Footpaths and other Surfacing shall be compelted with a wooden float.
label | Reference Documents: 703.25
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP Signed
label | IP
label | Responsibility: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 2.11 - Joints
label | Frequency: Each Joint
label | Acceptance Criteria: tool joints to be formed at each ACO joint.
label | Reference Documents: SPECIFICATION CLAUSE KLASSIKDRAIN K200 - LOAD CLASS A-B
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP Signed
label | IP
label | Responsibility: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.12 - Protection of concrete
label | Frequency: Each Lot
label | Acceptance Criteria: All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
label | ○ Vehicles equal to or less than 1.5 tonnes in weight may be permitted to cross after 4 days, vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
label | Reference Documents: 703.27
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP Signed
label | IP
label | Responsibility: Site Foreman
date | Date Completed:
checkpoint | 2.13 - Curing
label | Frequency: Each Lot
label | Acceptance Criteria: Concrete shall be cured immediately either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
label | ○ Curing compounds shall comply with AS 3799. The curing compound shall be applied in two coats using a fine spray at the rate stated on the certificate of compliance
label | Reference Documents: 703.1
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP Signed
label | IP
label | Responsibility: Site Engineer/ Site Foreman
date | Date Completed:
section | 3 - Completion
checkpoint | 3.1 - Carry out sampling of concrete - strength and consistency
label | Frequency: Each 50m3
label | Acceptance Criteria: Sampling and testing of the strength of concrete shall be carried out in accordance with Clause 6.2 of AS 1379.
label | ○ The consistency of the concrete shall be determined by a slump test of each concrete strength sample in accordance with AS 1012.3 and Clause 5.2 of AS 1379
label | Reference Documents: 703.11, CL001B, CL001C
label | Inspection / Test Method: Checklist
label | Record of conformity: ITP Signed/Test Records
label | TP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 3.2 - Tolerances
label | Frequency: Each Lot
label | Acceptance Criteria: Where matching in with existing surface levels, the new surface shall be within ± 5mm existing.
label | Section dimensions shall be constructed within the following tolerances:
label | ○ 5mm and 15mm for width; or
label | ○ ±3mm for dimensions less than 25mm.
label | Reference Documents: 703.15, Drawings
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP Signed
label | IP
label | Responsibility: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
date | Date:
signoff | Sign ITP
checklist | GT4-ITP-019 - Fire Services | itp |  |  |  | Yes | GT4-ITP-019 - Fire Services
section | 1 - Preliminary Works
checkpoint | 1.1 - Check that current revision drawings are being used
label | Frequency: Prior to Commencing Work
label | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
label | Reference Documents: IFC Project Drawings/ Drawing Register
label | Inspection / Test Method: Document review
label | Record of conformity: Latest revision IFC drawings
label | *WP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 1.2 - Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place
label | Frequency: Prior to Commencing
label | Acceptance Criteria: All environmental measures to be implemented as per current CEMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
label | Reference Documents: CEMP, Site induction
label | Inspection / Test Method: Document review & Site inspection
label | Record of conformity: ITP signed
label | *WP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 1.3 - Traffic Management (When required)
label | Frequency: Prior to Commencing Work
label | Acceptance Criteria: Approved TMP and WASIN (where required)
label | Reference Documents: Applicable TMP
label | Inspection / Test Method: Document review & Site inspection
label | Record of conformity: Approved TMP
label | *HP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 1.4 - Survey set out works
label | Frequency: Prior to Commencing Work
label | Acceptance Criteria: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and set out activity. IFC and latest available revision used.
label | Reference Documents: IFC Project Drawings
label | Inspection / Test Method: Site inspection
label | Record of conformity: Survey records & marks on the ground. This ITP Signed off.
label | *HP
label | Responsibility: Site Engineer / Surveyor / Superintendent
date | Date Completed:
section | 2 - Material Conformance
checkpoint | 2.1 - Water Pipes, Valves and fittings
label | Frequency: Every batch of new material
label | Acceptance Criteria: Fire Service pipe material to be free from defects and meet the following schedules
label | ○ As per B.6.1 Fire Pipe Schedule and B.6.2 Valves and Fittings Schedule.
label | Reference Documents: Specification: EW-FP-SPC-0000001(C.)
label | ○ B.6
label | ○ C.6.9
label | ○ C.6.10
label | Inspection / Test Method: Verify
label | Record of conformity: ITP signed, Receival Inspection Checklist
label | IP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 2.2 - Correct embedment / backfill materials onsite
label | Frequency: Every batch of new material
label | Acceptance Criteria: Inspect bedding and backfill material to ensure suitability. If watermain is to be protected, use stabilised sand or concrete encasement
label | Reference Documents: Specification: EW-FP-SPC-0000001(C.)
label | ○ C.6.10.2,3,4,6,
label | ○ Drawing(s): EW-FP-DRW-00-0001
label | Inspection / Test Method: Verify
label | Record of conformity: ITP signed, Receival Inspection Checklist
label | IP
label | Responsibility: Site Engineer
date | Date Completed:
section | 3 - Excavation of trenches
checkpoint | 3.1 - Trenching details
label | Frequency: Ongoing
label | Acceptance Criteria: Trench's to be excavated to conform with IFC drawing details.
label | ○ Ensure trench width and depth are within tolerance
label | ○ Ensure trench foundation & wall firm, stiff & suitable
label | ○ Provide minimum clear space of 100mm between pipe and trench face
label | Reference Documents: Specification: EW-FP-SPC-0000001(C.)
label | ○ C.6.10.3
label | ○ Drawing(s): EW-FP-DRW-00-0001
label | Inspection / Test Method: Verify
label | Record of conformity: ITP signed
label | IP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 3.2 - Benching & shielding (where required)
label | Frequency: As Required
label | Acceptance Criteria: Trench support is required where the trench is more than 1.5 metres, unless the trench has been assessed as safe by a geotechnical engineer and written confirmation provided as such.
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: ITP signed
label | *HP
label | Responsibility: Site Engineer
date | Date Completed:
section | 4 - Watermain Installation
checkpoint | 4.01 - Bedding
label | Frequency: Each Lot
label | Acceptance Criteria: Bedding materials : 7mm single sized aggregate used
label | ○ Bedding Depth: 75-100mm COMPACTED DEPTH, BEDDING MATERIAL INCREASED TO 150mm WHER EEXCAVATING IN ROCK
label | Reference Documents: Specification: EW-FP-SPC-0000001(C.)
label | ○ C.6.10.5
label | ○ Drawing(s): EW-FP-DRW-00-0001
label | Inspection / Test Method: Verify
label | Record of conformity: ITP signed
label | IP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 4.02 - Pipe Joints
label | Frequency: Each Lot
label | Acceptance Criteria: Ensure pipe joint deflection is acceptable, as per drawings and product specifications. Ensure all Butt Fusion Welds are completed are correctly (butt fusion weld indicator showing).
label | ○ Prior to completing any works on existing infrastructure, ensure line is isolated.
label | Reference Documents: Specification: EW-FP-SPC-0000001(C.)
label | ○ B.6.1
label | Inspection / Test Method: Verify
label | Record of conformity: ITP signed, photo of each joint
label | IP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 4.03 - Pipe Embedment
label | Frequency: Each Lot
label | Acceptance Criteria: Horizontal alignment of a completed length of pipework is laid beneath areas of normal usage but where passing under areas of vehicular traffic must be subject to a minimum cover of 750mm or as otherwise directed
label | ○ A minimum cover of 450mm and 750 mm for pipework must be provided under unpaved and paved area respectively
label | ○ 7mm Aggreate in Embedment layer.
label | Reference Documents: Specification: EW-FP-SPC-0000001(C.)
label | ○ C.6.10.1,3
label | ○ Drawing(s): EW-FP-DRW-00-0001
label | Inspection / Test Method: Verify
label | Record of conformity: ITP signed
label | IP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 4.04 - Survey pickup of Services
label | Frequency: Each Lot prior to Backfill
label | Acceptance Criteria: Survey pick for As-built to be completed prior to Backfill
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: ITP Signed
label | *HP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 4.05 - Pipe Backfill Material
label | Frequency: Each Lot
label | Acceptance Criteria: A compacted sand bed of 75mm minimum thickness over earth or 150mm minimum thickness over rock must be provided. The pipework must be topped with 100mm minimum thickness of sand compacted carefully by watering and hard or light vibratory tamping to a dense tight state.
label | Reference Documents: Specification: EW-FP-SPC-0000001(C.)
label | ○ C.6.10.2,3,4,6,
label | ○ Drawing(s): EW-FP-DRW-00-0001
label | Inspection / Test Method: Verify
label | Record of conformity: ITP signed
label | IP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 4.06 - Pipe Backfill Compaction
label | Frequency: Subbase one test per 1000 sq.m
label | Acceptance Criteria: Backfill compacted in <= 250mm loose layers to achieve minimum density R_D 95% (MDDR = 95%).
label | Reference Documents: Drawing(s): EW-FP-DRW-00-0001
label | Inspection / Test Method: Test report
label | Record of conformity: ITP signed
label | TP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 4.07 - Marking Tape
label | Frequency: Each Lot
label | Acceptance Criteria: Tape widths must be as recommended by the manufacturer for the size of pipe to be covered but must be not less than 75mm wide for pipework up to 50mm dia.
label | ○ DETECTABLE IDENTIFICATION -TAPE-300mm MINIMUM ABOVE PIPE.
label | Reference Documents: Drawing(s): EW-FP-DRW-00-0001
label | Inspection / Test Method: Verify
label | Record of conformity: ITP signed
label | IP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 4.08 - Valves
label | Frequency: Each Lot
label | Acceptance Criteria: Install valves in the vertical position and provide surface fittings and valve markings in accordance with Drawings
label | ○ Inspect the valve for damage. Repair any damage to the external coating in accordance with the manufacturer’s instructions
label | ○ Check the valve and off-take clamp flanges to ensure the sleeves fit in the bolt holes. Trim insulation sleeves such that they join inside one flange, and not at the flange joint.
label | ○ Ø150 U.P.V.C. (AS1477 CLASS 4.5) PIPE SLEEVE to be installed
label | Reference Documents: Drawing(s): EW-FP-DRW-00-0001, SLUICE VALVE DETAIL
label | Inspection / Test Method: Verify
label | Record of conformity: ITP signed
label | WP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 4.9 - Hydrants and Valve Covers
label | Frequency: Each Lot
label | Acceptance Criteria: Ø100 HOT DIPPED GALVANIZED PIPE RISER (SINGLE PIPE RISER FROM P.E. PIPE.) to be installed.
label | ○ 600mm x 600mm x 250mm CONCRETE PAD TO STABILIZE HYDRANT RISER. FINISH NOMINAL 25m ABOVE GROUND. Ø200 CAST IRON INSPECTION SHAFT COVER (Valves)
label | ○ Refer to Table B.6.1
label | Reference Documents: Specification: EW-FP-SPC-0000001(C.)
label | ○ C.6.10.2,3,4,6,
label | ○ Drawing(s): EW-FP-DRW-00-0001, EW-FP-DRW-20-0004, EW-FP-DRW-10-0001
label | Inspection / Test Method: Verify
label | Record of conformity: ITP signed
label | WP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 4.10 - Thrust blocks
label | Frequency: Where required
label | Acceptance Criteria: Thrust blocks must be installed in systems with unrestrained anchors.
label | Reference Documents: Specification: EW-FP-SPC-0000001(C.)
label | ○ C.6.10.2,3,4,6,
label | ○ Drawing(s): EW-FP-DRW-00-0001
label | Inspection / Test Method: Verify
label | Record of conformity: ITP signed
label | WP
label | Responsibility: Site Engineer
date | Date Completed:
section | 5 - Testing
checkpoint | 5.1 - Compaction Testing (when applicable)
label | Frequency: Completion of pipe installation & fittings.
label | Acceptance Criteria: Undertake field density testing of trench fill in accordance with the methods specified within Specifcation and Drawings.
label | ○ Testing not required where stablised sand is substitued for rock.
label | Reference Documents: Specification: EW-FP-SPC-0000001(C.)
label | Inspection / Test Method: Compaction Testing
label | Record of conformity: ITP signed, Test Records
label | WP
label | Responsibility: Site Engineer / Superintendent
date | Date Completed:
checkpoint | 5.2 - Pipeline Pressure Testing
label | Frequency: Completion of pipe installation & fittings.
label | Acceptance Criteria: Undertake pressure testing of pipelines in accordance with the methods specified in Specification: EW-FP-SPC-0000001(C.).
label | ○ Refer to Table B.6.1 - Fire Pipe Schedule and AS2419 - Section 7 for test requirements.
label | Reference Documents: Specification: EW-FP-SPC-0000001(C.), AS2419 - Section 7
label | Inspection / Test Method: Pressure Testing
label | Record of conformity: ITP signed, Test Records
label | WP
label | Responsibility: Site Engineer / Superintendent
date | Date Completed:
section | 6 - Completion
checkpoint | 6.1 - As constructed drawings
label | Frequency: Each Lot
label | Acceptance Criteria: Ensure all conduit deviations are captured on redline drawings for updating the IFC Drawings, and providing asbuilt data.
label | Reference Documents: Drawing(s):
label | ○ EW-FP-DRW-00-0001
label | ○ EW-FP-DRW-20-0004
label | ○ EW-FP-DRW-10-0001
label | ○ EW-FP-DRW-20-0001
label | Inspection / Test Method: Verify
label | Record of conformity: ITP signed
label | IP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
date | Date:
signoff | Sign ITP
checklist | GT4-ITP-020 - Sewer Rising Main | itp |  |  |  | Yes | GT4-ITP-020 - Sewer Rising Main
section | 1 - Preliminary Works
checkpoint | 1.1 - Check that current revision drawings are being used
label | Frequency: Prior to Commencing Work
label | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
label | Reference Documents: IFC Project Drawings/ Drawing Register
label | Inspection / Test Method: Document review
label | Record of conformity: Latest revision IFC drawings
label | *WP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 1.2 - Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place
label | Frequency: Prior to Commencing
label | Acceptance Criteria: All environmental measures to be implemented as per current CEMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
label | Reference Documents: CEMP, Site induction
label | Inspection / Test Method: Document review & Site inspection
label | Record of conformity: ITP signed
label | *WP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 1.3 - Traffic Management (When required)
label | Frequency: Prior to Commencing Work
label | Acceptance Criteria: Approved TMP and WASIN (where required)
label | Reference Documents: Applicable TMP
label | Inspection / Test Method: Document review & Site inspection
label | Record of conformity: Approved TMP
label | *HP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 1.4 - Survey set out works
label | Frequency: Prior to Commencing Work
label | Acceptance Criteria: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and set out activity. IFC and latest available revision used.
label | Reference Documents: IFC Project Drawings
label | Inspection / Test Method: Site inspection
label | Record of conformity: Survey records & marks on the ground. This ITP Signed off.
label | HP
label | Responsibility: Site Engineer / Surveyor / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Material Conformance
checkpoint | 2.1 - Water Pipes and fittings
label | Frequency: Every batch of new material
label | Acceptance Criteria: Sewer pipe material to be free from defects and be sized to the following:
label | ○ EW-CE-DRW-600-002- Schedule 1: New Pipe WSA-02-2014-3.1
label | Reference Documents:
label | ○ WSA-02-2014-3.1
label | ○ WSA PS 207
label | ○ WSA PS-230
label | Drawing(s):
label | ○ HB19198-C1271
label | ○ HB19198-C1272
label | ○ HB19198-C1273
label | ○ EW-CE-DRW-600-001
label | Inspection / Test Method: Verify
label | Record of conformity: ITP signed, Receival Inspection Checklist
label | IP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 2.2 - Correct embedment / backfill materials onsite
label | Frequency: Every batch of new material
label | Acceptance Criteria: Inspect bedding and backfill material to ensure suitability. If watermain is to be protected, use stabilised sand or concrete encasement
label | ○ TYPE R - REFER TO TRENCH DETAIL.
label | Reference Documents: MRWA-W-201 to 203, EW-CE-DRW-600-006
label | Inspection / Test Method: Verify
label | Record of conformity: ITP signed, Receival Inspection Checklist
label | IP
label | Responsibility: Site Engineer
date | Date Completed:
section | 3 - Excavation of trenches
checkpoint | 3.1 - Trenching details
label | Frequency: Ongoing
label | Acceptance Criteria: Trench's to be excavated to conform with IFC drawing details.
label | ○ Sides of excavation to be kept vertical to at least 150mm above the pipe.
label | ○ Ensure trench width and depth are within tolerance
label | ○ Ensure trench foundation & wall firm, stiff & suitable
label | Reference Documents: Drawing(s): MRWA-W-2023, EW-CE-DRW-600-006
label | Inspection / Test Method: Verify
label | Record of conformity: ITP signed
label | IP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 3.2 - Benching & shielding (where required)
label | Frequency: As Required
label | Acceptance Criteria: Trench support is required where the trench is more than 1.5 metres, unless the trench has been assessed as safe by a geotechnical engineer and written confirmation provided as such.
label | Reference Documents: Work Procedures
label | Inspection / Test Method: Verify
label | Record of conformity: ITP signed
label | *HP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 3.3 - Capping and grouting of abandoned mains
label | Frequency: Before bedding material is installed
label | Acceptance Criteria: Where it is necessary to fill a redundant pipeline, low strength grout (<5 MPa), similar material or sand shall be used.
label | Reference Documents: Drawing(s): WSA 03-2011 3.1, EW-CE-DRW-600-004
label | Inspection / Test Method: Verify
label | Record of conformity: Release of Hold Point
label | WP
label | Responsibility: Site Engineer/Superindendant
date | Date Completed:
section | 4 - Watermain Installation
checkpoint | 4.1 - Bedding
label | Frequency: Each Lot
label | Acceptance Criteria: Bedding materials : 5 or 7mm single sized aggregate used
label | ○ Bedding depth: 75mm>x>150mm for 150dia pipe
label | Reference Documents: AS2053.1:2001, MRWA-W-201, EW-CE-DRW-600-006
label | Inspection / Test Method: Verify
label | Record of conformity: ITP signed
label | IP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 4.2 - Pipe Joints
label | Frequency: Each Lot
label | Acceptance Criteria: Ensure pipe joint deflection is acceptable, as per drawings and product specifications.
label | ○ ALL JOINTS SHALL BE BUTT WELDED. WHERE BUTT WELDING IS NOT POSSIBLE MECHANICAL
label | ○ JOINTS SHALL BE USED. ELECTROFUSION SHALL NOT BE USED UNLESS APPROVED PRIOR BY THE SUPERINTENDENT.
label | Reference Documents: MRWA-W-103
label | ○ Drawing(s): EW-CE-DRW-600-001
label | Inspection / Test Method: Verify
label | Record of conformity: ITP signed, photo of each joint
label | IP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 4.3 - Pipe Embedment
label | Frequency: Each Lot
label | Acceptance Criteria: Embedment Type R including 5/7mm single sized aggregate.
label | ○ Min Overlay: 300mm (Compaction with ride on equipment)
label | ○ Side Support: 100mm>x>350mm
label | ○ Embedment placed under haunches by shovel and worked around pipe to ensure all voids at haunches are filled
label | Reference Documents: Table 201-D, MRWA-W-201, MRWA-W-202, EW-CE-DRW-600-006
label | Inspection / Test Method: Verify
label | Record of conformity: ITP signed
label | IP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 4.4 - Pipe Backfill Material
label | Frequency: Each Lot
label | Acceptance Criteria: Backfill material (Type R):
label | ○ Class 2 FCR (depth <1.5m)
label | ○ Class 4 FCR (depth >1.5m)
label | Reference Documents: MRWA-W-201
label | ○ Drawing(s): EW-CE-DRW-600-006
label | Inspection / Test Method: Verify
label | Record of conformity: ITP signed
label | IP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 4.5 - Pipe Backfill Compaction
label | Frequency: Each Lot
label | Acceptance Criteria: Backfill compacted in <= 200mm loose layers to achieve minimum density R_D 95% (MDDR = 95%). Avoid compaction within 500mm of top of pipe
label | ○ Trafficable Areas: R_D 95% (MDDR = 95%)
label | ○ Non-Trafficable Areas: Below 600mm = 90% MDDR, Above 600mm = 95% MDDR
label | Reference Documents: MRWA-W-201, MRWA Specification No. 04-03.
label | Inspection / Test Method: Test report
label | Record of conformity: ITP signed
label | TP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 4.6 - Marking Tape
label | Frequency: Each Lot
label | Acceptance Criteria: Marking tape to be laid along the route of the alignment ontop of first backfill layer
label | Reference Documents: MRWA-W-202
label | Inspection / Test Method: Verify
label | Record of conformity: ITP signed
label | IP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 4.7 - Valves
label | Frequency: Each Lot
label | Acceptance Criteria: Install valves in the vertical position and provide surface fittings and valve markings in accordance with Drawings
label | ○ Inspect the valve for damage. Repair any damage to the external coating in accordance with the manufacturer’s instructions
label | ○ Check the valve and off-take clamp flanges to ensure the sleeves fit in the bolt holes. Trim insulation sleeves such that they join inside one flange, and not at the flange joint.
label | ○ Lid on valve to be cenrally placed
label | Reference Documents: WSA 03-2011 3.1, MRWA-W-300, MRWA-W-301 and MRWA-W-302, EW-CE-DRW-600-004
label | Inspection / Test Method: Verify
label | Record of conformity: ITP signed
label | *HP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 4.9 - Scour/Pump Out Points
label | Frequency: Each Lot
label | Acceptance Criteria: DN100 SCOUR/PUMP OUT POINT IN A 1200 CONCRETE MH PIT to be installed where denoted on the drawings.
label | ○ SEWER SCOUR OUTLETS TO BE IN ACCORDANCE WITH STANDARD DRAWINGS SPS-1602 AND SPS-1603
label | Reference Documents: EW-CE-DRW-600-004
label | Inspection / Test Method: Verify
label | Record of conformity: ITP signed
label | *HP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 4.10 - Thrust blocks
label | Frequency: Where required
label | Acceptance Criteria: CONNECTION TO THE EXISTING RISING MAIN MUST BE ANCHORED TO PREVENT MOVEMENT CAUSED BY THRUST IN ACCORDANCE WITH MRWA-W-205A. THRUST BLOCK AREA = 0.89m2
label | Reference Documents: MRWA-W-205a, EW-CE-DRW-600-001
label | Inspection / Test Method: Verify
label | Record of conformity: ITP signed
label | WP
label | Responsibility: Site Engineer
date | Date Completed:
section | 5 - Testing
checkpoint | 5.1 - Compaction Testing (when applicable)
label | Frequency: Completion of pipe installation & fittings.
label | Acceptance Criteria: Undertake field density testing of trench fill in accordance with the methods specified in WSA 02 - 2014-3.1
label | Reference Documents: MRWA Backfill Spec 04-03.2, EW-CE-DRW-600-006
label | Inspection / Test Method: Compaction Testing
label | Record of conformity: Test Report
label | WP
label | Responsibility: FH Engineer / Superintendent
date | Date Completed:
checkpoint | 5.2 - Pipeline Pressure Testing
label | Frequency: Completion of pipe installation & fittings.
label | Acceptance Criteria: Undertake pressure testing of pipelines in accordance with the methods specified in WSA 02 - 2014-3.1 & WSA 03 - 2011-3.1.
label | ○ Gravity sewer to be tested for 28 Kpa for minimum 3 minutes and sewer rising main to be tested at 31m 1000 Kpa for minimum 2 hours.
label | Reference Documents: WSA 02 - 2014-3.1, WSA 03 - 2011-3.1, EW-CE-DRW-600-001
label | Inspection / Test Method: Pressure Testing
label | Record of conformity: Completed CL-003- Pressure Testing Record & CL-003(A, B or C) -Pressure Testing
label | HP
label | Responsibility: FH Engineer / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 6 - Completion
checkpoint | 6.1 - As constructed drawings
label | Frequency: Each Lot
label | Acceptance Criteria: Ensure all conduit deviations are captured on redline drawings for updating the IFC Drawings, and providing asbuilt data for AutoCAD
label | Reference Documents: EW-CE-DRW-600-004
label | Inspection / Test Method: Verify
label | Record of conformity: ITP signed
label | IP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
date | Date:
signoff | Sign ITP