## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | BOTTOM SHEET - B1.001 - B1.143
section | Material Inspection
checkpoint | Panel: Metecnospan 80mm roof panel
checkpoint | Internal liner colour: Surf Mist
checkpoint | External liner colour : Surf Mist
checkpoint | Trifixx fixings 14 x 150mm - bonded washer
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Metecno Spec to SHS steel member
checkpoint | Panels located correctly
checkpoint | Fixings as per Metecno Spec
checkpoint | Gun grade Butyl sealant to underside lap of panel 6mm
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | 2ND SHEET - B2.001 - B2.143
section | Material Inspection
checkpoint | Panel: Metecnospan 80mm roof panel
checkpoint | Internal liner colour: Surf Mist
checkpoint | External liner colour : Surf Mist
checkpoint | Trifixx fixings 14 x 150mm - bonded washer
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Metecno Spec to SHS steel member
checkpoint | Panels located correctly
checkpoint | Fixings as per Metecno Spec
checkpoint | Gun grade Butyl sealant to underside lap of panel 6mm
checkpoint | Secure lap packers installed correctly to purlins
checkpoint | Secure lap sealing strip installed with 14-20 tek screws to lower roof sheet
checkpoint | 11*25 hex head screwed from top sheet to bottom sheet
checkpoint | Roof sheet screwed as per Metecnospan spec
checkpoint | Roof clean of swarf & rubbish
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | 3RD SHEET - B3.001 - B3.143
section | Material Inspection
checkpoint | Panel: Metecnospan 80mm roof panel
checkpoint | Internal liner colour: Surf Mist
checkpoint | External liner colour : Surf Mist
checkpoint | Trifixx fixings 14 x 150mm - bonded washer
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Metecno Spec to SHS steel member
checkpoint | Panels located correctly
checkpoint | Fixings as per Metecno Spec
checkpoint | Gun grade Butyl sealant to underside lap of panel 6mm
checkpoint | Secure lap packers installed correctly to purlins
checkpoint | Secure lap sealing strip installed with 14-20 tek screws to lower roof sheet
checkpoint | Roof sheet screwed as per Metecnospan spec
checkpoint | Roof clean of swarf & rubbish
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | 4TH SHEET - B4.001 - B4.143
section | Material Inspection
checkpoint | Panel: Metecnospan 80mm roof panel
checkpoint | Internal liner colour: Surf Mist
checkpoint | External liner colour : Surf Mist
checkpoint | Trifixx fixings 14 x 150mm - bonded washer
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Metecno Spec to SHS steel member
checkpoint | Panels located correctly
checkpoint | Fixings as per Metecno Spec
checkpoint | Gun grade Butyl sealant to underside lap of panel 6mm
checkpoint | Secure lap packers installed correctly to purlins
checkpoint | Secure lap sealing strip installed with 14-20 tek screws to lower roof sheet
checkpoint | 11*25 hex head screwed from top sheet to bottom sheet
checkpoint | Roof sheet screwed as per Metecnospan spec
checkpoint | Roof clean of swarf & rubbish
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | 5TH SHEET - B5.001 - B5.143
section | Material Inspection
checkpoint | Panel: Metecnospan 80mm roof panel
checkpoint | Internal liner colour: Surf Mist
checkpoint | External liner colour : Surf Mist
checkpoint | Trifixx fixings 14 x 150mm - bonded washer
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Metecno Spec to SHS steel member
checkpoint | Panels located correctly
checkpoint | Fixings as per Metecno Spec
checkpoint | Gun grade Butyl sealant to underside lap of panel 6mm
checkpoint | Secure lap packers installed correctly to purlins
checkpoint | Secure lap sealing strip installed with 14-20 tek screws to lower roof sheet
checkpoint | 11*25 hex head screwed from top sheet to bottom sheet
checkpoint | Roof sheet screwed as per Metecnospan spec
checkpoint | Roof clean of swarf & rubbish
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | BOTTOM SHEET - C1.001 - C1.143
section | Material Inspection
checkpoint | Panel: Metecnospan 80mm roof panel
checkpoint | Internal liner colour: Surf Mist
checkpoint | External liner colour : Surf Mist
checkpoint | Trifixx fixings 14 x 150mm - bonded washer
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Metecno Spec to SHS steel member
checkpoint | Panels located correctly
checkpoint | Fixings as per Metecno Spec
checkpoint | Gun grade Butyl sealant to underside lap of panel 6mm
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | 2ND SHEET - C2.001 - C2.143
section | Material Inspection
checkpoint | Panel: Metecnospan 80mm roof panel
checkpoint | Internal liner colour: Surf Mist
checkpoint | External liner colour : Surf Mist
checkpoint | Trifixx fixings 14 x 150mm - bonded washer
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Metecno Spec to SHS steel member
checkpoint | Panels located correctly
checkpoint | Fixings as per Metecno Spec
checkpoint | Gun grade Butyl sealant to underside lap of panel 6mm
checkpoint | Secure lap packers installed correctly to purlins
checkpoint | Secure lap sealing strip installed with 14-20 tek screws to lower roof sheet
checkpoint | 11*25 hex head screwed from top sheet to bottom sheet
checkpoint | Roof sheet screwed as per Metecnospan spec
checkpoint | Roof clean of swarf & rubbish
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | 3RD SHEET - C3.001 - C3.143
section | Material Inspection
checkpoint | Panel: Metecnospan 80mm roof panel
checkpoint | Internal liner colour: Surf Mist
checkpoint | External liner colour : Surf Mist
checkpoint | Trifixx fixings 14 x 150mm - bonded washer
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Metecno Spec to SHS steel member
checkpoint | Panels located correctly
checkpoint | Fixings as per Metecno Spec
checkpoint | Gun grade Butyl sealant to underside lap of panel 6mm
checkpoint | Secure lap packers installed correctly to purlins
checkpoint | Secure lap sealing strip installed with 14-20 tek screws to lower roof sheet
checkpoint | Roof sheet screwed as per Metecnospan spec
checkpoint | Roof clean of swarf & rubbish
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | 4TH SHEET - C4.001 - C4.143
section | Material Inspection
checkpoint | Panel: Metecnospan 80mm roof panel
checkpoint | Internal liner colour: Surf Mist
checkpoint | External liner colour : Surf Mist
checkpoint | Trifixx fixings 14 x 150mm - bonded washer
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Metecno Spec to SHS steel member
checkpoint | Panels located correctly
checkpoint | Fixings as per Metecno Spec
checkpoint | Gun grade Butyl sealant to underside lap of panel 6mm
checkpoint | Secure lap packers installed correctly to purlins
checkpoint | Secure lap sealing strip installed with 14-20 tek screws to lower roof sheet
checkpoint | 11*25 hex head screwed from top sheet to bottom sheet
checkpoint | Roof sheet screwed as per Metecnospan spec
checkpoint | Roof clean of swarf & rubbish
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | 5TH SHEET - C5.001 - C5.143
section | Material Inspection
checkpoint | Panel: Metecnospan 80mm roof panel
checkpoint | Internal liner colour: Surf Mist
checkpoint | External liner colour : Surf Mist
checkpoint | Trifixx fixings 14 x 150mm - bonded washer
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Metecno Spec to SHS steel member
checkpoint | Panels located correctly
checkpoint | Fixings as per Metecno Spec
checkpoint | Gun grade Butyl sealant to underside lap of panel 6mm
checkpoint | Secure lap packers installed correctly to purlins
checkpoint | Secure lap sealing strip installed with 14-20 tek screws to lower roof sheet
checkpoint | 11*25 hex head screwed from top sheet to bottom sheet
checkpoint | Roof sheet screwed as per Metecnospan spec
checkpoint | Roof clean of swarf & rubbish
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | BOTTOM SHEET - D1.001 - D1.143
section | Material Inspection
checkpoint | Panel: Metecnospan 80mm roof panel
checkpoint | Internal liner colour: Surf Mist
checkpoint | External liner colour : Surf Mist
checkpoint | Trifixx fixings 14 x 150mm - bonded washer
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Metecno Spec to SHS steel member
checkpoint | Panels located correctly
checkpoint | Fixings as per Metecno Spec
checkpoint | Gun grade Butyl sealant to underside lap of panel 6mm
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | 2ND SHEET - D2.001 - D2.143
section | Material Inspection
checkpoint | Panel: Metecnospan 80mm roof panel
checkpoint | Internal liner colour: Surf Mist
checkpoint | External liner colour : Surf Mist
checkpoint | Trifixx fixings 14 x 150mm - bonded washer
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Metecno Spec to SHS steel member
checkpoint | Panels located correctly
checkpoint | Fixings as per Metecno Spec
checkpoint | Gun grade Butyl sealant to underside lap of panel 6mm
checkpoint | Secure lap packers installed correctly to purlins
checkpoint | Secure lap sealing strip installed with 14-20 tek screws to lower roof sheet
checkpoint | 11*25 hex head screwed from top sheet to bottom sheet
checkpoint | Roof sheet screwed as per Metecnospan spec
checkpoint | Roof clean of swarf & rubbish
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | 3RD SHEET - D3.001 - D3.143
section | Material Inspection
checkpoint | Panel: Metecnospan 80mm roof panel
checkpoint | Internal liner colour: Surf Mist
checkpoint | External liner colour : Surf Mist
checkpoint | Trifixx fixings 14 x 150mm - bonded washer
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Metecno Spec to SHS steel member
checkpoint | Panels located correctly
checkpoint | Fixings as per Metecno Spec
checkpoint | Gun grade Butyl sealant to underside lap of panel 6mm
checkpoint | Secure lap packers installed correctly to purlins
checkpoint | Secure lap sealing strip installed with 14-20 tek screws to lower roof sheet
checkpoint | Roof sheet screwed as per Metecnospan spec
checkpoint | Roof clean of swarf & rubbish
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | 4TH SHEET - D4.001 - D4.143
section | Material Inspection
checkpoint | Panel: Metecnospan 80mm roof panel
checkpoint | Internal liner colour: Surf Mist
checkpoint | External liner colour : Surf Mist
checkpoint | Trifixx fixings 14 x 150mm - bonded washer
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Metecno Spec to SHS steel member
checkpoint | Panels located correctly
checkpoint | Fixings as per Metecno Spec
checkpoint | Gun grade Butyl sealant to underside lap of panel 6mm
checkpoint | Secure lap packers installed correctly to purlins
checkpoint | Secure lap sealing strip installed with 14-20 tek screws to lower roof sheet
checkpoint | 11*25 hex head screwed from top sheet to bottom sheet
checkpoint | Roof sheet screwed as per Metecnospan spec
checkpoint | Roof clean of swarf & rubbish
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | 5TH SHEET - D5.001 - D5.143
section | Material Inspection
checkpoint | Panel: Metecnospan 80mm roof panel
checkpoint | Internal liner colour: Surf Mist
checkpoint | External liner colour : Surf Mist
checkpoint | Trifixx fixings 14 x 150mm - bonded washer
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Metecno Spec to SHS steel member
checkpoint | Panels located correctly
checkpoint | Fixings as per Metecno Spec
checkpoint | Gun grade Butyl sealant to underside lap of panel 6mm
checkpoint | Secure lap packers installed correctly to purlins
checkpoint | Secure lap sealing strip installed with 14-20 tek screws to lower roof sheet
checkpoint | 11*25 hex head screwed from top sheet to bottom sheet
checkpoint | Roof sheet screwed as per Metecnospan spec
checkpoint | Roof clean of swarf & rubbish
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative: