## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | ITP - Clearing and Grubbing, Earthworks - Cut, Fill and Subgrade Preparation Rev0 | itp | ITP - Clearing and Grubbing, Earthworks - Cut, Fill and Subgrade Preparation | 943963cb-7509-4a82-8d71-704335607fea
| section | 1 - Preliminary Works
| checkpoint | 1.1 Check for correct documentation
fdccc5e2-ea60-55d3-9c59-a6df0124fc97 | note | FREQUENCY: Prior to commencing any activity
cd736b2d-3317-5146-a91b-f3c3d77c5873 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
4f10ccab-6978-54f1-831e-7774d80ca708 | note | – using Issued for Construction (IFC) drawings
03d3b26a-85a9-52f6-a86d-358b531c4ccf | note | – using the correct and complete set of drawings
134b8bdf-13fb-55e4-854a-888f72a38fdd | note | – all drawings are the latest revision
80b4f315-6537-5113-bda8-845bd273424f | note | REFERENCE DOCUMENTS: IFC drawings and drawing registers
445a0eaa-604c-528c-91b1-8e342410e04b | note | INSPECTION/TEST METHOD: Document Review / Visual inspection
ea066a43-69b0-53cc-8fb2-d5de41a0c3c7 | note | RECORD OF CONFORMITY: This ITP signed
9b194ac7-f53a-59a7-b5cf-b98a72c8986e | note | HP*
e3a74e18-5452-5b2e-bd3c-6e87b6fe5c2c | note | RESPONSIBILITY: Site Engineer
dbc9e1a1-9ecd-57a4-b641-5a729ed93e49 | textbox | DATE:
| checkpoint | 1.2 Implementation of all measures and controls
8cb4784b-da11-582e-8fdb-8c048029f99c | note | FREQUENCY: Prior to commencing any activity
f41fac05-ad3e-52d4-925c-9459e16dfcea | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSMP, EMP, TMP, SWMS & WP. Access and egress inspected and assessed for stability.
49d1a49c-f88b-5ec6-b65f-cc97bcb385cb | note | REFERENCE DOCUMENTS: OHSMP, EMP, TMP, SWMS, WP
7701b14f-8da0-510b-8a15-8b478569af4d | note | INSPECTION/TEST METHOD: Visual Inspection
384c603f-ce68-5cb3-94f6-ef5c57bdcafc | note | RECORD OF CONFORMITY: This ITP signed
0ba0f76f-2854-5474-8071-ff0ffc457524 | note | HP*
9390f666-85ca-5231-a74e-47b98fc0da72 | note | RESPONSIBILITY: Site Engineer
648f40b8-f7e6-50fa-8157-8675c78067cb | textbox | DATE:
| checkpoint | 1.3 Ground Penetration Permit
ba7a25eb-e22f-5ed0-b372-505971ab5bf2 | note | FREQUENCY: Each Lot
30bf951f-ad4a-566c-848a-e1d5759e84bf | note | ACCEPTANCE CRITERIA: A ground penetration permit must be issued prior to excavation commencing.
cc9b0923-f8b7-5393-b655-593aaa47a87e | note | ○ Plant and equipment must be appropriate for the task.
4873d7a5-30c2-56f5-9abd-1182e1c9be77 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation.
7580c5e9-3c9f-5b21-9f75-8bfaffb460f1 | note | REFERENCE DOCUMENTS: Ground Penetration Permit
af546d51-a327-5a51-b926-9b75d9b6d636 | note | INSPECTION/TEST METHOD: Verify
0e0ba816-543d-5a0e-9109-e0190166a22d | note | RECORD OF CONFORMITY: This ITP signed
1515d61f-1a92-572c-9b14-1239293bc4c0 | note | IP
d80b5628-30a8-52c0-8965-8a81ce4e7654 | note | RESPONSIBILITY: Site Engineer
9776fefa-ef8d-5d0b-b067-c752e62f1e10 | textbox | DATE:
| checkpoint | 1.4 Implementation of environmental measures and controls
da62c147-e4c6-509d-b1cb-d20e35894c97 | note | FREQUENCY: Prior to commencing any activity
2b63c2bb-c477-538e-bcd2-5500b08c4968 | note | ACCEPTANCE CRITERIA: EMP meets the requirements of the specification and all controls have been implemented as per approved EMP
8a85b753-b356-57a3-8e4c-265ea728a3b2 | note | REFERENCE DOCUMENTS: Project Spec Cl176.A3, EMP
67462d38-eaa2-59a4-be6a-bce13377ab58 | note | INSPECTION/TEST METHOD: Verify
ee38dd63-cbac-53a9-845c-7ed4b17e55ae | note | RECORD OF CONFORMITY: This ITP signed
fe85515f-f067-58a5-9ac8-ccfabceb611b | note | IP
ce8df7d1-80ac-5a75-a401-bb45347f0bc4 | note | RESPONSIBILITY: Site Engineer
deb18ef2-c3ff-5cb1-aee2-69eafb5c8eb6 | textbox | DATE:
| checkpoint | 1.5 Flora and Fauna
00aa0536-fc20-54f5-83d5-e7831efd15d5 | note | FREQUENCY: Prior to removing vegetation
7794bf30-1614-5dae-9c05-dc0d40126794 | note | ACCEPTANCE CRITERIA: Hold Point
ab587352-4f6c-5cc5-9353-65d0c1fccbf2 | note | ○ Vegetation to be removed clearly marked and agreed. All removal consistent with contract drawings and permits. Shall fence and sign all sites nominated as No-Go Zones.
816b07e9-630a-5938-b799-24116ed2e21e | note | REFERENCE DOCUMENTS: Cl176.I1
5b607667-0caf-54a9-a231-3737c147391f | note | INSPECTION/TEST METHOD: Verify
ad7f6e09-ae44-5028-8a38-6a80c6bcf392 | note | RECORD OF CONFORMITY: This ITP signed
5c868d44-b3f3-58c6-ac2d-04fba90f810f | note | HP
dbd0b93e-ab72-5241-ab3e-890538bc9491 | note | RESPONSIBILITY: Site Engineer / QAV
fc14107b-730a-5c6c-8e40-bb94e1e6a57a | textbox | DATE:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.6 Protection of Existing Vegetation
3ac057a1-0241-553f-8ec4-6fe3ca04cb32 | note | FREQUENCY: Prior to comencement of any work
356d48ec-5c74-53ac-bf05-0f55b69da38a | note | ACCEPTANCE CRITERIA: Prior to the commencement of any work, the Contractor and the Superintendent shall conduct a joint inspection of the site to identify vegetation to be retained and protected.
5c13ac5c-aa1b-5471-9a4e-1ed0443e711a | note | ○ If directed by the Superintendent, existing trees, shrubs, native grasses and groundcovers and other areas of existing vegetation shall be protected by temporary fencing and incorporated into the works by the Contractor.
c2390f8e-11de-52fd-ace9-36bcda486f76 | note | ○ Protective fencing shall consist of, as a minimum, star pickets with three strands of wire and parawebbing.
aaa2202b-ef57-56b1-8c90-6f10754be7f0 | note | REFERENCE DOCUMENTS: EMP Cl201.1
138f9f10-c631-57b1-abb5-e2c3e2df15ad | note | INSPECTION/TEST METHOD: Visual inspection
37bc0212-acdc-530f-8b8d-e482c940cfc5 | note | RECORD OF CONFORMITY: This ITP signed
6c0f5fb0-c1a7-5810-9335-1a93edd2fb42 | note | IP
605a7d2e-8d22-5e84-9f04-6789b1ca5eeb | note | RESPONSIBILITY: Site Engineer / Superintendent
5c5b6e58-55ec-5e62-8e55-421fcfad44ef | textbox | DATE:
| checkpoint | 1.7 Flora and Fauna
7b24c7fe-81bb-5af8-89a6-fb7d142cea85 | note | FREQUENCY: Prior to removal of vegetation
cc6ada77-c137-56fd-b70c-4f2d889a9239 | note | ACCEPTANCE CRITERIA: Hold Point
675c54a0-b659-57ec-87a4-1cd8c390478b | note | ○ Nominated sites of archaelogical and / or heritage significance inspected on-site and clearly identified and protected as No-Go zones
a3d781c4-b87a-5c00-97bd-c01709baa0e1 | note | REFERENCE DOCUMENTS: EMP Cl176.J1
2892b50d-7275-5dc4-a5b8-62bc1b491b1c | note | INSPECTION/TEST METHOD: Verify
38b18232-ba15-52a7-a28c-8bb6e11f7fc4 | note | RECORD OF CONFORMITY: This ITP signed
d072c940-bd49-58d2-8702-a6f83697841b | note | HP
fdcced08-2d92-53ce-a6ef-47da320bdb67 | note | RESPONSIBILITY: Site Engineer / QAV
81b3a405-0cef-5d0e-8ef0-cbec091d96f3 | textbox | DATE:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.8 Authorisation for works
873c437b-9a3b-5752-8952-3d80941b25a2 | note | FREQUENCY: Prior to commencing works
1c42c370-458a-51c4-8efc-3448a80d73ba | note | ACCEPTANCE CRITERIA: Check that all relevant approvals have been granted including verification of the works area
460fa9eb-6774-5efa-ab40-899198eff7c6 | note | ○ Ensure work pack is reviewed & signed
f472f096-e952-5b58-9485-8dc407669924 | note | REFERENCE DOCUMENTS: Work Procedure
93769564-4201-50e1-b2e0-509bf7cb4ade | note | INSPECTION/TEST METHOD: Verify
9774ca58-c9cd-5b66-b8b8-df41d6b32f07 | note | RECORD OF CONFORMITY: This ITP signed
ac512570-db5c-5a79-b085-ddd83fc3b0da | note | HP*
c50b1024-760d-5d5d-913f-38c44dd9b867 | note | RESPONSIBILITY: Site Engineer
b648839c-ad70-5659-9706-93f17cd90aa0 | textbox | DATE:
| checkpoint | 1.9 Utilities
6b8a106a-1257-5345-90b4-4cee24142dc7 | note | FREQUENCY: Prior to commencing works
786f78ee-3088-5275-a508-b7e32593ea93 | note | ACCEPTANCE CRITERIA: DBYD - locate and mark all existing services and confirm clearance from proposed work
9a5bfe87-ceb4-5f62-94e4-b34b1816dc65 | note | REFERENCE DOCUMENTS: DBYD Records, Plan Mark-Ups
d41f4e60-1996-5214-bbac-f261a2f73770 | note | INSPECTION/TEST METHOD: Verify
bbc59a96-2dce-5742-a2bf-798f5630b1a7 | note | RECORD OF CONFORMITY: This ITP signed
86c5e77e-9d1d-50a5-a685-523687e18166 | note | IP
de0aec3e-be7c-519a-8dfe-ab33380a5f86 | note | RESPONSIBILITY: Site Engineer
a157d78b-9d40-5f35-af35-b45970ee52f9 | textbox | DATE:
| checkpoint | 1.10 Traffic Management
4ebef62d-c12e-57d7-9932-2c7fb45dcd95 | note | FREQUENCY: Prior to commencing works
08ce1ea6-8941-5fa2-a6a6-ac23a524cb73 | note | ACCEPTANCE CRITERIA: Consider the requirements for traffic management, ensuring all works comply with required TMS, TMP and TGS.
4033c1d2-c24b-5967-9d70-fc03b79e1a78 | note | REFERENCE DOCUMENTS: TMS
a00a9bf0-2d66-5c4c-8f5d-f22bcf82ae16 | note | INSPECTION/TEST METHOD: Verify
f1afa5ed-429b-5091-b481-efb60be6c5d8 | note | RECORD OF CONFORMITY: This ITP signed
1e05f737-9d7a-5588-a6ef-70d270dbcac2 | note | IP
76f1626f-f917-52d7-8953-9c460e1780be | note | RESPONSIBILITY: Site Engineer
d7fb4042-6270-5f45-b49d-78d4f95465df | textbox | DATE:
| section | 2 - Clear & Grub
| checkpoint | 2.1 Limits of work
b6314a2c-4bc5-5c2f-87a0-d8e688c0596a | note | FREQUENCY: Each Lot
6cabac53-e6df-514b-9928-9fe7e64bfa0b | note | ACCEPTANCE CRITERIA: Limits of clearing and grubbing shall be the whole length between the following chainages:
c5ccc9eb-8a4e-58d1-897c-c87854ab47b1 | note | REFERENCE DOCUMENTS: Cl201.03
399096b5-ce7a-5c5a-a88c-ebc33f0e56bf | note | INSPECTION/TEST METHOD: Visual Inspection
e0df8afb-9c27-5d2b-b610-2767eb9e152d | note | RECORD OF CONFORMITY: This ITP signed
b0b74b9b-8c86-56d8-ad68-843a0482a368 | note | IP
d2373b3c-0976-5cc8-95ed-3898b514511d | note | RESPONSIBILITY: Site Engineer
6b04d0a3-cd8c-529b-9224-9e91994b0e9e | textbox | DATE:
| checkpoint | 2.2 Clear and grub trees and vegetation
5dff701e-6667-5a84-bef3-433e18f9b597 | note | FREQUENCY: Each Lot
8c98a906-4537-5d5b-b831-cb29da422f90 | note | ACCEPTANCE CRITERIA: The area within the specified limits shall be cleared of all vegetation, refuse and obstructions down to natural surface. The Contractor shall not undertake any clearing work or any type of disturbance outside of the specified limits of work unless approved by the Superintendent.
13de8d08-619e-53cf-8f7b-05ed5b6e00c1 | note | REFERENCE DOCUMENTS: Cl201.04
13f6535f-7344-5b18-b2a8-794839f883b1 | note | INSPECTION/TEST METHOD: Visual Inspection
ba199e11-c60e-5cfa-9e00-f8fb933748df | note | RECORD OF CONFORMITY: This ITP signed
c344195a-b2eb-5486-b5af-8341d6788a57 | note | IP
5552b644-449c-53f7-8659-726f8b3482c4 | note | RESPONSIBILITY: Site Engineer
9f20b4be-2df7-50f5-aaba-f539c0bd9567 | textbox | DATE:
| checkpoint | 2.3 Clear and grub trees and vegetation
85eedc2c-fab2-575d-96e8-7cc767367984 | note | FREQUENCY: Each Lot
30da1601-d2d3-53af-8acd-ca8b8927c1cd | note | ACCEPTANCE CRITERIA: In areas where excavation is to occur: all vegetation, refuse and obstructions totally grubbed or grubbed > 0.3m below subgrade and batters (whichever is the lesser treatment)
e3753047-73f0-5ebc-b8e9-7167ed5b34c5 | note | REFERENCE DOCUMENTS: Cl201.05
6bd80dbb-dcb6-5396-b547-67788bb0606d | note | INSPECTION/TEST METHOD: Visual inspection
03c80fad-acb4-5e97-bd48-3eb9a52a71f9 | note | RECORD OF CONFORMITY: This ITP signed
4f40abf2-1335-54ca-a8c7-08aa8259baf5 | note | IP
9d8cd5d0-afb6-5d62-b116-d5744b8a28db | note | RESPONSIBILITY: Site Engineer
173fea29-a748-587e-9656-7942052978d0 | textbox | DATE:
| checkpoint | 2.4 Clear and grub trees and vegetation (embankment areas)
0d16c27f-ac7a-542e-b2ea-da7ce6b834be | note | FREQUENCY: Each Lot
6cc725ed-48dd-59ee-8b1d-aaa21e7380cf | note | ACCEPTANCE CRITERIA: In areas to be covered by embankments < 1.0m in height: all vegetation, refuse and obstructions grubbed > 0.3m below stripped surface OR > 0.6m below subgrade level (whichever is the lesser treatment)
e53ffdfb-07f9-5aef-a202-4b45ad27b197 | note | ○ In areas to be covered by embankments > 1.0m in height: foundations may remian if located or cut off not more than 0.4m above natural surface but not less than 1.0m below subgrade
e72179a3-b039-5380-a5a9-73e3a934cbbd | note | REFERENCE DOCUMENTS: Cl201.05
a075c214-59e2-57c9-9e19-77794886acc1 | note | INSPECTION/TEST METHOD: Visual inspection
a5006997-df38-5108-aaba-5f78068021e4 | note | RECORD OF CONFORMITY: This ITP signed
1036dd82-72f5-5196-bb70-2043c0258081 | note | IP
b845272d-831d-5d65-8e4e-4e4cbb661e80 | note | RESPONSIBILITY: Site Engineer
63fab47b-f928-5882-a955-a5fc3e5220ab | textbox | DATE:
| checkpoint | 2.5 Clear and grub trees and vegetation at culvert sites
35242c67-4036-55b5-a30d-cd21aeb53b05 | note | FREQUENCY: Each Lot
fe8c20a6-8b6b-522e-a15a-dec80028ba01 | note | ACCEPTANCE CRITERIA: Clear and grub trees and stumps within 10m of any proposed bridge or culvert having a waterway area > 6 m2 (unless otherwise shown on drawings)
59fe077b-4a8b-530d-a495-3754cab015f2 | note | REFERENCE DOCUMENTS: Cl201.06
e7421340-ecee-5120-ba40-2982839cb69c | note | INSPECTION/TEST METHOD: Visual inspection
50ab860b-5855-57be-8631-4d11474633de | note | RECORD OF CONFORMITY: This ITP signed
bfaa64c4-fe44-5e82-939e-02fb6b4bf050 | note | IP
13c66985-fa14-58ff-916a-469f06a26f9e | note | RESPONSIBILITY: Site Engineer
f075171d-80aa-51fb-8b8c-2d8614bbf11a | textbox | DATE:
| checkpoint | 2.6 Backfill holes
23a19375-552d-5d77-86ff-fa2ea3248c75 | note | FREQUENCY: After clearing
56045a5b-2f5c-5a36-89be-bb7fb5d52b76 | note | ACCEPTANCE CRITERIA: Any holes produced from grubbing operations have been backfilled with similar material and compacted to the same degree as the surrounding material
2085f60d-7ec6-5f8e-8137-918cf3cf425e | note | REFERENCE DOCUMENTS: Cl201.05
898df5d5-5231-5085-bca0-003e4378a0c2 | note | INSPECTION/TEST METHOD: Verify
73a0a10e-3049-502f-8aa2-c95f69ab832e | note | RECORD OF CONFORMITY: This ITP signed
1c195d66-126c-5e93-a275-7c6bec547aaa | note | TP
10c9cc3a-d0c5-581e-8002-9ff6289c6368 | note | RESPONSIBILITY: Site Engineer
109f9c00-ae43-59a6-b78a-9daee41abcfa | textbox | DATE:
| checkpoint | 2.7 Dispose of Trees and vegetation
52df8325-9f9c-5d5d-98fa-a0f031d86380 | note | FREQUENCY: After clearing
f427cdad-83c7-5e25-be59-735240ffc7ba | note | ACCEPTANCE CRITERIA: Tree trunks and large branches shall be removed from site. Small tree branches, weeds and shrubs shall be disposed of by chipping and mulching.
3f350d13-514e-53af-94b6-f8683dcce207 | note | REFERENCE DOCUMENTS: Cl201.07 (b)
f1405c23-89ce-57d1-8a28-f0887da47e15 | note | INSPECTION/TEST METHOD: Visual inspection
696f622e-b8e0-5245-8a83-13857f126ed1 | note | RECORD OF CONFORMITY: This ITP signed
4471c563-a858-5c0a-ac06-ff9a9c181a97 | note | IP
f83d2827-812d-5dc7-9da8-7480f67c56d2 | note | RESPONSIBILITY: Site Engineer
9991857f-5312-5785-baa9-e8b535f7144e | textbox | DATE:
| checkpoint | 2.8 Damage to Fencing
2f31fb68-ce5f-57b9-94b5-e6fa5a5170a5 | note | FREQUENCY: During Clearing
a740e3c5-1301-587c-811c-f58175b5c242 | note | ACCEPTANCE CRITERIA: Immediately repair any damage to fences to a condition at least equal to that before damage
a82cd98f-5560-57af-b73b-09cd1aeae1d2 | note | REFERENCE DOCUMENTS: Cl201.09
578a0ae7-4303-5eba-834d-71ecbbcdf085 | note | INSPECTION/TEST METHOD: Verify
d58a51f0-6bb8-5f6d-851f-d819d364561f | note | RECORD OF CONFORMITY: This ITP signed
b76d53d7-1b05-5de7-a78c-bb8c89284d69 | note | IP
f0c8c4cf-be2e-5d25-ba0e-70a188fdfdf8 | note | RESPONSIBILITY: Site Engineer
9e9c7568-4771-5747-afdc-70f3d7c9d338 | textbox | DATE:
| section | 3 - Earthworks
| checkpoint | 3.1 Material Categorisation
699d801d-90dc-529f-88b8-6ab7caab586e | note | FREQUENCY: Each Lot
487ee22a-b2bf-5f10-9783-081d0c2a2775 | note | ACCEPTANCE CRITERIA: Hold Point
6ba62c02-8d8b-5dde-ba31-c5fa5ee2c32b | note | ○ Prior to commencing excavation in any area and during excavation work, the contractor and Superintendent shall inspect and agree upon the type / category of material encountered
418153e7-10b2-5346-88ef-a2b59c065ab4 | note | REFERENCE DOCUMENTS: Cl 204.06c
4ee54cce-190f-50fd-9119-b6d51279f662 | note | INSPECTION/TEST METHOD: Verify
16a5f03c-d451-573f-a73e-4d4a6c6c1692 | note | RECORD OF CONFORMITY: This ITP signed
62863ea1-6774-5fd8-830d-2335b2908df2 | note | HP
8c620e1f-008b-5fbd-aed4-bacff4289593 | note | RESPONSIBILITY: Site Engineer / QAV
953ab194-50f5-5b8e-a345-7a67e558a93f | textbox | DATE:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 Stripping of Topsoil
53a99565-e472-529c-b1b9-58698e69e7c5 | note | FREQUENCY: Each Lot
c0ef778e-1708-5fc6-9109-cb6cfaaa6ba7 | note | ACCEPTANCE CRITERIA: Topsoil stripped to full width of the formation and placed in approved stockpile location. Stockpile shaped to shed water and stripped surfaces graded to be self draining. Topsoil shall not be removed from site unless approved by the superintendent.
7895d64a-511f-5fdf-afa8-3aa9b0b86a3a | note | REFERENCE DOCUMENTS: Cl 204.05
3f10d5e2-48ec-5b1c-a036-a678adb8159c | note | INSPECTION/TEST METHOD: Visual Inspection
18ec392d-7d93-514b-b582-32c6689e2eb7 | note | RECORD OF CONFORMITY: This ITP signed
dacbb894-04e1-5d22-9834-e8489ffd6ce7 | note | IP
3a801fa7-3bad-51eb-a026-c54a0fd8186e | note | RESPONSIBILITY: Site Engineer
4a74f564-7f03-58d4-bcc3-5c88fb74c49a | textbox | DATE:
| checkpoint | 3.3 Unsuitable Material
4ff9644f-4925-5100-b394-9d12945218f6 | note | FREQUENCY: Each Lot containing unsuitable material
75b624db-82ec-5ec1-9527-fa06e4da61ae | note | ACCEPTANCE CRITERIA: Hold Point
2b00260c-119a-50e7-bf4e-303c1cd84bd1 | note | ○ For unsuitable material, the proposed in-situ treatment or extent of excavation submitted to the Superintendent for review.
7c9e757b-56ac-582f-8d6d-bcb13d0c87c5 | note | ○ Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Superintendent
1b7c4948-fdf8-5287-a431-7a11c24e5254 | note | REFERENCE DOCUMENTS: Cl 204.04b, Cl 204.07d
b41be65b-4ec2-5399-980f-d45e5d39ab0e | note | INSPECTION/TEST METHOD: Verify
15aca7fb-484d-5e56-9c9d-af963618b3b2 | note | RECORD OF CONFORMITY: This ITP Signed
bb3ccee7-c247-5a3b-a944-5a8ac2dc2be4 | note | HP
59a51adc-b411-55aa-b54e-6ad1920c2d12 | note | RESPONSIBILITY: Site Engineer / QAV
23f0ea18-ea32-5527-ad5a-396306786e41 | textbox | DATE:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 Subgrade Fill Material
f1b013c5-769d-5d6c-83d0-72c6af4ccd64 | note | FREQUENCY: Each Lot
93472f95-73f1-5913-a14d-8c97a0836d22 | note | ACCEPTANCE CRITERIA: Fill material free of topsoil, deleterious and/or perishable matter.
947dec0f-7e35-58e8-ad8e-1906eca1f98b | note | ○ Type A material shall comply with the requirements of Table 204.041
46c18d30-ed86-5af0-9d5c-93b70c242bfd | note | ○ Type B material shall have minimum Assigned CBR of 4% and Assigned swell less than 2.5%. Materials with swell greater than 2.5% can only be used as Type B material if approved by the superintendent.
4cd566ff-57b7-591d-a432-01d34032fd43 | note | ○ Type C material shall be capable of being spread in layers of not more than 500mm
6e06c096-ae95-5316-b4c8-6635b34e715d | note | REFERENCE DOCUMENTS: Cl 204.04, Table 204.041
1e119301-bb37-5f02-aabe-5b09b6079320 | note | INSPECTION/TEST METHOD: Verify
6257571a-d8cb-596b-bc1c-98456bc72e98 | note | RECORD OF CONFORMITY: Test Report
1653374c-8808-54b0-b9e4-7cc3aa650e33 | note | TP
fc7cd6cd-d698-592c-8b5e-7875d90b25b3 | note | RESPONSIBILITY: Site Engineer
420cb92e-f4c4-509d-a183-be3e48fd1dc9 | textbox | DATE:
| checkpoint | 3.5 Treatment of Rock Subgrade
ad0ed8a7-644d-5953-b521-971b98fdde18 | note | FREQUENCY: Each Lot (prior to construction of regulating layer)
fe07b99c-8678-5341-afff-fb2b497aca1f | note | ACCEPTANCE CRITERIA: Hold Point
bfd91a53-de87-5896-8456-461d3396d524 | note | ○ Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
a3a33fcc-c9ea-547b-9c45-a21321b47faf | note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
5e2d43dc-4409-524f-a662-0998eb34f847 | note | REFERENCE DOCUMENTS: Cl 204.06f
1913a606-3526-5165-ba24-bcc2cffe86e4 | note | INSPECTION/TEST METHOD: Visual Inspection
5ae861ce-e4eb-5559-8751-d81bfafa205e | note | RECORD OF CONFORMITY: This ITP signed
4e9270c1-3ebb-5287-ad95-d0acc715a781 | note | HP
596fc743-6d7c-53d3-b863-ab1e2149b2fc | note | RESPONSIBILITY: Site Engineer / QAV
dc528688-4846-59ea-bd63-79111492ea6f | textbox | DATE:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.6 Groundwater
94638dde-6857-5ecb-abe0-ea11adae74f3 | note | FREQUENCY: Each Lot
2cec2dd6-3473-50fa-83a7-0c0b1b285388 | note | ACCEPTANCE CRITERIA: Hold Point
b05cd91d-9244-5f71-9294-b384556b355e | note | ○ Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
0f0d4d4f-6248-5ba9-ade4-206b90c40c67 | note | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater
146a411a-e163-5ef6-bb41-9271606b3c94 | note | REFERENCE DOCUMENTS: Cl 204.06h, EMP
50005083-729e-5cae-a383-b11458462805 | note | INSPECTION/TEST METHOD: Verify
5a16b923-10f3-5525-87d5-bd5d2ede764d | note | RECORD OF CONFORMITY: Water Authorities and Superintendent Approval, This ITP signed
97fbeb41-5609-5fd9-a90a-2d750acc76b8 | note | HP
1c11a3f0-517e-5c6b-ba09-78ff172a7482 | note | RESPONSIBILITY: Site Engineer / QAV
056fa0d9-46b3-5418-88d9-d223549e78f9 | textbox | DATE:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.7 Surface finish of batters
92d36719-550e-5088-9be6-8e8aaf594dd9 | note | FREQUENCY: Each Lot
75c4eacc-8bb0-5372-a582-a7e371275402 | note | ACCEPTANCE CRITERIA: Surface of cut and fill batters to be topsoiled and textured by scarifying or horizontal grooving
746575a3-5b7b-5f11-8630-64253c277be7 | note | REFERENCE DOCUMENTS: Cl 204.06i
b4151043-f8a6-54eb-8b3d-331522316989 | note | INSPECTION/TEST METHOD: Visual Inspection
80a4f871-31ec-533e-8483-bd907a3cae67 | note | RECORD OF CONFORMITY: This ITP signed
d101c915-b8a0-5c36-a0ab-3c3f968d0c3f | note | IP
8b938604-b0a6-5403-8bdd-d00afe6aa3a7 | note | RESPONSIBILITY: Site Engineer
ced4d33a-e540-5cc1-a16a-554c78a35630 | textbox | DATE:
| checkpoint | 3.8 Borrow Excavation
192a513e-091c-526c-afda-8fc850f94c0f | note | FREQUENCY: Each Lot
8c7a0bc6-6ed9-5014-a741-f81909711a03 | note | ACCEPTANCE CRITERIA: Hold Point
cf400097-d1b7-53d1-a451-cd8dbf2eed6b | note | ○ Borrow Excavations within the road reservation are not permitted without prior approval of Superintendent
863c8027-5e6f-5244-a94b-47ef7783f168 | note | REFERENCE DOCUMENTS: Cl 204.09
42b01fab-0105-592b-a71b-1d7c66935b1b | note | INSPECTION/TEST METHOD: Verify
63344397-3ba4-5dd7-8640-20019a375dac | note | RECORD OF CONFORMITY: This ITP Signed, Correspondance with superintendent
eea79759-e595-5ec3-ab62-c6548c9224f8 | note | HP
4b109ad4-c15c-5918-bb24-e71c1bf7e622 | note | RESPONSIBILITY: Site Engineer / Superintendent
da85e588-9118-53f8-888b-0a4797d7b72b | textbox | DATE:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.9 Areas upon which fills are to be constructed
2becb78e-5b8d-526e-b389-d322caf1ec33 | note | FREQUENCY: Each Lot
44f042eb-f6f2-5997-b37e-3b9d22733f37 | note | ACCEPTANCE CRITERIA: Hold Point
4deef030-ed86-5c47-b4ec-283f01bf5245 | note | ○ Areas where fill is to be constructed must be reviewed by the superintendent prior to the placement of any fill in the area
c1fd2b62-683a-532e-b934-882c2eed9f1c | note | REFERENCE DOCUMENTS: Cl 204.10b
20ca6fd3-7c82-5b88-932e-95cc2a12f7f1 | note | INSPECTION/TEST METHOD: Verify
c62158b6-e087-52b2-9b9e-c81f166078f0 | note | RECORD OF CONFORMITY: This ITP Signed
3903bc13-cb0a-569b-9f45-ccfa924eb7f0 | note | HP
1a24bc70-dc4b-510b-901a-d3370c8cca00 | note | RESPONSIBILITY: Site Engineer / QAV
ba758ed7-bb0b-507f-9536-d6fe1e86fb3d | textbox | DATE:
| checkpoint | 3.10 Placing of Fill
7e011582-24f9-5879-8fde-44f7d1f2e743 | note | FREQUENCY: Each Layer
ec8a5973-a4f4-5178-88bd-7ebb4a66d3ee | note | ACCEPTANCE CRITERIA: Fill placed and spread in uniform layers. Each layer keyed into the next with a textured surface. Any rocky material uniformly distributed throughout the layer.
49f110d3-a79b-5b6b-a233-c6c79cd0f9df | note | ○ Compacted layers do not exceed specified maximum thicknesses:
0a2e0785-cc07-550a-a73f-022269b23ac5 | note | ○ Type A: Maximum compacted thickness 200mm (can be used in locations specified for Type B material)
6f462ef1-b53b-532f-94f5-b9896b1d3f79 | note | ○ Type B: Maximum compacted thickness 200mm (can be used in locations specified for Type C material). Where > 25% rock by volume, loose layer thickness may equal 125% of typical maximum particle dimension up to max 500mm. No rocks > 80% of loose thickness of the layer.
3ef28a36-d1b0-5d6b-b394-729d8676b3f9 | note | ○ Type C: Maximum compacted thickness 300mm. Where > 25% rock by volume, loose thickness of each layer may equal the maximum particle dimension of the rock up to max 500mm. Reference table 204.111
770c890d-cb93-54f7-adf2-5211dd6afcf6 | note | REFERENCE DOCUMENTS: Cl 204.10d
b4d77610-47d6-50f1-b96f-7d079986718e | note | INSPECTION/TEST METHOD: Visual Inspection / Measure
36ec0d8b-8f60-573e-9dba-48cc746639d6 | note | RECORD OF CONFORMITY: This ITP signed
50399fd1-042b-5ae6-b3d2-51dd3823660b | note | IP
f5422a15-43e4-516d-af8b-3dae5377c764 | note | RESPONSIBILITY: Site Engineer
c413af09-cc94-55a0-82b8-a2fdd457ad63 | textbox | DATE:
| section | 4 - Testing and Surface Preperation
| checkpoint | 4.1 Test Rolling
64caad0d-d3fd-589d-a132-3b52158de079 | note | FREQUENCY: Each layer
b76e2ba3-d294-5a8d-8830-6bd31b90d235 | note | ACCEPTANCE CRITERIA: Hold Point
e12c3db8-07b0-59f7-bab6-ca5d14b747d4 | note | ○ Areas upon which fills are to be constructed, all layers of fill, material within 150 mm of the cut floor level in cuts, and all stabilisied material shall be test rolled in accordance with Section 173.
7da60ef7-f621-5d69-ae41-79f7114b22a2 | note | REFERENCE DOCUMENTS: Cl 173.03, Cl 204.12
dfa75f2b-119f-5387-ae51-e1230b4d0e7a | note | INSPECTION/TEST METHOD: Visual Inspection
8c10fb00-5413-5734-9893-dbaaa8b28593 | note | RECORD OF CONFORMITY: This ITP signed
75a6a5aa-6393-5388-8148-373c72a67acf | note | HP
ca532b9e-d461-52eb-9b05-8f082e7a3baf | note | RESPONSIBILITY: Site Engineer / QAV
135e15b0-576e-51dd-af95-7ee62d45a6e1 | textbox | DATE:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 Cut and Fill Tolerances
2907638b-ecc9-59a0-a1a4-31ad7fad13a2 | note | FREQUENCY: In accordance with Table 204.031. Lots < 4,000m²
ff06001d-d009-5648-bdf4-60b907825956 | note | ACCEPTANCE CRITERIA: Formation width and alignment: not less than the widths specified or shown on the drawings
49470046-3c63-583e-b419-2f26a35ab4e0 | note | ○ Formation level and shape: Verges match FSL at outer edge of shoulder or pavement (± 50mm from design level)
bb461ede-6bb4-5a68-825c-304c18046894 | note | ○ Boxing width and alignment: not less than specified or design levels & no deviation > 50mm from designed offset from the centreline or design line.
e65bd08b-ce85-5dce-89ec-341e70f930f8 | note | ○ Type A Material: thickness and width not less than specified at any point.
48c6ba5b-1768-57bb-b693-2df320280f38 | note | ○ Type B material (immediately below capping / selected material): +15mm -30mm specified level
e2bc10c7-e053-502f-a1d0-249979e8ab1d | note | ○ Cut floor level (when capping layer required): +15mm -30mm specified level
597cf39d-1010-55fd-b402-6415f664dbfe | note | ○ Cut floor level (no capping layer): same as subgrade tolerance
32c254ef-08f5-5f59-a37e-5b3a79d1400b | note | ○ Subgrade Scale A & B: random levelling Cl204.03(h). No point > 20mm below a 3m straightedge laid in any direction.
e1243f95-aef9-5952-a08d-2b2990f98847 | note | ○ Batter and slope: Not steeper than specified at any cross section.
16ca877b-23bf-5c7a-93a2-9c08127fff77 | note | ○ Batter line: Batter point < 10% of the batter height outside the calculated batter line.
744c9794-031c-5306-96f6-5d2942bd807e | note | ○ Surface Drains: Invert levels and side slopes ±50mm and free from depressions capable of retaining water.
0af165d4-8dfa-5e14-826f-722866145a75 | note | ○ The contractor shall establish a procedure to verify that compacted layers do not exceed the specified thickness. Verification records must provide evidence of measurements taken every three layers.
9b052840-1668-54d5-a20d-ec2e4ca5daa2 | note | REFERENCE DOCUMENTS: Cl 204.03, Table 204.031,
536d3c34-d0d4-572b-8330-66540b63e2d5 | note | INSPECTION/TEST METHOD: Verify
9824b764-be47-5a65-a62b-b64bc500f0dd | note | RECORD OF CONFORMITY: This ITP signed
31f76ea6-d9c2-51a0-96e2-bfa2f9d335bc | note | SCP
d7ccb37e-59b4-54c6-ac09-cd1788876f30 | note | RESPONSIBILITY: Site Engineer
37453b8d-d567-5269-9071-1c63e2379d47 | textbox | DATE:
| checkpoint | 4.3 Subgrade level conformity
c7bdeb4d-85ef-59db-a7d1-403d546683cc | note | FREQUENCY: Each Lot
c51f2d58-316e-5fc9-8fdf-5b89a5a37da7 | note | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
62033d42-1cbe-5f38-84de-8951a4b5125c | note | ○ Level tolerances:
3747dd2e-119c-5be6-ad4e-f187463c413a | note | ○ Scale A - 80 measurements per lot
73424a08-132e-5c39-8630-d2b523753eab | note | • Range = +5, -15mm
e2c87b7a-e5de-5838-b44f-8572a81fb6a3 | note | • Max S = 12 mm
0aff61d7-e440-5173-bcf8-44acaa1ff948 | note | ○ Scale B - 40 measurements per lot
577002ed-a5eb-52a6-9c07-ea29e588135f | note | • Range x = +5, -25mm
08b8e0d4-aaa0-560e-aafe-9b5d6af1b958 | note | • Max S = 15 mm
af6c92e7-b89a-5537-a3b2-e95d3d3453ad | note | REFERENCE DOCUMENTS: Cl 204.03
524dc349-8fcd-57fc-8b56-7583cb8c2da8 | note | INSPECTION/TEST METHOD: Verify
7ab0a58e-a17a-5b3d-80e0-6d36e5d7a538 | note | RECORD OF CONFORMITY: This ITP signed, Survey report
b60cd693-3fc2-58b1-b8ef-8ecf81120002 | note | SCP
1c8594df-5427-5694-8d18-9ce72077e861 | note | RESPONSIBILITY: Site Engineer
51bd29a5-61b9-5e86-a031-3af9d512d6ab | textbox | DATE:
| checkpoint | 4.4 Fill Material Compaction & Moisture Content Requirements
33b50acc-d243-5fc0-aea6-873b6e93e0be | note | FREQUENCY: Each Lot as defined in Table 204.142.
a89e872c-334d-53fe-9935-20729d8ac627 | note | ○ 6 tests per lot.
1ae11869-d267-569a-96e7-c52a7dce009c | note | ○ Small area lots (<500m2) as per Cl173.04d.
57ec7d19-de18-52c7-837d-efc155599c4c | note | ○ 3 test mean lots.
078a99f0-e0ee-5654-a2e6-4c14efac8d87 | note | ○ +2% compaction req.
3f29ce73-3ad9-521a-a23c-92b6ad61730b | note | ACCEPTANCE CRITERIA: Refer to Reference Documents for particular Tolerances, Properties and Testing Scales and subsequent Requirements.
d482de04-2302-501c-90f4-59bb4ef2ce94 | note | ○ Table 204.161 for Project Specific Scales for each applicable Road Name or Area.
6421c379-0e9f-5950-aa16-83d8485dbd94 | note | REFERENCE DOCUMENTS: Cl 204.13, Table 204.131, Table 204.161
6501eb2c-2bd9-5ee0-8e6d-4442ac1b8d0e | note | INSPECTION/TEST METHOD: Verify
dcd3d693-574f-543d-882d-b867ad1b89ef | note | RECORD OF CONFORMITY: This ITP signed
035c931c-2c5b-5790-a9f3-1f53a6871395 | note | TP
5449c765-7d21-5a3d-be84-d60f9687f006 | note | RESPONSIBILITY: Site Engineer
7b733aa1-1009-52fc-aebb-e0d7a102bff0 | textbox | DATE:
| checkpoint | 4.5 Material Properties Testing (Scale B)
45fa9bf9-bfd9-5453-b3e8-86dfed0da24b | note | FREQUENCY: Once per lot or per material change, as per Table 204.141
89c1e723-2296-5cd3-9e2e-9d39f6345f7e | note | ACCEPTANCE CRITERIA: Refer to Reference Documents for particular Frequency of Testing and Material Properties Testing Requirements.
109a857b-8a9d-5d77-9642-9ebf85343ee5 | note | ○ Table 204.161 for Project Specific Scales for each applicable Road Name or Area.
62d3027f-42a1-5f28-a217-ba60065f7dca | note | REFERENCE DOCUMENTS: Cl 204.14, Table 204.041, Table 204.161
8f86093f-68fc-519a-90cd-839a22a37ba7 | note | INSPECTION/TEST METHOD: Verify
f46e6372-d5b8-5aac-819e-f5922983632b | note | RECORD OF CONFORMITY: This ITP signed
5ed65b1b-8e3d-540d-979b-bc4b57662bad | note | TP
56765e94-8438-5d78-b3e5-57c44dbd66f4 | note | RESPONSIBILITY: Site Engineer
9eccc5be-8f24-55da-b4b1-eff326171c91 | textbox | DATE:
| checkpoint | 4.6 Preparation and Maintenance of Final Earthwork Surface and Subgrade
ea140e3f-bc70-5bff-84fa-01e1222c714a | note | FREQUENCY: Each Lot (Final Layer only)
5879d566-c5aa-508f-98e0-ae629114de53 | note | ACCEPTANCE CRITERIA: Smooth, hard, tightly bound surface presented. Free from depressions capable of holding water.
68f27d0a-8393-5ca7-baf1-5373321ce4f6 | note | ○ Material within 150mm of subgrade shall be maintained such that its moisture content is not less than 70% of OMC prior to placement of pavement layer.
5fe3553e-f84f-5690-9485-2c99c21cbc91 | note | REFERENCE DOCUMENTS: Cl 204.15
191de5b5-7b27-59bc-b1ad-a7103e14c827 | note | INSPECTION/TEST METHOD: Visual Inspection
2595c4c0-6a1a-5823-a851-6e446c4df0d2 | note | RECORD OF CONFORMITY: This ITP signed
d44baf71-4ee6-56c5-b5ce-f2b2388f7a04 | note | IP
5954c64f-e85d-5ce9-b0b1-1e150507c681 | note | RESPONSIBILITY: Site Engineer
32073444-01a3-5c81-adbd-8db1abcfb5fb | textbox | DATE:
| checkpoint | Final Inspection
04e3bb66-3f2c-5114-bd7f-429dcc8f8fca | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
8411cb16-4642-5c1d-b799-d2693f032cba | textbox | Print Name:
ef3711a9-74ab-515c-ad86-808a4fdacb85 | textbox | Position:
1bf524b7-1216-581c-b380-ea6504253521 | textbox | Date:
| signoff | Add Signature
| checkpoint-no-value | Table 204.031 Minimum Number of Level Measurements and Tolerances
50af9b7d-296c-5156-b592-aa2e5637cc78 | note | Scale of Surface Level Measurement ¦¦ Minimum Number of Measurements per Lot ¦¦ Tolerance: x̅ Range (mm) ¦¦ Tolerance: Maximum S (mm)
a40ce30d-7247-5dd5-bf88-f95817888174 | note | – – – – – – – – – –
28ececd2-3662-5f41-935b-e403a73bc808 | note | Scale A ¦¦ 80 ¦¦ +5 to -15 ¦¦ 12
8431348b-38a1-580a-a5eb-6341694163bc | note | Scale B ¦¦ 40 ¦¦ +5 to -25 ¦¦ 15
dcd8f0d3-2aa4-5af2-aa7c-5f8b5ceaffc7 | note | – – – – – – – – – –
0af73208-ba00-5271-8b06-73324df57450 | note | Notes:
58a7481d-c698-5789-9649-350d8da898a1 | note | 1. x̅ is the mean value of all level readings taken in the lot
79dfb71c-e20a-5da3-b93d-77020f9db3db | note | 2. S is the standard deviation of all level readings taken in the lot
cbd1f2b1-2cbd-53f2-bb2c-27417c15cd29 | note | 3. A negative value designates a measured departure below the design level and positive value designates a surface level above the design level
| checkpoint-no-value | Table 204.041
836a3d8d-ae50-55d3-9fbf-30453492d0d4 | note | Location and Use of Type A Material ¦¦ Physical Properties: Assigned CBR (min) % (1) ¦¦ Physical Properties: Swell % (1) ¦¦ Physical Properties: Permeability (max) m/s (2)
f9d6dd5f-ff28-5889-a19e-8cfd74830f62 | note | – – – – – – – – – –
449bd1c8-6b4e-5b6a-ac16-33121028d134 | note | Capping Layer ¦¦ ##:6 ¦¦ ≤ 1.5 ¦¦ 5 x 10^-9
64fe7ac5-31bf-555d-b8f6-348d2890cb64 | note | Selected Material ¦¦ ##:6 ¦¦ ≤ 1.5 ¦¦ Not Applicable
ede5f994-4bbc-57fc-b490-3d39d295a3aa | note | Verge Material ¦¦ ##:6 ¦¦ ≤ 1.0 ¦¦ 5 x 10^-9
2b366eab-4723-5340-9354-16c606108628 | note | Structural Material ¦¦ ##:6 ¦¦ ≤ 1.5 ¦¦ Not Applicable
56700d3d-4ea5-5a72-8b62-34cefdddb76e | note | Other Type A Material ¦¦ ##:6 ¦¦ ≤ 1.5 ¦¦ Not Applicable
a9f73faa-24da-571e-b8ae-75215b38fe04 | note | – – – – – – – – – –
008b1dc1-e37b-5e9f-a8a8-28724226a684 | note | Location and Use of Type A Material ¦¦ Limits of Grading (% passing by mass) :: Post Compaction Sieve Size AS (mm)
9b6474c1-c30c-547f-b5fa-ce1b8f5cd71e | note | – – – – – – – – – –
f38701a0-1bc0-54e0-a1cb-0427f6c33eae | note | Capping Layer ¦¦ 75.0 :: ##:100 ¦¦ 37.5 :: ##:- ¦¦ 4.75 :: ##:40-80 ¦¦ 0.425 :: ##:- ¦¦ 0.075 :: ##:10-40
b3eab129-96db-519d-a0d8-640e03886389 | note | Selected Material ¦¦ 75.0 :: ##:100 ¦¦ 37.5 :: ##:- ¦¦ 4.75 :: ##:40-80 ¦¦ 0.425 :: ##:- ¦¦ 0.075 :: ##:10-40
4aaa9f19-39f3-56c6-a227-6483c63e712c | note | Verge Material ¦¦ 75.0 :: ##:100 ¦¦ 37.5 :: ##:- ¦¦ 4.75 :: ##:40-80 ¦¦ 0.425 :: ##:- ¦¦ 0.075 :: ##:10-40
d49230b1-fa02-5083-a853-46693da9cdac | note | Structural Material ¦¦ 75.0 :: ##:100 ¦¦ 37.5 :: ##:- ¦¦ 4.75 :: ##:40-80 ¦¦ 0.425 :: ##:- ¦¦ 0.075 :: ##:10-40
7d3986ba-66d7-5e98-b649-28568d384b43 | note | Other Type A Material ¦¦ 75.0 :: ##:100 ¦¦ 37.5 :: ##:- ¦¦ 4.75 :: ##:40-80 ¦¦ 0.425 :: ##:- ¦¦ 0.075 :: ##:10-40
1551cdba-e30c-531e-8423-d53c9305c6b2 | note | – – – – – – – – – –
49fac8e3-85a7-53a2-83b8-dc6d7ad85ee8 | note | Notes:
96c2b013-ffc6-545e-9565-39d743ba7a28 | note | (1) The Assigned CBR and percentage swell values are to be determined in accordance with VicRoads Code of Practice RC 500.20. Sampling for CBR testing shall be undertaken after field compaction.
abb4f7a9-37ad-584f-88c0-b8a00955db63 | note | (2) The permeability value is to be determined in accordance with VicRoads Code of Practice RC 500.16. The permeability value is to be determined on specimens manufactured from that fraction of material which passes a 19.0 mm AS sieve, compacted at optimum moisture content and 98% of maximum dry density as determined by testing using standard compactive effort for CBR and swell.
| checkpoint-no-value | Table 204.111 Fill at Structures
5711910a-b318-5249-800f-6632f990c915 | note | Non Vibrating Rollers - Static Weight * (tonne) ¦¦ Vibrating Rollers - Total Applied Force ** (kN) ¦¦ Minimum Distance from Compaction Plant to Abutments, Retaining Walls and Wing Walls (m) ¦¦ Minimum Cover over Top of Culverts (m)
ef751469-2f1d-5943-ad2e-aa573163cd4b | note | – – – – – – – – – –
c5230e14-4c34-58ba-acd3-a733e897bff8 | note | Less than 2 ¦¦ Less than 20 ¦¦ 0.15 ¦¦ 0.15 ¦¦ 0.15
8a4deffe-1432-5046-80d4-e79298acd688 | note | 2 - 5 ¦¦ 21 - 50 ¦¦ 0.3 ¦¦ 0.3 ¦¦ 0.15
8cbb645c-ee83-59d9-a85a-4d31204ce626 | note | 6 - 10 ¦¦ 51 - 100 ¦¦ 1.2 ¦¦ 1.2 ¦¦ 0.4
498c5d95-b4a3-5ab0-9839-1d36b4f1e87a | note | 11 - 20 ¦¦ 101 - 200 ¦¦ 2.4 ¦¦ 1.2 ¦¦ 0.4
a8bad1fe-eac0-5bed-ae89-aa40a585de5e | note | 21 - 35 ¦¦ 201 - 350 ¦¦ 2.4 or height of structure (whichever is greater) ¦¦ 1.2 or height or structure (whichever is greater) ¦¦ 0.7
36c256cd-5d1c-5227-81de-5b0d5e7106a7 | note | – – – – – – – – – –
479fdde5-1ebd-5f5f-b94c-b57030947ab2 | note | * Includes vibrating rollers operating in non-vibrating mode.
f45bc227-1449-5004-aa1b-caf64a9e0993 | note | ** Total Applied Force is the sum of the static weight and the vertical component of centrifugal force.
| checkpoint-no-value | Table 204.131 Compaction Requirements
c59febc0-92e5-5bc1-a29c-46c6bbc88031 | note | Material Type and Location ¦¦ Scale A: Minimum Characteristic Value of Density Ratio (%) ¦¦ Scale B: Minimum Characteristic Value of Density Ratio (%) ¦¦ Scale C: Minimum Characteristic Value of Density Ratio (%)
9e120d8d-228f-56ea-8985-499314b68526 | note | – – – – – – – – – –
4fc7ec6e-20ba-5799-ba25-4ea1cf4fb3d6 | note | All Type A Material ¦¦ 99.0 ¦¦ 98.0 ¦¦ 100.0
241df32a-0618-58cf-b256-588b81d16a54 | note | Type B Material placed within 400 mm of top of Type B Material ¦¦ 99.0 ¦¦ 98.0 ¦¦ 100.0
0bb80e9d-260a-582c-afb8-af9f156cd230 | note | Ripped and re-compacted material below Cut Floor Level ¦¦ 99.0 ¦¦ 98.0 ¦¦ 100.0
ed7cb6bd-986f-5c64-8371-0079de9257a5 | note | Type B Material placed more than 400 mm below top of Type B Material ¦¦ 97.0 ¦¦ 95.0 ¦¦ 95.0
001a673d-3d0a-5d25-9d57-61be5c1c3ec7 | note | The top 150 mm of areas where fill is to be constructed ¦¦ 97.0 ¦¦ 95.0 ¦¦ 95.0
dc94a744-fd09-5972-a8d4-83742c2b5460 | note | Type C Material ¦¦ 97.0 ¦¦ 95.0 ¦¦ 95.0
| checkpoint-no-value | Table 204.142 Minimum Frequency of Testing for Compaction and Moisture Content
01d98850-e9fa-548d-8d5b-9b75029b574a | note | Material ¦¦ Acceptable Lot Size in a Single Layer of Work ¦¦ Minimum Testing Frequency
49bd0842-1192-5def-8fb1-95ebc47327da | note | – – – – – – – – – –
9c850363-4415-5100-af48-e506605aa183 | note | Type A Material ¦¦ One day's production or 5,000 m^2, whichever is the lesser ¦¦ Every second lot of like material and work
b9964201-eea4-5798-8b2e-fdca6729764a | note | – – – – – – – – – –
c7f30d39-430c-5c57-be59-b4c7c6ca6b47 | note | Type B Material
a8406815-a212-502f-8f5a-d8d8f0e282b7 | note | • Ripped and re-compacted below Cut Floor Level ¦¦ One day's production or 10,000 m^2, whichever is the lesser ¦¦ Every sercond lot of like material and work
e34c70e5-0def-5093-8c5b-bb4e9e461504 | note | • Placed within 400 mm of top of Type B Material ¦¦ One day's production or 10,000 m^2, whichever is the lesser ¦¦ Every second lot of like material and work
f4783cc7-31f9-5721-92b7-44c36d583d35 | note | • Placed more than 400 mm below top of Type B Material ¦¦ One day's production ¦¦ Every third lot of like material and work
b912fc53-fe20-5703-a123-09fcb5905c4b | note | – – – – – – – – – –
8e62c6ea-023d-5918-8f0d-d795246f2a31 | note | Type C Material ¦¦ One day's production ¦¦ Every sixth lot of like material and work
| checkpoint-no-value | Table 204.161 Schedule for Surface Tolerance, Material Properties and Compaction Testing
79c96ebd-90d5-5b70-b488-a9f6114f1611 | note | Road Name ¦¦ Chainage / Location ¦¦ Scale of Surface Level Measurement (A, B or C) ¦¦ Scale of Material Property Testing (A or B) ¦¦ Scale of Compaction (A, B or C)
56706627-5a8f-53d5-a748-7a521dc16051 | note | – – – – – – – – – –
1449c79c-9518-5e86-b068-ab596b847d34 | note | Bruny Island Main Road ¦¦ Within Limits of Works ¦¦ B ¦¦ B ¦¦ B
46fb36b7-f778-506a-89e9-a65b4fe0a21e | note | – – – – – – – – – –
5fd0dee4-21f7-5055-a58d-2a0a278619c1 | note | Note: Where no level of testing is nominated, Scale A applies.
| checklist | ITP - Linemarking & RRPM & Road Furniture and Signage Rev0 | itp | ITP - Linemarking & RRPM & Road Furniture and Signage | dc0225b4-8508-4de0-9c48-adc4e4617e24
| section | 1 - Preliminary Works
| checkpoint | 1.1 Check for correct documentation
6d00df20-9ceb-569b-a22c-74dc9e833886 | note | FREQUENCY: Prior to commencing any activity
7380c755-1b0c-5f03-a2bf-736002f5fc48 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
e5351206-c671-52bf-ad8a-e15e00da77ee | note | – using the correct and complete set of drawings
5755d473-5d5a-5054-b6bf-94123a415cac | note | – all drawings are the latest revision
ec88f987-22c3-5a4d-adb1-7b1e6538a8e4 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
61a4049a-29cb-55cc-b3d0-05f1c44e0237 | note | INSPECTION/TEST METHOD: Document review
7009731d-1796-5c7d-ae44-30fbe188051c | note | RECORD OF CONFORMITY: This ITP signed off
315716b4-da6c-5f16-b5fd-b40f6f9075fc | note | HP*
529e19d8-dbae-50d0-9d2d-937166e474d4 | note | RESPONSIBILITY: Site Engineer / Site Foreman
5c6b7c2c-eff8-5db7-9bfc-6a0b86f96eb2 | textbox | DATE:
| checkpoint | 1.2 Implementation of all measures and controls
50d46ce4-27b5-54ee-92a0-2dc900dd77e3 | note | FREQUENCY: Prior to commencing any activity
01dd9922-9f63-5dd2-8873-4dd8a5b836f3 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
e653b43e-6103-55d8-89c7-d8cb231e0d52 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
ebc31f88-f603-57dc-8b20-3dd2a18edbea | note | INSPECTION/TEST METHOD: Visual Inspection
0059462c-257f-58e5-b482-76842d208e8e | note | RECORD OF CONFORMITY: This ITP signed off
84039480-70eb-5467-ac14-b189711b2da1 | note | HP*
7770f2b4-34b7-5767-9d00-acfddbdf3b18 | note | RESPONSIBILITY: Site Engineer / Site Foreman
0b0ef1c3-218e-52a5-872e-1b363250f9db | textbox | DATE:
| checkpoint | 1.3 Signage Conformance
6d825ffe-4fd6-55fe-af8f-f48a9b64fcb9 | note | FREQUENCY: Before commencement of activity
729a13a5-5938-5f7d-9e05-15783ca9028f | note | ACCEPTANCE CRITERIA: Ensure sign size and image correspond with contract drawings Road Signage Installation
ec0e3f65-9c6e-56b8-8579-4cc7cf4879bb | note | REFERENCE DOCUMENTS: Drawings 2101-2116
409bfe31-fb50-5766-8933-8bdd88e10cfa | note | INSPECTION/TEST METHOD: Verify
48b38fb7-54d2-5c14-8d63-52297b165995 | note | RECORD OF CONFORMITY: This ITP signed off
97f56389-185a-5772-aa82-4e5bdd5660d2 | note | IP
62a44646-a4ae-5c9f-836b-54287638c2db | note | RESPONSIBILITY: Site Engineer
d0e22db2-1fb2-5282-bd7c-128bf741b93d | textbox | DATE:
| checkpoint | 1.4 Service Identification
011c0298-0994-5f45-8450-ab9af268ddff | note | FREQUENCY: Prior to start
6936f11c-8fee-578b-b3a1-4a678fd1602a | note | ACCEPTANCE CRITERIA: Check for any services in proximity to points of installation of posts (Road Sign Preparation)
643d2f7e-046a-550d-ac46-d09bd4a09e9f | note | REFERENCE DOCUMENTS: DBYD
b027c630-cb9d-52fc-94b2-13ce12a10723 | note | INSPECTION/TEST METHOD: Verify
54641dd6-197c-5bfd-bb83-23a544c5d943 | note | RECORD OF CONFORMITY: Ground penetration permit, This ITP signed off
7d875ba8-0553-508f-9ebb-12b59a0fca53 | note | IP
0ab2c3e1-1b48-52b0-a9f5-738ee6c505e8 | note | RESPONSIBILITY: Site Engineer
b7b20e60-5576-5620-a266-8c194438f505 | textbox | DATE:
| section | 2 - Linemarking Works
| checkpoint | 2.1 Set out of line markings; dimensions and spacings
8b77734d-eece-5ac8-8b9a-fc1394b5cb45 | note | FREQUENCY: Prior to commencing line marking works
39054c8f-5c62-57b8-a96b-6dd2f1585382 | note | ACCEPTANCE CRITERIA: Holding Point:
c210d516-361f-53fa-aa40-351f23f1832a | note | ○ Painting/application of material shall not commence until the Superintendent has inspected the set out and given consent to proceed, unless an exemption has been granted in writing by the Superintendent.
cf2ea610-a1d3-53ad-aaf8-6d30759fe7f6 | note | (a) New pavement markings shall be positioned in accordance with the following requirements:
46d976cb-7da9-5bf7-9163-35355cfc7855 | note | (i) set out by the Contractor in conformance with the appropriate standard required by Clause 721.A03
a8bfa854-de4a-56c3-b7ad-6ecda8cf890d | note | (ii) applied within the tolerances listed in Table 721.A101.
d073dbe6-9b6e-5348-a781-69efc2eca29b | note | (b) Temporary Reflective Markers Temporary reflective markers for new works shall be placed at the following minimum spacings on all longitudinal lane lines, except that on any curve less than 500 m in radius the spacing shall not be more than 12 metre centres:
9a4c9175-ec82-5f5a-bc9f-513ca8e9fb79 | note | ○ AADT ≥5,000 and National Highway 12 metre centres
65ada79f-fd60-54e6-a55e-23406f6409d9 | note | ○ AADT ≥1,000 and <5,000 24 metre centres
9f82c411-3fa3-591f-96dd-d689c87b554f | note | ○ AADT <1,000 48 metre centres
ee9a2f0c-13ca-5c34-9002-26f76bd1762a | note | REFERENCE DOCUMENTS: Cl.721.B05
1565a7ff-80c5-561c-a72a-2e9b9bbc77d1 | note | INSPECTION/TEST METHOD: Document review & Site inspection
d195920a-dd67-5001-b815-ce3b08d0f2f8 | note | RECORD OF CONFORMITY: Consent to proceed by Superintendent OR written exemption granted, This ITP signed
1f35cbee-0f6e-511b-8c5b-3d046bfb415d | note | HP
655bfc47-a444-5f7b-81f1-c5e5225dfdfe | note | RESPONSIBILITY: Site Engineer / QAV
9fc20979-f1f6-51a8-b06c-6c60e83cbebc | textbox | DATE:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 Verification of line marking material
ae213d80-3edb-5b7e-ad18-07ec67dfd7a9 | note | FREQUENCY: Prior to commencing line marking works
6e4478f8-69d8-5a1c-b5c9-12653f3b7aec | note | ACCEPTANCE CRITERIA: Line marking material is to comply with minimum requirements as specified in Spec Tables 721.D021 and 721.E021
219d91b9-cb10-575d-94c6-e69ecb5a15e1 | note | REFERENCE DOCUMENTS: Cl.721.D02, Cl.721.E02
65d67773-63fc-58f5-ba6f-c7211c74f8ea | note | INSPECTION/TEST METHOD: Document review
82946141-f09d-5034-9314-77d02f380847 | note | RECORD OF CONFORMITY: Material compliance, This ITP signed
36289bed-c1b1-5a9d-9195-419a64414f66 | note | IP
7485e0a9-b898-5fa1-a65a-c80795deb37c | note | RESPONSIBILITY: Site Engineer
8e2af366-df76-58b3-814d-bdb337e22607 | textbox | DATE:
| section | 3 - RRPMs
| checkpoint | 3.1 Materials
6e54275b-b6a7-5919-8de4-ccf809da6055 | note | FREQUENCY: Each lot
cbc75710-38e5-581f-9c06-5318cd7e5fdc | note | ACCEPTANCE CRITERIA: Markers shall comply with the relevant requirements of AS 1906, Part 3.
0de5bf64-6aa4-51fb-a400-2ebc0bcfa623 | note | ○ Epoxy adhesive shall be Standard Set or Rapid Set adhesive complying with the relevant requirements of AS 3554
107b327b-d11c-51fb-b034-681aba9a6874 | note | REFERENCE DOCUMENTS: Cl 710.03
581f69fe-4ef7-547b-b633-8d40264c65d1 | note | INSPECTION/TEST METHOD: Visual Inspection
82393986-79d5-5572-99cb-9684af426a75 | note | RECORD OF CONFORMITY: This ITP signed off
87017f58-a24b-5b0a-9e71-027abc8a28e6 | note | IP
078db9ed-f968-5e99-92a8-bf8a24ded46e | note | RESPONSIBILITY: Site Engineer
5d093ef4-4a30-5a6c-bec5-e706a2c9cc16 | textbox | DATE:
| checkpoint | 3.2 Preparing Adhesive
29693217-e1d6-5f1e-83af-4869686c9998 | note | FREQUENCY: Each lot
d67caaab-767d-52ec-93e3-b62b2b384ba2 | note | ACCEPTANCE CRITERIA: Adhesive components shall be batched so that the mixed adhesive contains not less than 45% nor more than 55% by volume of either component. Before starting work each day, or when changing to a different batch of adhesive, a hand mixed colour standard shall be prepared for reference during the day.
b78a8b61-97e1-5ca7-a4e0-19b1877b01cc | note | ○ When hand-mixing is used not more than 500 g of each component shall be mixed at any time.
de69e8c0-89d4-58dd-9dbb-e09af9b1bd7f | note | ○ The components shall be mixed on a flat surface and the mixed adhesive shall be used within 10 minutes of the time the two components are brought together.
b64a27c0-760f-5409-b923-e31dfecd6abc | note | ○ Hot melt bitumen adhesive shall not be used on days of total fire ban without the written approval of the Tasmanian Fire Service
6755d3bb-af5b-525f-96a2-8957945f43d5 | note | REFERENCE DOCUMENTS: Cl 710.04, Cl 710.05
0ea1abb4-cb33-53f3-a36c-0378ef876a1b | note | INSPECTION/TEST METHOD: Visual Inspection
e2d99a3a-84a6-5ea9-82ae-f4a6fcb6bb33 | note | RECORD OF CONFORMITY: This ITP signed off
17608d5e-f6fe-5eab-a0c9-a2a18e03fa43 | note | IP
a2da8653-1972-5f65-bf3c-1900edd368c7 | note | RESPONSIBILITY: Site Engineer
d8f100a0-6107-5d01-b186-09a61bae5a44 | textbox | DATE:
| checkpoint | 3.3 Pavement preparation
08acdd09-adce-55b1-8d41-4010a1f54a0b | note | FREQUENCY: Each lot
ae7bf53e-b924-56eb-a77e-237c721b8135 | note | ACCEPTANCE CRITERIA: The Contractor shall sweep or air blast each marker site as necessary to remove loose material before placing markers. Markers shall only be placed at locations where the pavement is free from dirt, oil, grease, paint, or any other material
9bdc0913-c876-5d47-b12f-9a1d755442cd | note | REFERENCE DOCUMENTS: Cl 710.06
3b75e88f-2b64-5e2a-abd3-52ebdad6dd4d | note | INSPECTION/TEST METHOD: Visual Inspection
122b55e1-e141-5f81-b948-efae14f5ebcd | note | RECORD OF CONFORMITY: This ITP signed off
3bb49577-8bda-5006-8434-d3a2ce122036 | note | IP
25469465-3664-51be-8f38-ac6400b07d3b | note | RESPONSIBILITY: Site Engineer
7482c8b4-be0e-5134-a9da-9b6af7cd89f4 | textbox | DATE:
| checkpoint | 3.4 Placing markers
ed4c2b30-89f5-5606-ac91-6adf1a5fc7a4 | note | FREQUENCY: Each lot
897e69e8-3ba4-5e87-b1b1-ff8eec55b00b | note | ACCEPTANCE CRITERIA: Markers shall not be placed in any of the following circumstances:
d231b453-ddf9-5f6b-a993-7eee48a7dc2d | note | • when the pavement is wet;
2cdf4367-ba76-5554-b832-d4cfc8e33f29 | note | • when the relative humidity is greater than 80%;
af31bb77-92a9-599f-b1a6-ad7fc36c5d4f | note | • when the ambient temperature or the temperature of the road surface is less than 15deg for standard set adhesive or 0deg for rapid set or hot melt adhesive.
8de120a5-80ca-5f68-a23b-3f8ddcbadc4d | note | ○ Where a marker is not positioned correctly within 10 seconds for hot melt bitumen adhesive, 2 minutes for rapid set machine mix adhesive, 4 minutes for standard set machine mix, or 10 minutes for standard set hand mix from the time mixing commences, it shall be discarded and a new marker placed.
ccacac74-ecb0-57b9-9880-b2e829d4105f | note | REFERENCE DOCUMENTS: Cl 710.07
aa7f6dca-bb3b-5a78-90b5-fa2d4572b142 | note | INSPECTION/TEST METHOD: Visual Inspection
fb32c69b-207a-55bc-a1e9-dba5ffb8c2c5 | note | RECORD OF CONFORMITY: This ITP signed off
469effab-6133-56f6-b4d6-e0f0f2774c66 | note | IP
b4cdfa49-e809-5da1-b880-541291d61042 | note | RESPONSIBILITY: Site Engineer
37397f7d-b056-5fda-8062-0154af0f41bc | textbox | DATE:
| checkpoint | 3.5 Tolerances
e5772af1-1a86-5f0f-9081-1769a8964a2b | note | FREQUENCY: Each lot
5679924f-203e-5df8-b9ec-a33cf3492795 | note | ACCEPTANCE CRITERIA: (a) Markers in Line with Broken Line Segments
c36a720c-4f6a-5e56-9cc8-7fa557b8a36e | note | ○ Transverse position within 25 mm of the centreline of the segments.
078acc2c-c4fa-5d92-873c-9ace272b6fb5 | note | ○ Longitudinal position within 0.5 m of the specified position.
e56689fb-1c34-51d1-affb-de9bee73e336 | note | (b) Markers in a Longitudinal Group
7c9f7ff8-cc76-5728-b174-6bae66283eda | note | ○ Transverse position of the centre of each marker within 25 mm of the specified position and within 10 mm of a line joining the centres of the end markers of the group.
53b56dad-e74a-5369-8d44-b811c5d1f4e4 | note | (c) Markers Adjacent to Unbroken Line
47be912a-3cf1-5f9f-a672-50bb5d45da9f | note | ○ Clearance to edge of line within 5 mm of that specified.
48beeda4-519e-586a-a945-28e840b7d5f9 | note | ○ Longitudinal mismatch between markers in transverse pairs at barrier line not more than 25 mm.
613d9811-0871-57a7-9695-d54d27ed0914 | note | (d) Orientation of Reflective Markers
0847baaf-70d0-5419-8d21-a2c66bf67a67 | note | ○ Lower edge of the reflective face at 85deg to 95deg to the centreline of the roadway or any adjacent line.
ec2b69a2-8dad-56a5-9b45-745c94b7058b | note | REFERENCE DOCUMENTS: Cl 710.02
646ca0eb-0807-5e23-9b47-6cdb26736ca7 | note | INSPECTION/TEST METHOD: Visual Inspection
1aa280d7-16ea-5f16-ab49-82dc985ce74f | note | RECORD OF CONFORMITY: This ITP signed off
4b2694bf-e3d5-502c-870e-2c4b19914cce | note | IP
21a7d50f-77de-5b3c-936e-d9ef8bb02031 | note | RESPONSIBILITY: Site Engineer
d2d09292-a275-528b-b37b-1aa8114606f9 | textbox | DATE:
| section | 4 - Testing
| checkpoint | 4.1 Line Marking Tolerances
6a17a098-59bd-535c-b4ef-b4f6338615f8 | note | FREQUENCY: After completion of works
91cddbad-042c-5633-983c-d17f049d1eb7 | note | ACCEPTANCE CRITERIA: Line marking shall comply with the tolerances shown in Table 721.A101.
f36876a3-c98a-5ecf-be3b-13ab5af7b43e | note | REFERENCE DOCUMENTS: Table 721.A131, Project Spec. Table 721.A101
6530987a-20d3-50af-bd86-74c0968285d5 | note | INSPECTION/TEST METHOD: Document review & Site inspection
221991b7-d9e2-5304-b8a7-59d4953111a7 | note | RECORD OF CONFORMITY: This ITP signed
e950824c-5d07-5f2a-b87e-3b4cc84c22d0 | note | IP
a714afa2-74c6-5b7c-8d83-c8ba89c6e8c9 | note | RESPONSIBILITY: Site Engineer
c568bf8a-8509-55a3-892e-0e956a8519b7 | textbox | DATE:
| checkpoint | 4.2 Removal of Non-compliant marking
a77642d6-7cf3-57fd-83d3-b9dd3e743a19 | note | FREQUENCY: After completion of works
81845d7e-a5d5-543a-97bb-563277b5ab58 | note | ACCEPTANCE CRITERIA: Hold Point
bdee237c-79d9-592f-8103-2a97eba03c5d | note | ○ Where the removal of unsuitable pavement marking is required, the method of removal shall be subject to the approval of the Superintendent before removal works commence
b2d99f4e-d81a-52c5-a3fa-2bb394e6be41 | note | REFERENCE DOCUMENTS: Project Spec. Cl.721.A12
07f5bbd3-4e28-5649-b9ad-f736c5bb4381 | note | INSPECTION/TEST METHOD: Document review
9d365791-d867-5cd2-ab45-fac5ed11a536 | note | RECORD OF CONFORMITY: Approval from Superintendent, This ITP signed
284441ce-c097-5205-9767-036bfa6b4c23 | note | HP
939520ad-6fc9-5a8a-98e8-9078e6f842e5 | note | RESPONSIBILITY: Site Engineer / Superintendent
0e90f987-6016-5e09-8387-de81d7f62404 | textbox | DATE:
| signoff | AUTHORITY HOLDPOINT
| section | 5 - Signage
| checkpoint | 5.1 Setting Out
42128eac-2dff-51b4-9b28-7d67ebb54a5e | note | FREQUENCY: Prior to start
fe25e434-ce5c-59f4-8594-50211f61fcbd | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections.
44e5018f-15f8-56d7-b603-6cb909333c12 | note | REFERENCE DOCUMENTS: Drawings 2101 to 2116
ea05f9d1-03ee-5c14-bb37-6901356c0806 | note | INSPECTION/TEST METHOD: Visual Inspection
b0df3e69-96d5-5287-882a-62509ae50d6d | note | RECORD OF CONFORMITY: This ITP signed off
ce3d4eae-b443-53cd-a833-3e0104d9bbc0 | note | IP
0b7e92e7-9718-5b95-aad9-4c9c9c27dec4 | note | RESPONSIBILITY: Site Engineer
7c9306e8-439b-56f1-8bb7-1749a00f89df | textbox | DATE:
| checkpoint | 5.2 Conformity with drawings
b48d95e2-553b-52b9-8c2f-0f392112971b | note | FREQUENCY: Four weeks prior to installation
1c24c74f-a1df-540e-b125-715a0a9c2e9f | note | ACCEPTANCE CRITERIA: Witness Point
48988239-987a-5daf-8679-fcd37bea8880 | note | ○ If the Contractor proposes to use an alternative method of installation, the Contractor shall submit full details to the Superintendent for approval not later than four weeks before the commencement of sign installation
5ee26742-3692-5a8e-966b-c4632b0d87d5 | note | REFERENCE DOCUMENTS: Cl 714.04
2394518f-f5a0-5ffd-949b-0ce79ba2672b | note | INSPECTION/TEST METHOD: Verify
1b0f8059-8762-5012-8bf6-48333c347b05 | note | RECORD OF CONFORMITY: This ITP signed off
2f9cb5ae-e058-5eed-bbf6-cc54e2968abc | note | WP
44fdff74-4b88-5174-9e06-8fc435ce0892 | note | RESPONSIBILITY: Site Engineer / QAV
849a1d88-9932-5bab-9941-1520ffe48ab4 | textbox | DATE:
| checkpoint | 5.3 Post & Foundations
4ecd34a2-ddae-5301-babf-f6e9241effb2 | note | FREQUENCY: Prior to Start
488635d1-73ba-56cf-8120-0020d97227a0 | note | ACCEPTANCE CRITERIA: Hold Point
37726c64-b563-51ca-863f-73c5a7f8db27 | note | ○ The required positions of all posts and signs shall be as directed by the Superintendent who shall confirm the positions before the erection of posts commences.
58ec7956-7ca9-59ad-bb81-9ad69d8a18bb | note | REFERENCE DOCUMENTS: Cl 714.06
94bf7ed9-b9f0-528a-aba6-490e90710525 | note | INSPECTION/TEST METHOD: Visual inspection
433ab03e-5764-52f0-99bf-e724f44d9119 | note | RECORD OF CONFORMITY: This ITP signed off
c0861ec3-9838-57bd-a0e0-7aab833bfacb | note | HP
d127f498-2799-5ab0-8848-011fdc0b38b7 | note | RESPONSIBILITY: Site Engineer / QAV
4ffd2dc8-09ca-508e-a175-515ea8341303 | textbox | DATE:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 Signage Install
6f7f9ac7-95c2-5f12-86da-b70daa5404a2 | note | FREQUENCY: Each Sign
ee7cd680-a6ec-5523-ad12-ea07c79c51c3 | note | ACCEPTANCE CRITERIA: Sign to be installed as per most current project and DSG standard drawings, local council documentation, and to the correct height and position.
c7772310-9c70-5993-bc28-56e22e1efba8 | note | ○ Signs specified to be re used are to comply with AS 1742 standards, and must be replaced if deemed in unsatisfactory condition
dd40e09a-b42b-5cca-99b4-b78f1262b29b | note | REFERENCE DOCUMENTS: DSG standard drawings. Cl 714.07
0aa7773f-cd3a-5998-beca-a08b267b4464 | note | INSPECTION/TEST METHOD: Verify
17a26a17-d561-5194-8a41-5fbc58af4468 | note | RECORD OF CONFORMITY: This ITP signed off
1b493ebd-c99e-5a9e-960e-2ef3d7b92da7 | note | IP
82ed90f8-9377-53d7-9865-73c9134f9214 | note | RESPONSIBILITY: Site Engineer
6dd33c0c-07aa-5d2b-be99-7b347ef5d940 | textbox | DATE:
| checkpoint | 5.5 Tolerances
cf8211f0-d39d-55d2-b62a-1bfb3037b754 | note | FREQUENCY: Each Sign
7597d3ec-7f29-5736-9e6c-ffa2087a2ad5 | note | ACCEPTANCE CRITERIA: Posts vertical with maximum deviation of 1 in 100
0881e0e7-3c91-57be-b0e2-991514f3a2dc | note | ○ Post tops 50mm +-10mm below top edge of sign
85eeabe9-7ab1-527f-b449-390c8f3f0570 | note | ○ Signs mounted level with maximum deviation of 1 in 100
5bd5da63-e883-5acb-8ec9-394df384020d | note | ○ +-40mm of the height specified in the Sign and Post schedule
81739f89-2655-5915-ba75-afb76388895b | note | ○ +-100mm of the pegged sign location or specified location
a46c9f76-1968-53b9-9dd9-087ef2143d96 | note | REFERENCE DOCUMENTS: Cl 714.05, Cl 714.07
cc212c26-e211-5f35-ba63-b2f669f4e3d9 | note | INSPECTION/TEST METHOD: Measure
8e283b71-e0eb-58ad-8378-990aa851aeaf | note | RECORD OF CONFORMITY: This ITP signed off
5b9aa747-c900-5479-88a1-d7aa927b76b2 | note | IP
22208f5b-6116-5565-adab-be805408746c | note | RESPONSIBILITY: Site Engineer
b191ca46-e03e-589c-994e-e134aa12eb49 | textbox | DATE:
| checkpoint | Final Inspection
24699211-bb9a-5920-9f34-3301dea1fcb9 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
b17beb6d-b80e-549e-9a7a-08d03e89f6ef | textbox | Print Name:
0c053b22-e505-5c89-89a5-d7c8eea8e808 | textbox | Position:
f73c87be-2e86-5cf3-8b36-1d8d82fa0e54 | textbox | Date:
| signoff | Add Signature
| checkpoint-no-value | Table 721.A101 Tolerances on Pavement Markings
de04391e-8d5b-562a-92dd-fdfb80668c00 | note | Markings ¦¦ Tolerance
e444821e-712b-52c7-81bf-2def9356dbc4 | note | – – – – – – – – – –
31d6232a-bb39-5957-976a-cb3907e7d718 | note | (A) Pavement Markings (1)
1e8ac295-3062-555e-a3d2-8b4f13e20a48 | note | Distance between the centreline of the marking and the centreline of the set out mark ¦¦ < 30 mm
5df0a430-181d-5591-ba87-492e3ff02fda | note | Distance between the centreline of the completed marking and the centreline of the previous marking ¦¦ < 15 mm
d3c8e3e2-153d-5a08-8b30-03bb16ed4335 | note | Width of completed painted markings ¦¦ ± 10 mm of the specified dimensions
d907a1c3-9d98-53b0-8776-d20a7cc4f0e0 | note | Width of completed markings for long life materials ¦¦ 0 mm to +10 mm
ad7a615b-3f4a-551c-8827-b4d198ecf6ca | note | Length of completed stripes and blocks ¦¦ 0% to +10% of the specified length
4360eac8-9460-538a-a123-1f8800220993 | note | Gap between dobule lines ¦¦ -10 mm to +0 mm of the required 100 mm gap (2)
6c5cac03-0bf2-5162-88c2-eed7dfd67793 | note | – – – – – – – – – –
322165cd-4047-56cd-9775-6306523593c4 | note | (B) Raised pavement markers
249e235d-d4b0-5309-8f83-485dfd18127d | note | (i) Markers in line with broken segments
d130f807-1850-5357-a8f1-046ef6bbea8f | note | Transverse position ¦¦ ±25 mm of the centreline of segments
72a25d4a-f946-5f25-81f9-45afc6077d38 | note | Longitudinal position ¦¦ ±0.5 mm of the specified position
c11aee24-c893-5751-9ce1-fd3548d827da | note | (ii) Markers in a longitudinal group
a5def445-8296-5492-b2a9-c5c8e8ce7c4c | note | Transverse position ¦¦ ±25 mm of specified position and ±10 mm of a line joining the centres of the end markers
765cfbb2-618d-5661-942b-07cff2dc0f16 | note | Longitudinal position ¦¦ ±0.5 mm
3d5e1e49-3d3a-5172-938a-74cba607b481 | note | Spacing of markers within the group ¦¦ ±50 mm of specified spacing
2208f81d-930c-5ca1-b689-b6b4f54cc1f4 | note | (iii) Markers adjacent to an unbroken line
29d43d63-cacc-57fe-9b4d-de83efda9f60 | note | Clearance to edge line ¦¦ ±5 mm of the specified dimensions
b3cc5294-479b-5bad-8859-9faf91ab866b | note | Longitudinal mismatch between markers in transverse pairs ¦¦ <25 mm
f694de2f-f539-5da6-83c4-fe1a8c006ade | note | (iv) Orientation of reflective markers ¦¦ Lower edge of the reflective face at 85° to 95° to centreline of roadway or adjacent line
0276442b-53d0-536b-839d-bb52e9e9eb2b | note | – – – – – – – – – –
eb9975d1-0cb6-5cba-83a4-2406e9aa0695 | note | (C) Thermoplastic profiled lines
706a7096-dbb4-566d-909f-740777b04b85 | note | (i) Tolerances on dimension
0c4caf0f-b9c3-5b44-bdad-1cb986bd416b | note | Line width ¦¦ +20 mm, -5 mm
c0113730-0a75-529c-94d9-4f747663b730 | note | Line height ¦¦ +2 mm, -0 mm
fbd80305-ea9f-55ea-88cb-abc66642d62e | note | Extrusion breadth ¦¦ +10 mm, -0 mm
bad1566c-05ec-5cb8-8279-e2185b5b862e | note | Extrustion spacing ¦¦ ±15 mm
20b863be-ebdd-5429-b8ba-083666d37bf6 | note | Extrustion shape ¦¦ ±25 mm at any point from rectangular shape
480a113c-8efc-593c-ad08-71a97f44c82d | note | (ii) Tolerances on position
fcdeda17-cfb9-5909-9d21-4fcada03b5a2 | note | Distance between the centreline of the marking and the centreline of the setout ¦¦ <30 mm
1570279e-e9a6-590b-bbed-44501fe84002 | note | Length of the completed lines ¦¦ -0% to +5% of the specified length
eb664992-4ac7-5bd7-9593-a406c238c715 | note | Longitudinal position of individual extrusions ¦¦ ±50 mm of any previously applied profiled lining
ff293b2f-37b9-5b0b-b682-58b77a36145a | note | – – – – – – – – – –
f9a6e00d-a82d-5d1f-aec5-470b8c0527d8 | note | (1) Apparent line of the markings is a smooth, continuous alignment when viewed in the direction of the line.
9ea3aebd-8933-5f61-9bb5-b038265d9fa6 | note | (2) Maintenance of pavement markings: If the gap between the existing lines is 90 mm or less the gap shall not be reduced by the maintenance application.
| checkpoint-no-value | Table 721.A131 Acceptance of Retroreflectivity
6079e825-214e-571b-a9f9-6eb673834856 | note | Testing Period (1) ¦¦ Initial Measurement: 3 - 5 weeks ¦¦ Additional Measurement: 5 - 6 months
c7544ea7-0717-565b-aeab-4d05370bc288 | note | Minimum level of retroreflectivity on sprayed seal surfaces ¦¦ Initial Measurement: 350 mcd/lux/m^2 ¦¦ Additional Measurement: 220 mcd/lux/m^2
37e0f6b4-9a84-5547-89f8-48ee443e849e | note | Minimum level of retroreflectivity on asphalt and all other surfaces ¦¦ Initial Measurement: 350 mcd/lux/m^2 ¦¦ Additional Measurement: 250 mcd/lux/m^2
772dfafb-c661-5c9d-8833-17fa857516c3 | note | – – – – – – – – – –
84415e56-5bf9-5544-9dec-cf782c6ececc | note | (1) Measured after application of the second/final coat of material.
| checkpoint-no-value | Table 721.D021 Minimum Requirements - Paint and Glass Beads
0fe19ecf-2a07-53f2-95ef-fdd500cbf198 | note | Paint (1) ¦¦ Glass Beads (2)
29a654f2-dce0-520a-8d38-c3e23d12001d | note | – – – – – – – – – –
1f078b81-3a80-52e9-9dfe-8b0924b363db | note | Linemarking
06421bf2-9988-5098-9347-63a04191d317 | note | • New Markings (initial application only)
9041b5ec-8efa-500b-a230-0245bb1b685d | note | 0.38 mm dft on sprayed seals ¦¦ Type D-HR (3)
c2ed1144-474b-5fd5-bf92-90be83ae65bc | note | 0.35 mm dft on asphalt and all other surfaces ¦¦ Type D-HR (3)
1c426dc8-d25f-5b98-8fc9-db459e7f867b | note | • Re-marking (including second application on new markings
1d8673de-d76c-520e-908d-10e50bd50ee7 | note | 0.38 mm dft on sprayed seals ¦¦ Type D-HR (3)
0515dbac-756d-5438-b9f6-2794898b31c3 | note | 0.35 mm dft on asphalt and all other surfaces ¦¦ Type D-HR (3)
eb0e6fb7-1167-56f9-b8d2-6c0bbedcc08e | note | – – – – – – – – – –
7240056a-7e91-5e10-aae8-aad2d5cf7b0b | note | Roadmarking
44b23d31-307e-5022-a80b-e982da89dab4 | note | • All marking
3a27973f-9f59-5e48-9d24-2e131067ff2d | note | 0.35 mm dft on sprayed seals ¦¦ Type B-HR
21343acf-b169-5907-8d86-fb76e6b5d7a2 | note | 0.30 mm dft on asphalt and all other surfaces ¦¦ Type B-HR
57adbab2-4fbd-5791-8fe8-5118e9547dbc | note | – – – – – – – – – –
418f1cb8-9f61-5334-b678-98694712ac51 | note | (1) The minimum dry paint film thickness (dft) specified above shall be the end product thickness measured on a 200 mm x 100 mm sheet metal test plate without beads. Consideration shall be given to the texture of the road surface and the method of application used to achieve the requirements of this section.
baad476b-fecd-5ebe-a22e-e88b9cc733e8 | note | (2) A minimum of 400 g/m^2 shall be retained in the painted marking for all glass beads.
816e65d4-25e4-5b75-98c2-e90001d45446 | note | (3) An alternative glass bead application rate shall be 300 g/m^2 of D-HR with a separate drop of 200 g/m^2 of B-HR provided that 75% minimum of the D-HR beads is retained at the 5 demonstrated by photographs at each test site.
| checkpoint-no-value | Table 721.E021 Minimum Requirements - Long Life and Glass Beads
e08d2f21-9361-5426-8d33-1bda86f0d6fb | note | Material ¦¦ Applied Minimum Thickness, Glass Bead and Other Requirements
99d37fd8-a833-5b41-b65c-8c1d82f84e93 | note | – – – – – – – – – –
76b1c359-3dc1-541a-8ec3-381a19812b45 | note | Thermoplastic
efbbca95-6779-54f8-a55f-38617f7462c4 | note | Sprayed markings ¦¦ 2.0 mm minimum thickness on logitudinal lines contaiing internmix beads and with a minimum of 400 g/m^2 of Type D-HR or Type B-HR(3) drop-on glass beads retained on the marking surface
ba82c1f5-3e5e-564f-9f92-f581ff18616a | note | Extruded line markings (1) ¦¦ 2.0 mm minimum thickness on longitudinal lines containing internmix beads and a minimum of 400 g/m^2 of the Type D-HR or Type B-HR drop-on glass beads retained on the marking surface
80d38d55-2d09-5828-a69a-b47936f78068 | note | Extruded road markings (1) ¦¦ 3.0 mm minimum thickness on intersections containing internmix beads and a minimum of 400 g/m^2 of Type D-HR or Type B-HR drop-on glass beads retained on the marking surface
a3c59ddc-055c-5167-9695-13470ad5a523 | note | Preformed markings ¦¦ 2.3 mm with a minimum skidding resistance value of 45 BPN (British Pendulum Number) and retroreflective properties agreed with the Superintendent
01d87a3e-4791-59ef-bde0-c636c69548ce | note | Profiled lines (1) ¦¦ 8.0 mm minimum thickness with a minimum of 400 g/m^2 of Type D-HR or Type B-HR drop-on glass beads retained on the marking surface
648f67a7-b3cf-59bb-9927-b5df3797652a | note | – – – – – – – – – –
b13ea094-e8b6-52a9-a216-9bc5aae18287 | note | Cold-applied Plastic
1674f827-3a8c-58bc-8c02-0383e2d688f9 | note | Sprayed line markings (2) ¦¦ 1.0 mm minimum thickness for longitudinal line markings only with a minimum of 400 g/m^2 of Type D-HR or Type B-HR glass beads retained in and on the marking surface
575b2b6c-7969-5c50-a62c-74d6aa384d5c | note | Sprayed road markings (2) ¦¦ 2.0 mm minimum thickness for all road markings containing intermix beads and a minimum of 400 g/m^2 of Type D-HR or Type B-HR drop-on glass beads retained on the marking surface
0ef549ce-5884-59d2-bc95-3ea31eebd430 | note | Trowelled, screeded, or extruded markings (1) ¦¦ 2.0 mm minimum thickness of markings containing intermix beads and a minimum of 400 g/m^2 of Type D-HR or Type B-HR drop-on glass beads retained on the marking surface
891b566a-dc13-5165-b478-353289474f8d | note | – – – – – – – – – –
1768bf1d-a1bb-56c9-b20d-e0efe2d1f68f | note | Pliant Polymer Tape
c9812776-93c9-59f0-931e-55485a09c9f9 | note | As approved by the Superintendent
377c2d7d-95d9-5a0c-9130-001fb31ffadb | note | – – – – – – – – – –
e3729a47-b378-5cce-8dbf-28aefec6aad5 | note | (1) The minimum thickness specified shall be the height above the upper road surface level or above the existing marking as appropriate.
88b0daa7-6f3e-5eb7-9789-39cb941c09e5 | note | (2) The minimum thickness specified shall be the height of the material between the glass beads on a metal test plate. All other thicknesses shall be as measured on a metal test plate including glass beads.
023f504b-1a3b-599c-a34f-751f7a2175b0 | note | (3) Pristine drop-on Type B glass beads (Type B-HR), as per Clause 721.A05.
| checklist | ITP - Stormwater and Subsurface Drainage Rev1 | itp | ITP - Stormwater and Subsurface Drainage | fcdf4262-b177-4341-aead-d0d14cd2de68
| section | 1 - Preliminary Works
| checkpoint | 1.1 Check for correct documentation
898e7514-dab7-5661-8faa-dd6333318203 | note | FREQUENCY: Prior to commencing any activity
37b35272-6e73-546d-92cd-7217005918c1 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
e2cd4045-b7f0-51cd-807c-91f12956eae0 | note | – using the correct and complete set of drawings
617df180-627e-5f1d-8eb5-5008c1ac3b08 | note | – all drawings are the latest revision
8672c42e-1c67-573e-8bc2-1cc93184ea9a | note | – Conflicting documents will be referenced to the hierarchy of documents listed in Section 175.03
27050c1a-226d-5a25-9e32-d8868cb7cbfa | note | REFERENCE DOCUMENTS: Drawings and drawing registers, Cl 175.03
eca9200a-29ef-5f2d-934d-fd9b79f4a13d | note | INSPECTION/TEST METHOD: Visual inspection
898b7140-b27a-5bd0-ba9a-b14ff6fc3d2a | note | RECORD OF CONFORMITY: This ITP Signed
5edfa41d-6281-5f32-aa0b-9b563286a51a | note | HP*
7ed06ee3-f215-573c-a741-e463040aca10 | note | RESPONSIBILITY: Site Engineer
d1f78816-d50e-5529-99ee-6d6b441f0104 | textbox | DATE:
| checkpoint | 1.2 Implementation of all measures and controls
a2a823da-1435-5b6d-b3b2-8a9ae0cf7902 | note | FREQUENCY: Prior to commencing any activity
646321ed-fb70-5995-bf64-4b5f95ee7ac8 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
7459c751-054b-577c-9ced-60463a94486c | note | REFERENCE DOCUMENTS: OHSMP, EMP, TMS, SWMS, WP
3211f07a-b288-58c2-9810-243994dcbbc6 | note | INSPECTION/TEST METHOD: Visual Inspection
a5a311ac-771f-54e0-b247-35a9c6e56500 | note | RECORD OF CONFORMITY: This ITP Signed
5ee8cb0e-6939-5772-bcb1-c9365c64cec1 | note | HP*
258ba98c-4365-50c0-a91a-05cc1b4265ef | note | RESPONSIBILITY: Site Engineer
c5e770c8-642a-5ec6-8f60-dabe8f8ec31f | textbox | DATE:
| checkpoint | 1.3 Material Classification
c3f7946e-e164-5a96-a70d-f42ece8e69ea | note | FREQUENCY: Each Lot
b612c77e-e278-5b27-9f2b-dcf30a743cf4 | note | ACCEPTANCE CRITERIA: Pipes supplied shall be of the category and diameter shown on the drawings or specified in clause 702.12 and shall comply with the requirements of the appropriate Australian Standard in accordance with Section 175 or as follows:
362f02e4-de01-55b8-a5da-9eb320c69fef | note | ○ Category 1: Perforated plastics Class 1000;
3f3a402e-7b65-5f74-8616-840d21c46d04 | note | ○ Precast concrete Class "2"
39e8052c-ced4-5503-a558-0e289e2f9140 | note | ○ Category 2: Perforated plastics Class 400
3cac9c73-e445-5edb-bec6-072b36200e64 | note | ○ Category 3: Geocomposite drains
0bd46a86-7d67-565b-a6a8-b6edc1f0727e | note | ○ Granular material as per clause 702.05, Geotextile material as per clause 702.06
0f70f197-3a8a-526f-93ba-65fedc0e8a2b | note | REFERENCE DOCUMENTS: Cl 702.04, Cl 702.05, Cl 702.06
0f7f8a18-58a1-5231-a3ab-4a25e10d4c64 | note | INSPECTION/TEST METHOD: Verify
f5989b64-ea7e-5d79-85c2-c93b3ecfc796 | note | RECORD OF CONFORMITY: Order acceptance certificate, This ITP signed off
607b288c-a80d-5a09-a38d-29eb44a4dfbc | note | IP
91950501-74e4-506f-bbdd-ec71780b17bf | note | RESPONSIBILITY: Site Engineer
2a8d5381-3c87-59b6-9d9d-56acc2ed7e38 | textbox | DATE:
| section | 2 - Procurement of Materials
| checkpoint | 2.1 Precast Reinforced Concrete Pipe Supply
2fc1f521-9f31-5ee7-9f8f-03038ac8d093 | note | FREQUENCY: Prior to works commencing
822952a4-cb91-5cd3-84d1-9f284d709ba6 | note | ACCEPTANCE CRITERIA: Pipe class and size and endwall type as per drawings and Cl 701.05
5e31eead-ed96-5cdc-b073-2b58af01a66c | note | REFERENCE DOCUMENTS: Cl 701.05, Drawings
256432bd-fa0a-5da6-a051-4cd1d43541f5 | note | INSPECTION/TEST METHOD: Verify
b18bb017-7252-55ef-bbab-d88e97a35ffd | note | RECORD OF CONFORMITY: This ITP Signed, Order acceptance certificate
3a91ee3f-1be2-5bf8-8d23-5fadfab3f02c | note | HP*
a35bc014-a6d3-5895-86cc-a0227f9c5e99 | note | RESPONSIBILITY: Site Engineer
220057ea-f0fd-5692-b119-0b4f61dd5f4f | textbox | DATE:
| checkpoint | 2.2 Precast Reinforced Concrete Inlet and Outlet Structures supply
51cef3dd-cc56-5520-99d7-65d3a6ec57b4 | note | FREQUENCY: Prior to works commencing
20a7e04b-b99c-5258-a907-fdc90cdec5d0 | note | ACCEPTANCE CRITERIA: The supply of precast inlet and outlet structures shall conform with D.S.G standard drawings
82a6bdef-f559-58e6-97c7-bf247f8c003a | note | ○ Concrete supply shall conform with Section 610 and reinforcement supply shall comply with Section 611.
89b30fc3-e08f-5343-9817-c9feee112f3f | note | REFERENCE DOCUMENTS: 610, 611, standard drawings
d8002c87-406b-5de3-b14c-d3579a0ecf69 | note | INSPECTION/TEST METHOD: Verify
8c5ed1e0-9fe4-5a56-bf77-e7cd4c4b2882 | note | RECORD OF CONFORMITY: This ITP Signed, Recievable Inspection Checklist
2742b9f9-c436-5291-b046-d83ecfafb0ea | note | HP*
9fac4714-9d2e-58f7-981e-db47470da5ae | note | RESPONSIBILITY: Site Engineer
8364790e-cd37-510a-949f-a778f7180712 | textbox | DATE:
| checkpoint | 2.3 Bedding and Backfill Material Specification
fcc6aed6-d2b2-5e23-894a-54f2e30bf518 | note | FREQUENCY: Grading 1 test per 1,000t
0bc211a4-b9f5-5775-8451-3052afa14de1 | note | ACCEPTANCE CRITERIA: Bedding and Backfill materials free from perishable matter and lumps and shall conform with the requirements of Table 701.091 and Table 701.092
89791a3a-ac6b-5c84-bbee-2050ccb50e25 | note | ○ Ordinary backfill shall be free from perishable matter and shall conform with the requirements of Table 701.091
c6f4e177-7e63-5519-9c8f-4d9c7719645f | note | REFERENCE DOCUMENTS: Cl 701.09(d), Table 701.091, Table 701.092
60f14e1b-b65e-56bf-8b8d-57b2f39f7bba | note | INSPECTION/TEST METHOD: Verify
fdee0419-703f-546a-afd0-f46b268d29dc | note | RECORD OF CONFORMITY: This ITP Signed, Quarry test report
d8dc2055-499d-566e-8104-690c62b917a2 | note | TP
feb2b1e1-317b-5e78-bdd9-187cc6eeaf55 | note | RESPONSIBILITY: Site Engineer
a03bc32c-7773-577e-a8de-a29d24d540e8 | textbox | DATE:
| checkpoint | 2.4 Setout of Works
85686a03-1a86-56c9-a71b-37b7c9d160d1 | note | FREQUENCY: Prior to works commencing
ff01c7cd-6a83-5a39-b773-c62d8739a34e | note | ACCEPTANCE CRITERIA: Hold Point
79c1dad8-10b3-5336-881a-12eac3e0cb8e | note | Prior to commencement of excavation for the culverts the contractor shall confirm the position of all culverts with the Superintendent
87d034ec-0b99-53a5-9d3a-3f0113b94764 | note | REFERENCE DOCUMENTS: Cl 701.10
7011f168-b521-5839-85dd-76eb71fdfbd5 | note | INSPECTION/TEST METHOD: Visual inspection
9237cb51-fa77-5cc2-b735-1c2f85dd1d56 | note | RECORD OF CONFORMITY: Survey records, pegs on ground & this ITP Signed
e2de0679-6b7d-510f-8125-242fa720fed1 | note | HP
f2546b78-e11a-5886-8a9a-ebfa25633723 | note | RESPONSIBILITY: Site Engineer / QAV
8c1825bb-8af9-56fe-a72d-bc1325cf0856 | textbox | DATE:
| signoff | AUTHORITY HOLDPOINT
| section | 3 - Installation of Underground Stormwater Drainage
| checkpoint | 3.1 Excavation Permit
393450d1-6de7-5467-a879-9b36c9aadf99 | note | FREQUENCY: Each lot
f391f343-8018-5464-93ae-fade7e0192e1 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
3a95b825-c406-59bb-90cf-41d8837fe680 | note | ○ Plant and equipment shall be appropriate for the task.
8743d191-d06a-5a1e-b1b6-b4bd77f872f9 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
c42a2928-7c43-5231-9250-3080df4164e3 | note | REFERENCE DOCUMENTS: Excavation permit
50a86928-f7a5-5452-9ebc-6af6e5f7ff1a | note | INSPECTION/TEST METHOD: Verify
58c90bf0-ee85-52b3-9588-aecbb7e773d0 | note | RECORD OF CONFORMITY: This ITP Signed
dd15c5bf-3cbc-5b48-a450-921baa7f2aec | note | HP*
b945fa48-c696-5b87-bb00-8edb5196d612 | note | RESPONSIBILITY: Site Engineer
afd6825c-676e-5e67-9d27-1b29b4b3aa7a | textbox | DATE:
| checkpoint | 3.2 Excavation for trench
c0ad9252-d105-532b-9d2c-f8703dc52784 | note | FREQUENCY: Each Lot
05437c52-13de-596e-8bd6-6f662694edd8 | note | ACCEPTANCE CRITERIA: Excavation for the installation of pipes shall allow for the clearance from the outside of the pipe to the wall of the trench between 300mm and 600mm;
e65dee8b-bd24-5814-a52c-64e40b6d9e3e | note | ○ The base of the trench shall be inspected to verify compliance with the requirements in this clause prior to placing bedding in comleted exacavations.The Superintendent shall be notified at least 24 hours prior to the inspection.
b4546c46-68ce-5386-b583-f023b4e4ee0f | note | REFERENCE DOCUMENTS: Cl 701.15 Table 701.151, Cl 702.08
cb90953d-cb3b-54f8-8da8-dd430415c209 | note | INSPECTION/TEST METHOD: Visual Inspection
0aa6eb74-06dd-5330-8143-c7e2973825a0 | note | RECORD OF CONFORMITY: This ITP Signed
c7fd10a9-3ff9-5c27-b129-8e8486d1cbcc | note | HP
de8c4530-bfaa-59d3-8ad6-da4a27c1c09d | note | RESPONSIBILITY: Site Engineer/ Superintendent
2a71a4e0-5b79-53a7-b288-d9fcfa72c90d | textbox | DATE:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 Trench Base Preparation / Bedding
6731dc4e-35e7-5c0f-b760-80541833c7db | note | FREQUENCY: Each Lot
6070aaa0-df17-5ede-95c7-c97c97d7c86a | note | ACCEPTANCE CRITERIA: Bedding material placed in full width of trench and compacted to at least 100mm thick, or; where the culvert is to be placed without trenching, to a width of 0.8m greater than the overall width of the culvert.
f4868af5-3772-5bad-a7eb-de73d52f18d0 | note | ○ Bedding of granular filter material of thickness between 25 mm and 50mm shall be placed across bottom of trench and shall be tamped and screeded or graded to level.
62b1cf16-1a4e-5b13-8f7a-9e8841dd8c00 | note | REFERENCE DOCUMENTS: Cl 701.16, Cl 702.09 (c)
346c060e-6444-52f9-b7b9-a46b41a45d94 | note | INSPECTION/TEST METHOD: Visual inspection / Measure
83ca6bad-8787-575c-8677-bd0e2bb8316d | note | RECORD OF CONFORMITY: This ITP Signed
211ec9ef-6b9f-58cc-a139-bbb49cc45193 | note | IP
7ae4e66a-5d3f-5605-b150-2e4b8dd15c02 | note | RESPONSIBILITY: Site Engineer
590c1575-7901-58d3-a1e4-e09b12bd3cee | textbox | DATE:
| checkpoint | 3.4 Laying/ Placing of pipes
269f4c58-9b91-59b2-bc2f-9ff2f6e92ca7 | note | FREQUENCY: Each Lot
8e4acf23-413b-58e6-ae14-e49498aed618 | note | ACCEPTANCE CRITERIA: Laying of pipes to commence from the downstream end. Pipes to be laid with rebate or socket end facing upstream and be fully entered. Departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250.
2949af9d-ab04-5463-aab0-e874ec2137c2 | note | ○ Pipes shall be placed centrally in the trench on the prepared bedding and held firmly in place
0342a6db-1cbb-5f90-b56e-f00f856b860a | note | REFERENCE DOCUMENTS: Cl 701.10d Cl 701.17, Cl 702.09 (d)
a48bb5f3-ab9c-5c2f-91a0-8ea301b778b9 | note | INSPECTION/TEST METHOD: Visual Inspection
efeb1238-bea4-5e25-aac3-4b1d80a07155 | note | RECORD OF CONFORMITY: This ITP Signed
98608911-1845-51a8-96ee-d791d1fd74fb | note | IP
9ea7f582-bda8-5a70-a4ad-8056f6bb24da | note | RESPONSIBILITY: Site Engineer
4dcf6f5d-0c2b-5daf-8235-95e9000bada9 | textbox | DATE:
| checkpoint | 3.5 Jointing
d756ac42-5866-5a70-ae31-f5991710884b | note | FREQUENCY: Each Lot
80875c08-d605-5392-a3f5-73ebc7b7ab77 | note | ACCEPTANCE CRITERIA: Rubber ring joint pipes shall be jointed with rubber rings. Rubber rings shall be kept undisturbed, clean, and free from dirt and other foreign materials and shall be stored undercover if pipes are not to be installed immediately.
2b0d47ba-3ec1-542f-8f51-39c7e163b488 | note | REFERENCE DOCUMENTS: Cl 701.18
16015501-b5d5-571c-b780-778df5efd500 | note | INSPECTION/TEST METHOD: Visual Inspection
942d0f5d-3108-544a-8853-a17dcd2d0615 | note | RECORD OF CONFORMITY: This ITP Signed
fafbcfae-416c-5517-a114-9ca52dd6a1d3 | note | IP
7ec40ed1-ec24-5f30-9f97-05d70081c56f | note | RESPONSIBILITY: Site Engineer
1f3cdcba-4058-553e-917f-798a5c7f3a5b | textbox | DATE:
| checkpoint | 3.6 Tolerance
9339a4b8-467a-5fb2-8b8c-15934eaf8b84 | note | FREQUENCY: Each Lot
770958ce-7ad8-5d19-8585-1e09911934f5 | note | ACCEPTANCE CRITERIA: Location of each culvert run verified by survey prior to backfilling and recorded in as-constructed drawings.
3b14de31-8a27-5b0f-b328-6ce7c0925e5c | note | ○ Tolerance:
d73780ca-4761-5de4-8cad-aaccc65a32ff | note | • Invert level of pipes at pits ± 50mm
28f88465-b29a-57a1-ad20-ee989016cd7a | note | • Departure from design grade of pipe runs ± 10mm in 10m provided min grade > 1:250
f8656dad-bf55-539c-ae30-6227568683a8 | note | REFERENCE DOCUMENTS: Cl '701.10
b2e20096-985c-5d80-99bc-4abdfb7c24c9 | note | INSPECTION/TEST METHOD: Verify
d73c0f45-ce9c-5d7d-8c7e-6b1069900531 | note | RECORD OF CONFORMITY: This ITP Signed
bfe5f741-13fc-5453-a738-822d60a93f86 | note | SCP
8d22c2d2-71c1-5cec-b6c3-42dd6db1e23e | note | RESPONSIBILITY: Surveyor, Site Engineer
f0a3f44d-31b2-5a7f-baf2-935c7e67c28d | textbox | DATE:
| section | 4 - Backfilling of Stormwater
| checkpoint | 4.1 Filling
bea23404-bd36-504e-9fdc-198fcaa41c5e | note | FREQUENCY: Each Lot
d32e711e-92ca-5af1-aae9-ff743c273254 | note | ACCEPTANCE CRITERIA: (i) Culvert Under Area to be Paved
4767e93c-9510-51d5-a79e-63d72bf1a074 | note | • The trench shall be backfilled to design subgrade level with selected material.
9fd97cef-d0d9-50ca-877a-727bc89db880 | note | (ii) Culvert Under Area not to be Paved
a57931e4-54ba-5aba-9c18-cc3044b0a756 | note | • The trench shall be backfilled with selected backfill material to a level 0.3 m above the top of the culvert and with ordinary backfill material above that level.
f1ace21f-6497-5aeb-afc7-d7c7f11d9c58 | note | REFERENCE DOCUMENTS: Cl 701.19
bca40b08-bb74-5acb-a9c6-11bf92fb12c1 | note | INSPECTION/TEST METHOD: Visual Inspection
11e96a62-2663-516b-af81-31e4b9df0844 | note | RECORD OF CONFORMITY: This ITP Signed
39a8299c-6e19-57da-9e4a-2aa544ed76a0 | note | IP
4361fcb1-d5c9-511c-8c88-830cf8f2c541 | note | RESPONSIBILITY: Site Engineer
40f6d4d2-7174-526a-8ece-8cc9400cff57 | textbox | DATE:
| checkpoint | 4.2 Placement of granular backfill
79ebb573-3e04-50f4-a5cd-8b4a19d3f506 | note | FREQUENCY: Prior to backfilling
f98b221e-4671-518c-82c1-aced05fd4e95 | note | ACCEPTANCE CRITERIA: Hold Point
d47e5101-a360-53ef-8e38-ea148b0a43ee | note | ○ Filter material shall be moistened and compacted with minimal disturbance to pipes. The method of compaction shall be in accordance with the submitted quality procedures
3762b944-3f80-5426-be19-bc155a254f84 | note | REFERENCE DOCUMENTS: Cl 702.09 (g)
28dd6eb1-b53a-58e3-8724-d351348f2940 | note | INSPECTION/TEST METHOD: Verify
310a4e2d-dc93-56d7-bf67-719d4ee988ee | note | RECORD OF CONFORMITY: This ITP signed
8a14478b-73c3-54da-b782-4ee247cd23a1 | note | HP
499257f7-83b3-557a-9d8f-8705b7f048ce | note | RESPONSIBILITY: Site Engineer/ Superintendent
fa36c5ec-95e5-5cb3-919c-f759df15c6a7 | textbox | DATE:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.3 Placement of no fines backfill
e17f1732-b9fc-5598-9ae9-e25ba124e8d1 | note | FREQUENCY: Each Lot
aaa4dcfb-5a8b-5544-98b5-5cbcd3d41ddd | note | ACCEPTANCE CRITERIA: Hold Point
c71eca3d-17d1-5342-a318-af6c237711d3 | note | ○ Where no fines concrete is used as filter material the Contractor shall submit quality procedures for review by the Superintendent which detail the method of placing the no-fines concrete to prevent segregation and the formation of a slurry layer at the surface of the concrete which may prevent the passage of water into the filter material.
ee8f0f47-b1a5-51fb-9601-fbbe9a76dd2d | note | REFERENCE DOCUMENTS: Cl 702.09 (g)
ffb73d37-e58f-5a39-8c2e-bd51c75d59a2 | note | INSPECTION/TEST METHOD: Verify
7efa27ff-e623-5855-81d4-33af502d7d41 | note | RECORD OF CONFORMITY: This ITP signed
a9f04834-c99e-5002-acf8-fff2bb56e206 | note | HP
3be51554-19c1-5592-8bdd-e6c5c723247c | note | RESPONSIBILITY: Site Engineer/ QAV
a4d1dca3-46a3-5017-aa29-6f70f7377875 | textbox | DATE:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.4 Testing and Acceptance of Fill Materials
ecfd01ae-1cb9-5f3b-9383-1c0bfeb59144 | note | FREQUENCY: 3 Tests per Lot tested with 20% of all Lots tested
9fe5d7ca-e369-5211-a88f-89fbd6a2f958 | note | ACCEPTANCE CRITERIA: Bedding and backfill materials shall be placed and compacted in layers not exceeding 150mm loose thickness and shall be assessed for compaction and moisture content.
4b27c704-14ff-52ca-a832-36e0a55f55c5 | note | Bedding shall be compacted to refusal using hand held mechanical equipment.
7bbe9a24-26a5-5fc1-9f02-599e9042b028 | note | Backfill material with nominal size < 40mm after compaction shall be compacted to a mean density ratio of not less than 97% CDR.
c9fb6292-f4e8-5357-af84-6c4ef4c10528 | note | Backfill material with a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
b0f28f8b-0919-5ea4-acc3-39774a71a6a9 | note | REFERENCE DOCUMENTS: Cl '701.20
e2f774dc-245c-5f30-b190-a5d86eaa187b | note | INSPECTION/TEST METHOD: Verify
0835774d-2ba0-54ad-85bb-8562d240e574 | note | RECORD OF CONFORMITY: Compaction Test Result OR This ITP Signed
440ea9eb-2eeb-5d55-bb16-177afd350e4a | note | TP
66024711-b384-5f60-b44b-e7d32348bba6 | note | RESPONSIBILITY: Site Engineer
09d01ea1-4173-579e-9521-d4abc0696131 | textbox | DATE:
| checkpoint | 4.5 Access Points and Flushouts
de3d094d-99a8-56ff-868f-3dcd03451c78 | note | FREQUENCY: Each Lot
6b6bf6cb-5a14-597d-bbb9-1445c77fce06 | note | ACCEPTANCE CRITERIA: Access point installed at the beginning and end of the drainage run and inspection openings at intervals between 100m and 150m. Flushout risers have same diameter as pipe.
a8429c87-9beb-57f6-a136-1b92e65a0625 | note | REFERENCE DOCUMENTS: Cl 702.10
240a4ee1-a3f6-53c9-85da-c23aa0fc93ba | note | INSPECTION/TEST METHOD: Verify
019a80b8-de01-59bb-98e9-3047ac534757 | note | RECORD OF CONFORMITY: This ITP signed
94e999ef-b9e0-59ed-9452-1033ca2161bf | note | IP
964c3bd1-4a2e-54fb-9a4f-c05b85a3c44f | note | RESPONSIBILITY: Site Engineer
f6244277-045c-59cb-a847-c378132926d0 | textbox | DATE:
| checkpoint | 4.6 Flushing Test
70c9c536-ee4d-5f62-af9e-474ad074f694 | note | FREQUENCY: At completion of stage
3de231b1-01db-53a5-add6-0302b85a0cb0 | note | ACCEPTANCE CRITERIA: Flushing test undertaken on each subsurface drainage line after completion of the drains, flushers and risers, and after completion of barriers and road furniture. The test should be witnessed by a representative nomitated by the superintendent. Record of flushing tests must be kept.
0c347830-f501-5725-a22a-999ceb27b062 | note | REFERENCE DOCUMENTS: Cl 702.09(h)
6efbb03f-9419-51f6-8ab4-c704e5220999 | note | INSPECTION/TEST METHOD: Site inspection
7e39d53e-56af-5442-bb50-cf560a8ad8a0 | note | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
32cb04d1-d2a3-5000-b6d8-0aa54bb32bd0 | note | TP
26a1f10e-3748-59ed-85a3-6bdfd22594b9 | note | RESPONSIBILITY: Site Engineer / QAV
99d2c3e0-7acc-5d05-afdd-41a32e0cd885 | textbox | DATE:
| checkpoint | 4.7 Installation of Inlet or Outlet Structure
3d1d7260-8c3c-537e-9a3a-6d7901f30ee0 | note | FREQUENCY: Each Lot
c5a22123-3936-5268-b65b-d8f5b2c00fd4 | note | ACCEPTANCE CRITERIA: Inlet and outlet structures shall be installed to a tolerance of +-20mm where matching kerbs or barriers or +-100mm in all other areas.
0f08fcb3-8ced-547e-bdd7-5546b535338c | note | REFERENCE DOCUMENTS: Cl '701.10 Cl 701.25
0e24a387-be45-53e1-8d35-ac1f790e71e0 | note | INSPECTION/TEST METHOD: Verify
d8297baa-3301-5a09-a2a5-0d2d65fbf639 | note | RECORD OF CONFORMITY: This ITP Signed
b8996a2e-c51f-5cce-a36c-9e2c218bfdd8 | note | IP
d5ca9678-f9ab-5107-8a61-c4f888c15738 | note | RESPONSIBILITY: Site Engineer
9046e811-0de2-5165-bb1a-84690d360034 | textbox | DATE:
| checkpoint | 4.8 Culvert Coverage
1ed6e044-3008-5b4d-96cc-7eed4a1f11ba | note | FREQUENCY: Each Lot
87f5c461-5f15-588f-a9f3-5c63cd99224c | note | ACCEPTANCE CRITERIA: Until the minimum compacted thickness of cover in Table 701.141 for axle or track loading has been provided, construction traffic shall not be permitted to cross the culvert.
f1069a68-0188-5c2b-96ce-b593292e2392 | note | REFERENCE DOCUMENTS: Cl 701.14 Table 701.141
b8162ca8-3498-5775-bede-167688524398 | note | INSPECTION/TEST METHOD: Visual inspection
fa3b0516-398a-544f-b0cb-9168f64e3a5b | note | RECORD OF CONFORMITY: This ITP Signed
083d870c-5271-50bd-ba22-dc7c0c785fec | note | IP
345a7555-7a52-5cb4-9f1a-9397e9777530 | note | RESPONSIBILITY: Site Engineer
4b69b333-63b0-569c-9cbd-090468b21817 | textbox | DATE:
| section | 5 - Subsurface / Subsoil Drainage
| checkpoint | 5.1 Excavation Permit
9c859b0b-e465-5795-b453-3ac84bd4a187 | note | FREQUENCY: Each lot
59faf9d4-6848-5627-945d-5d74b98f0f1c | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
a72dfab7-6510-5571-8ccb-8ee11a21789d | note | ○ Plant and equipment shall be appropriate for the task.
95c80582-846e-5876-917c-2af11ce66dc9 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
686c6e03-5e3a-5fe2-a47b-6d107383ce53 | note | REFERENCE DOCUMENTS: Excavation permit
d3df2ee9-a69d-52ac-bd1c-f2dee5e53667 | note | INSPECTION/TEST METHOD: Verify
a1362ca6-fd5f-523c-9a03-5b4670af8f17 | note | RECORD OF CONFORMITY: This ITP Signed Off
1eb385ab-5d33-57f9-8a50-13f5ebed4de2 | note | HP*
d86d34f9-77c9-5280-a924-c88da4fdfb40 | note | RESPONSIBILITY: Site Engineer
ff23cec9-9970-5ca5-a77f-632956976d5d | textbox | DATE:
| checkpoint | 5.2 Excavation of Trench
48ca7ff0-bff5-5da1-bc37-11f24f5c114d | note | FREQUENCY: Each Lot
1c85a894-914c-5b7b-b6e2-f6ad205b2a17 | note | ACCEPTANCE CRITERIA: Hold Point
61b98550-17b4-5c08-b380-0a4ddf6d4648 | note | ○ Bottom of trench shall be compacted and at a depth no more than 50mm below the specified pipe invert. Grade of the base of the trench shall not allow ponding of water Any loose material shall be removed. To be inspected by Superintendent
a070f604-d71f-5b2d-98e2-c73d317753f4 | note | REFERENCE DOCUMENTS: 702.08
6f535fa3-36f7-51b0-b21f-13316c50d5cf | note | INSPECTION/TEST METHOD: Visual Inspection
042ea146-dbe1-55f6-9d15-883ed5918a72 | note | RECORD OF CONFORMITY: This ITP signed off
2f856a8e-802e-5138-a367-045ec1933dc4 | note | HP
c239226a-dc73-56f9-b9b3-f4ef1a21c05f | note | RESPONSIBILITY: Site Engineer/ Superintendent
6bee5c74-468c-5c69-a6c9-3a1d3c64aec2 | textbox | DATE:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 Placement of bedding
e9c8ff25-e5b2-505d-a961-4c63fd574d26 | note | FREQUENCY: Each Lot
e7751ee4-e621-534d-b4f6-a60faa53ef80 | note | ACCEPTANCE CRITERIA: Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level
d6c59c0f-72f8-5e7d-822a-2d75ea356c9a | note | REFERENCE DOCUMENTS: 702.09 (c)
6134804c-1b5d-5973-b1e0-f20a1f78c91d | note | INSPECTION/TEST METHOD: Visual Inspection
3e532613-80d7-58c5-bdf1-830480e9640a | note | RECORD OF CONFORMITY: This ITP signed off
27888c90-88cb-563c-a6b8-45317e434705 | note | IP
9a204715-a5e4-5ff5-ac47-c3f73e82b7cb | note | RESPONSIBILITY: Site Engineer
22acee40-205e-5a5b-b031-88232ca3f9ed | textbox | DATE:
| checkpoint | 5.4 Placing pipes and geofabric (if required)
0c221870-f3fd-5114-8ba6-8941b3079d43 | note | FREQUENCY: Each Lot
206730b6-ca9b-5c5e-8452-91f667e73229 | note | ACCEPTANCE CRITERIA: Pipes placed centrally in trench and held firmly in place positioned with openings at the lower half of the pipe.
68d0f06f-007b-5822-a03c-b13f61b1b48c | note | ○ If geofabric required (subsurface drains installed in expansive materials), minimum width of geotextile used for wrapping is 450 mm
4cd55e8b-201f-5c48-9c13-ca0091df2b54 | note | REFERENCE DOCUMENTS: 702.09
3526636b-c525-5cd8-b723-da4154c908ef | note | INSPECTION/TEST METHOD: Visual Inspection
b77106d1-4c0f-5f1e-af63-eb7f5db71c5e | note | RECORD OF CONFORMITY: This ITP signed off
e285e52e-56f4-585d-94b9-64e8f654a527 | note | IP
6efd644a-3489-50c4-bff6-e9d0c01af5ed | note | RESPONSIBILITY: Site Engineer
e6782a62-f254-5627-a418-0a37f3f50245 | textbox | DATE:
| checkpoint | 5.5 Placement of granular backfill
49bad691-1de8-5b64-b2ee-03a98a412746 | note | FREQUENCY: Prior to backfilling
7f641861-baec-5132-a9f4-0a2c641264d4 | note | ACCEPTANCE CRITERIA: Hold Point
37cb3b78-2b1e-5878-b14e-76409d25e334 | note | ○ Filter material shall be moistened and compacted with minimal disturbance to pipes. The method of compaction shall be in accordance with the procedures and reviewed by the Superintendent.
7a0e786d-8498-549e-a59a-f38a1a2a3cc7 | note | REFERENCE DOCUMENTS: 702.09
ba9b95d3-d1f5-5ddd-bacd-f1f1b7cb99e4 | note | INSPECTION/TEST METHOD: Visual Inspection
dc93d0f1-6ffb-56c0-af57-a7da4c943df5 | note | RECORD OF CONFORMITY: This ITP signed off
c190f9e3-46c9-5634-af70-9579d4603a39 | note | HP
7c0f2f5a-5cd5-5777-8c30-b3b3e08280f8 | note | RESPONSIBILITY: Site Engineer/ Superintendent
d5545604-cdc6-5323-bee2-e07117ad266b | textbox | DATE:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.6 Placement of backfill
defbfd53-410f-545e-af9f-5c420703b043 | note | FREQUENCY: Each Lot
ae6dfcc8-ef38-5421-b375-cf9e4d8dcd33 | note | ACCEPTANCE CRITERIA: Granular filter material placed and compacted compacted in layers not exceeding 300mm with minimal disturbance to pipes. Concrete is to be placed and compacted within one hour of mixing
fca74f9d-62e7-56be-94cd-9c7dabf86ba4 | note | REFERENCE DOCUMENTS: 702.09 (g)
b86d717e-c2c3-561b-a4cc-df510136cc0f | note | INSPECTION/TEST METHOD: Visual inspection
9fefed17-fc69-5012-978b-e7abe5c29c52 | note | RECORD OF CONFORMITY: This ITP signed off
34d5630a-3261-5306-b335-fb3cbd86a028 | note | IP
1001a7f3-d131-5e37-916c-c2f5a71a3a5c | note | RESPONSIBILITY: Site Engineer
02e9bf9d-e9b1-5be4-b5b4-5d0f30d7ee4b | textbox | DATE:
| checkpoint | 5.7 Install Pits and Flushouts
dee58bd6-96c0-5b0d-8ccb-43f1591a580a | note | FREQUENCY: Each Lot
aadcc76e-b6f4-5720-b1e1-d640666c0bcf | note | ACCEPTANCE CRITERIA: Installed in accordance with drawings and Cl 702.10
0c9822c2-0b31-5abc-aed7-fcaeac75481b | note | REFERENCE DOCUMENTS: 702.1
71a2252e-10b6-59da-bc76-6e309670878f | note | INSPECTION/TEST METHOD: Verify
475f0bc8-331b-55cf-8a21-84e38208d085 | note | RECORD OF CONFORMITY: This ITP signed off
5e7b6f07-a1f3-5fc3-8a04-4a0618a0ade2 | note | IP
8f22dca2-2b44-5f25-a042-38abb59a3716 | note | RESPONSIBILITY: Site Engineer
3ba53792-2523-5fba-93ba-b2266f6b84b3 | textbox | DATE:
| checkpoint | 5.8 Flushing Test
3f0025e6-f2bd-53ae-8ef6-60067da76e95 | note | FREQUENCY: At completion of stage
7eb5e85c-4de7-5eab-87e2-852c9daf3e33 | note | ACCEPTANCE CRITERIA: Flushing test shall be witnessed by a representative nominated by the superintendent and shall confirm that the drainage line is free of obstruction. To be complete after installation of kerb and channel, barriers and road furniture.
2bf9f472-5e74-5ebf-92c5-a1cfc6733d86 | note | REFERENCE DOCUMENTS: C702.09(h)
84cdb2b3-0859-587a-91a6-669d44e69723 | note | INSPECTION/TEST METHOD: Site inspection
1f469a92-a82b-587a-a900-6401d14ce20e | note | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
07adb622-d46c-533b-b41a-fc8c5178c37b | note | WP
35ed1a00-6de0-50e4-bf46-ab3eb9aae830 | note | RESPONSIBILITY: Site Engineer
8a8b8e44-25c6-5655-8dc8-5ff1654894b6 | textbox | DATE:
| section | 6 - Finishing and Commissioning
| checkpoint | 6.1 Finishing and Rendering Pipes
4e34d7ac-dd09-558e-8aaf-1b0ff3c71f14 | note | FREQUENCY: Each Lot
ad54c4c0-fe78-5bc8-9f06-fc92bd4fbffc | note | ACCEPTANCE CRITERIA: All stormwater inlet and outlet connections shall be cut trimmed neat and finished with cementitious mortar.
3202c75b-f1c0-5dc9-a584-9c9cef50ec43 | note | REFERENCE DOCUMENTS: Work Procedure
9c0253a4-3266-5078-a63e-afb26826352e | note | INSPECTION/TEST METHOD: Verify
91fa2416-c764-5b57-84bf-79b40ab3b53f | note | RECORD OF CONFORMITY: This ITP Signed
bdbb597b-8995-5595-af25-8e2a4437c72a | note | IP
b0768f59-858f-5523-b1f2-562f045bb975 | note | RESPONSIBILITY: Site Engineer
c9eb5fba-da05-59d6-a260-beb40c8f449f | textbox | DATE:
| checkpoint | 6.2 Inspection of subsurface drainage lines
9aa588b3-1f7d-5d93-8736-bd04d3e39d09 | note | FREQUENCY: At completion of stage
c96c61bd-c9a6-5fd5-987d-498cb47bea1f | note | ACCEPTANCE CRITERIA: Hold Point
b17dbc38-0cf0-5fcb-8317-2f8fd5e625d1 | note | ○ All subsurface drainage lines constructed shall be inspected, after completion of the flushing test and prior to placement of asphalt, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
7712377f-afe2-59b2-9c1d-101347334c5c | note | REFERENCE DOCUMENTS: Cl 702.09(i)
d2701266-8c15-5acf-a267-3233f39aa8cb | note | INSPECTION/TEST METHOD: Site inspection
6c343355-2e8b-5694-8d65-180b7ff714b6 | note | RECORD OF CONFORMITY: This ITP signed
2c4ae361-daa5-5abe-9472-f0b392d03ce8 | note | HP
59bb08f1-fb81-510a-b89b-e01b04e4b920 | note | RESPONSIBILITY: Site Engineer / QAV
ac9cd61c-7cde-5181-992b-d2c9125d4a7c | textbox | DATE:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.3 Repair of Damaged Pipes
96a49025-ac02-5062-8aed-385b5e18af5d | note | FREQUENCY: Each Lot
9b9fc934-b888-5cec-b56e-aa2814f036e0 | note | ACCEPTANCE CRITERIA: Damaged pipes shall be repaired in accordance with 701.31 of the Specification, no repairs shall be undertaken without the Superintendent's approval of the repair materials and procedures.
e194365b-e8ae-597c-a40f-2d49862c6a9b | note | REFERENCE DOCUMENTS: Cl 701.31
ba3399f2-ee4a-5dd9-8868-1c61862de5f2 | note | INSPECTION/TEST METHOD: Verify
5d219f58-20fa-57ec-b7f8-39e167a8fde5 | note | RECORD OF CONFORMITY: This ITP Signed
45c987b9-51a9-5205-83c9-826c9c423a1a | note | HP
e2f03450-af05-54c7-9300-137b9cc91bee | note | RESPONSIBILITY: Site Engineer / Superintendent
4ea1d478-a2ca-5e29-b788-18ab282f42af | textbox | DATE:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.4 CCTV
be35d42f-2c30-5cfa-a842-7f33a59ab1b1 | note | FREQUENCY: Each Lot
d0446646-80c5-543b-a415-1602045dc042 | note | ACCEPTANCE CRITERIA: Hold Point
b7920f29-490a-529c-8a92-6e409678c5e6 | note | ○ All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
1554acc8-566a-5436-9daf-9a59970e05fb | note | REFERENCE DOCUMENTS: Cl 701.30 WSA 05-2013
caab3758-f0e8-5b80-9d0c-72ced53c88cd | note | INSPECTION/TEST METHOD: Verify
371048ea-d0df-59d6-b308-c305fe2f7b83 | note | RECORD OF CONFORMITY: This ITP Signed
beddff78-0368-5b36-b2d1-5eb8bd29b7c8 | note | HP
25873871-f238-5f7a-aa54-b8c443469c60 | note | RESPONSIBILITY: Site Engineer / QAV
8dd193ab-1bdd-573d-9361-7d7dc7a938d7 | textbox | DATE:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
a55f0d04-cdb9-5669-8954-ad39b668adff | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
d0e6a43e-4de9-5ed7-9f59-ae0bf708050f | textbox | Print Name:
2ef7f99e-55e0-542e-bf23-d66bb8f95cc3 | textbox | Position:
bc687a38-d72c-5f79-a212-10297c224829 | textbox | Date:
| signoff | Add Signature
| checkpoint-no-value | Table 701.091
18469a34-be15-5990-adfe-be6c3649f25d | note | Sieve Size - AS (mm) ¦¦ Percentage Passing (by mass)
33925c83-6bfd-5d58-a3b5-c9f826da6f18 | note | – – – – – – – – – –
5530eff7-7e8f-5aa3-9576-ae7101e1ba4f | note | Material: Backfill
5df78dff-32c6-5f76-b562-c7c04f287ffc | note | 75.0: - ¦¦ 37.5: - ¦¦ 19.0: 100 ¦¦ 2.36: - ¦¦ 0.075: 5-40
5f76b959-a3d8-50cb-8621-209b4056d964 | note | Material: Selected Backfill
a7cd150c-6324-5d38-9377-c9b5b849e3dc | note | 75.0: - ¦¦ 37.5: 100 ¦¦ 19.0: - ¦¦ 2.36: - ¦¦ 0.075: 5-40
305aa1e7-5f4b-5eda-8234-cfba4fc538e3 | note | Material: Ordinary backfill
72ad9756-c581-567c-8ab8-5a6f25c84126 | note | 75.0: 100 ¦¦ 37.5: - ¦¦ 19.0: - ¦¦ 2.36: 40-100 ¦¦ 0.075: -
| checkpoint-no-value | Table 701.092
48b3d925-1cd9-5578-8fb6-319ec46d2442 | note | Test ¦¦ Test Value
3c7e1f2c-495b-54de-bdef-415e004847cf | note | Plasticity Index (Max.) ¦¦ 20
| checkpoint-no-value | Table 701.141
6ac7290a-761d-55eb-b28a-46a951ffccab | note | Required Cover Thickness (Metre) (Min.)
52fc8b30-5bc9-5cd7-ae40-ab415c2ff732 | note | Type, Size, and Class of Culvert
46124be7-24d5-5621-97e0-26dc50f5ee2f | note | – – – – – – – – – –
a5e47deb-4b1a-5cf7-b7de-6c4cb6b2e9cd | note | Range of Axle or Track Loading (tonne): 0 - 9
d96b8cfc-4b32-5af0-9e10-c6354b8579b6 | note | • Pipe 2
e3739b6d-c6a3-53ca-9f7e-26c96a46cb88 | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
65759e99-13cf-5c13-80a3-cf0523bbee14 | note | 0.4 ¦¦ 0.4
ee91cadd-46a0-586d-9e35-32e18f4f52c0 | note | • Pipe 3
211c158e-68e8-5316-815f-d3ff954deb03 | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
249535de-3ccf-58c8-b671-6a16ef3be54e | note | 0.4 ¦¦ 0.4
5ea99bca-ec52-5dc0-9ca5-01ab6f4f99c6 | note | • Pipe 4
4331096a-aa7b-5686-9eca-8e62da32ed8c | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
40ee07d3-dcf2-5067-9fc8-6cc88858ee60 | note | 0.4 ¦¦ 0.4
087a965b-dd03-5587-af20-b88b5cd629dc | note | • Corrugated Metal: D 1200-3600 mm ¦¦ Box Culvert 90 kN Proof Load
02e9691f-05b6-502b-931c-e57c22fd98b8 | note | - ¦¦ 0.1
f54f084e-2773-5055-a67c-08c81801a687 | note | – – – – – – – – – –
3fd2fb20-3218-5d9e-99ba-22da33c36d58 | note | Range of Axle or Track Loading (tonne): 9 - 20
95803705-83bd-5bd5-b2b8-e4d3def54354 | note | • Pipe 2
ea16daaa-37e9-5c19-945c-33ac04fb842e | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
1979ca58-ce35-5399-bc45-d7499f04f7e7 | note | 0.4 ¦¦ 0.4
75db399e-1159-542c-86d8-939a3d4cec5c | note | • Pipe 3
159cd2cd-21f5-58ae-8fd1-926ba0f09772 | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
e814c803-8e3d-52d7-8a45-9497469fc462 | note | 0.4 ¦¦ 0.4
0d994b40-dbc3-531c-bd3c-09e2a3c16a81 | note | • Pipe 4
e02487cc-f023-59c5-9501-678fb7bf0aaa | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
3e9c6404-3f36-5d7a-b5c6-e45396f1c663 | note | 0.4 ¦¦ 0.4
adbffb2a-1478-501f-a847-03cce24784d4 | note | • Corrugated Metal: D 1200-3600 mm ¦¦ Box Culvert 90 kN Proof Load
a8f8f53f-844e-5acc-ac8d-b3fade3acbb0 | note | 1.2 ¦¦ 0.6
1d2820be-8c4d-5eef-b07f-1dc8e033b25d | note | – – – – – – – – – –
1a7d1168-f33e-56d3-927c-54b0365167a6 | note | Range of Axle or Track Loading (tonne): 20 - 35
e8e77cf7-a1e3-5066-9e6c-98aba3d10476 | note | • Pipe 2
9de955f1-8edc-599c-8811-470160af2c1d | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
3c8f0f75-18da-567f-b3ce-a845e3612977 | note | 0.7 ¦¦ 0.4
98131caf-2f66-5bdc-a69e-f4b41d2183ad | note | • Pipe 3
5d4c5757-63be-5fe4-8926-ba8b856ef4d6 | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
2bcb72f4-c519-58be-a517-9df678b31b12 | note | 0.4 ¦¦ 0.4
1ebabca3-996e-5ab3-b051-371529e36158 | note | • Pipe 4
1ec38cb4-0720-58f8-8f7f-e79e51fa82be | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
611104b9-3e35-545e-aa03-d77ad48fe145 | note | 0.4 ¦¦ 0.4
7e86ed97-c047-56d7-bb76-8477bef4279a | note | • Corrugated Metal: D 1200-3600 mm ¦¦ Box Culvert 90 kN Proof Load
94637e5c-4ceb-5c7a-8bc8-cf664fd678b7 | note | 1.5 ¦¦ 0.9
03263d0d-c7de-5137-9766-44c02c702bce | note | – – – – – – – – – –
11dd6fd4-34d8-568c-a0a6-e40d8eafd3e1 | note | Range of Axle or Track Loading (tonne): 35 - 50
cf2f41e7-4ae6-50a8-b26b-a57cd600c7e4 | note | • Pipe 2
dfca53b4-8e68-52ce-9b5a-06965dec8f3b | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
8694f993-5109-552b-9bbd-f91a12719813 | note | 0.9 ¦¦ 0.7
044f98a0-d176-5f2a-926a-d1236c6ba712 | note | • Pipe 3
e2995043-4049-54a1-8ced-fbd3ebcfc523 | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
f1f09f0d-c69d-5ea4-8b48-aa6d3f97bd44 | note | 0.6 ¦¦ 0.5
0f137d59-b637-573d-95c8-e8aa2a52e118 | note | • Pipe 4
1469d6df-0a9a-5fc5-b225-076384b6a635 | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
c7ad40c9-2a2f-55d6-ac2f-083f196e5dc0 | note | 0.5 ¦¦ 0.4
f79904be-f5a9-5ce1-a621-92ec568fa38a | note | • Corrugated Metal: D 1200-3600 mm ¦¦ Box Culvert 90 kN Proof Load
eb221ce1-738a-5e5c-9c0b-d12bae51c21d | note | 1.8 ¦¦ 1.2
91792818-4926-52d2-928d-d2128b9a2213 | note | – – – – – – – – – –
c736ea5d-1a0d-5163-8ce1-841949a4d8f8 | note | Range of Axle or Track Loading (tonne): 50 - 60
7ba2048c-fbb7-551d-9d62-0c1c1c74e532 | note | • Pipe 2
d93dc93d-38ad-5121-a7a3-b4e602ca7a0f | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
7c6dbb5d-c79b-5fce-b9c9-679839875d65 | note | # ¦¦ #
16efadc0-f168-52c4-8310-4f28beea080e | note | • Pipe 3
1e186793-9943-585f-9e16-2df9c57e2768 | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
ef9eca64-5f41-5359-a1ba-9fa02ab59b85 | note | 0.8 ¦¦ 0.8
ff6d27a0-201e-5b6d-9a2d-907a1ca63f5c | note | • Pipe 4
fb18ada2-6066-51d6-a87c-713823b07dc6 | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
09d2d8aa-f8c5-5cde-9e65-1506a084a2d0 | note | 0.7 ¦¦ 0.7
756e778e-58e9-5b9f-a1ed-ef68b7effe28 | note | • Corrugated Metal: D 1200-3600 mm ¦¦ Box Culvert 90 kN Proof Load
4cf7d1a2-cb29-58a7-8ce3-8cf172a06c45 | note | 2.1 ¦¦ 1.5
8b3e00ef-28df-57d7-815d-3bdcdd340535 | note | – – – – – – – – – –
fcbd4d54-088e-5b91-a80f-0efbca5288ad | note | # This range of loading not permissible.
287118cd-09ae-5a00-9451-8ddf46babaf9 | note | D Nominal Pipe Diameter
b20ea80a-15ed-54ea-bd4a-94fef6838e84 | note | D less than 1200 mm not permitted, D more than 3600 mm as directed by the Superintendent.
| checkpoint-no-value | Table 701.151
8807e7a2-a150-5910-9f38-5590d6c38afd | note | Pipe Type ¦¦ Nominal Pipe Diameter or Width (mm) ¦¦ Horizontal Clearance to Wall of Trench :: Min. (mm) / Max. (mm)
7f559d1b-839b-5a72-ba48-47ce4b398df3 | note | – – – – – – – – – –
ffd6dcfc-993e-5b94-adec-f65de89972cb | note | Corrugated Metal Culvert ¦¦ All :: 300 / 1,000
50afba7e-09b6-52bf-92a3-5f00dfd4dba9 | note | Other ¦¦ All :: 300 / 600
| checklist | ITP - Surfacing - Asphalt Placement & Spray Sealing Rev1 | itp | ITP - Surfacing - Asphalt Placement & Spray Sealing | e38a14f2-5853-43e7-986d-406b9ee83275
| section | 1 - Preliminary Works
| checkpoint | 1.1 Submission of Mix Design
bc83e25f-cdab-576b-8c89-2be9a8229178 | note | FREQUENCY: Prior to commencing paving
be8b1839-1ea8-5a6e-80c1-9b0764d50f2d | note | ACCEPTANCE CRITERIA: All asphalt mixes proposed for use in the works shall have a mix design registered by the Victorian Department of Transport as 'General', unless otherwise approved by the Victorian Department of Transport.
7ce05f60-2831-5d8c-af09-4db6ad3a8a29 | note | ○ The registration for all mixes incorporated into the works shall be current at the time of their use. The contractor shall submit documentation to the Superintendent nominating the asphalt mixes to be supplied no less than 7 days prior to their use.
812c190b-8240-5d20-bd32-32fc75c2fdd3 | note | REFERENCE DOCUMENTS: Cl 407.09
97e9595e-fafd-5eed-a678-09eab753399f | note | INSPECTION/TEST METHOD: Verify
64256c58-0fa9-57e5-8a37-e76f97151125 | note | RECORD OF CONFORMITY: Mix registration & correspondence
7cdba958-093f-5258-8702-7d6862f80476 | note | HP
0187c25f-0fb0-59fe-a963-a76a4330e515 | note | RESPONSIBILITY: FH Engineer/ Superintendent / QAV
ff61f4ed-3169-5b51-ae30-ad70472996a4 | textbox | DATE:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2 Implementation of all measures and controls
85b680e6-58ba-5535-8d01-f1747c6033e6 | note | FREQUENCY: Prior to commencing any activity
da76ba55-c8cc-5a2d-8907-3053c499ff84 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
e134f8c3-6859-557f-a36a-b61142ec578e | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
ccd18a02-31ac-5448-89c6-0ca0bdb56df3 | note | INSPECTION/TEST METHOD: Visual Inspection
d8218b4a-a963-5828-bf19-fa20b8aa768b | note | RECORD OF CONFORMITY: This ITP signed off
8c529f50-28cf-596e-8ebd-fb1c88448e94 | note | HP*
2ffdfcf9-7364-54b0-bc68-c06140eed628 | note | RESPONSIBILITY: FH Engineer
392560c5-522a-5ca2-807a-3481ae3dd6a5 | textbox | DATE:
| checkpoint | 1.3 Site Inspection and Base Condition
bdef9148-dae4-5dea-b8d9-73ca3590a44d | note | FREQUENCY: Prior to commencing paving
00e6f78b-bcc7-5930-8313-43d9ea2b845c | note | ACCEPTANCE CRITERIA: The surface on which asphalt is to be placed shall be essentially dry and free from surface water. Asphalt shall not be placed when the pavement surface is wet, or rain is imminent.
4c0a2ac9-f5c1-5a88-a3a7-25613a02a372 | note | REFERENCE DOCUMENTS: Cl 407.17 (a), AS2150 10.1, AS2150 10.3
71f22a03-c81b-5dc6-91fe-d0c58d5b87b4 | note | INSPECTION/TEST METHOD: Visual Inspection
0f7f7ec4-1e50-560f-8aa7-0d04991460fc | note | RECORD OF CONFORMITY: This ITP signed off
a48cd28e-1ebc-5f38-9453-c8fa8d89f812 | note | IP
969156da-b7fb-506b-a44a-8ecfc15c3710 | note | RESPONSIBILITY: FH Engineer / Superintendent
8c890a12-fe13-5dd4-bc08-709839b3ea88 | textbox | DATE:
| checkpoint | 1.4 Ambient Conditions for Placing
1a7b7c9f-bf4c-5a99-9e91-cad75f3ee56a | note | FREQUENCY: Prior to commencing paving
7eced97b-7d9a-50f5-9940-aacbca27e227 | note | ACCEPTANCE CRITERIA: Asphalt shall not be placed when majority of the area to be paved has a surface temperature less than that detailed as follows:
ae90d6f7-7f4b-5d15-866f-f1dd98dd1703 | note | ○ Base or Intermediate Courses: 5°C for specified binder class of C170 or C320; or 10°C for asphalt mixes with specified binder class of C600 or containing a PMB.
41059885-e465-5628-8b5f-160dda23ca51 | note | ○ Wearing Course: 10°C for specified binder class of C170 or C320; or 15°C for asphalt mixes with specified binder class of C600 or containing a PMB.
52664c48-e7fe-5a65-8460-3b8bf058da82 | note | REFERENCE DOCUMENTS: Cl 407.17 (a) Table 407.171
6ea541e7-928b-5ace-92e1-c82a0c5248fd | note | INSPECTION/TEST METHOD: Verify
a1ff6181-fde5-5ebe-9588-161ac1fff6c2 | note | RECORD OF CONFORMITY: This ITP Signed off
0f7b4577-e206-50e4-8605-024eab87182b | note | IP
8688e3a4-b512-574a-8499-bc30058b8e2d | note | RESPONSIBILITY: FH Engineer / QAV
6e77f8f6-403e-50a4-bce7-beeb5ebb1eac | textbox | DATE:
| section | 2 - Material Procurement for Spray Seal
| checkpoint | 2.1 Adhesion Agent
b510f552-4805-504a-917e-c7a00da43021 | note | FREQUENCY: Test cert. upon request
1f318640-c7f7-5126-9f54-a9ff78aaa59a | note | ACCEPTANCE CRITERIA: Satisfactory field performance. When adhesion agent is added to the binder, the total volume of adhesion agent ≤1% of the binder.
e6e7afee-f608-5cb3-8cca-9e04f427ab29 | note | REFERENCE DOCUMENTS: Cl 408.09 (a),
3d950707-f524-58a7-bfae-2bed2c78d14d | note | INSPECTION/TEST METHOD: Verify
d1d46218-02f1-545a-bbf4-f21963de1491 | note | RECORD OF CONFORMITY: This ITP Signed off
69f18e62-502b-52bf-a276-2f17e392e177 | note | IP
d20639fe-b136-5700-9639-495dc9f0c21c | note | RESPONSIBILITY: Site Engineer
2e56dff5-cb9f-58ae-aa4d-d216b2a8acba | textbox | DATE:
| checkpoint | 2.2 Aggregate Precoating Materials
3fe60873-8222-5603-bf1e-3d500265cd04 | note | FREQUENCY: Test cert. upon request
a1c33861-7530-5d19-9bdc-7792a3e5d125 | note | ACCEPTANCE CRITERIA: Aggregate Precoating Materials shall be distillate, distillate based product, cutback bitumen, emulsion based product or proprietary product.
05a18a23-cf9f-541e-81b2-5efc50037330 | note | REFERENCE DOCUMENTS: Cl 408.09 (b)
246db3c2-c840-5d1d-b712-159b416ff5f1 | note | INSPECTION/TEST METHOD: Verify
7db84995-638b-5151-b53e-d82b44cb6e2a | note | RECORD OF CONFORMITY: This ITP Signed off
07b4d606-1bf8-54ac-9f7a-c816e3c5d49f | note | IP
1f05809b-ae8a-5e9a-bd31-e18ae83b351c | note | RESPONSIBILITY: Site Engineer
c070daf8-75c9-5128-8aef-bcd9de1150a1 | textbox | DATE:
| checkpoint | 2.3 Bitumen
86328552-64f7-578e-ae5f-493d5839ba38 | note | FREQUENCY: Test cert. upon request
865a1ed9-05c6-51d0-832d-dc47e2fa7d4a | note | ACCEPTANCE CRITERIA: Bitumen shall be Class 170 complying with the requirements of AS 2008.
adbd809b-6079-5a43-bf59-4c64d75d2e87 | note | REFERENCE DOCUMENTS: Cl 408.08 (a), AS 2008
0e744209-0c78-5033-9d16-39003a530780 | note | INSPECTION/TEST METHOD: Verify
a05c008d-befd-544e-bb07-2013facab2f2 | note | RECORD OF CONFORMITY: This ITP Signed off
dbeebd50-7790-58d4-80b8-f0bd87d6d3a3 | note | IP
788de4de-cfc1-599c-a6e1-fc53195dd7fd | note | RESPONSIBILITY: Site Engineer
a6df071c-a818-52fe-aaaa-0ba991af1fac | textbox | DATE:
| checkpoint | 2.4 Bitumen Emulsion
956a2069-ebfa-5b53-ba4f-9f0a0aaced5f | note | FREQUENCY: Test cert. upon request
688de902-e623-5143-82fa-454a62ff7743 | note | ACCEPTANCE CRITERIA: Bitumen Emulsion shall comply with the requirements of AS 1160.
6969468c-5c4e-5a09-a035-c53b0fbe1feb | note | REFERENCE DOCUMENTS: Cl 408.08 (b), AS 1160
92df7333-9992-5860-a93f-b6fe262ba6bb | note | INSPECTION/TEST METHOD: Verify
a3a643a2-3a25-566a-b06a-02339719e714 | note | RECORD OF CONFORMITY: This ITP Signed off
d9c74b79-5007-53ac-a55c-f151d56d70d4 | note | IP
274521e2-e2f3-5aae-96e4-c529f9fa9540 | note | RESPONSIBILITY: Site Engineer
7b0541ae-69a2-5de4-b6f4-689f4dd6eabd | textbox | DATE:
| checkpoint | 2.5 Cutback Bitumen
6c908aee-c8c8-580a-b86d-5ebc5535c8fd | note | FREQUENCY: Test cert. upon request
c0162615-dfa6-5be6-9f61-d0288d0c844c | note | ACCEPTANCE CRITERIA: Cutback bitumen shall comply with the requirements of AS 2157.
35496b0d-0726-5042-bb4a-3a8b6463c24b | note | REFERENCE DOCUMENTS: Cl 408.08 (c), AS 2157
aa073858-99f6-57ed-9035-5c0a8018f08e | note | INSPECTION/TEST METHOD: Verify
3c8c2388-d766-5430-a898-12b25cf5bb3d | note | RECORD OF CONFORMITY: This ITP Signed off
f26703be-bcec-5c3e-8d5c-f7240f021847 | note | IP
bc17b3d8-4357-53a0-a3d8-c64848e51a55 | note | RESPONSIBILITY: Site Engineer
9e112586-87fd-5ef6-b07b-84076e7649a1 | textbox | DATE:
| checkpoint | 2.6 Cutter
dbadc998-892b-5ce9-a91f-8ab35c87148e | note | FREQUENCY: Test cert. upon request
2a9f7b63-419a-5532-a881-857a303f18f3 | note | ACCEPTANCE CRITERIA: Cutters shall comply with the properties in the Table 408.091.
9ca68c6b-92eb-5e9e-97bc-7f02f4836bdc | note | REFERENCE DOCUMENTS: Cl 408.09 (d) Table 408.091
ef6168d2-780a-5e31-a7e6-a803dd2c584e | note | INSPECTION/TEST METHOD: Verify
cce96828-c8a9-5de7-8971-fd99ee82d797 | note | RECORD OF CONFORMITY: This ITP Signed off
6e6eb209-e187-5800-8545-b44c8fee2c39 | note | IP
825b114f-7f9c-520b-80c2-81f8a1716264 | note | RESPONSIBILITY: Site Engineer
22600643-296a-5004-b247-e226e563e859 | textbox | DATE:
| checkpoint | 2.7 Polymer Modified Binder (PMB)
969e22fc-2466-53fc-ac73-eadc53852e8a | note | FREQUENCY: Test cert. upon request
fb494b1b-59da-5119-9b05-56dba2689b2b | note | ACCEPTANCE CRITERIA: The class of PMB shall comply with the requirements of Austroads Technical Specification ATS-3110. Alternative or 'ungraded' PMMBs which do not comply with the specified test requirements of ATS-3110 shall not be used without approval by the Superintendent and will be subject to the Contractor providing evidence that the product has delievered satisfactory fiels performance for a period of at least three years.
db805645-3b81-56bf-908d-a2c146cce6f6 | note | REFERENCE DOCUMENTS: Cl 408.08 (d), AST-3110
1210bd98-5024-5a8c-93f0-c28ac23121f8 | note | INSPECTION/TEST METHOD: Verify
92f8ac30-16c2-5e5e-8112-52669c687da9 | note | RECORD OF CONFORMITY: This ITP Signed off
da8c65f1-c57b-5fb3-958d-86716c66b45d | note | IP
deaa61ca-863e-548b-b13d-b2dde17c31b4 | note | RESPONSIBILITY: Site Engineer
13c1d2c9-d914-51af-b731-71b4dd879c25 | textbox | DATE:
| checkpoint | 2.8 Primer
0c912427-9447-540b-9f2e-52993aca6043 | note | FREQUENCY: Test cert. upon request
623dfb9f-c09f-5965-a6c6-c3f1f762f6df | note | ACCEPTANCE CRITERIA: The primer shall be cutback bitumen complying with the requirements of clause 408.08(c) and shall be water resistant, of uniform appearance and capable of providing a strong bond between the bituminous surfacing and the pavement.Bitumen emulsion alternative acceptable upon providing evidence that the emulsion product meets the same functional requirements.
fdf3e06a-2669-5ff6-bc86-5cdffb9fe6d3 | note | REFERENCE DOCUMENTS: Cl 408.08 (e)
5126df3c-307f-5a79-8ab4-b8e63ef6eb32 | note | INSPECTION/TEST METHOD: Verify
d1a7a3ea-7ed5-5d51-97f0-aa0ec204def7 | note | RECORD OF CONFORMITY: This ITP Signed off
334b06f8-2f69-5a06-a24d-d26b49b5f1ae | note | IP
4a0c770f-15e9-51a4-9d6e-01d30b9f5777 | note | RESPONSIBILITY: Site Engineer
c2cb15c4-cad4-5dd8-b33c-bb985cf7db52 | textbox | DATE:
| section | 3 - Aggregate
| checkpoint | 3.1 Aggregate Specification
21a8e780-4eed-5a71-937d-3b67d72a8210 | note | FREQUENCY: Each lot
e9428e44-0fd1-568f-a684-f73bc5eedc10 | note | ACCEPTANCE CRITERIA: Aggregate shall comply with sections:
531d9825-0229-5126-82f5-3fd9df04eeab | note | ○ 801 - Source Rock for the Production of Crushed Rock and Aggregates
cadea7e9-33f8-5f07-8a19-90ddb531b22f | note | ○ 831 - Aggregate for Sprayed Bituminous Surfacing
7e917920-7c4d-5d17-8427-9c5657f7671a | note | REFERENCE DOCUMENTS: Cl 408.11 (a)
e6c3e565-b216-59f4-a010-29d90bc2c476 | note | INSPECTION/TEST METHOD: Verify
f5826d02-fbb4-5643-b869-7a086eb9c996 | note | RECORD OF CONFORMITY: This ITP Signed off
0e072730-c7ea-5d78-bbe5-91e36a1680f0 | note | IP
9082eeab-2ad7-56e1-ae57-6a2b640629b2 | note | RESPONSIBILITY: Site Engineer
e8a61d30-f71c-5705-b22d-f7111b8ef2f2 | textbox | DATE:
| checkpoint | 3.2 Aggregate Precoating
57c0bdd4-ae9e-59b3-b2a3-4741bb2d38ac | note | FREQUENCY: Each lot
27b93941-f520-56af-b80e-651d1abee68c | note | ACCEPTANCE CRITERIA: Supply plant precoated aggregate or field precoated aggregate.
583349ba-9679-5cbf-8d9c-686e9666adba | note | ○ Aggregate precoating shall be undertaken using a purpose-built item of plant to apply to the precoating material in a controlled manner that produces a uniform coating.
fab83667-03fa-54c7-adbd-fbe0256d44cd | note | REFERENCE DOCUMENTS: Cl 408.11 (b)
2b4b8b2d-e4bb-531c-9dd4-e9ad5c3858df | note | INSPECTION/TEST METHOD: Verify
69e2e003-b3d1-5ad9-af98-97e7f34504dc | note | RECORD OF CONFORMITY: This ITP Signed off
34c0412f-93bc-5f4e-bd90-dae02a63c732 | note | IP
666bbd0a-77af-516a-a0b9-8773f9b461fc | note | RESPONSIBILITY: Site Engineer
441422c1-2e4f-5155-b9ce-f0676aefc910 | textbox | DATE:
| checkpoint | 3.3 Removal of loose aggregate
033faa7a-82b0-5c15-a13e-e9553cba884d | note | FREQUENCY: Each lot
05c8486b-7d36-512d-a5fa-885fbb5b23f6 | note | ACCEPTANCE CRITERIA: All areas – within 8 hours of sealing as it is mfreeway and AADT is greater than 5000, as per table 408.141, unless otherwise agreed with the Superintendent.
003d0737-ad97-57fb-b86c-8ec32cced70d | note | ○ For seal of nominal size ≥ 10mm, < 40 loose stones/m2 to remain after removal of loose aggregate. For seal of nominal size ≤ 7mm, < 60 loose stones/m2 to remain after.
1f16333e-0640-5a06-88fc-ef747323b4ff | note | REFERENCE DOCUMENTS: Table 408.141
815d0d11-c6a8-5c78-ae67-9264094d20f6 | note | INSPECTION/TEST METHOD: Verify
bf42dec5-e2ac-5954-8e75-d3e83e08164f | note | RECORD OF CONFORMITY: This ITP Signed off
97ab207d-4757-5c30-9b96-785e62a1c61e | note | IP
64af9395-5966-5a97-b2e8-0c9ba2683589 | note | RESPONSIBILITY: Site Engineer
a23aa158-e932-5a73-ab73-8fb402416302 | textbox | DATE:
| section | 4 - Asphalt Placement
| checkpoint | 4.1 Tack Coat
7a35b3bb-7554-508c-8c37-3ece3e34af00 | note | FREQUENCY: Prior to commencing paving
22b1734a-fccd-5d8c-bcc8-60ca400d9c8e | note | ACCEPTANCE CRITERIA: Tack coat shall consist of a bituminous based binder. From 1 July 2022 only trackles stack coat will be permitted. The contractor shall submit the details of the trackless tack coat proposed to be used in the works
773cb35f-c5a8-5dbe-9d9b-382f541cee28 | note | REFERENCE DOCUMENTS: Cl 407.08 (d) AS2150 11
388f627e-20cd-5984-ae2f-eb8305ac1ea6 | note | INSPECTION/TEST METHOD: Verify
ad6da0c0-ceb9-543a-86d5-95250e7bde1c | note | RECORD OF CONFORMITY: Hold Point Release
c400b205-e780-59e5-b7c4-6a805d7cefd5 | note | HP
1f3a134a-5010-566e-85c5-c311135f595b | note | RESPONSIBILITY: FH Engineer/ Superintendent
fe41b9b9-3647-51b8-894f-f4a916600690 | textbox | DATE:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 Application of Tack Coat
2a651c94-cbfb-52f8-98b1-2346b810c107 | note | FREQUENCY: Prior to Asphalt placement
b7e07a94-b0e3-5095-9bed-a1788a2204df | note | ACCEPTANCE CRITERIA: A tack coat shall be applied to all asphalt, concrete or sprayed seals on which asphalt is to be placed. The tack coat shall achieve an effective bond between the asphalt and the underlying layer.
9c359a13-3826-5077-aa35-6e3058528641 | note | REFERENCE DOCUMENTS: Cl 407.19
b07ec0c9-6009-5f3c-b094-6f374af92a03 | note | INSPECTION/TEST METHOD: Visual Inspection
cc0e1c41-0da8-5ddf-8d3d-25d0533b4cf0 | note | RECORD OF CONFORMITY: This ITP Signed off
a3b6ba47-eb45-5441-b924-0fb0254e4db4 | note | IP
48a95960-e813-51e4-b096-2cdc4a7eace6 | note | RESPONSIBILITY: FH Engineer / QAV
3731295b-6215-5ed9-8915-49d5ea105844 | textbox | DATE:
| checkpoint | 4.3 Commencement of Asphalt Placement
5457074c-d096-5357-b23d-a1461ad52de7 | note | FREQUENCY: Prior to commencing Paving
743145a2-2781-525b-b8fa-95b1d990f291 | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until approval to proceed is obtained from the Superintendent
00cc733a-cbaf-51a2-b298-fd4675b2b9e3 | note | REFERENCE DOCUMENTS: Cl 407.23
417ee4fa-c019-5893-a336-ca591a2e8db9 | note | INSPECTION/TEST METHOD: Verify
d8ae2612-8625-5783-bafd-690251561b55 | note | RECORD OF CONFORMITY: Hold Point Release
42dae730-f2e1-5933-903f-f2b2580aa553 | note | HP
b1d7d852-3599-5a44-bf8f-5c99ee17dcef | note | RESPONSIBILITY: FH Engineer / QAV
c064c2f7-91ed-51e9-9521-fe1fa03e5d06 | textbox | DATE:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.4 Delivery of Mix
75d70285-dc9c-5d36-a06f-bd6c7041fd3c | note | FREQUENCY: Each load
9de0843a-5434-5fea-adec-70ae9ac0ac7b | note | ACCEPTANCE CRITERIA: Asphalt delivered to site, which is segregated, has been overheated, is too cold, contains separated binder, uncoated particles or which does not comply with the Specification shall be removed from the site.
52c957b7-2fa1-5963-b48d-5cc749a509fe | note | REFERENCE DOCUMENTS: Cl 407.20 (a)
c33bac8d-363a-5b23-ab9d-2a9ead3a9972 | note | INSPECTION/TEST METHOD: Visual Inspection
3184aedc-2c3c-5e4a-a109-b8ea322c886f | note | RECORD OF CONFORMITY: Delivery Docket /Asphalt Traceability Sheet
909eaaa6-58df-5968-91d8-77caa1ee14d6 | note | IP
7841297b-60c8-5790-9229-9d8bc898142e | note | RESPONSIBILITY: FH Foreman / FH Engineer
c3724ba6-963b-5dfe-a042-47b8565d9c8e | textbox | DATE:
| checkpoint | 4.5 Layer Thickness and Scale of Level
27136c65-4f78-508a-8343-91750d628660 | note | FREQUENCY: Regularly during paving
76975239-f643-5142-bf45-ab7dbd617cb4 | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness and Scale for Level as specified on drawings or specifications
7d154515-81c6-5320-addc-cb2e26048c2d | note | REFERENCE DOCUMENTS: Cl 407.30 Drawings
3df93ee8-411d-5249-9bed-7fa81caad917 | note | INSPECTION/TEST METHOD: Verify
3a73b297-864f-5a1a-87dc-a7f24cd578e5 | note | RECORD OF CONFORMITY: Dips using ruler or dip stick
64f172ea-5b6e-526c-a2db-4f0ae84ea66d | note | IP
bc8b0a83-c5d6-5426-8e73-66380b456760 | note | RESPONSIBILITY: FH Foreman / FH Engineer
d253691e-961b-5dc7-8a66-312f8669a93b | textbox | DATE:
| checkpoint | 4.6 Paver Stoppages
62bfc4f4-ac27-5e3c-948e-40e340dbbbd9 | note | FREQUENCY: If paver stops
c7570766-ea7a-5b7d-a961-63d456af063f | note | ACCEPTANCE CRITERIA: If the paver is required to stop and asphalt in front of the screed cools to below 120°C , a transverse joint shall be constructed.
14856caf-4183-5ddc-a5c0-57bb4cc6d1fa | note | ○ Hand spreading shall only be used for small areas where it is not practical to use a paver
377043a5-fbfc-5792-aeda-e6719d058152 | note | REFERENCE DOCUMENTS: Cl 407.25
f60ee523-a2de-501b-a6bf-bf5aa3b7adb0 | note | INSPECTION/TEST METHOD: Verify
387d760e-ef69-5be5-b485-62d29fc4c8a7 | note | RECORD OF CONFORMITY: Thermometer
6554e996-6cde-5c33-89e4-1621702271c8 | note | IP
547452bf-292d-526a-9787-95e1ca7b122c | note | RESPONSIBILITY: FH Foreman / FH Engineer
d26cf2be-9631-56dc-b1f6-4e53217ca4d9 | textbox | DATE:
| checkpoint | 4.7 Surface Finish of Wearing Course
be6ab55c-fc5f-5715-a84e-ca39ccb4009c | note | FREQUENCY: During paving and after final roll
e049dd25-0d64-5fe0-b8bb-20b12ebdaa6e | note | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
e6a74a68-3578-5fe3-afbd-47be1f8bf2d0 | note | REFERENCE DOCUMENTS: Cl 407.29 (i)
bc6d5b8a-9664-57c8-99e5-008618e9829f | note | INSPECTION/TEST METHOD: Visual Inspection
796ab941-1e25-583d-a0c0-0c6928359a49 | note | RECORD OF CONFORMITY: This ITP signed off
a33403a7-1d41-551e-9b6a-a2e23f22a555 | note | IP
6dac27c0-2eca-5395-820d-a188dd4a04cf | note | RESPONSIBILITY: FH Foreman / FH Engineer
11124396-26f7-5b4d-8dbc-a44bc3cb647e | textbox | DATE:
| checkpoint | 4.8 Kerb and Channel
96cc9ba9-d7f2-5fbd-a539-4f8a2420c84d | note | FREQUENCY: During paving and after final roll
72e6dc5f-5891-587a-8c50-4b6e448ebea2 | note | ACCEPTANCE CRITERIA: Where asphalt is placed against kerb and channel the surface at the edge of the wearing course shall be either flush with or not more than 5mm above the lip of the channel.
e3c34c76-d731-579a-aba9-efbf52525c5d | note | REFERENCE DOCUMENTS: Cl 407.29 (ii)
298ced8e-2f2d-5eea-bf59-853fe4bb9b46 | note | INSPECTION/TEST METHOD: Visual Inspection
d0112ad8-faa6-5fd2-84ad-683a75bab127 | note | RECORD OF CONFORMITY: This ITP signed off
fd92b0e7-426a-5b18-a630-f79b72f8cdc6 | note | IP
ee8eb7fa-fc29-56fb-afab-f17cb6f00a07 | note | RESPONSIBILITY: FH Foreman / FH Engineer
c3f40412-ba6c-559d-a303-be3e68583b26 | textbox | DATE:
| checkpoint | 4.9 Alignment of layers not placed against concrete edge
3bcd2974-41c3-5dda-8519-aa9ee5a3526a | note | FREQUENCY: During paving and at completion of work
1905bc63-a055-512a-9842-56038faf1d07 | note | ACCEPTANCE CRITERIA: Where asphalt is not placed against a concrete edging, the edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designated offset from centreline or design line. Within these tolerances, the rate of change of offset of the edge of layer shall not be greater than 25mm in 10 m.
3ed3aa77-3893-53aa-ac48-09456d1a8bed | note | REFERENCE DOCUMENTS: Cl 407.29 (iv) Drawings
e06a3e5a-8504-5b2a-93d6-4053e9ecd7cb | note | INSPECTION/TEST METHOD: Visual Inspection
ef4c109c-4e07-50f3-9b59-e26009f3e4a0 | note | RECORD OF CONFORMITY: This ITP signed off
4662c190-a788-5151-824c-2475c6132023 | note | IP
dfb2863c-2eb8-57fb-bd67-bca8d8c593eb | note | RESPONSIBILITY: FH Foreman / FH Engineer
d806b986-089f-5844-bcf0-430791e8307f | textbox | DATE:
| checkpoint | 4.10 Width of layers not placed against concrete edge
fd2eae58-05ba-5943-9d91-dfcf4f983441 | note | FREQUENCY: During paving and at completion of work
ae9f378f-414b-53e8-81e9-210bd8f675d9 | note | ACCEPTANCE CRITERIA: Where asphalt placement is not placed against a concrete edging, the width of asphalt layers shall not be less than the design or specified width of layer by more than 50mm or greater than the design or specified width by more than 100mm. The average width over any 300 m shall not be less than the design or specified width.
a3a46174-1f81-50bf-8c8e-653e7337723d | note | REFERENCE DOCUMENTS: Cl 407.29 (v)
5d4282ff-88bc-5b91-a699-79b2511e0263 | note | INSPECTION/TEST METHOD: Visual Inspection
d32fc863-5696-5bef-9d18-3e1eab0a3236 | note | RECORD OF CONFORMITY: This ITP signed off
bdb2e4e5-683d-51d7-87b2-b59548b5def2 | note | IP
3c0b435f-5c6d-575a-b760-f76182dcd650 | note | RESPONSIBILITY: FH Foreman / FH Engineer
8ac444b8-c987-5826-8d63-bb55d054d037 | textbox | DATE:
| section | 5 - Spray Sealing
| checkpoint | 5.1 Rates of Application
23dba955-be11-5559-bca7-8700472e642b | note | FREQUENCY: Each lot
168fb235-7671-5c06-a640-939feb26b113 | note | ACCEPTANCE CRITERIA: Hold Point
89dd0bc3-2900-5112-8ea9-70ba8ce6d7ab | note | ○ At least one week prior to the commencement of work, the Contractor shall submit the initial design rates of application for bituminous material, aggregate, and rates for pre-treatment for review by the Superintendent.
361ef937-b9c6-5d59-8e51-2688b1924795 | note | REFERENCE DOCUMENTS: Cl 408.13 (a)
c1fbb3e9-6b18-5339-885e-d2baca3c82b6 | note | INSPECTION/TEST METHOD: Verify
27568b20-f99c-5b82-a797-42ed90c3a432 | note | RECORD OF CONFORMITY: Signed ITP
a08e4a71-940b-5e05-85a5-348a6b3f731a | note | HP
fb25fe53-93d3-5172-8f5d-b5a992db356d | note | RESPONSIBILITY: Site Engineer / QAV
15ab0cce-ca30-56a4-8371-e21f9d9e15fd | textbox | DATE:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.2 Surface Pre-treatment
ad49c351-fbd0-595f-85cd-b1d34ed036d6 | note | FREQUENCY: Each lot
d301b882-f2cf-5a7e-99b9-d0fb6f889e57 | note | ACCEPTANCE CRITERIA: Surface pre-treatments to correct variable surface texture shall be allowed for and carried out as part of the works to meet the requirements of Surface Texture and Aggregate Loss specified in Tables 408.152 and 408.153.
21435abf-8476-5f93-b658-944744ad7fc4 | note | REFERENCE DOCUMENTS: Cl 408.13 (b)
b4414a65-9a24-5b43-b5c1-77fa9abba9d5 | note | INSPECTION/TEST METHOD: Verify
6c4829ed-da52-539a-8801-23b877bc16e0 | note | RECORD OF CONFORMITY: Signed ITP
0a483d42-9f02-596d-8c6a-bf789459421e | note | IP
15faa170-bfd6-5fe0-976e-2f7b092a81e9 | note | RESPONSIBILITY: Site Engineer
8790f7ef-b46c-5536-a314-0a255744aa27 | textbox | DATE:
| checkpoint | 5.3 Calibration of Bitumen Sprayer
d9442e45-61be-5860-a9fe-f6db1059f7e1 | note | FREQUENCY: Prior to commencing works
87fcaa15-a1e0-5022-a1b0-9883d5f97556 | note | ACCEPTANCE CRITERIA: All sprayers used for application of bituminous materials shall have a current Certificate of Calibration showing compliance with Austroads Test Methods AGPT-T530, and AGTP-T536 and renewed every 12 months.
d417163e-5ce8-5c40-9225-13b0cccbc1df | note | REFERENCE DOCUMENTS: Cl 408.07
82515e1b-6997-5dfc-a50b-a5c0914690dc | note | INSPECTION/TEST METHOD: Verify
a08c1116-0646-552f-81e1-55e1d9329c53 | note | RECORD OF CONFORMITY: Signed ITP
e90397f6-aa9f-5e8b-9297-e11c65d6241a | note | IP
abbd55eb-9c73-5160-b38e-e67ae0fcaf01 | note | RESPONSIBILITY: Site Engineer
4b8ccd84-d2e4-50a9-81fe-cf55eb43113f | textbox | DATE:
| checkpoint | 5.4 Commencement of seal works
5d1d8aa1-d8a7-5a90-893c-44274c1e6a80 | note | FREQUENCY: Prior to commencing works
bcaf82f3-5641-5111-aa83-53fae665399e | note | ACCEPTANCE CRITERIA: Hold Point
b11993dc-9c1e-5064-96bf-b27b8d965e64 | note | ○ Work shall not commence until the Contractor & Superintendent have agreed that the road or pavement surface is fit and ready for surfacing no more than 24 hours prior to the works occuring. For Periodic Resurfacing and Maintenance Works this includes patching and other preparatory works, and for the Initial Seals on Construction Projects the requirements of Standard Section 310 shall be satisfied.
e3c34a88-fce1-52f9-8be9-896bbcce83e7 | note | REFERENCE DOCUMENTS: Cl 408.04
cd422950-30d1-572d-8b71-a88dd61a333e | note | INSPECTION/TEST METHOD: Verify
97913b21-ef48-52ba-a865-6a93ea24af59 | note | RECORD OF CONFORMITY: Signed ITP
51c0bf19-2d29-5f11-a0ff-70f0f3d4bfd9 | note | HP
d151b798-faab-5633-96b6-9611f78cf95d | note | RESPONSIBILITY: Site Engineer / QAV
91130669-ef3b-5b9b-8099-9521f8b3c51f | textbox | DATE:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.5 Commencement of seal works
b17b7095-86ac-5108-980f-f6ea59ccb446 | note | FREQUENCY: Prior to commencing works
fb2f1fc7-7e04-5765-88f7-7cda1e310afd | note | ACCEPTANCE CRITERIA: Hold Point
db241abf-f0b6-566b-8d17-a707553a9bbf | note | ○ Written confirmation of the works that will be undertaken the following day and obtain agreement from the superintendent to any variation in the design rates of appliaction to those provided under clause 408.13(a).
fafb10dd-b7c7-5fa6-8608-ca094dc4fdb9 | note | REFERENCE DOCUMENTS: Cl 408.04
0543bd6b-df96-528c-a1fe-0aabcd0425d2 | note | INSPECTION/TEST METHOD: Verify
d73a1b44-2f69-5f2e-9c1c-16a265ece668 | note | RECORD OF CONFORMITY: Signed ITP
cff9d94c-41c6-52aa-9e25-842f111811fd | note | HP
b7cfc6c4-fde7-517c-a55e-9713ce4cb257 | note | RESPONSIBILITY: Site Engineer / QAV
8f20f3d5-5df7-5cc6-a5aa-d139732351d8 | textbox | DATE:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.6 Records
df5d4c2b-c637-5afb-ad24-6715db91ad72 | note | FREQUENCY: Each lot
68b87728-0a7d-5fea-ab6a-25ef83b851b7 | note | ACCEPTANCE CRITERIA: Job completion report using the proforma included as Attachment A to Section 408, or an equivlant proforma as approved by the Superintendent, completed and submitted within 7 days of completion of sealing each job.
e24818f2-7200-5d0a-8d52-0a5d1df152e1 | note | REFERENCE DOCUMENTS: Cl 408.17
7e1a4d77-5d1b-502f-8461-5d75f2dc4977 | note | INSPECTION/TEST METHOD: Verify
074913dd-07e3-5c0f-85c7-db5749e7c520 | note | RECORD OF CONFORMITY: Signed ITP
fcc5e292-89fd-5846-8cce-196bc68987ff | note | IP
f01bdefd-f699-5494-80ab-69b70a249aa6 | note | RESPONSIBILITY: Site Engineer / QAV
c8fd38c7-668c-5b80-8f9c-917277002914 | textbox | DATE:
| checkpoint | 5.7 Binder application rates
ce8e5d9b-ea7c-5dd4-bd99-8421ab7f3d6b | note | FREQUENCY: Each lot
e7242ddc-b05a-5c8e-9115-65217c166f19 | note | ACCEPTANCE CRITERIA: The Contractor shall produce evidence to show that the actual rate of application complies with the design rates of application. Variation between the actual rates and the design rates will be assessed in accordance with Table 408.151.
3c8afd2a-a1ed-5005-bd48-42203c747920 | note | REFERENCE DOCUMENTS: Cl 408.15 (a)
d10995cb-89c4-5886-93c9-bddf9186f274 | note | INSPECTION/TEST METHOD: Verify
41930ae8-9f53-55b7-b12a-b37beb37a593 | note | RECORD OF CONFORMITY: Signed ITP
56ccccf6-c0ae-5010-8b93-2f7d189e554f | note | IP
8f9789dd-0f17-51c8-b0d7-631dcf7ba4f2 | note | RESPONSIBILITY: Site Engineer
66793897-b9bc-5cb4-88db-a436b1fe7b6c | textbox | DATE:
| checkpoint | 5.8 Surface Texture
f533e8a6-3ffa-5260-8695-1b023bc51a49 | note | FREQUENCY: Each lot
e3857be9-d509-51f4-aa9d-425b766d4d49 | note | ACCEPTANCE CRITERIA: Acceptance of work for surface texture and surface enrichment shall be based on visual assessment, or tested in accordance with VicRoads Test Method RC 317.01 and assessed in accordance with Table 408.152 if required by the Superintendent
061a79e4-04d9-5655-b91c-ce00f0593fdf | note | REFERENCE DOCUMENTS: Cl 408.15 (b)
87429536-1cbe-56b3-b069-ac4da17c9af6 | note | INSPECTION/TEST METHOD: Verify
feb67832-68f0-5e8d-8a3f-13417ea0551e | note | RECORD OF CONFORMITY: Signed ITP
9803e390-990e-5ecf-b76a-57749b56d970 | note | IP
5f1265bd-7cb7-57a9-97c8-f411bc729a78 | note | RESPONSIBILITY: Site Engineer
23f774c6-33b0-5f1c-906c-bd937c6e1b4b | textbox | DATE:
| checkpoint | 5.9 Aggregate retention
b8a2c801-91f5-5873-8eb6-05febfb955c8 | note | FREQUENCY: Each lot
2f46c39f-0a45-5382-b66f-7d2351be24ce | note | ACCEPTANCE CRITERIA: Acceptance of work for aggregate retention shall be based on visual assessment, or tested in accordance with the VicRoads Test Method RC 317.03 and assessed in accordance with Table 408.153 if required by the Superintendent.
c01358e7-1796-5d37-b9b1-689c90a4eab0 | note | REFERENCE DOCUMENTS: Cl 408.15 (c)
bf611ebb-5e87-5af4-8ed6-2523da87c472 | note | INSPECTION/TEST METHOD: Verify
fcf2baed-4e92-5aa8-b559-7867448182ac | note | RECORD OF CONFORMITY: Signed ITP
55576f8d-45c9-5ddb-92f4-a3ff96cd2bb8 | note | IP
697e6c5d-3718-50af-a935-7e335d54bb6b | note | RESPONSIBILITY: Site Engineer
c38644f4-e2e2-5113-94f9-ac77759f894f | textbox | DATE:
| checkpoint | 5.10 Visual Uniformity
41da225b-2132-5df8-a8c8-9ee89a5cc309 | note | FREQUENCY: Each lot
c26f747b-d551-514b-9609-0520c75327e8 | note | ACCEPTANCE CRITERIA: Provide a surface with uniform colour, texture and consistent appearance
384e60a4-e329-592a-83d4-2c2fa66a14d8 | note | REFERENCE DOCUMENTS: Cl 408.15 (d)
fc43dd6a-2de2-50a5-bd69-792bd0249e63 | note | INSPECTION/TEST METHOD: Verify
390a5712-9b2a-5605-a953-baf05ccf1ecf | note | RECORD OF CONFORMITY: Signed ITP
cbfa1b26-a6c0-5222-90d3-6c9d5a36865f | note | IP
567ca4f6-ef27-503d-8816-17efde6cc1ed | note | RESPONSIBILITY: Site Engineer
6b980d4f-5474-5b22-87bb-8af141af7b39 | textbox | DATE:
| checkpoint | 5.11 Maintenance of seals
44709297-6586-5623-9172-cfff0b4cef55 | note | FREQUENCY: Each lot
855a6b8b-cb5f-5371-8513-29799bed9697 | note | ACCEPTANCE CRITERIA: Hold Point
3a9b7997-a5dc-5011-a754-e4b858a5fc38 | note | ○ The contractor shall be responsible for the monitoring and maintenance of seals from the time of application until the end of the defects liability period. The Contractor shall advise the Superintendent in writing of the proposed treatment to effect the above work before undertaking the work
7b43064e-b297-5a88-ac7a-2cfc00694687 | note | REFERENCE DOCUMENTS: Cl 408.16
02415fe7-1bb5-58ef-885d-957229a5400f | note | INSPECTION/TEST METHOD: Verify
0ec764e9-6716-5f44-b49c-6e3cfb32893c | note | RECORD OF CONFORMITY: Signed ITP
d634fb65-31b5-5ecd-be4a-88e730c6784c | note | HP
cd5cf9f0-a587-5e18-935d-0bdd3674eb85 | note | RESPONSIBILITY: FH Engineer / Spray Supervisor / Superintendent
fad44ecf-05fb-5952-acb9-0b120956a4db | textbox | DATE:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.12 Maintenance of seals
8219b278-cec5-525e-af12-621a52f796eb | note | FREQUENCY: Each lot
e7d6d584-93a2-5ecf-97e7-17d55fa1360a | note | ACCEPTANCE CRITERIA: The Contractor shall obatin the agreement of the Superintendent of the proposed treatment before undertaking the work.
311bebba-a489-552c-8636-f71c2e61394b | note | REFERENCE DOCUMENTS: Cl 408.16
11b4b755-5307-5234-bcd8-9d614f37f127 | note | INSPECTION/TEST METHOD: Verify
673f96e1-03cc-50b8-af3f-9030d00f46ac | note | RECORD OF CONFORMITY: Signed ITP
f230bce5-2ec9-53cc-87d2-69f431af8ca3 | note | HP
41d3ab38-dbb9-54bb-b2a7-efd5fb240684 | note | RESPONSIBILITY: FH Engineer / Spray Supervisor / Superintendent
09db8387-c05b-5dc9-88c2-05a0fa084eea | textbox | DATE:
| signoff | AUTHORITY HOLDPOINT
| section | 6 - Testing
| checkpoint | 6.1 Compaction of Asphalt layers
017c8e18-3c07-5b31-9b22-be08489cb773 | note | FREQUENCY: Per Lot
7cda6157-4d6a-5bf0-ae73-e3943271f89e | note | ACCEPTANCE CRITERIA: For layers <= 50mm, if characteristic density ration is:
b4ac8bb7-54b9-51c6-b703-29967131ecc0 | note | • 95.0% or more - Accept Lot
59465f59-cfac-5aa3-bc50-dde6d5053af8 | note | • 94.9% to 93.0% - Lot may be accepted at reduced rate
c3d9b978-af1e-5fde-9635-a2d11b8544d5 | note | ○ For layers >= 50mm, if characteristic density ratio is:
36958093-1332-5ec2-ad76-b6509ab4197e | note | • 96.0% or more - Accept lot
e0e70b42-3c38-58a0-a2c1-595fc0f13c5a | note | • 94% to 95.9% Lot may be accepted at reduced rate
41ee7155-0488-5351-add0-f8e76bac2451 | note | REFERENCE DOCUMENTS: Cl 407.27 Table 407.271 Cl 173.04
88021923-1c73-52ae-a7b7-c767242a5183 | note | INSPECTION/TEST METHOD: Verify
4b163906-9cc8-5337-bde5-049b8604dcc2 | note | RECORD OF CONFORMITY: Test Report
b297aec9-5d30-5d18-adc8-e83d8a0e552e | note | TP
b587d4ba-6cc1-5eea-93b2-c0960c0e1877 | note | RESPONSIBILITY: FH Engineer/ Lab Technician
08fb265d-27fb-5f1a-8af2-ab61b80f2dc1 | textbox | DATE:
| checkpoint | 6.2 Level Conformance for Asphalt layers
c075e709-a401-5b82-9ea6-be71baed942d | note | FREQUENCY: Per 4,000m2 at completion of work
67a9c2e3-17dd-5d46-94fe-557b634e865e | note | ACCEPTANCE CRITERIA: Individual departures from design not to exceed ±5mm with a standard deviation of ±8mm (Scale B)
d018043c-68fa-52e3-94df-74ced112fe3a | note | REFERENCE DOCUMENTS: Cl 407.29 Table 407.293
d5c619c5-44f7-552b-a700-057f49ff3f92 | note | INSPECTION/TEST METHOD: Verify
72ae670c-0d0f-5766-9b83-d19b96e1860c | note | RECORD OF CONFORMITY: Visual match existing / This ITP signed off
a772dcc7-f762-5522-9bd3-83b85e0f3f8c | note | SCP
4e39d3bb-a4ae-51c3-b573-ad0536fe1455 | note | RESPONSIBILITY: FH Engineer/ Surveyor
2c05dbbe-15be-5ab2-bcd3-3c7c04598578 | textbox | DATE:
| checkpoint | Final Inspection
eab7bf60-921b-5b2c-b568-3b7f3c2eaf52 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
241c1708-99f2-500a-93d5-02fbafbf2c30 | textbox | Print Name:
c653ba24-2cd7-5a65-9fb8-9cf29be10bc5 | textbox | Position:
7450a077-c2b1-585b-8246-6506a23c08de | textbox | Date:
| signoff | Add Signature
| checkpoint-no-value | Table 407.171 Minimum Pavement Temperatures Prior to Laying Asphalt
b8e46ba2-4488-5647-ab27-29f9d09751df | note | Asphalt Type ¦¦ Intermediate or Base Courses ¦¦ Wearing Course
cc074606-d857-5304-8627-f7dfdc2b28b4 | note | – – – – – – – – – –
fa141827-7fa2-592e-8cca-0f27ada67c72 | note | All asphalt with a specified binder class of C170 or C320 ¦¦ 5°C ¦¦ 10°C
f49adb93-531e-5b46-a50b-a18c5a46135c | note | All asphalt with a specified binder class of C600 or containing a PMB ¦¦ 10°C ¦¦ 15°C
| checkpoint-no-value | Table 407.271 Limits for Characteristic Density Ratio (Six Tests)
bf7af788-dd84-5699-a909-5f7402ea5dcc | note | For layers less than 50 mm thick
06e6326c-150a-542c-9cbb-10a1b3858567 | note | Characteristic Value of the Density Ratio (Rc) ¦¦ Assessment
217c00ba-3f18-596c-b60a-8455a7c59fcc | note | – – – – – – – – – –
8f75c6bb-77f3-5a9c-a283-f047df2a4cb6 | note | 95.0% or more ¦¦ Accept lot subject to no other nonconformances raised for the lot
404ba0ad-15e2-53cb-91db-60b75e0de4fb | note | 94.9% to 93.0% ¦¦ Lot may be accepted at a reduced rate calculated by P = 15 Rc - 1325
7aa268e5-e784-535a-82c5-dcc932355bcb | note | 92.9% or less ¦¦ Remove and replace asphalt
3eb3373e-c40a-53be-90b4-b2416adec2ce | note | – – – – – – – – – –
986f1b05-b111-5f9c-898a-181cc5e5fe1f | note | For layers 50 mm thick or greater
a09b68c7-9128-5df1-832b-1c4237fd979f | note | Characteristic Value of the Density Ratio (Rc) ¦¦ Assessment
ea37b184-5bfb-5561-a94b-a1df5d757d68 | note | – – – – – – – – – –
fcb4719c-6a9b-5f55-8364-8f584dc2638e | note | 96.0% or more ¦¦ Accept lot subject to no other nonconformances raised for the lot.
53e1579e-b0cd-511f-8866-a5d54e27b801 | note | 95.9% to 94.0% ¦¦ Lot may be accepted at a reduced rate calculated by P = 15 Rc - 1340
459b686a-01d0-57e9-bcab-2384b7044a3b | note | 93.9% or less ¦¦ Remove and replace asphalt
| checkpoint-no-value | Table 407.292 Minimum Number of Level Measurements per Lot
d6f1bd77-64d7-5a1f-9fb4-d6d8069b00d1 | note | Scale of Surface Level Measurement ¦¦ Minimum Number of Measurements Per Lot
b001772f-0d08-529a-a1ac-5d4ec1966a89 | note | – – – – – – – – – –
377f0ba8-afba-5446-9d62-a46231b993ae | note | Scale A ¦¦ 80
7da2d0f1-db89-5731-89a9-9b3c43e1397c | note | Scale B ¦¦ 40
| checkpoint-no-value | Table 407.293 Mean Surface Level Tolerances for the Sub-base and Pavement Courses
3adfdc2c-7c6f-5c65-835b-966931bd9ab2 | note | Granular or Cement Treated Subbase: x̅ Range (mm) / Max. S (mm) ¦¦ Asphalt Layers: x̅ Range (mm) / Max. S (mm)
63c0b94d-9efe-5c51-ace8-57b9890792f6 | note | – – – – – – – – – –
1c4a63de-0f03-5867-988a-8615fa256954 | note | Scale of Surface Level Measurement: Scale A
75136dcf-c813-52d6-b9e5-74c840539224 | note | +4 to -8 / 8 ¦¦ ±5 / 8
ff852a3c-2e2b-50fa-9863-ca131bfb45c6 | note | – – – – – – – – – –
dfe76124-0912-5a25-aab9-749469f8b510 | note | Scale of Surface Level Measurement: Scale B
7075769e-cccf-554c-9d87-f661cb6150bf | note | +6 to -12 / 13 ¦¦ ±8 / 10
84f3f1cb-cdce-582d-9d84-76d7d280b2c4 | note | – – – – – – – – – –
b2ee9d3a-d25d-5f7e-a502-a6c7e37b25c4 | note | Notes on Table 407.293
50842b57-c239-5fc4-b5f5-760f9a7849a1 | note | x̅ is the mean value of all level readings taken in the lot (a negative value designates a measured departure below the design level and positive value designates a surface level above the design level)
89229065-bcc8-5daf-b7aa-6834f6a6dfa0 | note | S is the standard deviation of all level readings taken in the lot.
| checkpoint-no-value | Table 408.141 Maximum Time Limit for Removal of Loose Aggregate
551ad57b-f242-5469-a566-d8b14b6465a2 | note | Traffic Volume (AADT) * ¦¦ Maximum Time Limit
f98b5507-8af1-5995-9594-08086ec73a73 | note | – – – – – – – – – –
99cdc82b-c94d-5c53-b814-1dcec61babf1 | note | >5000 and all Freeways ¦¦ Within 8 hours of sealing
9708da86-690d-5d59-93c9-081217022ee2 | note | >2000 to 5000 ¦¦ Within 24 hours of sealing
965ba4f8-3da6-56d0-8b79-48283c9739d6 | note | >500 to 2000 ¦¦ Within 48 hours of sealing
9e604ebc-f46d-51d9-939b-ac77e4009ec1 | note | <500 ¦¦ Within 5 days of sealing
| checkpoint-no-value | Table 408.152 Surface Texture Requirements
06ebfff9-335c-55b7-94c5-99356d115712 | note | SINGLE/SINGLE TREATMENTS
e2aaad6f-0369-5999-bc66-d3b736a6370f | note | Mean Texture Depth (mm)
ad578414-a979-5ea8-ba07-b572db40a80f | note | Size 5 :: Size 7 :: Size 10 :: Size 14 ¦¦ Action Required
9a46b5e9-bd8b-5117-886c-2fd627f05dfb | note | – – – – – – – – – –
914554bc-d311-5635-97e6-d34091b8eefa | note | Treatment: Seals (All Types) (1)
70f9a00e-f5d0-5bc6-95a8-d2d7ddacf955 | note | 1.0 to 1.6 :: 1.3 to 1.8 :: 1.5 to 2.5 :: 2.0 to 4.0 ¦¦ Accept
c850e5c3-a425-50f3-8c7d-e34a4a343747 | note | 0.8 to 1.0 or 1.6 to 1.8 :: 1.2 to 1.3 or 1.8 to 2.0 :: 1.3 to 1.5 or 2.5 to 3.0 :: 1.7 to 2.0 or 4.0 to 4.5 ¦¦ The Superintendent may require rectification of the works or elect to reduce payment for the lot by $1.00/m^2
2f639471-30a1-53b0-af06-978f4aeb198a | note | < 0.8 or > 1.8 :: < 1.2 or > 2.0 :: < 1.3 or > 3.0 :: < 1.7 or > 4.5 ¦¦ Work to be rectified
f9d2a809-3e85-5eb6-883d-5e13cbafabca | note | – – – – – – – – – –
0715b50b-1aa0-53e9-ab70-a3d065ff9dd8 | note | Treatment: Initial Seals (2)
3699a082-f0b4-5800-a84b-a323332ccfdf | note | N/A :: 1.0 to 2.0 :: 1.2 to 3.0 :: N/A ¦¦ Accept
a71faedc-902b-500c-bcce-c3cece30ae43 | note | N/A :: < 1.0 or > 2.0 :: < 1.2 or > 3.0 :: N/A ¦¦ Work to be rectified
f0192e47-5d15-50e7-8abd-8edf4770efed | note | – – – – – – – – – –
46040a7b-3d4c-54de-87b2-c04b9cb0efd8 | note | Treatment: Surface Enrichment (1)
3e77d3ce-11d6-588f-a1d0-91252cfe7169 | note | N/A :: N/A :: 0.8 :: 0.8 ¦¦ Accept
301f3458-ad72-542a-a22b-8ca09d9ceea3 | note | N/A :: N/A :: < 0.8 :: < 0.8 ¦¦ Work to be rectified
e91c8fbd-c1c2-5a72-8d07-1be37e718d0c | note | – – – – – – – – – –
f8a7678b-49ce-5876-91a6-96df996b79ac | note | DOUBLE/DOUBLE TREATMENTS
ee43d27f-6aa3-53bf-a00e-7d1b1ca447c9 | note | Mean Texture Depth (mm)
d7092245-6379-5038-b960-b856ff651776 | note | Size 10/5 :: Size 10/7 :: Size 14/5 :: Size 14/7 :: Size 20/7 ¦¦ Action Required
db6a2518-7a6b-5e4b-a9c0-c34ae86ce45a | note | – – – – – – – – – –
3836a0cf-cbb4-522f-94e5-34bc41243dc3 | note | Treatment: Seals (All Types) (1)
85d10bc2-7819-5cf6-aaca-cf4899e70bbc | note | 1.3 to 2.1 :: 1.3 to 2.2 :: 1.3 to 2.4 :: 1.3 to 2.4 :: 1.4 to 2.5 ¦¦ Accept
a6487c29-3755-5d19-a91a-718de0b59b9f | note | 1.2 to 1.3 or 2.0 to 2.3 :: 1.2 to 1.3 or 2.1 to 2.4 :: 1.2 to 1.3 or 2.4 to 2.7 :: 1.2 to 1.3 or 2.4 to 2.7 :: 1.3 to 1.4 or 2.5 to 2.8 ¦¦ The Superintendent may require rectification of the works or elect to reduce payment for the lot by $1.00/m^2
49cd8821-471e-5df5-b2bf-f92e044fbdc2 | note | < 1.1 or > 2.3 :: < 1.1 or > 2.4 :: < 1.2 or > 2.7 :: < 1.2 or > 2.7 :: < 1.3 or > 2.8 ¦¦ Work to be rectified
5148043f-c7d8-5c97-85df-5ae50405bbe0 | note | – – – – – – – – – –
966326e0-54a3-544d-a5e9-044703ccf74f | note | Treatment: Initial Seals (2)
7d931c24-a815-5dea-b1a3-eb56e6886b99 | note | 1.0 to 2.0 :: 1.0 to 2.0 :: N/A :: N/A :: N/A ¦¦ Accept
34ee6a69-8e26-59f0-99b1-f12b8a8ee0a0 | note | < 1.0 or > 2.0 :: < 1.0 or > 2.0 :: N/A :: N/A :: N/A ¦¦ Work to be rectified
85716e82-d48a-5867-bdf7-c5cc56c2a4c1 | note | – – – – – – – – – –
5f662e0a-ca5b-5e98-b8f0-19628d208ba2 | note | Notes:
12a36438-c714-53d1-a77f-476511447f51 | note | (1) Surface texture measurements for sprayed seals and surface enrichment may be undertaken at any time during the Defects Liability Period, but final acceptance of works is not affected until the end of the Defects Liability Period.
85df923d-4854-5c8f-a103-a6f1828e1896 | note | (2) Surface texture measurements for initial seals shall be undertaken between 10 and 15 weeks after placement. If tests are not undertaken in this period and later test results require the works to be rectified, the later test results are to be used for acceptance of the works.
| checkpoint-no-value | Table 408.153 Assessment of Aggregate Retention
6bf548f4-1a78-593a-8266-e4f4f008ac8d | note | Degree of Aggregate Stripping ¦¦ Action Required
0066fe21-ee5e-555a-a1d3-05d5256abcfb | note | – – – – – – – – – –
43c89bc4-5db6-51dd-bba4-f8c6aebbc038 | note | 0 to 2 ¦¦ Accept
6139593f-6e7f-5669-9395-76814a31bd06 | note | 3 to 5 ¦¦ Work to be re-tested within one month prior to the end of the Defects Liability Period. If the Degree of Aggregate Stripping has increased since it was last tested, the work shall be rectified before the end of the Defects Liability Period.
025a7f12-9faf-5d78-b7cf-fa9056487f40 | note | Greater than 5 ¦¦ Work shall be rectified within 5 days.
b73b6f4b-1eac-53ee-88be-79be7b2d407e | note | – – – – – – – – – –
63ac5abf-198b-51e0-9681-f5a7ccdf0d0c | note | Note: Aggregate retention measures may be undertaken at any time during the Defects Liability Period, but final acceptance of works is not affected until the end of the Defects Liability Period.
| checklist | ITP - Unbound Flexible Pavement Construction Rev0 | itp | ITP - Unbound Flexible Pavement Construction | c0d5111a-45c6-457a-b3ea-debe21871010
| section | 1 - Preliminary Works
| checkpoint | 1.1 Check for correct documentation
20c08f0d-3510-5ede-af7d-b1f8459344f6 | note | FREQUENCY: Prior to commencing any activity
3b16e17a-7080-5901-9a4e-0a653961d8bd | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
d986752e-0e8a-5a0d-9932-2debc59f5dc4 | note | – using the correct and complete set of drawings
4c12eede-ab5e-5d5b-a94d-506052ffe8e3 | note | – all drawings are the latest revision
e496c0e8-abf8-5635-9f6a-46f8127beba2 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
98e8adef-99b3-5e05-9f9c-d2d6fdec5461 | note | INSPECTION/TEST METHOD: Visual inspection
f95ac980-c774-5d3d-b1af-70999da807f5 | note | RECORD OF CONFORMITY: This ITP signed
0a423bdf-517d-53a9-be2c-7664f614103b | note | HP*
f1ca6a5c-5e14-53dd-a5a3-46534ba1e398 | note | RESPONSIBILITY: Site Engineer
57f5dd9a-f441-5522-bdeb-42e0b0a75e92 | textbox | DATE:
| checkpoint | 1.2 Material Classification
5c90763e-0164-59a7-81c7-914dc09b721c | note | FREQUENCY: Prior to commencing works
7bca7658-2035-51f4-9e37-e14ee765f8cb | note | ACCEPTANCE CRITERIA: Hold Point:
1fcf3968-7b0e-5977-a290-122bd7615c09 | note | ○ All crushed rock proposed for use shall be current registered mixes in accordance with VicRoads RC500.02 and conform to specified requirements applicable to that class of product
da17fade-e24e-5ca4-96a5-3606bd5d2bb1 | note | REFERENCE DOCUMENTS: 812.04 VicRoads RC500.02
028d238e-742d-500e-8d3e-2199b0ab07f2 | note | INSPECTION/TEST METHOD: Document Review
a4bcb719-0527-55ae-a29a-b1b0099947a5 | note | RECORD OF CONFORMITY: This ITP signed
05936957-d321-5984-ade1-a7e9c65e30ab | note | AP
ec0bfe91-732a-5c63-92c9-6785bd53e6e7 | note | RESPONSIBILITY: Site Engineer / QAV
6c3c1f9d-9026-5f99-8da2-8f7a1390d622 | textbox | DATE:
| checkpoint | 1.3 Implementation of all measures and controls
2ac91f5a-ea30-5fd1-8529-7c315009c5bf | note | FREQUENCY: Prior to commencing works
464a42ae-32e1-53c4-bfaf-8754357e4f6f | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP`
c9d8f0d2-b194-5ef5-b806-a2b587c59f1d | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
c981a4ff-13e5-5928-a7a8-dfbd11e445a7 | note | INSPECTION/TEST METHOD: Visual Inspection
0d3e840e-6c8f-5fd6-909b-455fe04ae617 | note | RECORD OF CONFORMITY: This ITP signed
b79819e2-2057-579a-a2bc-307bbbc6db8a | note | HP*
f0a6722f-048d-587a-b48a-390c574b6a4a | note | RESPONSIBILITY: Site Engineer
67399c39-51f9-5314-bd07-bf0890352d4f | textbox | DATE:
| checkpoint | 1.4 Plant and Equipment
46650b5c-2777-576c-a8a0-6d78bb9a8d35 | note | FREQUENCY: Prior to commencing works
f86409c2-f989-531d-ac8b-9dc9071a40dd | note | ACCEPTANCE CRITERIA: Plant and equipment used in the Works are appropriate to achieve specification requirements and is inducted
33c2e6a0-7749-5f3b-a742-831be722be7e | note | REFERENCE DOCUMENTS: N/A
51816054-63f1-5ec4-b1a0-f037df7c1728 | note | INSPECTION/TEST METHOD: Visual Inspection
37b36107-9414-5f24-889d-02c0d559f6a9 | note | RECORD OF CONFORMITY: This ITP signed
5d855e9b-ea4c-5645-8b51-e0e427e51d1d | note | IP
434a0420-f7e5-537a-8f50-54f572e10542 | note | RESPONSIBILITY: Site Engineer
95395234-c246-5c97-9a94-5184f9431891 | textbox | DATE:
| section | 2 - Placement
| checkpoint | 2.1 The commencement of construction of base and subbase
e34983cd-d5ae-5feb-b53a-79be8e2f7144 | note | FREQUENCY: Prior to placing subbase
45c0a2c6-599c-5202-9b0c-8c42444c837e | note | ACCEPTANCE CRITERIA: Underlying ITP signed off
b4f229f6-bfe8-51e7-966e-dc4b2eea38ff | note | ○ Identifying and removing soft areas to a minimum of 200mm depth. Underlying layer shall be clean of all foreign matter. The edges of previously placed materials shall be watered. Proof roll underlying layer prior to commencing
7746553d-51f3-5e4f-957a-b0a71c803e23 | note | REFERENCE DOCUMENTS: Drawings
3859e7e0-249d-5509-94bf-c4fdc83ee8b8 | note | INSPECTION/TEST METHOD: Verify
3b109470-3bbd-5f41-b625-177ac7285494 | note | RECORD OF CONFORMITY: This ITP signed
b3dd6e33-832d-5ec5-90f2-11f7af28d06c | note | IP
1fde7aba-45d3-5523-be06-8af818b44a21 | note | RESPONSIBILITY: Site Engineer
45ee67fd-b620-5ea7-91cb-68d6741b5ba2 | textbox | DATE:
| checkpoint | 2.2 Delivery Dockets
07e72a25-23a4-52ad-9ddb-d15aceeae193 | note | FREQUENCY: Each lot
76ab261f-328b-554e-ade8-09b387c8b961 | note | ACCEPTANCE CRITERIA: Where material is scheduled for measurement by loose volume in delivery vehicles or by mass, a delivery docket for each load shall be issued to the Superintendent at the point of delivery.
cd89dfbd-e213-51df-b060-69bbac6cf2ce | note | REFERENCE DOCUMENTS: –
e07bc5aa-ce77-5ab7-a677-8debd2c19784 | note | INSPECTION/TEST METHOD: Verify
86edc33d-ae17-573f-83ae-1ad2e07141f2 | note | RECORD OF CONFORMITY: This ITP signed
a647dbd4-790b-5403-977a-649ad5b1acf0 | note | IP
93ea7fc0-812c-59ea-a028-92082c2cbcbe | note | RESPONSIBILITY: Site Engineer
de4efde0-5773-5ff6-bbfc-d63bf4131ccb | textbox | DATE:
| checkpoint | 2.3 Layer Thickness
8b0143f5-999d-527b-b8d6-3c5e8e854022 | note | FREQUENCY: Each layer
003f626b-019b-5c47-b6bd-89553b553d4c | note | ACCEPTANCE CRITERIA: Material is to be compacted to the overall thickness shown in the drawings (dependent on pavement type), subbase not less than the specified thickness by more than 15 mm
1c504c9d-e99b-5da0-ad20-2a7dbb183a46 | note | REFERENCE DOCUMENTS: Drawings and 304.06(c)
4d8dc2c4-07f1-5e3e-bea4-d5794fff307c | note | INSPECTION/TEST METHOD: Visual and Measure
23eff415-41f4-5897-96a5-2605359bab87 | note | RECORD OF CONFORMITY: This ITP signed
e98aa3c4-6065-586d-aede-35ed7193655c | note | IP
699937ec-8f4e-5e70-a749-8697de73577c | note | RESPONSIBILITY: Site Engineer
a406359a-3380-5ca7-b139-9b1082b36b13 | textbox | DATE:
| checkpoint | 2.4 Conformity with Drawing
d9495f54-38a5-517d-85a8-680e3e6d1480 | note | FREQUENCY: Each lot
036ed919-fcdd-5e58-bbb5-d47795f78662 | note | ACCEPTANCE CRITERIA: Width of each side of the pavement shall not be less than the specified offset width or more than 50 mm outside the specified offset width when measured at right angles from the centre line or design line.
f2a5d867-970d-5fa0-81fe-447c086e6b13 | note | ○ Where pavement is to be constructed to the lip level of kerb and channel, it shall be constructed flush with the lip of the channel or not more than 5 mm above.
e9168546-4d0d-5718-854e-f14074d62eac | note | ○ Any material that has been compacted and then trimmed from the compacted surface to conform
f2918b4b-baba-50b8-b5d4-44dd1dd45c7e | note | REFERENCE DOCUMENTS: –
75268b6a-562e-5455-9ae7-81df7bceb0f6 | note | INSPECTION/TEST METHOD: Verify
6f2c2edd-ee81-5d0a-a3e8-fb974b46ca95 | note | RECORD OF CONFORMITY: This ITP signed
46c32083-4cef-5afd-99d7-0f60d1e17b9a | note | IP
87cfd8fc-620d-5366-920d-f663a94a0bda | note | RESPONSIBILITY: Site Engineer
8ba337ae-c52d-5668-a337-44bcdd7aff82 | textbox | DATE:
| checkpoint | 2.5 Jointing
b0bcaa11-b34d-57ec-a2d0-df521d61f728 | note | FREQUENCY: Each lot
32c9636f-7115-513b-ad5f-41a3aaea81c5 | note | ACCEPTANCE CRITERIA: (a) material shall be spread in such a manner as to minimise the number of joints
7311f811-6c61-57c1-a126-b9b5123f1f9e | note | (b) transverse joints shall be offset from one layer to the next by not less than 2m
08e961f7-b51e-55b9-9930-bfb32b0e49ab | note | (c) longitudinal joints shall be offset from one layer to the next by not less than 150mm.
5d28bd33-6502-54e8-a044-ad19556feffd | note | (e) longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane.
bf179042-d9fa-5a29-ac69-ed0592764dbc | note | REFERENCE DOCUMENTS: 304.07
4c421e11-b0f6-5749-be63-55aadb7c46b7 | note | INSPECTION/TEST METHOD: Visual Inspection
11d1ecda-6eb4-5203-8c2b-d758ccfe1b2b | note | RECORD OF CONFORMITY: This ITP signed
cc8909a4-c410-5b69-bcec-528dbffad6f5 | note | IP
0081b4eb-460b-54f9-921f-9a6912410e55 | note | RESPONSIBILITY: Site Engineer
fbfad4e9-fa62-5bd8-89d0-3e47c1e6ca3b | textbox | DATE:
| section | 3 - Testing and Conformance
| checkpoint | 3.1 Determine Testing Scale & Initial testing frequency
c34e5440-7bd2-5898-be84-740d3c57cec0 | note | FREQUENCY: Prior to Testing
6d8ff497-1823-5ce2-a135-bf2fd75402f9 | note | ACCEPTANCE CRITERIA: Where testing is specified in Clause 304.10(c) or (d) and Clause 304.12 requires it to be Scale B, the first lot of each pavement course shall be tested for post-compaction grading and PI.
71d0ee69-1519-5c74-b78d-f068f02b190b | note | ○ If the first lot each pavement course satisfies the specified post compaction requirements in Clause 304.10(a) and (b), as applicable, no further post-compaction testing will be required for that pavement course.
d8592025-e38f-573e-87e3-746e553beab8 | note | REFERENCE DOCUMENTS: Table 204.161 304.10 (c or d) 304.10 (a) 304.10 (b)(ii) Table 304.101 Table 304.103 304.11 (c) (ii)
8372b9ed-ca1c-5e52-92b7-fe11baa3bc86 | note | INSPECTION/TEST METHOD: Document Review/ Site Inspection
58ea654e-d02f-5198-b1b6-6adc44359fb0 | note | RECORD OF CONFORMITY: This ITP signed
c139a05f-5bb6-54c8-a955-8f90a2decc90 | note | AP
232917f9-da9d-5bf7-90ec-ed735dd11dfb | note | RESPONSIBILITY: Site Engineer
6531a882-3660-5e96-887f-8fc2c08f0666 | textbox | DATE:
| checkpoint | 3.2 Post Compaction Testing
49a8e664-3f95-5ba0-8ffb-58ffdf112c4a | note | FREQUENCY: Each Lot 304.10 (a) & (b)
e07804c9-98e6-5e2d-97ac-f333bb61688a | note | ACCEPTANCE CRITERIA: If the first lot does not meet the requirements specified in Clause 304.10(a) and (b), the Contractor shall then seek approval from the Superintendent before work proceeds.
2d7a56ec-ecc8-5bd8-9c38-b610f01d0746 | note | REFERENCE DOCUMENTS: 304.11 (c) (ii)
a94af22c-b167-59e3-8e87-3af02627dce4 | note | INSPECTION/TEST METHOD: PI
7d7245d3-db55-595c-85db-00cdc7ceee72 | note | RECORD OF CONFORMITY: This ITP sIgned
2e4d0aae-2d7b-5a13-98e9-f03c4d8abbbb | note | HP
e8baf0a7-ec43-5941-b58c-c6bfcfee04c3 | note | RESPONSIBILITY: Site Engineer
1b836761-113c-5b5f-8122-0e45062afcf0 | textbox | DATE:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 Test Rolling
7d1c8f6a-ebd3-5efd-aa9c-8c283cf2dc4f | note | FREQUENCY: Each lot
2d194143-1ab2-5528-be88-f6a0197c7f63 | note | ACCEPTANCE CRITERIA: Hold Point:
5ec4ae42-67a5-5388-bcb2-b2506bb7f927 | note | ○ All pavement layers shall be compacted to withstand rolling and shall be test rolled in accordance with Section 173, prior to acceptance of the layer.
5d4ea901-3eb6-5ab7-9e37-d65ac220b13f | note | REFERENCE DOCUMENTS: 304.08
585046e8-0862-560e-8bb3-8e7ccff6f92c | note | INSPECTION/TEST METHOD: Test Roll
96137b78-5d0e-5c4b-b560-1f313ca36a46 | note | RECORD OF CONFORMITY: This ITP signed
e5eba66f-31b4-58fe-8131-65c72ad67721 | note | HP
908ec942-3bd2-56be-a25c-9121d02f8a0f | note | RESPONSIBILITY: Site Engineer / QAV
fb3f84b2-b7bf-5178-af26-78351196db7c | textbox | DATE:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 Compaction Testing
abb5edfa-4349-5fd2-9a1d-4559878c6ee8 | note | FREQUENCY: Every Lot, Every second lot (reduced frequency)
660625a5-6d37-55bf-9ad2-9ab039e617df | note | ACCEPTANCE CRITERIA: The calculation of density ratio shall be based on tests performed using Modified compactive effort. The work shall be assessed for compliance with Scale B requirements for testing and acceptance of compaction as specified in the table below
20cf2690-59d2-50b5-b72c-fa236b99926b | note | – – – – – – – – – –
c5696aa8-206c-5591-a95a-dbe8997dccf8 | note | Characteristic Density Ratio % (six tests)
697d18de-68ac-556b-9f63-84297a324760 | note | Lower Subbase Layers ¦¦ Upper Subbase Layers ¦¦ Base Layers: Layer directly beneath the Bituminous Surfacing ¦¦ Base Layers: Other Layers
b8371182-6d5a-5a1a-b054-c88017229eed | note | – – – – – – – – – –
a5f02c07-bc9a-539b-8fd2-d4626aa70092 | note | ○ Compaction Scale: A
779fd69c-28e6-50d2-815c-32864228208b | note | Not less than 98.0 ¦¦ Not less than 98.0 ¦¦ Not less than 100.0 ¦¦ Not less than 99.0
f09ea3dc-53b7-5f6d-9d43-36ab21e7b216 | note | ○ Compaction Scale: B
bf3a075d-791e-51db-a1f1-b0472699dc5e | note | Not less than 97.0 ¦¦ Not less than 97.0 ¦¦ Not less than 98.0 ¦¦ Not less than 98.0
cfc0ee90-0f46-5ec2-9922-c2c2c33f0e3c | note | – – – – – – – – – –
99fcf5f3-96d9-5a97-ae9d-66e85a0fa18c | note | REFERENCE DOCUMENTS: 304.08 Table 304.061 304.11 (b) Table 304.111
7e1eb8d5-9d7e-5897-a2ab-377416c88cbb | note | INSPECTION/TEST METHOD: Test point
20d1f3ee-32af-5d15-a04d-1c49f9668df0 | note | RECORD OF CONFORMITY: This ITP signed
12cb06ac-8aed-51ae-a5eb-3c2d99d3d9f8 | note | TP
adaba692-73a5-5bf9-a507-de2aab20118b | note | RESPONSIBILITY: Site Engineer
0695cdda-ca8f-5b10-8c1a-cfc4f3f5adbc | textbox | DATE:
| checkpoint | 3.5 Post Compaction Testing
cdf42d7f-480a-52cf-b860-f7d641eb4248 | note | FREQUENCY: Refer to table 304.111 for various minimum frequency or testing for Grading and PL
2725fbb6-95ea-5e72-9f2c-b9b3ed372507 | note | ACCEPTANCE CRITERIA: If specified in Clause 304.10(c) or Clause 304.10(d), following completion of compaction, material shall be tested for post-compaction grading or Plasticity Index (PI) at the frequency specified in Clause 304.11 for the appropriate Scale of Testing specified in Clause 304.12(a).
e1f8f885-ec37-5117-8c71-9676aad547dc | note | REFERENCE DOCUMENTS: 304.10 Table 304.101
0c2fec92-9458-52da-b813-42aa9fcddc9a | note | INSPECTION/TEST METHOD: Test point
76c30498-ad11-5dae-ad42-659967f096ea | note | RECORD OF CONFORMITY: This ITP signed
ed5c3909-8a0b-5978-8933-0742d4d19fd2 | note | TP
0d8472c8-c980-58c6-bcc2-a42e7c9cb5ab | note | RESPONSIBILITY: Site Engineer
46f73a58-ff7a-53cb-a4b4-96b2987f300c | textbox | DATE:
| checkpoint | 3.6 Shape
59462887-1cd0-5f72-acf3-6ae4060140c3 | note | FREQUENCY: Each lot
87f9bfe3-7c95-57ef-8737-0e0590bd2007 | note | ACCEPTANCE CRITERIA: Layer to be finished to a smooth and uniform surface and after compaction shall have no point deviation > 8mm from 3m straight edge. The subbase shall also not be less than the specified thickness by more than 15mm
fb155bc3-2173-515b-aeef-f801c3b09606 | note | REFERENCE DOCUMENTS: 304.06(b, d, i) Drawings Table 304.062
106018ca-56ae-525d-98dd-22e55e2b1c32 | note | INSPECTION/TEST METHOD: Survey
590c2b3d-d2e1-5dc9-909d-65cc06ea41ae | note | RECORD OF CONFORMITY: This ITP signed
4a914cc6-fbca-51d1-805e-2eeab1d64e84 | note | IP
0bbd9d9d-b308-57fc-92a4-d3ea79860262 | note | RESPONSIBILITY: Site Engineer
5acb962e-6756-53ca-829e-c89f8c6a1322 | textbox | DATE:
| checkpoint | 3.7 Completed Surface Level Compliance
124e3713-5fa8-55d4-9390-71470bfb17a9 | note | FREQUENCY: Each lot
9bdedf87-8add-5bd0-b189-941fc7003c8f | note | ACCEPTANCE CRITERIA: Each level measurement shall be taken at random locations over the area of the lot in accordance with the VicRoads Test Method and the number of measurements taken within each lot shall not be less than the number specified in Table 304.061.
cdd19ad8-c9b8-5586-9d54-c73d7131a322 | note | ○ The mean and standard deviation of the departures from the design surface level for the pavement courses at their respective levels within each lot shall meet the requirements of Table 304.062.
91708643-8f62-54b1-925e-b841c01e8371 | note | – – – – – – – – – –
07a875bd-f6b3-5e5b-86ce-3900842732e2 | note | Table 304.062 Surface Level Tolerances for the Pavement Courses
11525267-fd0a-59b3-b200-359a2f4053b9 | note | – – – – – – – – – –
67fb5061-5a31-5163-94b4-e7a4812dc9d6 | note | Scale of Level Measurement: Scale A
2c729cf6-1ddd-5dab-a117-6acb7d752a5f | note | Lower Subbase: x̅ Range (mm) ¦¦ Max. S (mm)
b3517ab0-1b74-595e-a0af-d21a9d736b82 | note | +6 to -10 ¦¦ 10
818a2de1-f112-5956-bc1a-3d87416e503e | note | Upper Subbase: x̅ Range (mm) ¦¦ Max. S (mm)
3457eb9e-1791-5958-9547-3412ab470c82 | note | +4 to -8 ¦¦ 8
5b752529-b5e3-51ac-84d8-bdd7f0d69e19 | note | Base: x̅ Range (mm) ¦¦ Max. S (mm)
e256b9df-6e3e-5d82-9079-268eb9c9e6b6 | note | ±5 ¦¦ 8
fad352d2-565a-51de-959f-e294a355581b | note | – – – – – – – – – –
bf4b9e53-0753-59bc-8fe7-490afded0c39 | note | Scale of Level Measurement: Scale B
f43e2593-377f-5b87-9935-7c548963a290 | note | Lower Subbase: x̅ Range (mm) ¦¦ Max. S (mm)
0b15cee1-e119-57c5-b040-ae37849ce376 | note | +8 to -16 ¦¦ 15
a496a345-f3a3-541d-8fd2-7928f6bbea0b | note | Upper Subbase: x̅ Range (mm) ¦¦ Max. S (mm)
971d2cf2-5310-5f5f-8ff7-dbdc9d5c1f79 | note | +6 to -12 ¦¦ 13
0445ba17-141d-5898-a672-e25c157a3f6b | note | Base: x̅ Range (mm) ¦¦ Max. S (mm)
ebf15fa6-d178-59cb-87bb-0276d64c55f3 | note | ±8 ¦¦ 10
563fe151-494b-5540-808a-ddd60d1a34ef | note | – – – – – – – – – –
670f5380-526b-56e5-87b0-b8e94d77cab9 | note | Notes:
a7bbe063-25ab-594f-a7ed-aa824b0b17b7 | note | 1. x̅ is the mean value of all level readings taken in the lot
487cfced-6b2f-564f-adc8-735277f22702 | note | 2. S is the standard deviation of all level readings taken in the lot
9accf3ff-3ce5-5d72-a47b-73bf7785df9d | note | 3. A negative value designates a measured departure below the design level and positive value designates a surface level above the design level
6506ceca-4bc9-56e0-9072-e8740bc4e00e | note | – – – – – – – – – –
f97b58e4-81fe-5255-ae65-3da73f58e3ba | note | REFERENCE DOCUMENTS: 304.06(b) Drawings Table 304.062
3bf7838e-646d-5c45-8ec1-8d4df7dc8316 | note | INSPECTION/TEST METHOD: Survey
25204065-19e6-5ed0-a8d2-d3340ce216e1 | note | RECORD OF CONFORMITY: This ITP signed
d3373374-350f-5e7d-be1c-28f941601330 | note | SCP
a0d2b0bb-39df-51ff-b69f-b0cf3ce46463 | note | RESPONSIBILITY: Site Engineer
815ecd26-58a5-5b4d-9a7c-27cf9892d5eb | textbox | DATE:
| checkpoint | Final Inspection
5e8b1cc9-4c6e-5251-8e5c-40a195e282b5 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
3a212a39-4b21-5ee9-94d4-c402f9a77fc2 | textbox | Print Name:
f24c88cf-462c-50c4-bac5-54568392633b | textbox | Position:
e54d2548-a1d7-5340-aae1-7aa2b50655f8 | textbox | Date:
| signoff | Add Signature
| checkpoint-no-value | Table 204.161 Schedule for Surface Tolerance, Material Properties and Compaction Testing
4eff359b-9495-5191-96c9-ed29e16b51d7 | note | Road Name ¦¦ Chainage/Location ¦¦ Scale of Surface Level Measurement (A, B or C) ¦¦ Scale of Material Property Testing (A or B) ¦¦ Scale of Compaction (A, B or C)
b795b5a7-37fa-50e5-9bae-bc7c01f1962a | note | – – – – – – – – – –
768d80dd-8104-5b4b-ad39-a5303be8d5ef | note | Bruny Island Main Road ¦¦ Within Limits of Works ¦¦ B ¦¦ B ¦¦ B
| checkpoint-no-value | Table 304.081 Acceptance Limits for Scale A and Scale B Standards of Compaction
6fb89f6f-5895-593a-af96-f6c2cf8cbe31 | note | Characteristic Density Ratio % (six tests)
72c8cd72-6180-58a5-9cf6-de2c39df6a2c | note | Lower Subbase Layers ¦¦ Upper Subbase Layers ¦¦ Base Layers: Layer directly beneath the Bituminous Surfacing ¦¦ Base Layers: Other Layers
2c304757-8c47-56ba-a2a4-91786d8065f8 | note | – – – – – – – – – –
b1184cba-8269-567e-a8f1-1ad437676040 | note | Not less than 98.0 ¦¦ Not less than 98.0 ¦¦ Not less than 100.0 ¦¦ Not less than 99.0
ffe603e5-09fd-5246-934a-a5785df88d72 | note | Not less than 97.0 ¦¦ Not less than 97.0 ¦¦ Not less than 98.0 ¦¦ Not less than 98.0
| checkpoint-no-value | Table 304.101 Post-Compaction Grading Requirements for Crushed Materials
39cfa484-8682-5eac-966d-e54ad0564961 | note | Post-Compaction Grading Limits (% Passing by Mass)
36ab4cf5-c0d3-58af-8203-07d92562d61f | note | – – – – – – – – – –
c76218b8-24e6-598b-8774-09921fc512f8 | note | Class 1 or Class 2 Crushed Rock
47394385-723f-5c8e-94d4-f19e41630253 | note | Crushed Scoria Base
a0bd9d28-e8e3-5187-8886-391ca49bf776 | note | Class CC2 Crushed Concrete
d801e283-add4-5afc-8ca8-1804dc35c924 | note | – – – – – – – – – –
0fcb49cf-580f-5534-8df3-1d9d3cfbf962 | note | Sieve Size ¦¦ Nominal Size (mm): 20
281e98a1-9df7-571e-bed4-cb7749ecd954 | note | – – – – – – – – – –
fb6f4b89-3fdc-5cec-a601-5568595caf6b | note | 53.0 ¦¦ -
3bad5f35-a7f3-53bf-bd6f-bc9ae22b40b9 | note | 37.5 ¦¦ -
e25dc9bc-0957-52f9-9157-810fc5efc30d | note | 26.5 ¦¦ 100
eca94e6d-88f0-5239-a10c-27aaa3c3a586 | note | 19.0 ¦¦ 95 - 100
e39492a6-8aef-5a82-a55e-8cdd89bd0ac3 | note | 13.2 ¦¦ 78 - 92
1203a3ad-b7a7-5a8e-9a20-fe9f3e4f38e3 | note | 9.5 ¦¦ 63 - 83
07ca9a56-1eeb-5d99-af12-82f75c334df6 | note | 4.75 ¦¦ 44 - 64
d0d448f7-83fe-5929-8e09-d9241ca8b52d | note | 2.36 ¦¦ 30 - 49
daf6cb02-fdfd-57c9-809b-fb6e08d33518 | note | 0.425 ¦¦ 14 - 23
74d5fdaa-b871-519f-9c90-7225dc348978 | note | 0.075 ¦¦ 6 - 12
f9717420-2953-5d4c-8d27-b21aff004997 | note | – – – – – – – – – –
7fed31ae-c4f8-5065-9994-08ece0aad048 | note | Class 3 Crushed Rock
524d8c03-f56d-52b8-a7a3-b6e09ecde3d6 | note | Crushed Scoria Upper Subbase
c4c6cd48-d3be-5d63-86b4-6c3217c87c85 | note | Crushed Concrete Class CC3
f58d25d3-5575-5b15-b612-6fb371f4c549 | note | – – – – – – – – – –
b0466f1b-2376-5b8e-bf64-2cfaba046bdf | note | Sieve Size ¦¦ Nominal Size (mm): 20 ¦¦ Nominal Size (mm): 40
c39a7f31-f168-5027-a0b4-7cf1e90b1127 | note | 53.0 ¦¦ - ¦¦ 100
41b5bfb1-bc69-5414-9249-6753c4f02f85 | note | 37.5 ¦¦ - ¦¦ 95 - 100
31c50d96-d0a2-53c4-9ba3-9b69a85f866a | note | 26.5 ¦¦ 100 ¦¦ 75 - 95
3bb7e490-9e3a-55a6-b416-e648e1532d37 | note | 19.0 ¦¦ 95 - 100 ¦¦ 64 - 90
99824d16-dbb5-5047-85db-62866ba845f4 | note | 13.2 ¦¦ 75 - 95 ¦¦ -
03d98ced-bbb5-5df2-9277-1543932f9c05 | note | 9.5 ¦¦ 60 - 90 ¦¦ 42 - 78
a737f611-0cc4-590c-9a33-13cdfe4abdfe | note | 4.75 ¦¦ 42 - 76 ¦¦ 27 - 64
fa1deacc-65f2-574a-a42a-be1ed132041b | note | 2.36 ¦¦ 28 - 61 ¦¦ 20 - 51
ba7f105f-03a5-576b-888f-58feded5bbfa | note | 0.425 ¦¦ 14 - 29 ¦¦ 10 - 24
97b67620-5529-5c93-9429-d70894ad1b7d | note | 0.075 ¦¦ 6 - 14 ¦¦ 6 - 13
| checkpoint-no-value | Table 304.103 Post-Compaction Requirements for Plasticity Index
ca32f1da-d35d-5929-8376-10cbe6cba0af | note | Material ¦¦ Plasticity Index: Minimum ¦¦ Plasticity Index: Maximum
75219315-0a4b-5147-8efa-5bf1fd084982 | note | – – – – – – – – – –
5ab05826-2ac5-59bd-925e-11aa10990b5a | note | Class 1 Crushed Rock ¦¦ 0 ¦¦ 6
45b498a8-6db7-5d16-9708-547e3f38119d | note | Class 2 Crushed Rock ¦¦ 0 ¦¦ 6
16a501c3-44e3-5153-83a8-1dc01c66fc00 | note | Class 3 Crushed Rock ¦¦ 0 ¦¦ 10
| checkpoint-no-value | Table 304.111 Maximum Lot Size and Minimum Frequency of Testing for Compaction, Post-compaction Grading and PI (after passing the minimum number of qualifying lots)
fedffc28-c39f-577b-858b-dca09e9d17f9 | note | Maximum Allowable Lot Size for a Single Layer of Work ¦¦ Minimum Frequency of Testing for Compaction ¦¦ Minimum Frequency of Testing for Scale A Post-compaction Grading ¦¦ Minimum Frequency of Testing for Scale A Post-compaction PI
178a601b-a0b9-5ad0-a282-971ad84a71d4 | note | – – – – – – – – – –
f31a611d-9ec6-5950-ae12-c73f5044e1b9 | note | Pavement Layer: Upper Base Layer
9e475c2d-1e6e-58e3-b861-0c6a932a1fa7 | note | The lesser of 4000 m^2 or one day's production ¦¦ One per 2 lots ¦¦ One per 2 lots ¦¦ One pair per 4 lots
390883de-19f6-5925-aa77-8ab255a9e743 | note | – – – – – – – – – –
782e62cd-1843-5550-be99-6da128a8f0de | note | Pavement Layer: Lower Base Layer
7f919396-9dd3-5955-9d4c-fa271a7f9c08 | note | The lesser of 4000 m^2 or one day's production ¦¦ One per 2 lots ¦¦ One per 2 lots ¦¦ One pair per 8 lots
73695007-a5d3-5a13-8685-ac03549f7fc3 | note | – – – – – – – – – –
445eec52-0253-52c1-b64f-8d972d6c3e9b | note | Pavement Layer: Upper Subbase
4079936b-49fa-5d8c-bf6b-5a88d7cbf7ee | note | The lesser of 4000 m^2 or one day's production ¦¦ One per 2 lots ¦¦ One per 4 lots ¦¦ One pair per 8 lots
69200bed-00ae-58eb-be00-92feb21cdfc1 | note | – – – – – – – – – –
8b69a443-a19e-5b36-bb6f-60091d937a0c | note | Pavement Layer: Lower Subbase
6e2eee05-1636-5f01-9efb-175ffce54de2 | note | The lesser of 4000 m^2 or one day's production ¦¦ One per 2 lots ¦¦ – ¦¦ –
| checkpoint-no-value | Table 310.032 Testing Schedule for Pavement Dryback and Embedment
1e5089a7-e50c-5758-acf7-e13841a06de4 | note | Road ¦¦ Location/Chainage ¦¦ Testing Scale
3f64d4a0-e3bf-5ce8-8faa-b15e7f3d6257 | note | – – – – – – – – – –
4d02e34b-ad5d-56ee-bc1a-3f0f43b6ca67 | note | Bruny Island Main Road ¦¦ Within the limits of works ¦¦ B