## Master List Templates
Id | Type | Name | Values | Prompting Name
e8b7e6a3-55fb-5b7f-b21f-add66bfe88b2 | checklist | ITP - Clearing and Grubbing, Earthworks - Cut, Fill and Subgrade Preparation Rev0 | itp | ITP - Clearing and Grubbing, Earthworks - Cut, Fill and Subgrade Preparation
56f12a57-1e96-5877-8041-0f0eb46d12c8 | section | 1 - Preliminary Works
8cd47aa7-19e4-55e7-9939-09ffbf3c7b11 | checkpoint | 1.1 Check for correct documentation
fd553fda-354a-5952-839d-b2b70108ad82 | note | FREQUENCY: Prior to commencing any activity
69806cea-88fe-5790-915b-3c7590a55620 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
612d1b99-d9c8-5d2a-8f0f-41ea738c1c42 | note | – using Issued for Construction (IFC) drawings
762f6efd-e1e1-5cce-a1a5-b711e6a54baa | note | – using the correct and complete set of drawings
cb452a39-4875-5aae-ac77-89e09677b09a | note | – all drawings are the latest revision
c5044544-3b60-5fbf-ae8e-12fa4817c172 | note | REFERENCE DOCUMENTS: IFC drawings and drawing registers
795d899e-5b03-5e22-a6c6-b266b7543fbc | note | INSPECTION/TEST METHOD: Document Review / Visual inspection
b5cbc93d-c4b1-5400-9a22-bddee1f96f30 | note | RECORD OF CONFORMITY: This ITP signed
f8f5264b-a725-56b6-89be-99eddf7f840d | note | HP*
b4ded78a-93a5-5b32-8f4e-1945d5c6b050 | note | RESPONSIBILITY: Site Engineer
1fe651c1-cc7e-5020-8807-ed7e695f7a5c | textbox | DATE:
6a9380d5-4e77-5177-a005-cf90a26e111a | checkpoint | 1.2 Implementation of all measures and controls
c9af49db-caec-5ea2-a445-bcea9d07a9d0 | note | FREQUENCY: Prior to commencing any activity
9032ffd6-e916-533a-8e55-adde2387f6b2 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSMP, EMP, TMP, SWMS & WP. Access and egress inspected and assessed for stability.
40616984-45f7-5e64-a7e7-f0aca7434941 | note | REFERENCE DOCUMENTS: OHSMP, EMP, TMP, SWMS, WP
238bc8d2-16d8-5c8c-9fe9-4013a1e3c4ce | note | INSPECTION/TEST METHOD: Visual Inspection
aed6e00b-b51a-5f14-a657-33ffee5ce66d | note | RECORD OF CONFORMITY: This ITP signed
7fe9d349-5437-526a-9076-255b89bf20b1 | note | HP*
a0d26f8d-c244-5659-aa4e-07bc219d55d2 | note | RESPONSIBILITY: Site Engineer
0f6c27cd-9747-5262-beb0-cd4103d8731b | textbox | DATE:
6bd4549a-6e18-5e09-8f96-c466a3500247 | checkpoint | 1.3 Ground Penetration Permit
17412751-57c3-538f-a166-a15084ae5062 | note | FREQUENCY: Each Lot
94128682-413c-5135-a711-595cfd88988e | note | ACCEPTANCE CRITERIA: A ground penetration permit must be issued prior to excavation commencing.
a56d9772-e07c-5291-b0b8-6c4e39c84800 | note | ○ Plant and equipment must be appropriate for the task.
4e082d61-d07a-5f3a-a9a3-fd7b0decac61 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation.
349a9dab-1632-5a6e-8ec6-027e6659c7a7 | note | REFERENCE DOCUMENTS: Ground Penetration Permit
e57deb77-35e8-5ba2-bde4-64fb5e2815ae | note | INSPECTION/TEST METHOD: Verify
faf269ab-ef93-5c04-8f62-22692041788f | note | RECORD OF CONFORMITY: This ITP signed
7b507885-ffd6-5d10-adf0-fa7ea7038b0e | note | IP
06259900-2057-5029-a9dc-8601191d1f6a | note | RESPONSIBILITY: Site Engineer
d62f7407-1b5d-5728-b408-76a5ae83cb9f | textbox | DATE:
27ed74e7-0c37-5573-aad5-ff5d0ea8dc12 | checkpoint | 1.4 Implementation of environmental measures and controls
985f2821-3649-5b17-be4b-2d11f0d052c9 | note | FREQUENCY: Prior to commencing any activity
9a3327ba-e2e1-5ceb-a29d-5ed7dc723cf3 | note | ACCEPTANCE CRITERIA: EMP meets the requirements of the specification and all controls have been implemented as per approved EMP
36d9e1fd-161e-5df5-a022-7a18e69b0476 | note | REFERENCE DOCUMENTS: Project Spec Cl176.A3, EMP
1846038a-f7db-5b08-8397-60eb80022a73 | note | INSPECTION/TEST METHOD: Verify
1ef1e609-1420-5e1c-a20a-735d78abb194 | note | RECORD OF CONFORMITY: This ITP signed
d22f2d4a-f747-5bcf-b965-1da8a35e79f1 | note | IP
18b739c6-6223-5a2f-a664-06d281325930 | note | RESPONSIBILITY: Site Engineer
b961246b-1e3d-5ecf-807d-e4a97214564e | textbox | DATE:
bf2138e3-0c18-5405-9d2f-c8c2c6ef5c05 | checkpoint | 1.5 Flora and Fauna
2ebc6a36-6a01-54fe-9da5-a2ec54ef33a5 | note | FREQUENCY: Prior to removing vegetation
c3ad1b63-cbd1-5fa2-bd52-b03abe20d636 | note | ACCEPTANCE CRITERIA: Hold Point
faedd84c-2b9c-5760-ae50-e7a766bd4906 | note | ○ Vegetation to be removed clearly marked and agreed. All removal consistent with contract drawings and permits. Shall fence and sign all sites nominated as No-Go Zones.
ce559b48-0297-5a29-8bf5-a2eb2e6abf23 | note | REFERENCE DOCUMENTS: Cl176.I1
e637e93f-1372-55bd-9e6f-60e68eb6d0b3 | note | INSPECTION/TEST METHOD: Verify
ce4f97f6-7c23-575d-92ef-364cbee970de | note | RECORD OF CONFORMITY: This ITP signed
a1f91046-1e9f-565d-b992-026428a8205e | note | HP
d55c6e03-a65a-53ed-aafa-373f6d80bb71 | note | RESPONSIBILITY: Site Engineer / QAV
e14b8ac4-83bc-54f6-be94-be1586f5c76a | textbox | DATE:
d6a09a3c-930f-5118-a171-0d37af395fae | signoff | AUTHORITY HOLDPOINT
f98cb518-15a0-58dc-b994-9a65150a7364 | checkpoint | 1.6 Protection of Existing Vegetation
b1b8d4f2-26e7-5187-b812-62dfa1fca0e4 | note | FREQUENCY: Prior to comencement of any work
685ff687-2bc1-5aca-bc11-fb519dd089bb | note | ACCEPTANCE CRITERIA: Prior to the commencement of any work, the Contractor and the Superintendent shall conduct a joint inspection of the site to identify vegetation to be retained and protected.
ad03df2f-6616-5ae0-8606-6721e71bc4e6 | note | ○ If directed by the Superintendent, existing trees, shrubs, native grasses and groundcovers and other areas of existing vegetation shall be protected by temporary fencing and incorporated into the works by the Contractor.
d73c7b27-fcbf-5484-8b5a-c504a28e52fb | note | ○ Protective fencing shall consist of, as a minimum, star pickets with three strands of wire and parawebbing.
5997fdae-f257-5cd3-89de-59b74b930cd9 | note | REFERENCE DOCUMENTS: EMP Cl201.1
902627b3-93e6-55c1-93ca-3f9836c5ccc9 | note | INSPECTION/TEST METHOD: Visual inspection
cdfab1fa-75e6-5901-ae8a-2d4e9367d678 | note | RECORD OF CONFORMITY: This ITP signed
98e269e1-7ab8-5dae-9c78-545e87ceebce | note | IP
9a94ddac-3ca5-525b-9d57-36db725cd7d8 | note | RESPONSIBILITY: Site Engineer / Superintendent
46950e3d-7464-5f4a-a4e7-6913d8e08b94 | textbox | DATE:
4714ed26-e6ff-58ff-b9a9-eeb7d22f7a32 | checkpoint | 1.7 Flora and Fauna
c50b867d-f1e1-5e94-92f8-9742a53fb89a | note | FREQUENCY: Prior to removal of vegetation
6382b4f1-6543-58b5-8dca-8d835433d2e2 | note | ACCEPTANCE CRITERIA: Hold Point
a841fd2b-7faa-5328-98d3-0a192e54fee4 | note | ○ Nominated sites of archaelogical and / or heritage significance inspected on-site and clearly identified and protected as No-Go zones
67fa512b-2bfe-58f9-82e0-55a19f2772db | note | REFERENCE DOCUMENTS: EMP Cl176.J1
2da0042b-23df-56c2-a4fd-911b4e15e1f6 | note | INSPECTION/TEST METHOD: Verify
bd12edbc-611e-578f-8198-a42ee7f9e423 | note | RECORD OF CONFORMITY: This ITP signed
6f77f083-8be9-5160-9fbd-bf47637db21b | note | HP
51adfdeb-4b10-5a8e-a11a-27748bdd32e7 | note | RESPONSIBILITY: Site Engineer / QAV
e175b611-27de-5922-b546-45c19f67ab4b | textbox | DATE:
9f3d6870-4056-51f7-839c-6a211269777e | signoff | AUTHORITY HOLDPOINT
889a1390-a3ad-539d-96ce-268c924d4094 | checkpoint | 1.8 Authorisation for works
3adafb81-4036-55e5-8e6d-a47493646d1e | note | FREQUENCY: Prior to commencing works
6d2ae7fd-ed6f-5064-85c4-b2d96bc1a5da | note | ACCEPTANCE CRITERIA: Check that all relevant approvals have been granted including verification of the works area
029b3de6-cb1b-504e-a41a-4b6116a5f561 | note | ○ Ensure work pack is reviewed & signed
b5f1251b-c614-5537-8c69-e868593f789a | note | REFERENCE DOCUMENTS: Work Procedure
a881284d-0200-5a01-8e05-637f32c4b048 | note | INSPECTION/TEST METHOD: Verify
92dc42fe-bb3f-5058-bba5-73dd2215a0ef | note | RECORD OF CONFORMITY: This ITP signed
58d1b289-0840-55eb-9809-29d885f65b9c | note | HP*
abdaad9e-512b-552b-8063-7679cb99934d | note | RESPONSIBILITY: Site Engineer
bcc209d5-6071-5263-9eaf-77b4f4e9b027 | textbox | DATE:
1744920f-72d1-5c9c-9026-69f20bd90b83 | checkpoint | 1.9 Utilities
346065b7-8ace-5ed8-89c6-ef39b2c4d91d | note | FREQUENCY: Prior to commencing works
ce60f14d-effb-578f-a089-95bd6779f35e | note | ACCEPTANCE CRITERIA: DBYD - locate and mark all existing services and confirm clearance from proposed work
3cd59002-b5f8-594d-9939-3f9682511744 | note | REFERENCE DOCUMENTS: DBYD Records, Plan Mark-Ups
6c04de51-c832-5dd8-989f-6f9c50f3335a | note | INSPECTION/TEST METHOD: Verify
2ae4f666-ae15-564c-b0f8-d1cbdefea060 | note | RECORD OF CONFORMITY: This ITP signed
73db2577-c7dc-5aac-8db9-a6ed9672f67d | note | IP
e850a8e8-d47f-56ab-80bc-9c7dd4e53fe0 | note | RESPONSIBILITY: Site Engineer
59f8da8f-c43a-57ea-b9b0-757aab71dbf6 | textbox | DATE:
f62619bf-a144-54f8-8546-5ec3648792e5 | checkpoint | 1.10 Traffic Management
2041ab5b-7517-5fce-8fde-00942508ccf0 | note | FREQUENCY: Prior to commencing works
34962964-1a79-53f9-a86e-cb1426ce3c0c | note | ACCEPTANCE CRITERIA: Consider the requirements for traffic management, ensuring all works comply with required TMS, TMP and TGS.
9ab76b23-611f-5f3e-9a2a-dbbf82d8c583 | note | REFERENCE DOCUMENTS: TMS
16efb7c3-60d7-5e00-b82d-b1437b200078 | note | INSPECTION/TEST METHOD: Verify
0b12ccc4-5863-5793-be5f-e20dbfaf5922 | note | RECORD OF CONFORMITY: This ITP signed
d1d59e04-57a0-5229-a83a-d835399389ad | note | IP
f0075cae-4c76-5bef-b38c-9e9e564727cf | note | RESPONSIBILITY: Site Engineer
b4a2e067-8c4a-52ac-8197-52c1469feb12 | textbox | DATE:
f23a833c-aab2-521b-9e38-fea7eba3b0df | section | 2 - Clear & Grub
0e06d871-b1bc-5643-a24a-6d18926f9949 | checkpoint | 2.1 Limits of work
013cbb8b-80c5-53c0-a8c1-c58fe5c3648a | note | FREQUENCY: Each Lot
9463abe3-6aa9-54fd-b5e6-23471bb9a0ee | note | ACCEPTANCE CRITERIA: Limits of clearing and grubbing shall be the whole length between the following chainages:
beda7fa6-9625-5518-8cbb-977474b8c7c1 | note | REFERENCE DOCUMENTS: Cl201.03
7737045f-30b6-58b1-9fee-edc3f16afc5d | note | INSPECTION/TEST METHOD: Visual Inspection
69cc62f0-46b4-5f4c-b0d3-9471d0011d05 | note | RECORD OF CONFORMITY: This ITP signed
0e9cfb84-68b5-549b-9a13-ce7f5060fc8d | note | IP
4bdbd1c6-b513-5ab2-b937-10e7d6d2b189 | note | RESPONSIBILITY: Site Engineer
059ae2c8-3880-5948-8aa9-84c1271e58e7 | textbox | DATE:
a9701ea3-49f6-53a4-a57b-3651dbeb42e4 | checkpoint | 2.2 Clear and grub trees and vegetation
efb31794-a8e2-5434-ac49-7ed74de48b94 | note | FREQUENCY: Each Lot
95f65447-8c71-529e-a095-0d58ae768616 | note | ACCEPTANCE CRITERIA: The area within the specified limits shall be cleared of all vegetation, refuse and obstructions down to natural surface. The Contractor shall not undertake any clearing work or any type of disturbance outside of the specified limits of work unless approved by the Superintendent.
d3baa5bc-4e8a-5a2d-bce6-89f91a595ef9 | note | REFERENCE DOCUMENTS: Cl201.04
ed028e87-33a5-5cf3-aad6-db058f1defc0 | note | INSPECTION/TEST METHOD: Visual Inspection
17ebfe0c-a01d-50f8-a150-dd6698ae9c38 | note | RECORD OF CONFORMITY: This ITP signed
3b5f9ebe-b8b9-5340-b495-f50278d3c4c9 | note | IP
af18cdc7-a4f5-51fc-97cb-94d54ab9246b | note | RESPONSIBILITY: Site Engineer
366c645d-a3c6-5b6c-9594-35978acd9dd3 | textbox | DATE:
70609955-d6fd-585b-a4db-d4443c8249d1 | checkpoint | 2.3 Clear and grub trees and vegetation
b905d95f-d3db-53ba-ab59-d27bed0d79a6 | note | FREQUENCY: Each Lot
c52dd357-1dcf-5615-b605-677f3a495af6 | note | ACCEPTANCE CRITERIA: In areas where excavation is to occur: all vegetation, refuse and obstructions totally grubbed or grubbed > 0.3m below subgrade and batters (whichever is the lesser treatment)
8a0def96-be42-567e-b995-0ddfc22adcb1 | note | REFERENCE DOCUMENTS: Cl201.05
2a691d19-c013-5fd8-9ce6-44a3d4dae6e2 | note | INSPECTION/TEST METHOD: Visual inspection
9e8acb57-a1b9-588b-83a4-a5f56f4bac2b | note | RECORD OF CONFORMITY: This ITP signed
341af11b-c45d-572d-a50c-f6e1d6a8b4c2 | note | IP
9796895b-fa73-578d-a35d-8c3de95ccbc8 | note | RESPONSIBILITY: Site Engineer
f3975bf3-bb51-581a-843b-04b6dab1ee9d | textbox | DATE:
3a5483c2-28ef-56b9-bf08-0f218d678dcb | checkpoint | 2.4 Clear and grub trees and vegetation (embankment areas)
18d35b1f-69b5-5909-b286-e3a8886983bd | note | FREQUENCY: Each Lot
ba94f577-f95f-5287-b2bb-6b9f6d2c4e9c | note | ACCEPTANCE CRITERIA: In areas to be covered by embankments < 1.0m in height: all vegetation, refuse and obstructions grubbed > 0.3m below stripped surface OR > 0.6m below subgrade level (whichever is the lesser treatment)
c57e8167-5587-566b-b30a-b17d5b794dca | note | ○ In areas to be covered by embankments > 1.0m in height: foundations may remian if located or cut off not more than 0.4m above natural surface but not less than 1.0m below subgrade
03d23513-5fa6-586d-a6c9-035b3ff60b71 | note | REFERENCE DOCUMENTS: Cl201.05
67fb4335-d579-50ba-933f-003d952c3166 | note | INSPECTION/TEST METHOD: Visual inspection
8738f59d-8c81-5731-85de-956e76b18e83 | note | RECORD OF CONFORMITY: This ITP signed
985d609d-4dc2-5b80-93f9-db0bafd15359 | note | IP
d5130cb1-83ca-56b9-8d3c-093c11f20fca | note | RESPONSIBILITY: Site Engineer
bb874952-4671-5d57-a736-2a20a9efc5d7 | textbox | DATE:
b3dccb73-1b37-5894-a2c9-b91dbf4002f7 | checkpoint | 2.5 Clear and grub trees and vegetation at culvert sites
f22485ba-0729-5986-98ed-5e5ecdeacf04 | note | FREQUENCY: Each Lot
d0485d54-3f83-5167-b59b-0d1959720b8e | note | ACCEPTANCE CRITERIA: Clear and grub trees and stumps within 10m of any proposed bridge or culvert having a waterway area > 6 m2 (unless otherwise shown on drawings)
1df587a4-bb4f-5b68-b04a-8d88470a7566 | note | REFERENCE DOCUMENTS: Cl201.06
08f56b1f-9241-5458-bbed-3446c503de4c | note | INSPECTION/TEST METHOD: Visual inspection
30001595-93bc-5fc5-99c4-c9e7dd8e20b6 | note | RECORD OF CONFORMITY: This ITP signed
07170e84-eadd-598e-9928-7971aff6e998 | note | IP
db4e256e-cb84-5930-a4c2-bbf58c872a31 | note | RESPONSIBILITY: Site Engineer
140d1f7b-1c95-5f42-bd1f-4488e5b56752 | textbox | DATE:
5ddd8d33-69f2-53d1-955c-19aba67e8a70 | checkpoint | 2.6 Backfill holes
a86fb196-0384-52bb-b8cc-e005a4028c15 | note | FREQUENCY: After clearing
1c36b40f-1865-504a-b07c-45522ba016b2 | note | ACCEPTANCE CRITERIA: Any holes produced from grubbing operations have been backfilled with similar material and compacted to the same degree as the surrounding material
4482846f-1290-5b95-a0de-2ef329ec8830 | note | REFERENCE DOCUMENTS: Cl201.05
820c39c3-6d8d-5253-bd05-8360f9d89e6f | note | INSPECTION/TEST METHOD: Verify
58e4a7e4-18a2-5c6d-bb52-ab12bba39abe | note | RECORD OF CONFORMITY: This ITP signed
c8b96a7a-2a9d-5d80-a570-f682500dd095 | note | TP
f335f75a-e6a4-56a5-a8b4-d362a7da5224 | note | RESPONSIBILITY: Site Engineer
f665a98e-a137-5ca6-b789-98ae8bd616ee | textbox | DATE:
984750d8-974b-5431-87b6-3d8b0c635dfe | checkpoint | 2.7 Dispose of Trees and vegetation
e12bfe5d-deba-5abc-92ab-c5e10791fd4c | note | FREQUENCY: After clearing
0222047e-57eb-5b4f-990b-9332dbbbbd9b | note | ACCEPTANCE CRITERIA: Tree trunks and large branches shall be removed from site. Small tree branches, weeds and shrubs shall be disposed of by chipping and mulching.
66c7ae8d-dbb3-5641-a575-dba8491d74eb | note | REFERENCE DOCUMENTS: Cl201.07 (b)
b7e64e67-5a28-540f-8d57-e898e0564c67 | note | INSPECTION/TEST METHOD: Visual inspection
c9f8fb95-5fbb-582e-ab20-87f735a8c165 | note | RECORD OF CONFORMITY: This ITP signed
dc2e5f76-2bb4-5d1c-971b-04a3594874bb | note | IP
97b569aa-68a1-58b3-af24-ed6a1cccd0ae | note | RESPONSIBILITY: Site Engineer
6a3ad02b-96c5-52f0-afcb-3c2373bed492 | textbox | DATE:
3700abe7-410e-5d6e-a214-250423730afb | checkpoint | 2.8 Damage to Fencing
33af6e19-27da-5528-94f6-eb624ed73306 | note | FREQUENCY: During Clearing
b7e16d99-0a82-50b8-9f76-b62118624322 | note | ACCEPTANCE CRITERIA: Immediately repair any damage to fences to a condition at least equal to that before damage
30a83faa-468d-55cb-8d17-fe075fef8477 | note | REFERENCE DOCUMENTS: Cl201.09
2bf02ed2-61b6-5a17-b002-1b70c8b91f6e | note | INSPECTION/TEST METHOD: Verify
0a932d44-a088-52de-917d-9bff8b52cfd2 | note | RECORD OF CONFORMITY: This ITP signed
f6736839-ed61-5287-b27e-2fa9a0a62978 | note | IP
6074eba2-ff9c-506c-a9e2-289de9323ae4 | note | RESPONSIBILITY: Site Engineer
f8f41ae5-fcad-53c9-a4c7-1be82b6e5245 | textbox | DATE:
9acc3916-1a81-5422-8451-c6549244219f | section | 3 - Earthworks
cd48969e-c153-58f5-8087-1e5987b39930 | checkpoint | 3.1 Material Categorisation
55ba76f2-ddb9-5e9d-a315-6ce8c9bd1626 | note | FREQUENCY: Each Lot
0d1d1f47-8e8d-5f0e-bc65-9d1b47ad8b8a | note | ACCEPTANCE CRITERIA: Hold Point
739df47c-2e65-5f80-8ce4-6703c8cc45fe | note | ○ Prior to commencing excavation in any area and during excavation work, the contractor and Superintendent shall inspect and agree upon the type / category of material encountered
5b63d0c5-5439-5289-8b11-46d13505174e | note | REFERENCE DOCUMENTS: Cl 204.06c
8937d24e-be76-531e-8efc-bcd64bb72766 | note | INSPECTION/TEST METHOD: Verify
a12fed69-8fd0-5964-9b75-e0a20691bc72 | note | RECORD OF CONFORMITY: This ITP signed
86a0c63f-8539-5d19-bdc8-ca4007cc568f | note | HP
c0ff7059-cfe8-501b-b470-d91e3daa8385 | note | RESPONSIBILITY: Site Engineer / QAV
af2f2c06-2b59-5c63-9eb9-a82763728e0a | textbox | DATE:
f7942a23-9623-59db-aac5-757135e4ccd0 | signoff | AUTHORITY HOLDPOINT
2fa6b602-59b1-5e97-8332-70dc6dbb3ef3 | checkpoint | 3.2 Stripping of Topsoil
d1a3df8f-68b9-5782-9755-5dc1248aa2e6 | note | FREQUENCY: Each Lot
99a0ac54-fbb6-5ac8-8540-71ed1bf4f5e2 | note | ACCEPTANCE CRITERIA: Topsoil stripped to full width of the formation and placed in approved stockpile location. Stockpile shaped to shed water and stripped surfaces graded to be self draining. Topsoil shall not be removed from site unless approved by the superintendent.
24d44851-ec73-528e-b5fd-0e698d23a3d6 | note | REFERENCE DOCUMENTS: Cl 204.05
61e232c0-a85d-5d38-a27e-7110ef717d58 | note | INSPECTION/TEST METHOD: Visual Inspection
3084cb20-aa24-5e00-92d3-4b9f341596a0 | note | RECORD OF CONFORMITY: This ITP signed
f4258e55-e74d-5418-b723-fae7d2d0c488 | note | IP
1ce662e7-3dd3-5eed-96fc-ed3d803adc4e | note | RESPONSIBILITY: Site Engineer
badf6a70-2ced-50fb-a38c-e261a5dea1bb | textbox | DATE:
f3406247-3ec6-5035-8837-d419ca50ece0 | checkpoint | 3.3 Unsuitable Material
5e612ccf-f4c1-5d18-a6e5-c9be2a932f80 | note | FREQUENCY: Each Lot containing unsuitable material
b09fbede-1143-51e9-b1cd-9e1e570d6976 | note | ACCEPTANCE CRITERIA: Hold Point
14f57eb5-4806-54be-a81b-55d326d2a5c1 | note | ○ For unsuitable material, the proposed in-situ treatment or extent of excavation submitted to the Superintendent for review.
a46b638f-e41d-53fb-8e47-4270979c8ced | note | ○ Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Superintendent
b1300954-cd65-5395-a4e7-a7afe06bc2dd | note | REFERENCE DOCUMENTS: Cl 204.04b, Cl 204.07d
02a282d9-298a-58a4-bd66-3af347e31426 | note | INSPECTION/TEST METHOD: Verify
ea83a39f-74c6-5674-8465-b7b9b2eaa193 | note | RECORD OF CONFORMITY: This ITP Signed
351f703f-d1f6-5d31-a489-7eb8e4cb11cf | note | HP
9e342a27-1526-5600-b854-63cab4530b41 | note | RESPONSIBILITY: Site Engineer / QAV
80b0f039-d825-55b4-95dd-de7da7d9b8b4 | textbox | DATE:
f79b78a5-d832-5ce0-9aa8-6b3907cef153 | signoff | AUTHORITY HOLDPOINT
dad60652-7939-5b19-8eb4-3b57fa3ad1e2 | checkpoint | 3.4 Subgrade Fill Material
24729364-da3a-5c52-90a9-8e133908fe5b | note | FREQUENCY: Each Lot
05d2ccfd-bf49-5093-b0cd-7544c8a0f1b4 | note | ACCEPTANCE CRITERIA: Fill material free of topsoil, deleterious and/or perishable matter.
a9ec8bd0-3c1b-5a3a-847e-72b88268d229 | note | ○ Type A material shall comply with the requirements of Table 204.041
b7b8b02c-f80e-540b-93a4-9cecf024411c | note | ○ Type B material shall have minimum Assigned CBR of 4% and Assigned swell less than 2.5%. Materials with swell greater than 2.5% can only be used as Type B material if approved by the superintendent.
794d85ce-2502-59a1-96cd-ede53da7a80a | note | ○ Type C material shall be capable of being spread in layers of not more than 500mm
7448b7b9-7cb9-58e0-a34b-57ee585762b4 | note | REFERENCE DOCUMENTS: Cl 204.04, Table 204.041
7d25f7c2-6928-5fd1-a8ed-ec6663d1e982 | note | INSPECTION/TEST METHOD: Verify
e02b6054-2989-5e3f-ae5d-2edf09b80f47 | note | RECORD OF CONFORMITY: Test Report
b68871d2-89f7-5db4-b348-16d7970d7f1e | note | TP
003a5a12-e377-5b05-85aa-7cad996c84ed | note | RESPONSIBILITY: Site Engineer
9f8202ea-05c0-56ac-a974-fbb9af722c54 | textbox | DATE:
70e7341a-1e37-565f-b55f-7b67b2a9da1a | checkpoint | 3.5 Treatment of Rock Subgrade
097fbb95-548f-558c-b7a5-d50bd1b5621f | note | FREQUENCY: Each Lot (prior to construction of regulating layer)
9457ae17-2363-50d5-93c3-e3c36f3ee70b | note | ACCEPTANCE CRITERIA: Hold Point
662a9b9c-24b9-5250-90b4-24a3c35ddb3c | note | ○ Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
09adf65d-8aa6-59ca-9723-b20867b5d2c2 | note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
62601984-233d-53a7-80c5-5165a590b3c7 | note | REFERENCE DOCUMENTS: Cl 204.06f
8984a4b8-fcb1-5992-870b-48305032f02e | note | INSPECTION/TEST METHOD: Visual Inspection
74048b71-cd49-5d18-a18f-09083babf174 | note | RECORD OF CONFORMITY: This ITP signed
ae2f3233-ae64-5e2f-996b-264f88414aaa | note | HP
356a80b6-c454-5ca2-b070-e3dbe2494dd6 | note | RESPONSIBILITY: Site Engineer / QAV
d09809ce-da37-5d5c-9ba3-81073e6568ff | textbox | DATE:
52fdadb3-ee78-5e67-9ce2-f1037232b03b | signoff | AUTHORITY HOLDPOINT
eda72af9-b069-52a5-90c1-29d3533f2e70 | checkpoint | 3.6 Groundwater
2515f4b1-4352-5053-b645-6cc9d310a07b | note | FREQUENCY: Each Lot
2ad4a866-a3ce-5b07-a539-62f7b16bdc54 | note | ACCEPTANCE CRITERIA: Hold Point
cce1a755-fe21-5b8d-a6bd-4a15f1ef58bb | note | ○ Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
99de2870-7dcf-5ee0-8e74-beacdc634596 | note | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater
d2f4cbed-9bb3-5905-816d-693101e5cc6f | note | REFERENCE DOCUMENTS: Cl 204.06h, EMP
603b83a7-71d9-59d3-920d-1d34766e9737 | note | INSPECTION/TEST METHOD: Verify
98433b61-a90b-5146-8d58-2c26575684b2 | note | RECORD OF CONFORMITY: Water Authorities and Superintendent Approval, This ITP signed
21be86bf-1d43-5bbd-ae15-5bb3ccd4a035 | note | HP
d8c27ca8-6193-5cd2-b486-ac363a439545 | note | RESPONSIBILITY: Site Engineer / QAV
96938a37-cc2d-54e9-b08b-33f5398e6d87 | textbox | DATE:
488c759e-2060-5cd2-8dbb-0a318e8df41b | signoff | AUTHORITY HOLDPOINT
715c54ef-c1d3-558b-b17c-4ca2ac78bf20 | checkpoint | 3.7 Surface finish of batters
a27eaf83-e26a-5556-8e17-d205d94cf068 | note | FREQUENCY: Each Lot
7dec2baa-1726-5cce-b5db-d0d6b74fb606 | note | ACCEPTANCE CRITERIA: Surface of cut and fill batters to be topsoiled and textured by scarifying or horizontal grooving
76312b38-52f2-5346-9957-422239ad8b7d | note | REFERENCE DOCUMENTS: Cl 204.06i
5d498bdd-29e0-50f3-b1cb-74fdcaf1f7e8 | note | INSPECTION/TEST METHOD: Visual Inspection
b1a5f4b0-d848-52f7-b15d-923b42e7b3a8 | note | RECORD OF CONFORMITY: This ITP signed
20e5032f-4182-570b-91cb-67f00279deb1 | note | IP
e7d98a1c-1d09-57fa-8d30-e37ea5b3c7dd | note | RESPONSIBILITY: Site Engineer
c4642038-d28c-55fc-84b6-0f2a587be058 | textbox | DATE:
42a1c57a-67d3-556c-b552-9ad95331eb9a | checkpoint | 3.8 Borrow Excavation
89eea4fa-7cc9-5dc9-8f94-c725d61cfbe9 | note | FREQUENCY: Each Lot
7cc89a60-65d7-5c10-ac9f-68efc755b399 | note | ACCEPTANCE CRITERIA: Hold Point
02fa2a9b-bd8a-5d1e-8ae6-4e0b367b2ccc | note | ○ Borrow Excavations within the road reservation are not permitted without prior approval of Superintendent
526c5d1d-5b0b-5b70-a9f5-eb4ef5fe8fe1 | note | REFERENCE DOCUMENTS: Cl 204.09
43cc0b98-e8b7-56bb-8238-58a7808ed7a1 | note | INSPECTION/TEST METHOD: Verify
7f14cfed-d742-575e-a1a7-4ced6091c594 | note | RECORD OF CONFORMITY: This ITP Signed, Correspondance with superintendent
5d89c945-2b5c-550f-b2bf-b13ad210dcc7 | note | HP
9a23cb46-dc25-54c9-8965-08e486643835 | note | RESPONSIBILITY: Site Engineer / Superintendent
0ee4ee41-0a62-5419-b7a6-83c848be72c5 | textbox | DATE:
099072f7-acc5-57e7-b50c-9e602fbe2ee3 | signoff | AUTHORITY HOLDPOINT
1a75dd0e-6722-5525-b1d5-c81535df7754 | checkpoint | 3.9 Areas upon which fills are to be constructed
8805f00b-22b1-5c33-80a3-3e147a1081ab | note | FREQUENCY: Each Lot
6d5e08ca-6f7a-5495-8f18-6c6d070b9756 | note | ACCEPTANCE CRITERIA: Hold Point
965916bd-6487-5a71-913a-6c5bd9b5c3c9 | note | ○ Areas where fill is to be constructed must be reviewed by the superintendent prior to the placement of any fill in the area
f65f25db-6f3c-5c90-a78a-cd690a5ca3d0 | note | REFERENCE DOCUMENTS: Cl 204.10b
b48261d2-7dc0-591b-aeab-fab55d509e71 | note | INSPECTION/TEST METHOD: Verify
f2112d73-fea3-5a3e-a7e6-ffae9c6449f3 | note | RECORD OF CONFORMITY: This ITP Signed
96152dc6-b599-55d7-b0b3-45b27b94f144 | note | HP
97347ee4-5574-5d3a-925a-52b6a496b120 | note | RESPONSIBILITY: Site Engineer / QAV
a832215e-ed1b-5463-8ab4-6af33e6ed1db | textbox | DATE:
ff99f82b-073f-59bc-97ea-7a670d93e296 | checkpoint | 3.10 Placing of Fill
4959fa1a-63a4-5a0c-b5d1-01ebaaa6cee6 | note | FREQUENCY: Each Layer
13b53694-6dac-53e3-a67f-2b4e32e95506 | note | ACCEPTANCE CRITERIA: Fill placed and spread in uniform layers. Each layer keyed into the next with a textured surface. Any rocky material uniformly distributed throughout the layer.
ee3acd80-4352-5df2-b45e-553c89dfce95 | note | ○ Compacted layers do not exceed specified maximum thicknesses:
96b2f63d-4364-53a1-b457-949b3a93af99 | note | ○ Type A: Maximum compacted thickness 200mm (can be used in locations specified for Type B material)
face4206-a373-504a-9dec-959d05416d70 | note | ○ Type B: Maximum compacted thickness 200mm (can be used in locations specified for Type C material). Where > 25% rock by volume, loose layer thickness may equal 125% of typical maximum particle dimension up to max 500mm. No rocks > 80% of loose thickness of the layer.
c6c3813d-191f-5f0e-a9cf-4cfc0ebc156e | note | ○ Type C: Maximum compacted thickness 300mm. Where > 25% rock by volume, loose thickness of each layer may equal the maximum particle dimension of the rock up to max 500mm. Reference table 204.111
9153bb5f-ee3d-5744-83f2-fecef18f9565 | note | REFERENCE DOCUMENTS: Cl 204.10d
6a7c7a80-161e-5d49-a232-0f056445f68e | note | INSPECTION/TEST METHOD: Visual Inspection / Measure
5a3a2217-2a7a-56df-94b8-655d6da6f8c9 | note | RECORD OF CONFORMITY: This ITP signed
b4bac8af-b9f1-5a9d-bd20-4e7353d2f73c | note | IP
f0ec20e5-63b8-5c10-8363-bb8141629071 | note | RESPONSIBILITY: Site Engineer
163c9c02-ac63-5979-8f1e-499e390b9cd1 | textbox | DATE:
0a183ee1-b98f-53d5-9cdb-e9fa54f7cb71 | section | 4 - Testing and Surface Preperation
a8d6997f-aa37-5e67-acd9-6cafcc549829 | checkpoint | 4.1 Test Rolling
9e7fdef6-e57b-5b1f-b86f-3424ee37ef4f | note | FREQUENCY: Each layer
22644122-846f-5da6-a42d-fad73c20ae4b | note | ACCEPTANCE CRITERIA: Hold Point
32f77fd4-5a44-5971-b254-2af5090cd644 | note | ○ Areas upon which fills are to be constructed, all layers of fill, material within 150 mm of the cut floor level in cuts, and all stabilisied material shall be test rolled in accordance with Section 173.
f926ef4d-7148-5de0-a31b-14327cb6b85e | note | REFERENCE DOCUMENTS: Cl 173.03, Cl 204.12
11f09014-56bb-5637-8739-e07d1fc694c0 | note | INSPECTION/TEST METHOD: Visual Inspection
fecf19b2-d4ca-5f6c-be81-4c48b542d6ea | note | RECORD OF CONFORMITY: This ITP signed
98f7ce26-5fd8-570b-9776-4bf20944e283 | note | HP
14349753-7e3f-5146-a35f-8f4729356f90 | note | RESPONSIBILITY: Site Engineer / QAV
fcbbc1b6-45d9-524b-bcad-796e5eb28399 | textbox | DATE:
f38a8130-c143-5aab-830f-f5adc6c716b8 | signoff | AUTHORITY HOLDPOINT
0c447284-5a0c-5b99-b2f2-2ae0e5f5b1a3 | checkpoint | 4.2 Cut and Fill Tolerances
614b866e-7399-59ad-9a3a-0d4ee560b1a8 | note | FREQUENCY: In accordance with Table 204.031. Lots < 4,000m²
635e47c0-3f2c-5939-87f7-352da54157e6 | note | ACCEPTANCE CRITERIA: Formation width and alignment: not less than the widths specified or shown on the drawings
9b4500f8-5baf-52c3-ac46-d331a657d7af | note | ○ Formation level and shape: Verges match FSL at outer edge of shoulder or pavement (± 50mm from design level)
fc241fad-d365-5feb-8ad9-8cf8997f8fca | note | ○ Boxing width and alignment: not less than specified or design levels & no deviation > 50mm from designed offset from the centreline or design line.
33a325cf-3a8a-50ea-9161-fd8ff661befe | note | ○ Type A Material: thickness and width not less than specified at any point.
8323f868-ef2d-537e-9e91-e10372da6c5a | note | ○ Type B material (immediately below capping / selected material): +15mm -30mm specified level
bf3555ff-9906-5d2e-bf7d-b5672ec835a2 | note | ○ Cut floor level (when capping layer required): +15mm -30mm specified level
f52dbd57-7ac2-5ff0-b91d-a04fd8de77a3 | note | ○ Cut floor level (no capping layer): same as subgrade tolerance
47ae1f91-0783-5935-bd04-e94af30ff217 | note | ○ Subgrade Scale A & B: random levelling Cl204.03(h). No point > 20mm below a 3m straightedge laid in any direction.
d1b79306-52f3-5081-b24d-bbf1dd892c7c | note | ○ Batter and slope: Not steeper than specified at any cross section.
6be7b08c-ef1a-5166-bcb3-3aa73de6fb4e | note | ○ Batter line: Batter point < 10% of the batter height outside the calculated batter line.
fd3b8cd5-52c9-5818-9ff4-252bf76907ce | note | ○ Surface Drains: Invert levels and side slopes ±50mm and free from depressions capable of retaining water.
c50c6a9d-badc-532d-a301-806423e0da67 | note | ○ The contractor shall establish a procedure to verify that compacted layers do not exceed the specified thickness. Verification records must provide evidence of measurements taken every three layers.
04ec9adc-fa6e-5e3e-b36d-bdd91e538a4c | note | REFERENCE DOCUMENTS: Cl 204.03, Table 204.031,
12b70c52-a01f-5c5d-a07d-95ce92579067 | note | INSPECTION/TEST METHOD: Verify
6db0b27f-44a1-59ef-a0a6-c269cc210593 | note | RECORD OF CONFORMITY: This ITP signed
5d5c8048-96cb-5eea-8b09-271f3d79a69b | note | SCP
af03e8f6-7800-54ef-a92d-4265e3b4c2fd | note | RESPONSIBILITY: Site Engineer
4ee5aa89-8ab6-5b20-ae42-fa1ef0ee25a9 | textbox | DATE:
05ed80bc-5b62-506a-937f-f3fa6f474b44 | checkpoint | 4.3 Subgrade level conformity
839c7229-6f54-5d05-a78c-3e6a96066069 | note | FREQUENCY: Each Lot
b1cb0782-014f-57ce-8542-09b26491c6ee | note | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
3c32ef8b-ffea-5010-b011-a89d97f12359 | note | ○ Level tolerances:
93e61a1c-9f75-5d1a-a8e4-dc1dad3a6dec | note | ○ Scale A - 80 measurements per lot
e88a8ca3-1871-5e35-bdaa-8ca8836b912c | note | • Range = +5, -15mm
aef674d1-5f14-5644-af05-a91d11d83258 | note | • Max S = 12 mm
27c9b065-3f84-55a9-aeed-29ac94a37ad2 | note | ○ Scale B - 40 measurements per lot
20705992-77d5-5df6-a0ce-b393cb26ad82 | note | • Range x = +5, -25mm
7fd1fc2b-d71d-56b7-a9d4-be2a6cf1a641 | note | • Max S = 15 mm
48c1f5c5-9917-5218-88f7-7be9d2f065ea | note | REFERENCE DOCUMENTS: Cl 204.03
83ff0246-60af-5c60-b039-5632ea8d62a0 | note | INSPECTION/TEST METHOD: Verify
1107b479-e50d-5700-adfb-2a660d68468d | note | RECORD OF CONFORMITY: This ITP signed, Survey report
ec788772-ded0-53c2-bb46-107292de4456 | note | SCP
926035c3-3f7d-5af8-b996-cf490c8ec8ae | note | RESPONSIBILITY: Site Engineer
2df00923-ec22-54fa-b8cf-8c7f706a3e8b | textbox | DATE:
104441db-fdf5-582d-9f72-8a700018944b | checkpoint | 4.4 Fill Material Compaction & Moisture Content Requirements
c5fa28aa-822d-5082-b6ca-d19c37f6e243 | note | FREQUENCY: Each Lot as defined in Table 204.142.
a567c897-7bd1-5226-9dfb-2c9f9dc06266 | note | ○ 6 tests per lot.
60accbb1-2866-5ff3-a03a-7871e285b38e | note | ○ Small area lots (<500m2) as per Cl173.04d.
e7185b33-b7ca-540a-8ea2-29c7d96c4284 | note | ○ 3 test mean lots.
d891a574-8d6e-51a1-9def-fb0dca0bb608 | note | ○ +2% compaction req.
a6d12b13-4511-5e10-8f44-f1dd1ab7c416 | note | ACCEPTANCE CRITERIA: Refer to Reference Documents for particular Tolerances, Properties and Testing Scales and subsequent Requirements.
8182385b-ea9c-56f3-baf6-d9035241fca2 | note | ○ Table 204.161 for Project Specific Scales for each applicable Road Name or Area.
a33c6f57-83e7-545f-8ed8-784314aaae27 | note | REFERENCE DOCUMENTS: Cl 204.13, Table 204.131, Table 204.161
3114802f-1a4d-5fd5-bb50-9d886001d6f9 | note | INSPECTION/TEST METHOD: Verify
8d0031d7-b6fa-525f-a1f7-e60f63afb6ff | note | RECORD OF CONFORMITY: This ITP signed
80b0c042-9459-5bc9-9a54-8084b02d3d4f | note | TP
ce1ba6ce-895d-5bb9-8ca4-42c551d6192e | note | RESPONSIBILITY: Site Engineer
904d7a77-9913-5b9b-ba41-c561e990cdce | textbox | DATE:
e0af7d43-b945-5250-8dd3-5f60a1ef0dbe | checkpoint | 4.5 Material Properties Testing (Scale B)
13e671b4-012f-51ef-930f-d03391c0d9c9 | note | FREQUENCY: Once per lot or per material change, as per Table 204.141
4275360d-9f64-5b9c-a4bd-48f2c6e4ff55 | note | ACCEPTANCE CRITERIA: Refer to Reference Documents for particular Frequency of Testing and Material Properties Testing Requirements.
1faae274-202b-535e-9a0e-8f57bee2a624 | note | ○ Table 204.161 for Project Specific Scales for each applicable Road Name or Area.
1e2fc7f7-e333-5e3c-b5db-bb7b53542c80 | note | REFERENCE DOCUMENTS: Cl 204.14, Table 204.041, Table 204.161
ec7ac8b9-0c8b-5526-bfe0-be758764c649 | note | INSPECTION/TEST METHOD: Verify
df47894f-5512-5f5b-82de-bb35a187cc02 | note | RECORD OF CONFORMITY: This ITP signed
a7023b12-29cb-5e85-b242-30b43504667d | note | TP
8fa9be29-9402-5e21-b708-50fa4fc56bb2 | note | RESPONSIBILITY: Site Engineer
23230a02-0eba-58ae-bfc3-15f5ca7a03f5 | textbox | DATE:
a14f193f-1952-5a8c-bdf4-552fb86e49ba | checkpoint | 4.6 Preparation and Maintenance of Final Earthwork Surface and Subgrade
8e50b809-a0d4-5e66-b458-9d2a746d1e03 | note | FREQUENCY: Each Lot (Final Layer only)
a0e0a2e5-30d9-5828-a4ee-271962fc91a5 | note | ACCEPTANCE CRITERIA: Smooth, hard, tightly bound surface presented. Free from depressions capable of holding water.
9cd07ab3-9a5a-5cd7-b0b4-a99ff47af390 | note | ○ Material within 150mm of subgrade shall be maintained such that its moisture content is not less than 70% of OMC prior to placement of pavement layer.
260498d5-e46d-5c8a-9b32-35e5feb7ea57 | note | REFERENCE DOCUMENTS: Cl 204.15
d1b2af4f-c7a9-5704-b319-42faa3a8127f | note | INSPECTION/TEST METHOD: Visual Inspection
34ac4ed2-83b9-5f26-b31d-c1921dca465b | note | RECORD OF CONFORMITY: This ITP signed
4cbbffb8-6503-5ade-9fc7-6918afbba3e3 | note | IP
af5aee9d-026f-59a0-91c1-68ac0a6d2cf2 | note | RESPONSIBILITY: Site Engineer
2a6fd3af-6196-5ff7-9585-9702aa6f2c28 | textbox | DATE:
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
f27117bd-4260-5794-9a1e-b14fc3fb3274 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
ad53fdfe-e26a-5075-8860-01d7aaef3b12 | textbox | Print Name:
815095b1-da36-5c66-af65-92d687afdcdb | textbox | Position:
59c90ae9-b784-5a9f-8bba-d75b19e404f5 | textbox | Date:
a0c663c6-4171-59c1-b168-9abeb4fc1adc | signoff | Add Signature
dd9a8a2b-e49f-5ba9-b8c4-40a2c6d450aa | checkpoint-no-value | Table 204.031 Minimum Number of Level Measurements and Tolerances
0f1dec45-7570-524d-b7e2-b1df27796ace | note | Scale of Surface Level Measurement ¦¦ Minimum Number of Measurements per Lot ¦¦ Tolerance: x̅ Range (mm) ¦¦ Tolerance: Maximum S (mm)
382f9d10-d94a-56d3-9ca6-18fbc2f74d13 | note | – – – – – – – – – –
92a30b35-119b-5525-a814-7d04b82d1499 | note | Scale A ¦¦ 80 ¦¦ +5 to -15 ¦¦ 12
140c40b8-411b-5d10-b396-9f20b2ce3711 | note | Scale B ¦¦ 40 ¦¦ +5 to -25 ¦¦ 15
48040c0a-b46e-5604-877d-878f96603b5e | note | – – – – – – – – – –
6c9d4cb6-6106-52e4-898b-0e5a8eede25e | note | Notes:
cc73740f-25a1-5bf6-95c7-4ed87a64e14b | note | 1. x̅ is the mean value of all level readings taken in the lot
17c612dc-95d6-56c5-8c6c-0c72a65b991a | note | 2. S is the standard deviation of all level readings taken in the lot
aeb773c4-de70-5928-b590-bf4f9f004014 | note | 3. A negative value designates a measured departure below the design level and positive value designates a surface level above the design level
a6f8a824-8b4d-5175-85fd-87e03b3f7113 | checkpoint-no-value | Table 204.041
52e1bd9a-c706-544a-bebe-0b93098be54f | note | Location and Use of Type A Material ¦¦ Physical Properties: Assigned CBR (min) % (1) ¦¦ Physical Properties: Swell % (1) ¦¦ Physical Properties: Permeability (max) m/s (2)
2cd916a9-cceb-51b5-9315-382fac104724 | note | – – – – – – – – – –
7815dec5-5229-5bab-9bb4-d4bc15309933 | note | Capping Layer ¦¦ ##:6 ¦¦ ≤ 1.5 ¦¦ 5 x 10^-9
fd09bd21-301e-5597-99a7-5e917321eb11 | note | Selected Material ¦¦ ##:6 ¦¦ ≤ 1.5 ¦¦ Not Applicable
718a0feb-f1dc-582e-aa84-2ec861d93a5e | note | Verge Material ¦¦ ##:6 ¦¦ ≤ 1.0 ¦¦ 5 x 10^-9
afcff6f6-90d3-51df-bf89-bca571e9d1a9 | note | Structural Material ¦¦ ##:6 ¦¦ ≤ 1.5 ¦¦ Not Applicable
d44c9597-da3e-528e-b83d-47a0bfe85760 | note | Other Type A Material ¦¦ ##:6 ¦¦ ≤ 1.5 ¦¦ Not Applicable
bfdc58d0-8e8c-5119-87e8-0a031849ba9f | note | – – – – – – – – – –
7aac4370-74de-549d-9546-8bf7724a429b | note | Location and Use of Type A Material ¦¦ Limits of Grading (% passing by mass) :: Post Compaction Sieve Size AS (mm)
4bc413ac-ecec-5ba0-940b-378fe5be73a6 | note | – – – – – – – – – –
1f144122-f552-5b42-a936-e043b952de98 | note | Capping Layer ¦¦ 75.0 :: ##:100 ¦¦ 37.5 :: ##:- ¦¦ 4.75 :: ##:40-80 ¦¦ 0.425 :: ##:- ¦¦ 0.075 :: ##:10-40
1180cc2c-b344-5c47-9d9a-0ca6395d23b8 | note | Selected Material ¦¦ 75.0 :: ##:100 ¦¦ 37.5 :: ##:- ¦¦ 4.75 :: ##:40-80 ¦¦ 0.425 :: ##:- ¦¦ 0.075 :: ##:10-40
f11f3f66-7ecf-505f-ac99-80f8242f3632 | note | Verge Material ¦¦ 75.0 :: ##:100 ¦¦ 37.5 :: ##:- ¦¦ 4.75 :: ##:40-80 ¦¦ 0.425 :: ##:- ¦¦ 0.075 :: ##:10-40
c9514600-96c7-5819-aa29-38cbdd480da2 | note | Structural Material ¦¦ 75.0 :: ##:100 ¦¦ 37.5 :: ##:- ¦¦ 4.75 :: ##:40-80 ¦¦ 0.425 :: ##:- ¦¦ 0.075 :: ##:10-40
f0a5c143-8f62-566b-86ed-836430c87c6c | note | Other Type A Material ¦¦ 75.0 :: ##:100 ¦¦ 37.5 :: ##:- ¦¦ 4.75 :: ##:40-80 ¦¦ 0.425 :: ##:- ¦¦ 0.075 :: ##:10-40
272de9e5-5b4f-5a9e-a193-3e763e40c489 | note | – – – – – – – – – –
32bcd2ab-f528-5c3a-a903-d6870d16bded | note | Notes:
d033d1c5-0bb9-5249-b05a-d6d446aa6823 | note | (1) The Assigned CBR and percentage swell values are to be determined in accordance with VicRoads Code of Practice RC 500.20. Sampling for CBR testing shall be undertaken after field compaction.
3d68d2ef-34fc-5456-9cc3-dc2c5e390ee6 | note | (2) The permeability value is to be determined in accordance with VicRoads Code of Practice RC 500.16. The permeability value is to be determined on specimens manufactured from that fraction of material which passes a 19.0 mm AS sieve, compacted at optimum moisture content and 98% of maximum dry density as determined by testing using standard compactive effort for CBR and swell.
370af1b8-cb16-5c30-9714-af98f82ce6dd | checkpoint-no-value | Table 204.111 Fill at Structures
47f6877f-2c62-5138-bd2a-ab247604675e | note | Non Vibrating Rollers - Static Weight * (tonne) ¦¦ Vibrating Rollers - Total Applied Force ** (kN) ¦¦ Minimum Distance from Compaction Plant to Abutments, Retaining Walls and Wing Walls (m) ¦¦ Minimum Cover over Top of Culverts (m)
16dc9383-20e9-5cbc-a08e-c19fce72287c | note | – – – – – – – – – –
902d30fb-4c36-5254-a41c-9e40c41b90b9 | note | Less than 2 ¦¦ Less than 20 ¦¦ 0.15 ¦¦ 0.15 ¦¦ 0.15
e1816bae-ea36-5e03-a160-8e931071d830 | note | 2 - 5 ¦¦ 21 - 50 ¦¦ 0.3 ¦¦ 0.3 ¦¦ 0.15
419f1931-21a8-5746-9e17-bf7b26fc0541 | note | 6 - 10 ¦¦ 51 - 100 ¦¦ 1.2 ¦¦ 1.2 ¦¦ 0.4
86602e1e-4a52-5a16-8ec7-9ec4e7c6d0dd | note | 11 - 20 ¦¦ 101 - 200 ¦¦ 2.4 ¦¦ 1.2 ¦¦ 0.4
2cbf9565-21f5-5df2-960c-3fa9aabc52bc | note | 21 - 35 ¦¦ 201 - 350 ¦¦ 2.4 or height of structure (whichever is greater) ¦¦ 1.2 or height or structure (whichever is greater) ¦¦ 0.7
cd87c9c5-5dd6-5da0-9846-bf389dd0a366 | note | – – – – – – – – – –
bb927682-bccf-567c-a3a7-23487cb47a4e | note | * Includes vibrating rollers operating in non-vibrating mode.
0e898301-40e2-52d5-bf92-ebb85eee9173 | note | ** Total Applied Force is the sum of the static weight and the vertical component of centrifugal force.
4a584b18-9522-58a8-8b70-92e140f71fa6 | checkpoint-no-value | Table 204.131 Compaction Requirements
f6e3240b-366d-5cf8-ae64-7f7aa7ed27f3 | note | Material Type and Location ¦¦ Scale A: Minimum Characteristic Value of Density Ratio (%) ¦¦ Scale B: Minimum Characteristic Value of Density Ratio (%) ¦¦ Scale C: Minimum Characteristic Value of Density Ratio (%)
de0fab43-f842-5214-a080-697df04c460d | note | – – – – – – – – – –
75feaace-1a08-5793-b73d-469321c176a0 | note | All Type A Material ¦¦ 99.0 ¦¦ 98.0 ¦¦ 100.0
174b8c60-a1f6-5e89-b222-a68f1c581420 | note | Type B Material placed within 400 mm of top of Type B Material ¦¦ 99.0 ¦¦ 98.0 ¦¦ 100.0
6b3ee273-e3bb-52b3-8d65-dd36be2b1f65 | note | Ripped and re-compacted material below Cut Floor Level ¦¦ 99.0 ¦¦ 98.0 ¦¦ 100.0
2d887ddb-d242-5e10-87f8-5580cea17d0b | note | Type B Material placed more than 400 mm below top of Type B Material ¦¦ 97.0 ¦¦ 95.0 ¦¦ 95.0
b4d806dd-7cfe-5d52-b647-3be2493d39ec | note | The top 150 mm of areas where fill is to be constructed ¦¦ 97.0 ¦¦ 95.0 ¦¦ 95.0
26bc0020-61f1-5840-8679-b03b66d31838 | note | Type C Material ¦¦ 97.0 ¦¦ 95.0 ¦¦ 95.0
e6f455ae-beca-5d8a-b84d-ab500c066ae0 | checkpoint-no-value | Table 204.142 Minimum Frequency of Testing for Compaction and Moisture Content
640c85f7-5eee-5be8-808f-27a14bdf8fde | note | Material ¦¦ Acceptable Lot Size in a Single Layer of Work ¦¦ Minimum Testing Frequency
28c807a2-f1df-5bdb-ab38-bf144d464c16 | note | – – – – – – – – – –
ce144744-1dca-5e82-93cf-b0fe0b769dbd | note | Type A Material ¦¦ One day's production or 5,000 m^2, whichever is the lesser ¦¦ Every second lot of like material and work
7c5439f2-d8c2-50d7-8369-4440057dcd09 | note | – – – – – – – – – –
f47fa1b5-addf-5bbb-9706-69aca7f3acff | note | Type B Material
73cae90f-ab3c-5853-9c7c-c802efa5a395 | note | • Ripped and re-compacted below Cut Floor Level ¦¦ One day's production or 10,000 m^2, whichever is the lesser ¦¦ Every sercond lot of like material and work
91b5d338-ef81-5698-851a-a868f62af5ad | note | • Placed within 400 mm of top of Type B Material ¦¦ One day's production or 10,000 m^2, whichever is the lesser ¦¦ Every second lot of like material and work
5c73c33a-1da4-53a5-a8fc-1ea840773785 | note | • Placed more than 400 mm below top of Type B Material ¦¦ One day's production ¦¦ Every third lot of like material and work
154048ef-2626-55d7-96d0-26ba8e00f5fe | note | – – – – – – – – – –
5b286360-da3e-54cb-abe3-e69d03752dc1 | note | Type C Material ¦¦ One day's production ¦¦ Every sixth lot of like material and work
f0dc6815-a506-5c61-968b-b5ee0266d8a4 | checkpoint-no-value | Table 204.161 Schedule for Surface Tolerance, Material Properties and Compaction Testing
39fdfa8c-e9ca-5779-a8cb-7fd7e8cd6aa2 | note | Road Name ¦¦ Chainage / Location ¦¦ Scale of Surface Level Measurement (A, B or C) ¦¦ Scale of Material Property Testing (A or B) ¦¦ Scale of Compaction (A, B or C)
70396700-d558-5c19-b8e4-8dec393801e5 | note | – – – – – – – – – –
78a1609a-bc8c-5d78-ac91-3febbcc117e2 | note | Bruny Island Main Road ¦¦ Within Limits of Works ¦¦ B ¦¦ B ¦¦ B
db88f3aa-973b-5976-8136-28396aa4b3f1 | note | – – – – – – – – – –
08f4a318-0035-5521-86b0-17ef2552ec13 | note | Note: Where no level of testing is nominated, Scale A applies.
6c4b3fc1-fe5c-5746-95e6-a819a0863ca2 | checklist | ITP - Linemarking & RRPM & Road Furniture and Signage Rev0 | itp | ITP - Linemarking & RRPM & Road Furniture and Signage
56f12a57-1e96-5877-8041-0f0eb46d12c8 | section | 1 - Preliminary Works
8cd47aa7-19e4-55e7-9939-09ffbf3c7b11 | checkpoint | 1.1 Check for correct documentation
0b9c54ad-d2d9-5f71-b8cb-bbe8f17c35af | note | FREQUENCY: Prior to commencing any activity
1fe43753-8f9f-52e3-b866-936d1b6474cd | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
f7e12a3d-ad75-502b-93ac-bbb109300461 | note | – using the correct and complete set of drawings
1b035351-a663-5b9d-88b3-24c86094cd93 | note | – all drawings are the latest revision
79f17335-b9ab-5277-a134-2a22042c26c5 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
1bd48ae4-4f1c-5e21-b433-f95c5012b3e4 | note | INSPECTION/TEST METHOD: Document review
bb20dbc3-cd7b-57b1-9ac2-6179042c783f | note | RECORD OF CONFORMITY: This ITP signed off
7e870c73-5d7e-509c-a1fd-de8dfb70e53d | note | HP*
06cd8180-e500-5635-98b6-513b19120b81 | note | RESPONSIBILITY: Site Engineer / Site Foreman
83261935-a6d3-5c41-b513-3cb973be7f25 | textbox | DATE:
6a9380d5-4e77-5177-a005-cf90a26e111a | checkpoint | 1.2 Implementation of all measures and controls
2186f17a-690b-5f89-a75b-b8eaa18b36cc | note | FREQUENCY: Prior to commencing any activity
97df31df-c7a1-5ced-af1d-25718c263d9d | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
deda09f1-3a03-5f6e-918e-1381d205a90d | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
ac879991-2d8a-5bb2-9901-77a66455f475 | note | INSPECTION/TEST METHOD: Visual Inspection
abf79570-1ce9-5eb7-9832-bc80c7f089b6 | note | RECORD OF CONFORMITY: This ITP signed off
b400be62-e894-5171-9f02-22de4581ad78 | note | HP*
e13650a3-e1e7-52d6-967a-3bbb6fcd1040 | note | RESPONSIBILITY: Site Engineer / Site Foreman
ae7c3d75-2930-5dd9-8528-cff14bddecd8 | textbox | DATE:
4017f938-701a-5bde-a9a9-6e2efb1399f1 | checkpoint | 1.3 Signage Conformance
2a15b2cb-04b3-5734-8107-341e42a1adcd | note | FREQUENCY: Before commencement of activity
c4768252-a625-5c68-abff-d38ba9569a1a | note | ACCEPTANCE CRITERIA: Ensure sign size and image correspond with contract drawings Road Signage Installation
7c9a07ea-8d17-5db1-9e51-e92e3f7e2228 | note | REFERENCE DOCUMENTS: Drawings 2101-2116
ea9bc90f-ccc3-5732-9f31-0349964b67e7 | note | INSPECTION/TEST METHOD: Verify
c8713943-1bb7-5dad-b573-6700b509e17c | note | RECORD OF CONFORMITY: This ITP signed off
b66b4cb6-2490-595f-89e0-09570b5985b8 | note | IP
1caf94df-b76f-586f-8121-497b9a4a88fb | note | RESPONSIBILITY: Site Engineer
c7f41d03-39ec-548d-bfba-7ae33a1e36d0 | textbox | DATE:
3debb25f-a5c0-53c1-a980-fb6ac7188c16 | checkpoint | 1.4 Service Identification
780c32e3-7ede-5572-afd4-77e7d6d25628 | note | FREQUENCY: Prior to start
78ac2a25-232b-5498-bc15-7b466f241d30 | note | ACCEPTANCE CRITERIA: Check for any services in proximity to points of installation of posts (Road Sign Preparation)
5d8654a8-25cb-56fe-8afa-af26b3c4967e | note | REFERENCE DOCUMENTS: DBYD
8607e6c3-dea7-5ed0-81d5-ca5fd1e78c0f | note | INSPECTION/TEST METHOD: Verify
2352f9f1-ca0a-5675-9d7a-11626356c7f7 | note | RECORD OF CONFORMITY: Ground penetration permit, This ITP signed off
8b5872b4-3b8c-5c27-b3ed-9ea3fc353e67 | note | IP
27abbb9f-e825-5c77-8f2b-01f36efc811b | note | RESPONSIBILITY: Site Engineer
5e5a59d7-d91b-59d1-b0fb-e54a127621ff | textbox | DATE:
0bd3aa71-6e9f-5780-b9cb-c76610b181b0 | section | 2 - Linemarking Works
72cc7b91-1f87-5f9d-a209-a64d9de98bea | checkpoint | 2.1 Set out of line markings; dimensions and spacings
38e8b859-6ae5-5cdd-bdfb-d7803c113a9e | note | FREQUENCY: Prior to commencing line marking works
c0d7a54c-b8dd-5831-a4cb-8016f2264177 | note | ACCEPTANCE CRITERIA: Holding Point:
ca9bae20-3c84-5be7-ac9d-c1c60fc659d4 | note | ○ Painting/application of material shall not commence until the Superintendent has inspected the set out and given consent to proceed, unless an exemption has been granted in writing by the Superintendent.
8803c48a-6457-5bc0-affb-17a2fa1a119d | note | (a) New pavement markings shall be positioned in accordance with the following requirements:
3806eaec-5860-5c98-9308-f850f09f4d03 | note | (i) set out by the Contractor in conformance with the appropriate standard required by Clause 721.A03
dd4dc2c2-946e-5408-9c68-94bb6d647a0a | note | (ii) applied within the tolerances listed in Table 721.A101.
3b896978-bdb6-5d72-a7b2-db14e0f830f5 | note | (b) Temporary Reflective Markers Temporary reflective markers for new works shall be placed at the following minimum spacings on all longitudinal lane lines, except that on any curve less than 500 m in radius the spacing shall not be more than 12 metre centres:
540ece18-012b-58b8-acdb-cf8367db49e4 | note | ○ AADT ≥5,000 and National Highway 12 metre centres
3b733ca0-2733-5704-bad6-881031ea71e7 | note | ○ AADT ≥1,000 and <5,000 24 metre centres
a6b65708-c1d9-543e-a2c6-1219a0831e2c | note | ○ AADT <1,000 48 metre centres
da29ebaf-6cea-5bfe-8faf-50fffb56af29 | note | REFERENCE DOCUMENTS: Cl.721.B05
b8369213-2cf8-5b97-b15c-4675daa53a79 | note | INSPECTION/TEST METHOD: Document review & Site inspection
853753b4-a426-5c01-818d-d5184ed54f58 | note | RECORD OF CONFORMITY: Consent to proceed by Superintendent OR written exemption granted, This ITP signed
61641c49-9607-5755-8008-1c7526d54dca | note | HP
df279a53-5f20-594a-afe3-8e383fc11951 | note | RESPONSIBILITY: Site Engineer / QAV
23b812d5-53bb-5725-b4fc-247b197aa239 | textbox | DATE:
79f102e2-be88-593a-9510-93ebad0efa85 | signoff | AUTHORITY HOLDPOINT
d8131644-8560-593e-bee3-da19474503ed | checkpoint | 2.2 Verification of line marking material
f110fbce-f032-5bac-87fe-3be58d53993f | note | FREQUENCY: Prior to commencing line marking works
8ad21028-8439-5ce5-90e6-6401c0b227e8 | note | ACCEPTANCE CRITERIA: Line marking material is to comply with minimum requirements as specified in Spec Tables 721.D021 and 721.E021
ae5c24c2-21e0-55f4-b586-ccdc73c5ed7e | note | REFERENCE DOCUMENTS: Cl.721.D02, Cl.721.E02
0024b2be-b37f-5d20-9f9c-f403f2e97723 | note | INSPECTION/TEST METHOD: Document review
d0f8ec78-5337-567d-9eab-67c8144381c1 | note | RECORD OF CONFORMITY: Material compliance, This ITP signed
c23afc40-4c3b-5e97-98a5-68f14bc37d67 | note | IP
1d377449-4351-5bd4-9f27-a249c2971f0a | note | RESPONSIBILITY: Site Engineer
5a321611-1d6c-587e-8eed-a6be866f1746 | textbox | DATE:
e8669535-4cff-5af6-9832-f974730b1316 | section | 3 - RRPMs
6abe4c97-ae91-5941-ade9-9a5d0ad2ec93 | checkpoint | 3.1 Materials
5ea59abf-f6b8-5ec1-b518-6ace0b20d16a | note | FREQUENCY: Each lot
a45e391a-7941-5f40-b85c-c9150b149619 | note | ACCEPTANCE CRITERIA: Markers shall comply with the relevant requirements of AS 1906, Part 3.
451593d0-fc37-5982-90c6-52497016d5de | note | ○ Epoxy adhesive shall be Standard Set or Rapid Set adhesive complying with the relevant requirements of AS 3554
ae388d08-0dcf-5661-a524-b47a1e42f3dd | note | REFERENCE DOCUMENTS: Cl 710.03
15336e68-a6d1-5e08-9de2-bf9c07444102 | note | INSPECTION/TEST METHOD: Visual Inspection
d2ceffe5-ac7a-5b16-bf56-53a45fa9d9af | note | RECORD OF CONFORMITY: This ITP signed off
a6581436-c7fa-5506-a5d6-0a9898211e70 | note | IP
f40cff6b-cb54-56fd-9e8f-c9fafd56af62 | note | RESPONSIBILITY: Site Engineer
1a80d96d-ffe1-5264-aba1-d28ec623223c | textbox | DATE:
47e2f789-3e1e-597a-bac4-56438ca20871 | checkpoint | 3.2 Preparing Adhesive
95b98a44-3075-50d8-85dd-707f541558e6 | note | FREQUENCY: Each lot
9d9ed737-fa98-5763-bf9f-67ba5b93f8a3 | note | ACCEPTANCE CRITERIA: Adhesive components shall be batched so that the mixed adhesive contains not less than 45% nor more than 55% by volume of either component. Before starting work each day, or when changing to a different batch of adhesive, a hand mixed colour standard shall be prepared for reference during the day.
0da6ae4d-108b-5f32-bf88-d78bc90d70c7 | note | ○ When hand-mixing is used not more than 500 g of each component shall be mixed at any time.
7ae6d7e6-0cbc-5045-8d03-715426f03a00 | note | ○ The components shall be mixed on a flat surface and the mixed adhesive shall be used within 10 minutes of the time the two components are brought together.
496c688a-4644-5b8c-8a7e-4edb5c3c78e2 | note | ○ Hot melt bitumen adhesive shall not be used on days of total fire ban without the written approval of the Tasmanian Fire Service
5dba2d81-8021-5eac-b4c9-a48758ba9e4b | note | REFERENCE DOCUMENTS: Cl 710.04, Cl 710.05
d98e8a2f-a9ac-5e4c-a994-650fcf9cdcfa | note | INSPECTION/TEST METHOD: Visual Inspection
5ead8ae3-e1c7-51ae-b563-854e817f8096 | note | RECORD OF CONFORMITY: This ITP signed off
6047b1ce-4151-5c1d-86bc-252e3c1ce1cc | note | IP
f02ca565-3dcc-5a1b-9edc-102e7eebf635 | note | RESPONSIBILITY: Site Engineer
ce248828-15a1-5631-9066-7975fd7b2b3d | textbox | DATE:
3bc48a60-4db8-5e86-863f-a01d0ef02ee1 | checkpoint | 3.3 Pavement preparation
7edf86ce-f56e-524b-8382-fd715c91dc24 | note | FREQUENCY: Each lot
130c5c49-f286-5c76-a76a-ca23c6907a70 | note | ACCEPTANCE CRITERIA: The Contractor shall sweep or air blast each marker site as necessary to remove loose material before placing markers. Markers shall only be placed at locations where the pavement is free from dirt, oil, grease, paint, or any other material
da4a5d55-310f-51e9-97ac-9fe26174be40 | note | REFERENCE DOCUMENTS: Cl 710.06
d0dbde0f-9ce1-536b-8946-411e4433da0a | note | INSPECTION/TEST METHOD: Visual Inspection
c79b7400-bd6d-5a99-9441-83456562f64a | note | RECORD OF CONFORMITY: This ITP signed off
cb6b3a66-93bc-5472-ab2a-d1c9efc56848 | note | IP
2957d621-963c-518c-a75a-36477af99c08 | note | RESPONSIBILITY: Site Engineer
e485c300-6cf6-52c6-9676-517a72a59ed9 | textbox | DATE:
685a03fe-e33a-519b-9b0c-d6573d1cdf86 | checkpoint | 3.4 Placing markers
4069850a-3d23-5469-b2b5-d82c05ca18e2 | note | FREQUENCY: Each lot
5646607a-4937-5fb3-addf-6a81cc35828f | note | ACCEPTANCE CRITERIA: Markers shall not be placed in any of the following circumstances:
b568f0d2-23c7-5428-bd49-c2d880661fa5 | note | • when the pavement is wet;
6496fa81-0d2a-5dea-b9d3-aca42d25416b | note | • when the relative humidity is greater than 80%;
1bdd0d23-d5b9-5d85-a1b2-de16f4e73319 | note | • when the ambient temperature or the temperature of the road surface is less than 15deg for standard set adhesive or 0deg for rapid set or hot melt adhesive.
78519838-a1fe-5c25-a078-b5c519634419 | note | ○ Where a marker is not positioned correctly within 10 seconds for hot melt bitumen adhesive, 2 minutes for rapid set machine mix adhesive, 4 minutes for standard set machine mix, or 10 minutes for standard set hand mix from the time mixing commences, it shall be discarded and a new marker placed.
35bff9fb-63a8-5ef1-badb-dfbc4b13ad93 | note | REFERENCE DOCUMENTS: Cl 710.07
c143a6ae-c4a2-5f8d-b43d-097050d3ccdd | note | INSPECTION/TEST METHOD: Visual Inspection
457f5c31-501a-58e2-925c-674ff9ee1d69 | note | RECORD OF CONFORMITY: This ITP signed off
51723e1e-6e5f-58eb-b8f9-d1809ca0f042 | note | IP
25c6ad85-edf9-5ce1-bf8d-6349d63c0460 | note | RESPONSIBILITY: Site Engineer
6c6bb0bb-ff59-5457-b791-e827e13f776e | textbox | DATE:
19f8df37-fec8-5d8d-94a8-c8878162ab0c | checkpoint | 3.5 Tolerances
11b42dfc-fd3b-5cde-a252-e592aa00a80d | note | FREQUENCY: Each lot
bb9e8a0d-0f54-5a40-9abb-760d6002093c | note | ACCEPTANCE CRITERIA: (a) Markers in Line with Broken Line Segments
b8d45628-fa59-521b-9892-3d3174019fdd | note | ○ Transverse position within 25 mm of the centreline of the segments.
0b977679-9017-591f-bd3e-23cc71b84626 | note | ○ Longitudinal position within 0.5 m of the specified position.
fd6cb9c5-1d0c-5177-b33d-c3dff315a54b | note | (b) Markers in a Longitudinal Group
c1e4af46-390b-5251-b48c-7d219883ec2f | note | ○ Transverse position of the centre of each marker within 25 mm of the specified position and within 10 mm of a line joining the centres of the end markers of the group.
a20b91f7-0190-5d76-8583-9ba89e755625 | note | (c) Markers Adjacent to Unbroken Line
0d76f315-8c99-5ee5-baf6-0fe8ae69f551 | note | ○ Clearance to edge of line within 5 mm of that specified.
223c45e0-878c-5879-9e25-95d04d92f482 | note | ○ Longitudinal mismatch between markers in transverse pairs at barrier line not more than 25 mm.
7244d634-a3de-5087-b811-5e896f87b8e0 | note | (d) Orientation of Reflective Markers
98618ca5-cba7-56a0-8f87-24b92e87670f | note | ○ Lower edge of the reflective face at 85deg to 95deg to the centreline of the roadway or any adjacent line.
de60b547-1eef-5351-9c94-8afdd7e23659 | note | REFERENCE DOCUMENTS: Cl 710.02
c2e1c577-3628-5f46-a4c1-422c8a2ac4e0 | note | INSPECTION/TEST METHOD: Visual Inspection
77b85da4-b7b3-52d7-80fc-b23480d17047 | note | RECORD OF CONFORMITY: This ITP signed off
b6fb96a9-a314-5c46-b921-680233dd5f69 | note | IP
9d04473f-0a93-5ba3-b04b-1fdab4ebd6fb | note | RESPONSIBILITY: Site Engineer
4ebaaa35-43b1-575a-833c-0b141b5c24a3 | textbox | DATE:
ed090b7c-466d-5492-828b-3467643789d6 | section | 4 - Testing
9ef68905-eb5e-52e3-b28b-5100d40a8185 | checkpoint | 4.1 Line Marking Tolerances
9544d705-148b-5013-93c6-a9ad6aad14d7 | note | FREQUENCY: After completion of works
ef1125be-7c6a-553a-aa13-a79b9fd8f161 | note | ACCEPTANCE CRITERIA: Line marking shall comply with the tolerances shown in Table 721.A101.
b4ee4f78-c2ec-58ca-92dc-4fb6c321ac7c | note | REFERENCE DOCUMENTS: Table 721.A131, Project Spec. Table 721.A101
0ca4c4e2-f541-5c02-8ad6-3fcc150a53b5 | note | INSPECTION/TEST METHOD: Document review & Site inspection
c30fa804-b725-5cc2-9c84-8d125e18087e | note | RECORD OF CONFORMITY: This ITP signed
cbedc6ba-ab04-5595-aec8-157e2219a87b | note | IP
95e0c2e0-3028-5912-b298-33f961c6ed49 | note | RESPONSIBILITY: Site Engineer
f370e005-d827-51b5-8829-ca491250170c | textbox | DATE:
9d953758-6ff8-51f3-956b-cc26bc6f2979 | checkpoint | 4.2 Removal of Non-compliant marking
a95ebb38-03e0-54d5-9c02-ea7f10e73d0c | note | FREQUENCY: After completion of works
fc72631c-a7d0-5773-891f-3ddc37092cd2 | note | ACCEPTANCE CRITERIA: Hold Point
b3a3c0fc-2304-5e2c-9872-4ba71b255617 | note | ○ Where the removal of unsuitable pavement marking is required, the method of removal shall be subject to the approval of the Superintendent before removal works commence
9d3eafcf-7b09-56de-a755-ffd6cd6bab93 | note | REFERENCE DOCUMENTS: Project Spec. Cl.721.A12
00ed1896-fd64-5170-93e9-c7a2e30e6231 | note | INSPECTION/TEST METHOD: Document review
bb427e78-ef59-50a9-ad4e-fccdbd4e9fb3 | note | RECORD OF CONFORMITY: Approval from Superintendent, This ITP signed
905ce0fa-d8af-5fde-b633-9508a4d79858 | note | HP
da317a3b-d325-5154-a5b0-30a1f26d42ed | note | RESPONSIBILITY: Site Engineer / Superintendent
bfb1eefc-e981-5d70-a642-7d82003c6307 | textbox | DATE:
13f2851a-77ab-54c8-a93a-6ca4bdfd9c50 | signoff | AUTHORITY HOLDPOINT
8ef4d50c-fcb3-5eae-92f9-e01a830b81ce | section | 5 - Signage
04ca821c-906a-5909-9e6a-4eb13fe03eff | checkpoint | 5.1 Setting Out
31abd87b-a316-51fb-b3b5-6d228a6dcef4 | note | FREQUENCY: Prior to start
298d2891-fa36-5c66-aac8-b9eb9ef5e939 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections.
ee701fe0-e44e-5b83-9aae-843fb2cc8d74 | note | REFERENCE DOCUMENTS: Drawings 2101 to 2116
194febd4-ebe7-5821-86ac-266112c3d921 | note | INSPECTION/TEST METHOD: Visual Inspection
9c17a8d7-5cd9-5eec-87a6-ed7a7adcf22d | note | RECORD OF CONFORMITY: This ITP signed off
af58cc7e-fa96-5ca6-a8fe-8397638188af | note | IP
254e384d-5df4-568c-be62-468da89d8e94 | note | RESPONSIBILITY: Site Engineer
2813e590-42b0-5541-806d-32c562b5a966 | textbox | DATE:
4061d27f-d90d-553d-8c80-f376f7db7bad | checkpoint | 5.2 Conformity with drawings
8b34d21d-fdc2-5dd0-be32-229773aa9512 | note | FREQUENCY: Four weeks prior to installation
82728837-d340-5cdb-9823-13284b1f9784 | note | ACCEPTANCE CRITERIA: Witness Point
6bb17b87-26dc-5b61-ae38-fd219b495f78 | note | ○ If the Contractor proposes to use an alternative method of installation, the Contractor shall submit full details to the Superintendent for approval not later than four weeks before the commencement of sign installation
2b7db2a3-006e-5d31-bb89-9db42af4f8af | note | REFERENCE DOCUMENTS: Cl 714.04
36c58bfe-52db-50df-8de1-fca35dfa67d8 | note | INSPECTION/TEST METHOD: Verify
e105f55d-1f2a-5e89-82bb-a0f0a26c93de | note | RECORD OF CONFORMITY: This ITP signed off
80df0d15-9cb0-5a8d-8ad7-31fc4c0fa245 | note | WP
344c09f2-2b76-5c69-ad89-9015950369c1 | note | RESPONSIBILITY: Site Engineer / QAV
683f5950-2549-5d66-bcc1-71acdb6380cc | textbox | DATE:
645d5d67-c2fa-5149-9de6-083b4add21cd | checkpoint | 5.3 Post & Foundations
d525fab6-c913-56c8-88ca-a7ec7bf1dd6d | note | FREQUENCY: Prior to Start
1996dc2e-2e5f-5640-8924-6a4ad407c9bc | note | ACCEPTANCE CRITERIA: Hold Point
bf1c7a42-e080-5dc3-b798-fdac29eb8f51 | note | ○ The required positions of all posts and signs shall be as directed by the Superintendent who shall confirm the positions before the erection of posts commences.
63baa2fe-d23c-5d6f-a00d-076f7ceef669 | note | REFERENCE DOCUMENTS: Cl 714.06
2c6487d2-621f-55f8-9409-d2e54192e687 | note | INSPECTION/TEST METHOD: Visual inspection
356afe70-61c6-5205-9896-537853d2954e | note | RECORD OF CONFORMITY: This ITP signed off
c2cdd085-9b17-58c9-9f82-5edd9f50a672 | note | HP
986c0530-9c95-515e-8948-f3a4010e6f77 | note | RESPONSIBILITY: Site Engineer / QAV
b40dc32f-e36d-5902-a5e7-1f1a0f5ba6b5 | textbox | DATE:
59bd4cd8-a11e-53fa-abac-e2e651f79ea8 | signoff | AUTHORITY HOLDPOINT
20991af5-0f57-5e3c-9492-8f386963190c | checkpoint | 5.4 Signage Install
05725e03-74e2-5131-9c34-044d907ea064 | note | FREQUENCY: Each Sign
d8484d03-d5c2-59fc-a56c-499f71d56af2 | note | ACCEPTANCE CRITERIA: Sign to be installed as per most current project and DSG standard drawings, local council documentation, and to the correct height and position.
6995c581-2fa2-52b3-bae6-6d8ba1454b17 | note | ○ Signs specified to be re used are to comply with AS 1742 standards, and must be replaced if deemed in unsatisfactory condition
8aa3cf4f-e804-5382-9ee6-cb6cca208072 | note | REFERENCE DOCUMENTS: DSG standard drawings. Cl 714.07
273f47af-5b6f-50ed-8af4-0aa7ecdcd870 | note | INSPECTION/TEST METHOD: Verify
0d0bb156-45d1-5512-80dc-423047651c02 | note | RECORD OF CONFORMITY: This ITP signed off
88b5660a-d675-5caa-9923-1991265c61b4 | note | IP
143ffdd5-3d17-5ce5-bfb4-7c7872acd0d6 | note | RESPONSIBILITY: Site Engineer
4823ceca-414b-509e-872d-889c481eb287 | textbox | DATE:
6514a39e-e67a-5142-9f65-03a2483555be | checkpoint | 5.5 Tolerances
75630129-356b-5155-94fe-f25c982c0fee | note | FREQUENCY: Each Sign
c3d2af8a-1802-55f2-af03-d135562a9cae | note | ACCEPTANCE CRITERIA: Posts vertical with maximum deviation of 1 in 100
5e005fd2-a9bd-5060-9bd0-580f37825dfb | note | ○ Post tops 50mm +-10mm below top edge of sign
66800478-a917-5bf1-acfb-cb473e534223 | note | ○ Signs mounted level with maximum deviation of 1 in 100
0a19157e-36bc-5625-9558-048189c8e8fe | note | ○ +-40mm of the height specified in the Sign and Post schedule
f76bb5e5-6b2c-5f68-9db5-b112f0cf9f0e | note | ○ +-100mm of the pegged sign location or specified location
49bd6505-83be-5886-92ca-e427a961b618 | note | REFERENCE DOCUMENTS: Cl 714.05, Cl 714.07
b55ec938-f371-5066-aa60-1139b2f5d1cf | note | INSPECTION/TEST METHOD: Measure
2892f3b0-416a-5294-82da-0f9bfb9884bf | note | RECORD OF CONFORMITY: This ITP signed off
6e7dc3b9-c77b-5bda-8a5e-f24f57eb8e5f | note | IP
eaa6a46a-91e9-5ed0-82ff-dd17b3fa808e | note | RESPONSIBILITY: Site Engineer
afbf4b83-b1fd-56aa-a2cd-91784b909ebd | textbox | DATE:
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
eb9f3841-52e0-53fd-b14a-80dec00b52f0 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
0e82aa04-0611-5381-8498-a667ebfd096c | textbox | Print Name:
3dfbf5b5-a5ef-5ef5-9f92-b1fe252de2e7 | textbox | Position:
384e9033-8844-505b-b13c-ebe17c9c7ffa | textbox | Date:
a0c663c6-4171-59c1-b168-9abeb4fc1adc | signoff | Add Signature
33f428d3-9dca-50b1-9072-05bb7f65e8f6 | checkpoint-no-value | Table 721.A101 Tolerances on Pavement Markings
66387696-e9c2-544e-96fc-a0f489622b76 | note | Markings ¦¦ Tolerance
5fd7b8e7-4b23-55dd-a067-171f3a8766ec | note | – – – – – – – – – –
526e61f9-5459-5006-a9ff-b3a6fc31765f | note | (A) Pavement Markings (1)
ff18387b-8fee-59e0-8711-520f096cd115 | note | Distance between the centreline of the marking and the centreline of the set out mark ¦¦ < 30 mm
a95b40c6-7da7-5944-84f0-6023825ac32d | note | Distance between the centreline of the completed marking and the centreline of the previous marking ¦¦ < 15 mm
f85d4b8c-d5bb-5720-9b48-e9b750c6681b | note | Width of completed painted markings ¦¦ ± 10 mm of the specified dimensions
2c400636-db33-5219-984e-04d41dfd9a9d | note | Width of completed markings for long life materials ¦¦ 0 mm to +10 mm
9b25e336-7039-5296-a683-e364744b74be | note | Length of completed stripes and blocks ¦¦ 0% to +10% of the specified length
2622dca3-5dc7-576f-acde-26583837d4a8 | note | Gap between dobule lines ¦¦ -10 mm to +0 mm of the required 100 mm gap (2)
b0365dde-2194-55f9-af4d-7ce08654a300 | note | – – – – – – – – – –
761bde3a-3066-5ab0-bea0-8f4895c665e5 | note | (B) Raised pavement markers
dd05bcb3-86b1-5b29-947e-e48788cf049d | note | (i) Markers in line with broken segments
7bd597b8-1fbf-54c9-92cc-d3c3186ac509 | note | Transverse position ¦¦ ±25 mm of the centreline of segments
6bfc4cd5-eaa1-54c4-a30e-e45c3b3e86f5 | note | Longitudinal position ¦¦ ±0.5 mm of the specified position
f4341801-717e-5c3f-a9a5-7e1fd8ee0293 | note | (ii) Markers in a longitudinal group
5ce5f182-b9d4-50e6-9c74-0aa44c6507d2 | note | Transverse position ¦¦ ±25 mm of specified position and ±10 mm of a line joining the centres of the end markers
2cae4d61-0389-5e1c-9325-d317e49069fe | note | Longitudinal position ¦¦ ±0.5 mm
c5bb328a-5e09-567d-ab6e-8d27aa58424f | note | Spacing of markers within the group ¦¦ ±50 mm of specified spacing
3e624a0e-6d61-5154-96fc-c84e36f841f4 | note | (iii) Markers adjacent to an unbroken line
70fa5b25-f9d2-558e-8932-6e4b342bc955 | note | Clearance to edge line ¦¦ ±5 mm of the specified dimensions
12d0b7a1-012c-5dc6-bde7-a771ae00046f | note | Longitudinal mismatch between markers in transverse pairs ¦¦ <25 mm
70386f8a-4588-5700-a72b-b3efe38f44b8 | note | (iv) Orientation of reflective markers ¦¦ Lower edge of the reflective face at 85° to 95° to centreline of roadway or adjacent line
619117cc-6422-5b2d-96d6-b4b040908c6c | note | – – – – – – – – – –
026ee1f4-950b-525a-88d8-713fe2fa4385 | note | (C) Thermoplastic profiled lines
7b5fa731-9947-5944-8e3a-49a12b6ef46b | note | (i) Tolerances on dimension
222e5abc-01d8-5320-91dc-c496eba4373b | note | Line width ¦¦ +20 mm, -5 mm
cb75ed74-01e1-545d-9f50-828e4aa44630 | note | Line height ¦¦ +2 mm, -0 mm
20ffd12e-5906-5957-a5a8-0d0c1de2dd37 | note | Extrusion breadth ¦¦ +10 mm, -0 mm
a3803ea1-ec1f-59a9-a2cc-c6b49fbb79ad | note | Extrustion spacing ¦¦ ±15 mm
63bcb6ac-c5ba-501d-969e-bbcce851071a | note | Extrustion shape ¦¦ ±25 mm at any point from rectangular shape
307a2c37-d1c8-5ca9-9849-d59404358fcb | note | (ii) Tolerances on position
1ae3e5cf-0aaa-593a-ae1d-de221038a5e6 | note | Distance between the centreline of the marking and the centreline of the setout ¦¦ <30 mm
1981965b-836c-5ff4-8d52-04d040e9a645 | note | Length of the completed lines ¦¦ -0% to +5% of the specified length
069abf9d-507d-5bd0-b940-707cee3be579 | note | Longitudinal position of individual extrusions ¦¦ ±50 mm of any previously applied profiled lining
4ec469e8-c262-55ab-b191-65997f4db9c4 | note | – – – – – – – – – –
dde3808b-563a-51c7-bc4c-657abb5168af | note | (1) Apparent line of the markings is a smooth, continuous alignment when viewed in the direction of the line.
5f6e8cd3-2d2c-58d2-b8cf-e4a337141b5c | note | (2) Maintenance of pavement markings: If the gap between the existing lines is 90 mm or less the gap shall not be reduced by the maintenance application.
8285d8de-af87-5b34-a514-08165b564011 | checkpoint-no-value | Table 721.A131 Acceptance of Retroreflectivity
f3929411-a94c-5217-aec8-0c84fc440804 | note | Testing Period (1) ¦¦ Initial Measurement: 3 - 5 weeks ¦¦ Additional Measurement: 5 - 6 months
67b79319-3ae9-5d84-a49c-57b9e053bb25 | note | Minimum level of retroreflectivity on sprayed seal surfaces ¦¦ Initial Measurement: 350 mcd/lux/m^2 ¦¦ Additional Measurement: 220 mcd/lux/m^2
5a879189-18ae-56f8-8c92-1ad8be6335a1 | note | Minimum level of retroreflectivity on asphalt and all other surfaces ¦¦ Initial Measurement: 350 mcd/lux/m^2 ¦¦ Additional Measurement: 250 mcd/lux/m^2
277c3d2d-e318-5b05-a24a-3e7eab3398bd | note | – – – – – – – – – –
5c8380eb-13c1-5132-80bc-78a1eb30da2b | note | (1) Measured after application of the second/final coat of material.
7cd6b692-e838-51ec-9156-48fec5431d49 | checkpoint-no-value | Table 721.D021 Minimum Requirements - Paint and Glass Beads
900ff560-1f0a-52d4-af77-f84de2d3e576 | note | Paint (1) ¦¦ Glass Beads (2)
2b8c4b4b-c3b9-55bb-872b-18ad5df06c1c | note | – – – – – – – – – –
9a39094b-174a-5ae1-9d03-dd05e6aea40b | note | Linemarking
116168e2-0b1a-5acf-a417-20e54e38657d | note | • New Markings (initial application only)
62e05aa8-66f7-5c32-a4dd-afb8f916affa | note | 0.38 mm dft on sprayed seals ¦¦ Type D-HR (3)
7001f526-20a9-5970-9931-e6cf48c5471c | note | 0.35 mm dft on asphalt and all other surfaces ¦¦ Type D-HR (3)
d1a5205c-2601-53a2-bd30-a15335833ac6 | note | • Re-marking (including second application on new markings
a508f538-1bed-5df0-9863-cf76bbd3919f | note | 0.38 mm dft on sprayed seals ¦¦ Type D-HR (3)
66197ba9-0487-5c46-aeeb-b2ccd695d115 | note | 0.35 mm dft on asphalt and all other surfaces ¦¦ Type D-HR (3)
76fa2aee-73b4-54f2-87d2-7b32c40c2eb9 | note | – – – – – – – – – –
1492625b-17ae-5729-8f9f-9b211a469534 | note | Roadmarking
a6754359-67a6-5102-9eca-365bcf972226 | note | • All marking
f462d967-f208-5c32-91a9-b895aecedaff | note | 0.35 mm dft on sprayed seals ¦¦ Type B-HR
967ba0dc-56df-591d-8f6d-3275e3711347 | note | 0.30 mm dft on asphalt and all other surfaces ¦¦ Type B-HR
a53f0591-1cb0-5a55-96b6-55babee9d637 | note | – – – – – – – – – –
4b488ed1-dc4a-50f4-9e7c-605cbaeae009 | note | (1) The minimum dry paint film thickness (dft) specified above shall be the end product thickness measured on a 200 mm x 100 mm sheet metal test plate without beads. Consideration shall be given to the texture of the road surface and the method of application used to achieve the requirements of this section.
b65ddede-156b-5580-b3f0-426b747dccaf | note | (2) A minimum of 400 g/m^2 shall be retained in the painted marking for all glass beads.
39d26529-af3d-5c2f-87c6-7972ccfce71d | note | (3) An alternative glass bead application rate shall be 300 g/m^2 of D-HR with a separate drop of 200 g/m^2 of B-HR provided that 75% minimum of the D-HR beads is retained at the 5 demonstrated by photographs at each test site.
6a77d232-1191-57f3-bd7e-c2445350664a | checkpoint-no-value | Table 721.E021 Minimum Requirements - Long Life and Glass Beads
75145691-1987-50ac-af2e-74cce8f31813 | note | Material ¦¦ Applied Minimum Thickness, Glass Bead and Other Requirements
7fc69ef4-e314-5af6-894d-bdfdf9841fc5 | note | – – – – – – – – – –
311c854f-5605-5e6f-b8a8-2bdb83aa8f65 | note | Thermoplastic
1a92ba90-ac64-5c0f-95a3-7103f4521831 | note | Sprayed markings ¦¦ 2.0 mm minimum thickness on logitudinal lines contaiing internmix beads and with a minimum of 400 g/m^2 of Type D-HR or Type B-HR(3) drop-on glass beads retained on the marking surface
efb65208-ff32-563e-a44e-f3c79ea08b9c | note | Extruded line markings (1) ¦¦ 2.0 mm minimum thickness on longitudinal lines containing internmix beads and a minimum of 400 g/m^2 of the Type D-HR or Type B-HR drop-on glass beads retained on the marking surface
a4c5ca31-9cc1-5f1d-ad11-1930223ed121 | note | Extruded road markings (1) ¦¦ 3.0 mm minimum thickness on intersections containing internmix beads and a minimum of 400 g/m^2 of Type D-HR or Type B-HR drop-on glass beads retained on the marking surface
47f255ed-40e7-5005-92fc-bbdcccd99c16 | note | Preformed markings ¦¦ 2.3 mm with a minimum skidding resistance value of 45 BPN (British Pendulum Number) and retroreflective properties agreed with the Superintendent
cb21368e-0d59-504a-aa6d-e759e531bf16 | note | Profiled lines (1) ¦¦ 8.0 mm minimum thickness with a minimum of 400 g/m^2 of Type D-HR or Type B-HR drop-on glass beads retained on the marking surface
2b346d6f-a460-5b2f-b771-1e11acb5c564 | note | – – – – – – – – – –
f4764081-dc50-5f23-a6af-86453ef39bdf | note | Cold-applied Plastic
e26f03f7-5172-54ce-ae6a-2fe9a445e271 | note | Sprayed line markings (2) ¦¦ 1.0 mm minimum thickness for longitudinal line markings only with a minimum of 400 g/m^2 of Type D-HR or Type B-HR glass beads retained in and on the marking surface
c31a1958-4007-5a12-a102-b0ef9433c7b3 | note | Sprayed road markings (2) ¦¦ 2.0 mm minimum thickness for all road markings containing intermix beads and a minimum of 400 g/m^2 of Type D-HR or Type B-HR drop-on glass beads retained on the marking surface
206ca49d-5bcc-586c-a579-549d11352c1a | note | Trowelled, screeded, or extruded markings (1) ¦¦ 2.0 mm minimum thickness of markings containing intermix beads and a minimum of 400 g/m^2 of Type D-HR or Type B-HR drop-on glass beads retained on the marking surface
f8e76197-7964-5015-a656-72da07be7969 | note | – – – – – – – – – –
190782ba-184a-5875-be8f-293bd8bee297 | note | Pliant Polymer Tape
bddd0336-a4bb-5693-bfad-758cedc43c5a | note | As approved by the Superintendent
bb36c791-2d21-562f-8b19-cb922315b7ec | note | – – – – – – – – – –
79dad238-6918-5041-adab-a228ae5ab15f | note | (1) The minimum thickness specified shall be the height above the upper road surface level or above the existing marking as appropriate.
38649dba-da9b-526a-ad8f-2ef72498ecd7 | note | (2) The minimum thickness specified shall be the height of the material between the glass beads on a metal test plate. All other thicknesses shall be as measured on a metal test plate including glass beads.
70c25263-1c9c-57eb-94a2-2330ba5dcd36 | note | (3) Pristine drop-on Type B glass beads (Type B-HR), as per Clause 721.A05.
47883de0-10fe-5a6b-a3dc-7d5dbc6a5920 | checklist | ITP - Stormwater and Subsurface Drainage Rev1 | itp | ITP - Stormwater and Subsurface Drainage
56f12a57-1e96-5877-8041-0f0eb46d12c8 | section | 1 - Preliminary Works
8cd47aa7-19e4-55e7-9939-09ffbf3c7b11 | checkpoint | 1.1 Check for correct documentation
aadd5836-d158-5bfa-ac7c-084f5aa4b3ef | note | FREQUENCY: Prior to commencing any activity
8fcb46d7-f32b-5c4e-adeb-2006104de526 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
a6fc99e9-ef5f-51a9-acff-d2b85543ae60 | note | – using the correct and complete set of drawings
c4149716-8439-5fa3-ba74-5a8edde0c703 | note | – all drawings are the latest revision
26f6327c-4ac4-5f1d-882d-890a98336fc1 | note | – Conflicting documents will be referenced to the hierarchy of documents listed in Section 175.03
87db04db-b991-556e-8e99-029954c9a46a | note | REFERENCE DOCUMENTS: Drawings and drawing registers, Cl 175.03
93269ebb-6b68-5f95-ab9d-309e7772e865 | note | INSPECTION/TEST METHOD: Visual inspection
c3783deb-7aae-5588-a075-268ecab0cc77 | note | RECORD OF CONFORMITY: This ITP Signed
6f2631dd-0a3e-52fe-9391-3884f3ab5370 | note | HP*
0dec4317-9595-5773-be59-2c2056495a70 | note | RESPONSIBILITY: Site Engineer
35843ea7-a277-549b-b9dc-285255603a94 | textbox | DATE:
6a9380d5-4e77-5177-a005-cf90a26e111a | checkpoint | 1.2 Implementation of all measures and controls
b01511d0-f72d-56de-931b-642623fc4893 | note | FREQUENCY: Prior to commencing any activity
86180b05-be6b-5932-893b-0d0a7861fc06 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
a3839bd5-69be-501f-b0f9-6e6a40d57b0f | note | REFERENCE DOCUMENTS: OHSMP, EMP, TMS, SWMS, WP
02e5d554-6734-5f56-af1b-d954a0e2dfa6 | note | INSPECTION/TEST METHOD: Visual Inspection
97c73170-b269-5002-a56e-6289a127432b | note | RECORD OF CONFORMITY: This ITP Signed
3fa93443-1302-56dc-a89a-a2bd3ebb8533 | note | HP*
aa94a176-f1d5-5807-9f0f-8424f1f5016b | note | RESPONSIBILITY: Site Engineer
532079d2-47c7-5efa-902d-6bc089e293d6 | textbox | DATE:
e4b6dfe1-c519-5374-9783-4e7acd3c830e | checkpoint | 1.3 Material Classification
1d2556bf-ac86-5667-b39e-1e094fc29d77 | note | FREQUENCY: Each Lot
5f66e0e0-361a-5348-8344-d3cffde033c7 | note | ACCEPTANCE CRITERIA: Pipes supplied shall be of the category and diameter shown on the drawings or specified in clause 702.12 and shall comply with the requirements of the appropriate Australian Standard in accordance with Section 175 or as follows:
5d62384a-a168-5353-948f-6d24e3c06f0e | note | ○ Category 1: Perforated plastics Class 1000;
dfe67a3f-197d-59fb-8615-26a94ded1d3d | note | ○ Precast concrete Class "2"
2f50ed21-221d-5d0a-8dff-96743ff3f59b | note | ○ Category 2: Perforated plastics Class 400
95c269a8-bb93-58cc-83f8-d88656df3a70 | note | ○ Category 3: Geocomposite drains
30da9d19-6634-5c0b-a784-ac63f762ab71 | note | ○ Granular material as per clause 702.05, Geotextile material as per clause 702.06
2da1665f-8861-5989-b384-4f51075e0274 | note | REFERENCE DOCUMENTS: Cl 702.04, Cl 702.05, Cl 702.06
84a815f6-a7e9-5da2-a586-83eef950dd1b | note | INSPECTION/TEST METHOD: Verify
18d965df-697d-5d5c-88df-267280666754 | note | RECORD OF CONFORMITY: Order acceptance certificate, This ITP signed off
feb47c0f-7080-5854-8348-e50ee4517444 | note | IP
9eb3b88f-cd16-540b-b557-dc7d367a62e3 | note | RESPONSIBILITY: Site Engineer
2f0f92f0-7a74-5b18-a527-70f24bae2738 | textbox | DATE:
2bbcb3e5-d8cd-5b7e-b658-10bcbfe29857 | section | 2 - Procurement of Materials
0965eb9f-bd10-5408-bb98-4ab82d9cdf22 | checkpoint | 2.1 Precast Reinforced Concrete Pipe Supply
4ac6a268-ee76-5253-a726-c2e791e3500b | note | FREQUENCY: Prior to works commencing
a267e2ff-240f-55e7-8b06-fc893a8a111b | note | ACCEPTANCE CRITERIA: Pipe class and size and endwall type as per drawings and Cl 701.05
08f7bb94-9e7d-52a5-b105-51916d213691 | note | REFERENCE DOCUMENTS: Cl 701.05, Drawings
80d0c9e7-624a-533f-a843-1f3ac7ea8992 | note | INSPECTION/TEST METHOD: Verify
eabff487-abad-58ce-91ee-35848b162a2a | note | RECORD OF CONFORMITY: This ITP Signed, Order acceptance certificate
74117473-b1ef-582f-ad2a-2ff35afa9b88 | note | HP*
aad970e7-234a-52be-81c1-6e9bc001ec0d | note | RESPONSIBILITY: Site Engineer
a23ffb04-f55f-57a1-bf2c-5ea733bf349c | textbox | DATE:
10d3dc59-608b-5f8c-a4c7-393d2d0bacc2 | checkpoint | 2.2 Precast Reinforced Concrete Inlet and Outlet Structures supply
be1aa30d-03c1-55ef-b80d-4ec7cf467f72 | note | FREQUENCY: Prior to works commencing
6a40ca8c-f146-5429-8d4b-497bbd407b5b | note | ACCEPTANCE CRITERIA: The supply of precast inlet and outlet structures shall conform with D.S.G standard drawings
ec4cb1c1-f04f-5bf6-a893-a911a5c22824 | note | ○ Concrete supply shall conform with Section 610 and reinforcement supply shall comply with Section 611.
1bb347fa-041f-5038-b0c9-10cf7f4816f2 | note | REFERENCE DOCUMENTS: 610, 611, standard drawings
98e0d4cb-1d87-5abe-b961-19d6d3b20724 | note | INSPECTION/TEST METHOD: Verify
ed816072-8dd7-5bc5-9714-c97e6571f16c | note | RECORD OF CONFORMITY: This ITP Signed, Recievable Inspection Checklist
1f9221f2-f851-536b-9630-1c6b5e5e4d41 | note | HP*
8e7712cb-7999-523d-9f7b-84fe1dca8d3a | note | RESPONSIBILITY: Site Engineer
8243c642-5c26-5b0b-ae43-90ede2d4244d | textbox | DATE:
b2f73a87-526a-5417-b69b-15a39f076f27 | checkpoint | 2.3 Bedding and Backfill Material Specification
b477d0b8-9818-51fa-b2e0-ef4b4189d8b5 | note | FREQUENCY: Grading 1 test per 1,000t
fd6f98ad-dda6-5ee0-87aa-01da820f1742 | note | ACCEPTANCE CRITERIA: Bedding and Backfill materials free from perishable matter and lumps and shall conform with the requirements of Table 701.091 and Table 701.092
d2f3411b-1072-5ef4-841d-bb98de6f3125 | note | ○ Ordinary backfill shall be free from perishable matter and shall conform with the requirements of Table 701.091
437a99f2-1ae2-5c0d-85f6-04ab661af14a | note | REFERENCE DOCUMENTS: Cl 701.09(d), Table 701.091, Table 701.092
8a8bfcee-17eb-5817-ae40-bef6d6396e4e | note | INSPECTION/TEST METHOD: Verify
d80ec588-b722-5535-8ca8-85b5998c5007 | note | RECORD OF CONFORMITY: This ITP Signed, Quarry test report
a440aead-9c56-5c01-a90f-dd4f02a030d3 | note | TP
0f4c934e-67fb-5de2-beef-9f4af49b7253 | note | RESPONSIBILITY: Site Engineer
e392f043-fe6b-54bb-a6f9-0726bccde40a | textbox | DATE:
91a8bcf0-cacc-5ef8-8d7f-78886084dc6c | checkpoint | 2.4 Setout of Works
b7910742-9d53-5d57-881d-94c8f8e99c3f | note | FREQUENCY: Prior to works commencing
2892dd7c-d078-538b-a1bb-80673ee5bbf3 | note | ACCEPTANCE CRITERIA: Hold Point
57949dca-bb49-5cb8-9a2f-c392a2866d2c | note | Prior to commencement of excavation for the culverts the contractor shall confirm the position of all culverts with the Superintendent
ae092f99-2ffd-52d5-bddd-c6ff9971d941 | note | REFERENCE DOCUMENTS: Cl 701.10
8b575dc3-6035-5517-adc1-2483a2c0a72a | note | INSPECTION/TEST METHOD: Visual inspection
c52ab3d2-f1eb-59e2-9bea-8d6bb0c351ca | note | RECORD OF CONFORMITY: Survey records, pegs on ground & this ITP Signed
eb109ab8-eeed-53c2-b10d-e733e7431b1f | note | HP
b545e2d9-5493-583d-9978-1ffc50f5101c | note | RESPONSIBILITY: Site Engineer / QAV
d817ad45-c44f-52e6-8f33-58322a1f20bb | textbox | DATE:
f99e3efa-a1a3-5c49-bdbe-8704561405a8 | signoff | AUTHORITY HOLDPOINT
2b285ef2-1d49-5244-b091-20366ccf7a24 | section | 3 - Installation of Underground Stormwater Drainage
f9093f9b-448f-5356-bd63-b5f29ef327fc | checkpoint | 3.1 Excavation Permit
34529269-c022-523e-afad-1f99ceb334ea | note | FREQUENCY: Each lot
e352bfb5-9669-5e8d-9ac4-3c2fc4fa4f8d | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
635b66bf-7e2f-5864-84d8-dc8a8590345a | note | ○ Plant and equipment shall be appropriate for the task.
887fe3e8-f2a4-59d3-8d43-5357d8b26d58 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
027ce59e-cbf6-5683-8ba9-d3293f374a1c | note | REFERENCE DOCUMENTS: Excavation permit
4f3623c3-effa-5c22-99c3-20312080f266 | note | INSPECTION/TEST METHOD: Verify
e3593d09-24d0-5f71-a31d-a433a86ecd09 | note | RECORD OF CONFORMITY: This ITP Signed
9b2f7c0b-c487-5872-bda0-bb836faba327 | note | HP*
65e4560c-5a78-54b2-8373-416ccf8d6446 | note | RESPONSIBILITY: Site Engineer
c9229162-6aaa-51d8-9309-04a2de356e15 | textbox | DATE:
26ec6797-81d5-5d3b-bba2-a5968fd13c1d | checkpoint | 3.2 Excavation for trench
c7dffadd-e73b-5324-a7e4-b129be4374c2 | note | FREQUENCY: Each Lot
7516aeec-85ac-5e38-b6aa-ebf1eb463584 | note | ACCEPTANCE CRITERIA: Excavation for the installation of pipes shall allow for the clearance from the outside of the pipe to the wall of the trench between 300mm and 600mm;
39bd87e3-6cfd-5cca-97c8-34c3c5892fa9 | note | ○ The base of the trench shall be inspected to verify compliance with the requirements in this clause prior to placing bedding in comleted exacavations.The Superintendent shall be notified at least 24 hours prior to the inspection.
c5232082-57a8-5142-880a-1ec56547d112 | note | REFERENCE DOCUMENTS: Cl 701.15 Table 701.151, Cl 702.08
44ea78ad-485d-5181-b4b1-a75a03690a70 | note | INSPECTION/TEST METHOD: Visual Inspection
f27f5d63-ae5f-5970-b685-a9e8f1582151 | note | RECORD OF CONFORMITY: This ITP Signed
9616255a-360f-5f75-905e-7ae4aeb5eaaf | note | HP
7304bf7c-6acd-55e5-9de5-dbc55f9af1ab | note | RESPONSIBILITY: Site Engineer/ Superintendent
633267a1-81db-56ab-8983-894fa583adb9 | textbox | DATE:
b67ffe91-49fc-59d9-a5ca-16a9e52365fb | signoff | AUTHORITY HOLDPOINT
dae340d9-776c-5fbe-880e-777d0f3db266 | checkpoint | 3.3 Trench Base Preparation / Bedding
9880606a-77f3-5821-97a0-1fca354ef20c | note | FREQUENCY: Each Lot
1442e9a3-f332-5d71-8e55-fecb67c975f9 | note | ACCEPTANCE CRITERIA: Bedding material placed in full width of trench and compacted to at least 100mm thick, or; where the culvert is to be placed without trenching, to a width of 0.8m greater than the overall width of the culvert.
0beecb1f-88e9-5bb0-8d90-21ba181ae008 | note | ○ Bedding of granular filter material of thickness between 25 mm and 50mm shall be placed across bottom of trench and shall be tamped and screeded or graded to level.
0991f5c5-1078-5ce8-bf49-b862169c60a9 | note | REFERENCE DOCUMENTS: Cl 701.16, Cl 702.09 (c)
495fd12e-0b11-59e0-abcf-5677bf0d9282 | note | INSPECTION/TEST METHOD: Visual inspection / Measure
e22288bb-fbf7-5b1f-a7c3-4e8870a6fd45 | note | RECORD OF CONFORMITY: This ITP Signed
5d959986-9f9a-5829-ba4f-acfe35c267e2 | note | IP
6dbe343e-9fd9-5088-a1ec-d955017054c2 | note | RESPONSIBILITY: Site Engineer
8cf8d4c0-ca09-504e-a541-2c5347af018b | textbox | DATE:
b8a923d5-8270-5bf6-95f1-bca4c6eb2562 | checkpoint | 3.4 Laying/ Placing of pipes
a042a96b-cd1d-5a6e-a56e-3596aa6e8db4 | note | FREQUENCY: Each Lot
5aad2370-206a-5535-86dc-2636039fb200 | note | ACCEPTANCE CRITERIA: Laying of pipes to commence from the downstream end. Pipes to be laid with rebate or socket end facing upstream and be fully entered. Departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250.
d29d46b6-122c-5d10-a01e-667d48e11830 | note | ○ Pipes shall be placed centrally in the trench on the prepared bedding and held firmly in place
ce59e005-dbac-59ec-a70a-db99970d4d91 | note | REFERENCE DOCUMENTS: Cl 701.10d Cl 701.17, Cl 702.09 (d)
bf5e251f-625e-5930-83d1-5b33fe7d8be2 | note | INSPECTION/TEST METHOD: Visual Inspection
8ba87c2f-e150-51a8-97a6-7814b718401d | note | RECORD OF CONFORMITY: This ITP Signed
99b277b9-2d4f-53d2-a668-6904f495f7dd | note | IP
15bfd186-c9cb-59fd-a802-b8cda5e4960b | note | RESPONSIBILITY: Site Engineer
c23d71a0-1cef-555a-8552-12bfbbd09601 | textbox | DATE:
5471bc14-7bd6-5b6e-999f-63051125172d | checkpoint | 3.5 Jointing
6ddf04a6-f732-5ff4-bc14-98d97199acb5 | note | FREQUENCY: Each Lot
c25e0b27-0e2d-5127-a546-d2747d6e8af9 | note | ACCEPTANCE CRITERIA: Rubber ring joint pipes shall be jointed with rubber rings. Rubber rings shall be kept undisturbed, clean, and free from dirt and other foreign materials and shall be stored undercover if pipes are not to be installed immediately.
6322edd8-e2ab-566d-a413-ad1460fa8b94 | note | REFERENCE DOCUMENTS: Cl 701.18
c271a322-87c9-5e49-a9cf-4689e45c0b9c | note | INSPECTION/TEST METHOD: Visual Inspection
18503638-9bda-5a2d-95f6-ca0a05aad74f | note | RECORD OF CONFORMITY: This ITP Signed
6f2ffd2f-4847-58e9-b9f2-815fcb341893 | note | IP
6b0a46eb-f65b-53ee-86b5-1cdb27f945b5 | note | RESPONSIBILITY: Site Engineer
84dc9af5-fead-5222-aa9f-14e205c38875 | textbox | DATE:
ef53ccbc-cc18-57dc-b7a4-cd155f2c4129 | checkpoint | 3.6 Tolerance
c77e3e97-358f-5229-83fe-1e7e799c779d | note | FREQUENCY: Each Lot
c51d85a4-2365-5448-8a93-2a0493f97ec8 | note | ACCEPTANCE CRITERIA: Location of each culvert run verified by survey prior to backfilling and recorded in as-constructed drawings.
02eb9dc7-a484-5a90-afe7-301fbc198a81 | note | ○ Tolerance:
3c3c8c62-b9f0-58cb-ba3c-de47ebdf8b34 | note | • Invert level of pipes at pits ± 50mm
df55a3bc-c739-5803-863f-f46519bb755d | note | • Departure from design grade of pipe runs ± 10mm in 10m provided min grade > 1:250
f26900fd-8f2c-57d9-b0f6-5a46d1c89fac | note | REFERENCE DOCUMENTS: Cl '701.10
b1783887-0209-594d-bd81-e3118ac62a62 | note | INSPECTION/TEST METHOD: Verify
35efa206-bcec-5980-b92c-8bd607e79768 | note | RECORD OF CONFORMITY: This ITP Signed
effa7108-54bc-5d83-a3e7-456f39092f26 | note | SCP
39d7bf61-e2f4-50b2-b62e-4e99d48794d3 | note | RESPONSIBILITY: Surveyor, Site Engineer
bc309f55-6d47-56c8-b9ae-d917c18f415c | textbox | DATE:
80bc4394-0463-5fa4-bc8f-18ea74386156 | section | 4 - Backfilling of Stormwater
08f90a26-8eef-5591-a811-36dcb298fc60 | checkpoint | 4.1 Filling
3890b741-5365-5a3b-939a-e49d3f7ebb96 | note | FREQUENCY: Each Lot
8ac3efd3-5a73-5cac-9c60-5adacca8fed4 | note | ACCEPTANCE CRITERIA: (i) Culvert Under Area to be Paved
b88366c8-553f-531d-bb9c-4d1132a80050 | note | • The trench shall be backfilled to design subgrade level with selected material.
7405a271-ba83-5f85-a5d2-a1a0d6d3551f | note | (ii) Culvert Under Area not to be Paved
a06cbd9b-df65-572e-8f95-cc5eb48affad | note | • The trench shall be backfilled with selected backfill material to a level 0.3 m above the top of the culvert and with ordinary backfill material above that level.
71b4ee89-0e5a-53ea-a995-9ce71903b083 | note | REFERENCE DOCUMENTS: Cl 701.19
e53fbcbd-86b4-599f-a1a3-69e525b142f1 | note | INSPECTION/TEST METHOD: Visual Inspection
135bc85b-0492-5740-87a6-cc10826731d9 | note | RECORD OF CONFORMITY: This ITP Signed
3a27a065-394c-50f2-a397-a3e528d46010 | note | IP
3ecda391-cd7f-5342-be44-33558c8b145b | note | RESPONSIBILITY: Site Engineer
119be229-b7ee-5c05-91d2-205eec0caae2 | textbox | DATE:
506597d7-552a-5bb0-a50b-d50ecde87a03 | checkpoint | 4.2 Placement of granular backfill
34b953b8-bbb7-5024-bc19-e1044f367bd3 | note | FREQUENCY: Prior to backfilling
4c44f580-9fed-5771-ae4d-fd2acf491d1d | note | ACCEPTANCE CRITERIA: Hold Point
00c0629d-2d74-523c-a165-ea469ce63357 | note | ○ Filter material shall be moistened and compacted with minimal disturbance to pipes. The method of compaction shall be in accordance with the submitted quality procedures
ef79967f-65e3-5799-b611-c907b55c8732 | note | REFERENCE DOCUMENTS: Cl 702.09 (g)
0c3abf5e-3584-5d2b-9b82-fdf0d4f5849f | note | INSPECTION/TEST METHOD: Verify
2d7fc420-fb4f-5c18-a000-65c86529fac5 | note | RECORD OF CONFORMITY: This ITP signed
f46ec9db-7b30-5c23-8174-081109d51dd2 | note | HP
7aa242e8-e796-5a6f-9d89-aab69738355f | note | RESPONSIBILITY: Site Engineer/ Superintendent
28fd5d46-b8a9-57dd-975b-97b6d38afd1c | textbox | DATE:
2577f7c7-ad32-54fb-adcb-7ea152b2f234 | signoff | AUTHORITY HOLDPOINT
0f75935d-77a6-5567-aa86-a96dd27fc8d1 | checkpoint | 4.3 Placement of no fines backfill
4a6e9ac5-c127-5d95-ba38-db9099455b11 | note | FREQUENCY: Each Lot
59dd22f6-a34f-5a65-8662-2d2c91a36b3a | note | ACCEPTANCE CRITERIA: Hold Point
85674430-9df1-58b8-8d04-4c74664c8243 | note | ○ Where no fines concrete is used as filter material the Contractor shall submit quality procedures for review by the Superintendent which detail the method of placing the no-fines concrete to prevent segregation and the formation of a slurry layer at the surface of the concrete which may prevent the passage of water into the filter material.
58640d4e-2ed3-5dd5-b2ab-62bb9b0f11bc | note | REFERENCE DOCUMENTS: Cl 702.09 (g)
bb8947f3-4b20-5418-9cb9-f31cdc516072 | note | INSPECTION/TEST METHOD: Verify
b58aae4f-4c8d-577a-9b55-ccd3b32acfc5 | note | RECORD OF CONFORMITY: This ITP signed
33a9d8f2-c39b-52b3-95bd-1947f6eb0c9f | note | HP
c1163324-5be6-5128-bbc8-8b2d7225428b | note | RESPONSIBILITY: Site Engineer/ QAV
3b65cc4e-cad5-57e5-ab21-4986a1313ab7 | textbox | DATE:
f9dcc213-8b8b-5deb-856b-d4acb9131b19 | signoff | AUTHORITY HOLDPOINT
283b0457-2cde-5403-be3c-072be722835f | checkpoint | 4.4 Testing and Acceptance of Fill Materials
534f0585-e076-5da4-aa35-73c7458f5440 | note | FREQUENCY: 3 Tests per Lot tested with 20% of all Lots tested
d59ac54a-5dbd-56e1-b399-80c95b8a9dd7 | note | ACCEPTANCE CRITERIA: Bedding and backfill materials shall be placed and compacted in layers not exceeding 150mm loose thickness and shall be assessed for compaction and moisture content.
87dbff43-6a0c-54c0-abc2-11f2411d889f | note | Bedding shall be compacted to refusal using hand held mechanical equipment.
ccd9b70b-4b37-5ada-af02-0c32c662eedb | note | Backfill material with nominal size < 40mm after compaction shall be compacted to a mean density ratio of not less than 97% CDR.
87910ed1-b7c9-515a-a42c-fdb52f70db38 | note | Backfill material with a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
aacb47e8-f735-50bb-8b62-0eaa16f8e6bc | note | REFERENCE DOCUMENTS: Cl '701.20
791b9cd7-f360-5daf-b06a-16be110dbc4c | note | INSPECTION/TEST METHOD: Verify
cd0398ed-9431-508a-afa6-f914f7da0100 | note | RECORD OF CONFORMITY: Compaction Test Result OR This ITP Signed
97e6823f-e940-5101-8e0b-5b72195f647d | note | TP
79066a1a-e58d-5a6c-9850-c9d17d456368 | note | RESPONSIBILITY: Site Engineer
73fce6bc-2f44-5a9d-963b-5022e03343b1 | textbox | DATE:
57a4b66f-fae7-5f81-9328-f0a084bbf82e | checkpoint | 4.5 Access Points and Flushouts
2a36a1fd-7b71-530e-8b90-f79c20689474 | note | FREQUENCY: Each Lot
dff259de-62d4-57f3-bb32-7f5f318694ec | note | ACCEPTANCE CRITERIA: Access point installed at the beginning and end of the drainage run and inspection openings at intervals between 100m and 150m. Flushout risers have same diameter as pipe.
0de465ba-5801-58b6-9fe3-eb38fa289160 | note | REFERENCE DOCUMENTS: Cl 702.10
4a514d8a-9b6c-5d10-9e70-3ed91519a689 | note | INSPECTION/TEST METHOD: Verify
e6e5eddf-903e-5c3e-970d-c9cc8ea637a8 | note | RECORD OF CONFORMITY: This ITP signed
f61f732c-86e0-58f2-855e-3314d90f201a | note | IP
f5ca4eec-272c-5764-97a3-11a9780c8beb | note | RESPONSIBILITY: Site Engineer
90c0e290-ed7e-5f4e-bbc0-ec6319b91dea | textbox | DATE:
fff793e2-679d-5145-84e8-dcc3be36f2aa | checkpoint | 4.6 Flushing Test
d0ae7c8b-d2e1-5291-b356-cf83cf15e232 | note | FREQUENCY: At completion of stage
ba9ecf07-92fb-5725-9f1b-46dae25b30d3 | note | ACCEPTANCE CRITERIA: Flushing test undertaken on each subsurface drainage line after completion of the drains, flushers and risers, and after completion of barriers and road furniture. The test should be witnessed by a representative nomitated by the superintendent. Record of flushing tests must be kept.
a5d80a5d-a9ad-5a55-b0ab-eab210b4f31d | note | REFERENCE DOCUMENTS: Cl 702.09(h)
cb2e061e-7d0c-575f-a2ef-7b5e3a38e7a6 | note | INSPECTION/TEST METHOD: Site inspection
6ed9b76d-0211-53e5-bb9a-9afb0998d515 | note | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
6da7d2c6-89b5-50c6-8aee-dd4579207a8f | note | TP
c69b5bc4-8360-54f1-bb8f-c04115603f2e | note | RESPONSIBILITY: Site Engineer / QAV
e7f8d999-9de3-5134-8358-2085db1a2fe7 | textbox | DATE:
ac4d2c97-942b-51b4-8f2b-6a8ff638dda4 | checkpoint | 4.7 Installation of Inlet or Outlet Structure
f5660809-663a-5d66-a481-78eb944c4b70 | note | FREQUENCY: Each Lot
0adbe5c5-862f-55af-8ef6-8d35bb1064b1 | note | ACCEPTANCE CRITERIA: Inlet and outlet structures shall be installed to a tolerance of +-20mm where matching kerbs or barriers or +-100mm in all other areas.
74360b53-d8f5-589a-8774-498e6fc08613 | note | REFERENCE DOCUMENTS: Cl '701.10 Cl 701.25
45832d25-c8fa-584f-9e04-06ee3e374f77 | note | INSPECTION/TEST METHOD: Verify
668037f1-5d7e-57a9-9ff7-f474dfeffcd9 | note | RECORD OF CONFORMITY: This ITP Signed
e0724462-3979-5ed2-82d9-0fdfc4240b5a | note | IP
52b42938-d189-5659-9e7a-84831ea1be56 | note | RESPONSIBILITY: Site Engineer
ccb33719-3d21-5fe7-b360-ed0cae5bff14 | textbox | DATE:
a5881f93-1da6-5d79-8191-cdf6a37239b8 | checkpoint | 4.8 Culvert Coverage
8fbf0aa5-2c9b-5b6e-a55a-96adc6c77c5d | note | FREQUENCY: Each Lot
6498b58a-b13b-50bd-a449-6cd638679832 | note | ACCEPTANCE CRITERIA: Until the minimum compacted thickness of cover in Table 701.141 for axle or track loading has been provided, construction traffic shall not be permitted to cross the culvert.
9f6a296a-90bf-565b-adb1-09a8708e6132 | note | REFERENCE DOCUMENTS: Cl 701.14 Table 701.141
658ce9b7-c82b-549c-abff-cfd2720b7b4e | note | INSPECTION/TEST METHOD: Visual inspection
9b251dc9-62cc-5ccf-88de-19d98fb40240 | note | RECORD OF CONFORMITY: This ITP Signed
dbfb8fe2-af3d-5d5f-83e4-cd60a5ce54e0 | note | IP
604e65e1-4d67-58a6-9527-097fbb8832c9 | note | RESPONSIBILITY: Site Engineer
d22f9fab-71af-5d24-8c86-d3b29a1a66e0 | textbox | DATE:
4029361e-80a4-5f47-b848-18b310d6d059 | section | 5 - Subsurface / Subsoil Drainage
f6e268cd-d9f1-54d7-9431-b94d940803c6 | checkpoint | 5.1 Excavation Permit
a76e405f-2971-52ef-ad98-e175c07832e7 | note | FREQUENCY: Each lot
3dc00568-727e-5214-a4bc-1d15fcc964a7 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
5a224d94-5865-5a17-aae9-d3f326431563 | note | ○ Plant and equipment shall be appropriate for the task.
4062d0c5-33b5-5c63-a5a5-737d20b65edc | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
b1627b48-ef13-512e-834e-185aedba5a90 | note | REFERENCE DOCUMENTS: Excavation permit
f015faae-6ad9-5bfc-afc4-b9a0a389a7b3 | note | INSPECTION/TEST METHOD: Verify
45c24e12-ec23-52fd-8de5-890fbd57d5fe | note | RECORD OF CONFORMITY: This ITP Signed Off
bf04d91b-4572-5e0f-b91e-e08a8dac4be4 | note | HP*
d5e52ec8-9efc-5686-9a22-031750b3735c | note | RESPONSIBILITY: Site Engineer
c6cbf7be-f26c-5d70-a9b3-b444f5d5e841 | textbox | DATE:
15fe5090-9ed4-5396-9d7f-4443b2371617 | checkpoint | 5.2 Excavation of Trench
e2b6124a-aff8-531c-bedf-06ba22853c24 | note | FREQUENCY: Each Lot
1e52aaad-b6f2-5b6b-bf11-d41f34f5a72b | note | ACCEPTANCE CRITERIA: Hold Point
374f3256-3672-5ed3-9b67-77acc1aa52bc | note | ○ Bottom of trench shall be compacted and at a depth no more than 50mm below the specified pipe invert. Grade of the base of the trench shall not allow ponding of water Any loose material shall be removed. To be inspected by Superintendent
494acd1c-e56f-5fa3-839a-217ba43146b6 | note | REFERENCE DOCUMENTS: 702.08
7c5fbf06-63f0-5b9c-a02b-9671020c37c7 | note | INSPECTION/TEST METHOD: Visual Inspection
e6cc975d-ed94-5c32-ad0b-279ecdd4ac63 | note | RECORD OF CONFORMITY: This ITP signed off
0c6b94a8-28c3-5f3e-9ef4-1b1c2dd81e9d | note | HP
7f02702a-dbee-5b17-822d-21d25de2bbb1 | note | RESPONSIBILITY: Site Engineer/ Superintendent
e225085e-28eb-5a9a-b0c1-0a4b0e3898e5 | textbox | DATE:
8fe7a47a-56b4-5a08-a89a-ce837e8a9947 | signoff | AUTHORITY HOLDPOINT
579268d5-da9a-54d2-b23f-52520dcc116a | checkpoint | 5.3 Placement of bedding
a635d6d5-c529-5dc1-8949-56872aa46672 | note | FREQUENCY: Each Lot
908b63f4-c7c6-56e6-847f-3c55525503e6 | note | ACCEPTANCE CRITERIA: Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level
37890a34-0be9-5f08-884d-956edfd5a342 | note | REFERENCE DOCUMENTS: 702.09 (c)
c2e4a185-fef1-5d49-856c-cace955eb335 | note | INSPECTION/TEST METHOD: Visual Inspection
a429b93f-a875-5fdf-9908-cdbb1bb2bae6 | note | RECORD OF CONFORMITY: This ITP signed off
12ede0aa-c258-53c2-89e3-61480812772d | note | IP
aaee63cf-aac9-56a1-8f94-9f5aacc6ebdd | note | RESPONSIBILITY: Site Engineer
24525f49-c858-5fe9-933a-b1ed3dbb3d1b | textbox | DATE:
e869f709-ff71-555a-8087-436dde5703eb | checkpoint | 5.4 Placing pipes and geofabric (if required)
f35f4763-a3da-549d-bf82-6999ac2e46e8 | note | FREQUENCY: Each Lot
eb35dc37-3c7b-5f3b-ace4-e25868e538d8 | note | ACCEPTANCE CRITERIA: Pipes placed centrally in trench and held firmly in place positioned with openings at the lower half of the pipe.
0f1b60bb-686b-5f8c-8cfc-711ef0951947 | note | ○ If geofabric required (subsurface drains installed in expansive materials), minimum width of geotextile used for wrapping is 450 mm
1b9f16d4-40a2-55f7-adcf-296b7104355a | note | REFERENCE DOCUMENTS: 702.09
5d1a26c0-0ddb-59d1-8257-d74a2c09932b | note | INSPECTION/TEST METHOD: Visual Inspection
daaf009f-4379-56dc-8b4e-b37961edb69a | note | RECORD OF CONFORMITY: This ITP signed off
2cbcab84-a353-5f7f-9462-ef593e36acbb | note | IP
1b2e79eb-fd0f-5d68-a25a-4f40aeacfa12 | note | RESPONSIBILITY: Site Engineer
31e84a15-8ae4-568f-b787-2778ef750f6d | textbox | DATE:
1469ccf9-509c-5b5f-86f2-0e77ed382ad2 | checkpoint | 5.5 Placement of granular backfill
ff52a88c-8a44-513a-a384-5b895ed518f4 | note | FREQUENCY: Prior to backfilling
c3ef01e2-dcb1-5f44-bb19-2a65e7f81cda | note | ACCEPTANCE CRITERIA: Hold Point
50c35ac2-7469-59b1-8b24-0bd8621ef97b | note | ○ Filter material shall be moistened and compacted with minimal disturbance to pipes. The method of compaction shall be in accordance with the procedures and reviewed by the Superintendent.
b3fe7ccc-fd85-51eb-a86c-0f12b218d8de | note | REFERENCE DOCUMENTS: 702.09
b5638be9-2a0a-5c32-a80f-eafdb4bc4040 | note | INSPECTION/TEST METHOD: Visual Inspection
506f43b7-8253-577c-9d94-594cdf6bf4d2 | note | RECORD OF CONFORMITY: This ITP signed off
9a0f9a9e-deac-5daa-9af7-b868bb6480e8 | note | HP
076d11af-5085-53b8-89cf-11695856ce88 | note | RESPONSIBILITY: Site Engineer/ Superintendent
3ff8162e-5286-5e5f-a3b7-d8e37ef9c6cc | textbox | DATE:
ca09406b-8408-5800-bb9d-813003c331b0 | signoff | AUTHORITY HOLDPOINT
636cb2dd-a125-5797-a3e4-14a5d25b2c8d | checkpoint | 5.6 Placement of backfill
342af6d2-9b61-5881-ab0b-97a2c5659767 | note | FREQUENCY: Each Lot
988ad521-69be-54f8-9c54-12c767486c17 | note | ACCEPTANCE CRITERIA: Granular filter material placed and compacted compacted in layers not exceeding 300mm with minimal disturbance to pipes. Concrete is to be placed and compacted within one hour of mixing
c3217405-96f3-5ecd-bbc8-2b1815ebb074 | note | REFERENCE DOCUMENTS: 702.09 (g)
659e9666-1daf-5d62-a9da-d34bb1d0805b | note | INSPECTION/TEST METHOD: Visual inspection
aa2e0ebc-075f-58db-96fa-df7d213a2c6d | note | RECORD OF CONFORMITY: This ITP signed off
1e47e456-b41e-56db-b8ad-6c8a43c63cce | note | IP
d6a24766-1118-51d7-941c-79e5695ee659 | note | RESPONSIBILITY: Site Engineer
faf239ad-5f6e-5dc6-95fc-7ead3802a890 | textbox | DATE:
25135ad9-cab3-5ec5-ba03-4a7981185b4e | checkpoint | 5.7 Install Pits and Flushouts
fb3ab97a-a7a6-500b-b28b-45e9078ab7f0 | note | FREQUENCY: Each Lot
dec72da7-1843-53a1-9f38-815de23bb303 | note | ACCEPTANCE CRITERIA: Installed in accordance with drawings and Cl 702.10
db37a166-aa48-54b5-bfab-e41554905b71 | note | REFERENCE DOCUMENTS: 702.1
949b6cbb-28f3-5106-91d0-58534982cd0d | note | INSPECTION/TEST METHOD: Verify
0f9053b1-2c3e-56f8-930b-4060d55390cd | note | RECORD OF CONFORMITY: This ITP signed off
162711a2-51bb-57cb-b78f-df0a7f75be39 | note | IP
45038713-cedd-5c0d-b350-8048364b0ac9 | note | RESPONSIBILITY: Site Engineer
9d36dbcd-2856-5c3e-bafa-546510e89112 | textbox | DATE:
c0d55ac4-acaf-5cc7-8b04-c21806a28142 | checkpoint | 5.8 Flushing Test
4a3dfcd3-05d2-5902-9446-a66248aa1953 | note | FREQUENCY: At completion of stage
dfcaa7ec-c635-55df-9e09-91317ff697ba | note | ACCEPTANCE CRITERIA: Flushing test shall be witnessed by a representative nominated by the superintendent and shall confirm that the drainage line is free of obstruction. To be complete after installation of kerb and channel, barriers and road furniture.
9e6ffcb9-6719-5182-b33e-7e9d4b43ca03 | note | REFERENCE DOCUMENTS: C702.09(h)
984ab8b6-c384-5de8-9713-b13008cc9b69 | note | INSPECTION/TEST METHOD: Site inspection
d8794b60-9c99-5be3-b350-69ec34dee80c | note | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
ce2b39a0-3aeb-57bf-8559-60df2ad8cf02 | note | WP
ef6cfc1c-430a-58bc-b0c5-e3d430e6436f | note | RESPONSIBILITY: Site Engineer
fa36ae5b-5cb4-512c-abaf-7f4fdb166277 | textbox | DATE:
23386ec2-07aa-5425-ad85-e2a0f40cccf9 | section | 6 - Finishing and Commissioning
88c295c2-ca6a-5764-a519-073ec3584dc4 | checkpoint | 6.1 Finishing and Rendering Pipes
9b0ddfb2-9540-519f-9619-e21da9c091b6 | note | FREQUENCY: Each Lot
5ff04f46-43be-5901-bb6d-1dc93ad93384 | note | ACCEPTANCE CRITERIA: All stormwater inlet and outlet connections shall be cut trimmed neat and finished with cementitious mortar.
ca877189-3ec3-56c9-8e7c-3d3ede927051 | note | REFERENCE DOCUMENTS: Work Procedure
e3a62af2-9125-5eea-9bfb-ae69df8be10a | note | INSPECTION/TEST METHOD: Verify
829432fe-e709-5815-baed-d7748d25af2b | note | RECORD OF CONFORMITY: This ITP Signed
6547edb8-e856-5303-95e7-bb2db2806165 | note | IP
8c66baaa-e326-54fd-86cb-cf63f186867a | note | RESPONSIBILITY: Site Engineer
e9aa94f7-3f37-54c8-9fcf-4ed54e020d83 | textbox | DATE:
296d5e63-2b3e-5e66-ab0b-95497a742dcb | checkpoint | 6.2 Inspection of subsurface drainage lines
d618a1dc-d716-5a93-8a83-e1c15113ea5a | note | FREQUENCY: At completion of stage
c37be953-321d-545c-864a-c09bd8240b09 | note | ACCEPTANCE CRITERIA: Hold Point
38f46a94-2987-5ad2-8b49-ac3b2c04f3ea | note | ○ All subsurface drainage lines constructed shall be inspected, after completion of the flushing test and prior to placement of asphalt, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
6b9380ee-d7b7-51b7-b52f-cb70da1cc708 | note | REFERENCE DOCUMENTS: Cl 702.09(i)
05124b2f-3541-55e3-bee8-b688af3148b7 | note | INSPECTION/TEST METHOD: Site inspection
8f38f31f-d256-5eda-88ba-9a032bc4dbd2 | note | RECORD OF CONFORMITY: This ITP signed
e92660e3-9589-5084-95a3-8a9448787e16 | note | HP
a59a298e-863d-5b6d-adb6-7d423aa56655 | note | RESPONSIBILITY: Site Engineer / QAV
6f5098ad-5e60-5a01-985e-e3c0e622e2af | textbox | DATE:
221f656f-35d4-584a-a25b-0417223c7662 | signoff | AUTHORITY HOLDPOINT
f83802d7-bec1-564b-91ad-7e4d8f68de53 | checkpoint | 6.3 Repair of Damaged Pipes
1aec2329-7098-59a8-bcf8-6756a25de264 | note | FREQUENCY: Each Lot
7f3e92f2-908a-5732-8016-99c2b29e11ee | note | ACCEPTANCE CRITERIA: Damaged pipes shall be repaired in accordance with 701.31 of the Specification, no repairs shall be undertaken without the Superintendent's approval of the repair materials and procedures.
3d20d069-8c4b-58fe-bd72-526af706af81 | note | REFERENCE DOCUMENTS: Cl 701.31
a10ce4a1-1ccc-581e-8e94-9878414fe212 | note | INSPECTION/TEST METHOD: Verify
748804ed-c5ff-5625-bca0-d8d8fc9ba34a | note | RECORD OF CONFORMITY: This ITP Signed
e3c79777-2fe5-5d94-94e7-21513a6e98b5 | note | HP
f6322522-013a-5ff6-81f4-3ccfd0959994 | note | RESPONSIBILITY: Site Engineer / Superintendent
5e992c51-58cf-5bff-aa77-9fcb7c765ee4 | textbox | DATE:
4a941b65-0946-57d3-bc6a-786fdea00a3f | signoff | AUTHORITY HOLDPOINT
39023f41-2b98-510a-970d-103e31c2a6c2 | checkpoint | 6.4 CCTV
5032d007-0f88-56c0-9691-eba5e6e56e0f | note | FREQUENCY: Each Lot
e8b73a02-9ede-5ad7-a9de-af795dd46a89 | note | ACCEPTANCE CRITERIA: Hold Point
2c7671b1-075a-55f5-aebd-21a3307e9f10 | note | ○ All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
913b271e-4a7d-5bcc-a06f-e93a6295de35 | note | REFERENCE DOCUMENTS: Cl 701.30 WSA 05-2013
be01887f-e705-509d-9faf-301b91ae08de | note | INSPECTION/TEST METHOD: Verify
d0406cba-0c7e-5cd8-bcc9-ea452d53aa32 | note | RECORD OF CONFORMITY: This ITP Signed
db202109-79a9-5701-8a46-42b8db8bc585 | note | HP
9a781c87-b27a-53b2-96f7-e22b13174dcf | note | RESPONSIBILITY: Site Engineer / QAV
e496ab5c-425b-5589-a93c-75badbdcdaea | textbox | DATE:
3bc43474-e793-5dca-88b0-f7585715e5df | signoff | AUTHORITY HOLDPOINT
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
cc3995c5-41ee-5712-938c-d11b58ba3d65 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
4f67a198-1e6c-5491-9ce3-610dbadeb16e | textbox | Print Name:
337693f4-d530-5493-8a40-c05270a52f7a | textbox | Position:
6156ef0c-dbf8-52ed-8a26-4f731e3bb7d4 | textbox | Date:
a0c663c6-4171-59c1-b168-9abeb4fc1adc | signoff | Add Signature
1b5b420b-5d7c-5349-a342-206aeffe06de | checkpoint-no-value | Table 701.091
aae3cc03-b612-5bd2-8a52-cd66b5bd77fa | note | Sieve Size - AS (mm) ¦¦ Percentage Passing (by mass)
052d4d98-fbed-55a9-8b20-0a4b20439a0a | note | – – – – – – – – – –
22eaf925-2267-580c-877c-d75688df3cbb | note | Material: Backfill
53ac9aef-5937-5303-a1bf-1d2b2a351edc | note | 75.0: - ¦¦ 37.5: - ¦¦ 19.0: 100 ¦¦ 2.36: - ¦¦ 0.075: 5-40
916b16c1-ceac-51e2-8c2a-a131bdbee4bd | note | Material: Selected Backfill
4cdd5551-7704-5e3e-a434-33ed53b87add | note | 75.0: - ¦¦ 37.5: 100 ¦¦ 19.0: - ¦¦ 2.36: - ¦¦ 0.075: 5-40
010d59fc-b100-51b2-81ba-e596bbc6c045 | note | Material: Ordinary backfill
fb3130df-e56f-526b-a2dc-7004711a234c | note | 75.0: 100 ¦¦ 37.5: - ¦¦ 19.0: - ¦¦ 2.36: 40-100 ¦¦ 0.075: -
e84e0b5b-8578-5793-b6db-2b8599c008ad | checkpoint-no-value | Table 701.092
fecec510-1911-547b-ad76-bd302900003d | note | Test ¦¦ Test Value
6025b7a3-adae-52be-9bfb-15b97991d1cd | note | Plasticity Index (Max.) ¦¦ 20
d2d52495-918e-5488-aff7-e80222c7d5f6 | checkpoint-no-value | Table 701.141
db5f3546-47a0-5759-8ce7-31a4acd76bec | note | Required Cover Thickness (Metre) (Min.)
ecefb9ce-73b5-59ad-947e-32992c5ed0d0 | note | Type, Size, and Class of Culvert
76a822a1-9259-5115-83a5-a5208cde71b8 | note | – – – – – – – – – –
ea3ee9af-ebad-572b-9453-fe8f26c6e06c | note | Range of Axle or Track Loading (tonne): 0 - 9
e5ab18b8-bb11-5d23-a75f-9685975eb67f | note | • Pipe 2
d2a98b0e-21a6-5b16-af53-48b3c8af3a90 | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
cb733d37-6a52-5116-8b38-3d0c85101f85 | note | 0.4 ¦¦ 0.4
89fc9107-26ec-5a8c-b511-d404738b5adb | note | • Pipe 3
1be82f2d-9093-5b40-8639-847c7430c452 | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
d72fe00d-ae06-5b82-aec0-5de5a3ea9f19 | note | 0.4 ¦¦ 0.4
d3ca5379-1b16-599b-9895-5569b4b31baa | note | • Pipe 4
39f4933b-4df9-531c-a8c3-063e6233ad95 | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
f5858b07-55e2-5b2f-a221-39823cb23ca3 | note | 0.4 ¦¦ 0.4
bfe661ee-fbe0-5497-9a7d-ba42874faf83 | note | • Corrugated Metal: D 1200-3600 mm ¦¦ Box Culvert 90 kN Proof Load
eab00c29-9795-59fc-a60b-5997caa9ffc9 | note | - ¦¦ 0.1
686ae772-ffe5-5126-a0b6-ca349be34432 | note | – – – – – – – – – –
0212885b-288c-542c-a9c4-c4b9b2f17119 | note | Range of Axle or Track Loading (tonne): 9 - 20
fcf5545b-15a4-5ee2-afea-71544c558810 | note | • Pipe 2
69de36f4-3e0a-5b76-89ca-9e4fccccc715 | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
226b0c0e-f5b7-50e7-b074-94df563d5f46 | note | 0.4 ¦¦ 0.4
961dcbd7-38e0-5963-b129-34fbbe734e0c | note | • Pipe 3
ee170c55-b64b-5e51-8ab4-f8a2478f2de9 | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
b92b4f06-a59c-5417-a5a0-39fefff3c096 | note | 0.4 ¦¦ 0.4
40f85acf-24fd-54d1-901e-36de93edec3c | note | • Pipe 4
57d23da9-48d3-5bd0-b167-68ad9815c751 | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
bf7c6797-4666-5b5a-b840-c007d2981a80 | note | 0.4 ¦¦ 0.4
97022427-51d8-50ea-96f0-0bb3faf25fba | note | • Corrugated Metal: D 1200-3600 mm ¦¦ Box Culvert 90 kN Proof Load
1b102327-b16a-5c01-b525-358f55fae81c | note | 1.2 ¦¦ 0.6
322d13f6-ac2c-5cf3-8ceb-982a22858e7e | note | – – – – – – – – – –
190d5066-a5ed-5167-bf5b-3c4d56cd4de8 | note | Range of Axle or Track Loading (tonne): 20 - 35
968b2e4c-bcf2-554d-8ad1-d407ee488276 | note | • Pipe 2
8da0066b-91f3-5827-b4a7-210b2244947b | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
e24d4bfa-d807-5d19-85d7-107c5509f09c | note | 0.7 ¦¦ 0.4
e51a54f4-d6f9-5d04-8d74-c35e9d852a47 | note | • Pipe 3
d71adef3-29a3-5e92-8ed7-18ba43ecb458 | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
834a6fdc-8966-52a4-96aa-c09f7697acf2 | note | 0.4 ¦¦ 0.4
0aa43555-677e-5356-8df6-6227a94cd843 | note | • Pipe 4
91311f3e-dad8-53fe-9976-208e71fddfb4 | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
e23690cd-6241-5590-8659-1f662bc3d061 | note | 0.4 ¦¦ 0.4
8021aefc-6587-5596-b6b6-5a0ad943add6 | note | • Corrugated Metal: D 1200-3600 mm ¦¦ Box Culvert 90 kN Proof Load
78641f56-6fa1-5f5f-bb0b-cb4ebacae10e | note | 1.5 ¦¦ 0.9
1573bfaf-677c-5eb0-94d9-cb8caeddb814 | note | – – – – – – – – – –
453ef30e-96ea-5a9a-a8ec-18d08ebe462c | note | Range of Axle or Track Loading (tonne): 35 - 50
f7fd4335-aaf2-5984-852e-6b48a10e8b38 | note | • Pipe 2
53ccbdda-fa2e-58a5-811d-fdad8c67160d | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
438be1c6-2af3-516b-b9a0-89b7aa68f44f | note | 0.9 ¦¦ 0.7
80afa893-7a88-5c8d-9d26-e9ee5eb5841d | note | • Pipe 3
2baafe4a-668d-5273-8bbc-acf237662fa0 | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
bb71a490-11ee-5fd5-b6b4-b1c64988d76c | note | 0.6 ¦¦ 0.5
fe8995af-23e7-5d2f-adb0-b0274654ee2b | note | • Pipe 4
9ccc9e8e-bc1e-5ad9-b48a-1c952be943c1 | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
0675f072-f1be-5da0-8a23-e6662a0e51d3 | note | 0.5 ¦¦ 0.4
d68fc172-046e-5ef3-a0d8-023a5a76de76 | note | • Corrugated Metal: D 1200-3600 mm ¦¦ Box Culvert 90 kN Proof Load
ae3c441b-5f6b-5c5e-bbfc-fab5a8867c61 | note | 1.8 ¦¦ 1.2
725f8501-0797-5716-93a5-901c6f8ee680 | note | – – – – – – – – – –
22e8e819-4c72-5e30-a81f-f1587d0b6a11 | note | Range of Axle or Track Loading (tonne): 50 - 60
005110ef-263b-55c4-822a-2bfc44f53205 | note | • Pipe 2
f746d0de-4983-52f0-85ae-0cf00f420ed8 | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
ae9355af-f326-55b4-90d8-b63bab04862b | note | # ¦¦ #
66a73dfc-9e3b-587c-9b6b-c019d2ec87fd | note | • Pipe 3
d6f12a6d-ad40-5d5a-a8db-7559b52a7a3f | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
fdd92f97-6273-5269-95a9-4eb42dbc9caf | note | 0.8 ¦¦ 0.8
ac6a5732-33ea-5940-9682-28ad0dabfcfb | note | • Pipe 4
8dbc0cb8-0af6-5e82-bc0f-8b61e97d938e | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
b730ab5f-ccdb-5bcd-aa75-49e1cfd28592 | note | 0.7 ¦¦ 0.7
7286729a-39ae-5128-a6a7-1a168d814c61 | note | • Corrugated Metal: D 1200-3600 mm ¦¦ Box Culvert 90 kN Proof Load
54380ee2-6754-50bb-9912-6ec185df5de2 | note | 2.1 ¦¦ 1.5
545bfacb-a45b-59f1-bd30-28e9769b0157 | note | – – – – – – – – – –
e03f3c44-2e7b-5ebc-9b98-f526abee9425 | note | # This range of loading not permissible.
7897ea93-1950-545a-94b3-01aaa2c922fd | note | D Nominal Pipe Diameter
fddc8da7-a927-5ecd-b8ec-9c88012fc799 | note | D less than 1200 mm not permitted, D more than 3600 mm as directed by the Superintendent.
db1db21b-9a19-57d1-93d7-16d7c79ef093 | checkpoint-no-value | Table 701.151
78d3d931-4d38-585c-9d38-e263d50310dd | note | Pipe Type ¦¦ Nominal Pipe Diameter or Width (mm) ¦¦ Horizontal Clearance to Wall of Trench :: Min. (mm) / Max. (mm)
e6b93431-e964-50d8-b3c3-4b34703ee3aa | note | – – – – – – – – – –
be06e736-6a85-50d7-858e-6db237d4b0c0 | note | Corrugated Metal Culvert ¦¦ All :: 300 / 1,000
d7822ed5-a877-50e8-8f8b-8d0c966dd4b9 | note | Other ¦¦ All :: 300 / 600
1d617b92-b6a5-5422-abba-61f78db94bc8 | checklist | ITP - Surfacing - Asphalt Placement & Spray Sealing Rev1 | itp | ITP - Surfacing - Asphalt Placement & Spray Sealing
56f12a57-1e96-5877-8041-0f0eb46d12c8 | section | 1 - Preliminary Works
db5bd2d1-0961-5fd8-9948-8f023044220b | checkpoint | 1.1 Submission of Mix Design
a90bb2db-d914-528c-9ad6-90a4a049bcca | note | FREQUENCY: Prior to commencing paving
49762bad-fd3e-5425-8936-049aa9bc408b | note | ACCEPTANCE CRITERIA: All asphalt mixes proposed for use in the works shall have a mix design registered by the Victorian Department of Transport as 'General', unless otherwise approved by the Victorian Department of Transport.
aca1afd5-ccea-508c-b54c-66cdb9beaaae | note | ○ The registration for all mixes incorporated into the works shall be current at the time of their use. The contractor shall submit documentation to the Superintendent nominating the asphalt mixes to be supplied no less than 7 days prior to their use.
a02afa44-4ebb-529c-a41c-b9d1b0704930 | note | REFERENCE DOCUMENTS: Cl 407.09
34e69457-5244-5ec5-b4ac-3ae8bc43fbe3 | note | INSPECTION/TEST METHOD: Verify
0da91c8d-7046-52c0-98c2-769efc61cf5e | note | RECORD OF CONFORMITY: Mix registration & correspondence
40b1f64d-d95b-58b0-afa8-4a8045742335 | note | HP
e55e2b8f-faf3-55f4-a678-be69a819d95d | note | RESPONSIBILITY: FH Engineer/ Superintendent / QAV
762582d4-05ca-56b3-8515-8772696a4aba | textbox | DATE:
b15a6d30-c312-5831-af66-61cf4d31512e | signoff | AUTHORITY HOLDPOINT
6a9380d5-4e77-5177-a005-cf90a26e111a | checkpoint | 1.2 Implementation of all measures and controls
d8a4cd24-2916-5a10-8a5a-dff9ab88d77b | note | FREQUENCY: Prior to commencing any activity
5bb0eb75-0bf5-5135-86f8-970e4bb7ea68 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
c6875eab-4539-5fe4-84f8-277ef6b66867 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
f288b42a-cae5-57c2-977b-8700dbb67c0e | note | INSPECTION/TEST METHOD: Visual Inspection
83c852b4-094c-5b05-bc34-ea4fe282db83 | note | RECORD OF CONFORMITY: This ITP signed off
21ded376-2800-5a93-8246-efe7a7bfc1a0 | note | HP*
0072f1df-c920-5d58-8d91-682b3d5db6cd | note | RESPONSIBILITY: FH Engineer
42c6842c-ea51-579b-ac72-72a28588c923 | textbox | DATE:
d13a1dda-0a40-5188-a8e7-e2df1a01079b | checkpoint | 1.3 Site Inspection and Base Condition
2a2d3844-11ae-5cc4-8dc6-c1c3881643c8 | note | FREQUENCY: Prior to commencing paving
05c508df-0944-535e-8eee-e1cc1b82b8fc | note | ACCEPTANCE CRITERIA: The surface on which asphalt is to be placed shall be essentially dry and free from surface water. Asphalt shall not be placed when the pavement surface is wet, or rain is imminent.
1ee659a9-2b77-562e-88f3-c1b7b94e6640 | note | REFERENCE DOCUMENTS: Cl 407.17 (a), AS2150 10.1, AS2150 10.3
e0e49a65-bc61-592e-93b2-28ca77d2dfb8 | note | INSPECTION/TEST METHOD: Visual Inspection
9faeb286-3e2c-580c-880f-61091be0abe0 | note | RECORD OF CONFORMITY: This ITP signed off
779d9011-2cde-5f01-90a9-0ef3084970ff | note | IP
e3599813-794b-50d1-838d-11c96c6fbd09 | note | RESPONSIBILITY: FH Engineer / Superintendent
374453bf-b108-5dd1-a751-879e65432e50 | textbox | DATE:
068c5c83-52b0-58f2-954f-1b435da43940 | checkpoint | 1.4 Ambient Conditions for Placing
7b070cd3-06c5-5371-b993-4228fcbb1448 | note | FREQUENCY: Prior to commencing paving
a7c88c26-1b90-55af-ae4b-704286488db6 | note | ACCEPTANCE CRITERIA: Asphalt shall not be placed when majority of the area to be paved has a surface temperature less than that detailed as follows:
8346652f-f03c-598e-a76b-5763d9f487d9 | note | ○ Base or Intermediate Courses: 5°C for specified binder class of C170 or C320; or 10°C for asphalt mixes with specified binder class of C600 or containing a PMB.
b0b87aac-30e4-5556-8056-074520cef46d | note | ○ Wearing Course: 10°C for specified binder class of C170 or C320; or 15°C for asphalt mixes with specified binder class of C600 or containing a PMB.
6674c4b6-dc5a-5235-9993-b8d2bff1c58f | note | REFERENCE DOCUMENTS: Cl 407.17 (a) Table 407.171
1a27aaa6-b9d3-57aa-a3b4-f0b9a42f1ea0 | note | INSPECTION/TEST METHOD: Verify
7345be76-6fca-5e88-acf1-1892b0bbd86b | note | RECORD OF CONFORMITY: This ITP Signed off
104110fd-9076-5221-8261-cef5bf2c5fb2 | note | IP
849f3c82-b5e6-52b5-9698-f6775ad1cb47 | note | RESPONSIBILITY: FH Engineer / QAV
64f24c29-6d18-5d75-96b2-a1dc46962ede | textbox | DATE:
ad008d80-fab8-51bc-b496-6a541b0ccafd | section | 2 - Material Procurement for Spray Seal
f1c23559-3c4d-5d4b-b4b3-3bc095cea273 | checkpoint | 2.1 Adhesion Agent
b5532f40-f6dc-5035-852a-0a673640e627 | note | FREQUENCY: Test cert. upon request
885113ba-0b20-58f4-a93b-99fd261fbd89 | note | ACCEPTANCE CRITERIA: Satisfactory field performance. When adhesion agent is added to the binder, the total volume of adhesion agent ≤1% of the binder.
575845b1-8fa1-5c42-9165-ddb4652ff149 | note | REFERENCE DOCUMENTS: Cl 408.09 (a),
05ad42cb-b5c9-59e9-ac4e-80110debb8fc | note | INSPECTION/TEST METHOD: Verify
9dd50237-cb57-5498-8321-b27d89f729ed | note | RECORD OF CONFORMITY: This ITP Signed off
72fd5ec6-e9ca-5c40-a84e-ba23caad4856 | note | IP
9ed0e7dc-0d3b-5d71-a385-90b6e7824fb5 | note | RESPONSIBILITY: Site Engineer
ba7dc1db-5f16-5041-b965-a85abdca6445 | textbox | DATE:
70ab2049-4af0-593f-87d3-b1622235d60b | checkpoint | 2.2 Aggregate Precoating Materials
5bfae134-54d6-51ef-8fd9-d1881b8c39cc | note | FREQUENCY: Test cert. upon request
c93e1d19-dacf-5f8c-b2c3-93fe55b41c23 | note | ACCEPTANCE CRITERIA: Aggregate Precoating Materials shall be distillate, distillate based product, cutback bitumen, emulsion based product or proprietary product.
0acb8c0b-9fe6-5c58-ba87-0f0346ead87e | note | REFERENCE DOCUMENTS: Cl 408.09 (b)
d4d34b55-863a-524e-84cc-48d926e8b596 | note | INSPECTION/TEST METHOD: Verify
f08378f3-e5d6-5284-b666-fe657bfe4e57 | note | RECORD OF CONFORMITY: This ITP Signed off
2a44676f-2cb2-5038-afd9-51eb4e4f9ec1 | note | IP
3b7bd609-5e93-593a-aed8-7b2d63ff2d72 | note | RESPONSIBILITY: Site Engineer
39e1b567-8868-5214-bd0e-2efa64614cfd | textbox | DATE:
2c8891c0-81dc-50ff-afa8-496f2c8e1bbe | checkpoint | 2.3 Bitumen
5dc38d17-85ba-5aad-9dfe-9240ef8cb044 | note | FREQUENCY: Test cert. upon request
3db271d1-a42d-5fbd-ba5c-0d7f77c2d252 | note | ACCEPTANCE CRITERIA: Bitumen shall be Class 170 complying with the requirements of AS 2008.
c90bab39-93e9-516b-8708-d328f73a33f2 | note | REFERENCE DOCUMENTS: Cl 408.08 (a), AS 2008
fbaea5f4-001e-506a-b9a1-ca07ba8f7ae5 | note | INSPECTION/TEST METHOD: Verify
ce3a2a21-f315-5477-8aec-edc1a2e36f63 | note | RECORD OF CONFORMITY: This ITP Signed off
0fee489d-25ec-5cfe-969a-50bed7db0741 | note | IP
cbd496b5-f41c-5e0c-9cf1-75e8232207b9 | note | RESPONSIBILITY: Site Engineer
082ee384-5d78-5ebb-a67c-92c034e21a5d | textbox | DATE:
4a1000bd-45dc-56d1-9a7d-9ba6017012b8 | checkpoint | 2.4 Bitumen Emulsion
a7d695dd-7383-5cee-a6b1-1bfdec71c712 | note | FREQUENCY: Test cert. upon request
60a77768-1b8e-5b31-a5e8-919e25555c17 | note | ACCEPTANCE CRITERIA: Bitumen Emulsion shall comply with the requirements of AS 1160.
0003f46b-06de-50e3-961d-faf8eb06ae4b | note | REFERENCE DOCUMENTS: Cl 408.08 (b), AS 1160
3a940211-c957-5673-a04e-7ef0bf57fd16 | note | INSPECTION/TEST METHOD: Verify
2caabf3c-7958-509d-a1b4-72b8199bf032 | note | RECORD OF CONFORMITY: This ITP Signed off
1caa2266-9842-5250-a9ab-2c66a210a1ff | note | IP
fd1fa68d-1775-5f40-8e46-54736ea3b294 | note | RESPONSIBILITY: Site Engineer
5f92cab1-7ec8-5a75-8927-303fa26f0f91 | textbox | DATE:
61b33dae-78ea-53e1-93e1-ef1aff752cbc | checkpoint | 2.5 Cutback Bitumen
95178b1e-52ca-5a79-ab97-dbc42cca920b | note | FREQUENCY: Test cert. upon request
cebd5cb5-d2dc-5a01-8a0c-46468cdaed73 | note | ACCEPTANCE CRITERIA: Cutback bitumen shall comply with the requirements of AS 2157.
02c9bbfa-4f15-517f-83af-a1fcef73d58e | note | REFERENCE DOCUMENTS: Cl 408.08 (c), AS 2157
6826b4f9-c6ee-5cda-a8f5-56feb8165a0f | note | INSPECTION/TEST METHOD: Verify
cbc1e0d3-3a73-5f8a-a6ea-6cc02bc77424 | note | RECORD OF CONFORMITY: This ITP Signed off
bdaef431-ad47-58ea-b759-b15d74cba459 | note | IP
6628dcc6-baec-5a1a-aaa5-d5281a9af15a | note | RESPONSIBILITY: Site Engineer
29458cb7-4f96-54f3-9fc7-5d7026e7ac64 | textbox | DATE:
ee9448d2-6ee0-5d1d-b063-75a20784856a | checkpoint | 2.6 Cutter
544a25c1-27b0-5fd2-ac66-08274fab23c0 | note | FREQUENCY: Test cert. upon request
74f5050f-0b2a-5d06-b70f-2abce292eec5 | note | ACCEPTANCE CRITERIA: Cutters shall comply with the properties in the Table 408.091.
21b863f4-923f-5b26-8d65-55e0532de4cb | note | REFERENCE DOCUMENTS: Cl 408.09 (d) Table 408.091
3d045827-8086-5c89-817e-004c24ca6b22 | note | INSPECTION/TEST METHOD: Verify
29b509df-c657-58ad-b786-158d5f14b780 | note | RECORD OF CONFORMITY: This ITP Signed off
0d68030d-2de5-5ec7-8933-3462bb2a98c8 | note | IP
ec75c018-8e12-5e6e-bf28-030e67cdf65d | note | RESPONSIBILITY: Site Engineer
bc198a08-74cb-5522-9cc1-0a56e13cd0e5 | textbox | DATE:
6bcb14dd-a4f2-58db-bbd1-7962cbc06d82 | checkpoint | 2.7 Polymer Modified Binder (PMB)
99747aa5-1eb3-5aa2-af9c-dfe13499ec1f | note | FREQUENCY: Test cert. upon request
fc7e3217-d40a-562b-b865-529920aee3eb | note | ACCEPTANCE CRITERIA: The class of PMB shall comply with the requirements of Austroads Technical Specification ATS-3110. Alternative or 'ungraded' PMMBs which do not comply with the specified test requirements of ATS-3110 shall not be used without approval by the Superintendent and will be subject to the Contractor providing evidence that the product has delievered satisfactory fiels performance for a period of at least three years.
f747f9a1-200a-5afc-ad3b-a452ec95f219 | note | REFERENCE DOCUMENTS: Cl 408.08 (d), AST-3110
cd95df30-e2eb-5b5a-8f67-919a2e3de540 | note | INSPECTION/TEST METHOD: Verify
9f4dbb2c-d4d3-599d-bb63-b575fcde7776 | note | RECORD OF CONFORMITY: This ITP Signed off
d53e3261-8a9c-56d8-98b8-f27f502d28f7 | note | IP
999bccc8-8c4f-5d9f-8ec2-bb2f101e19a5 | note | RESPONSIBILITY: Site Engineer
ad39a8d0-99b9-52d7-9dd9-540c8653e6eb | textbox | DATE:
b55112fc-2224-5643-b885-a6792540e4d5 | checkpoint | 2.8 Primer
4d95c97c-c351-5aa9-b2a2-94e7e1f7a8a9 | note | FREQUENCY: Test cert. upon request
d5f81be8-778a-5bc2-b4bc-6b80505f0dac | note | ACCEPTANCE CRITERIA: The primer shall be cutback bitumen complying with the requirements of clause 408.08(c) and shall be water resistant, of uniform appearance and capable of providing a strong bond between the bituminous surfacing and the pavement.Bitumen emulsion alternative acceptable upon providing evidence that the emulsion product meets the same functional requirements.
b4a49b96-3650-5f37-bc6c-107eada4eabb | note | REFERENCE DOCUMENTS: Cl 408.08 (e)
31ea0ed1-e0b4-59e6-861d-b10582e80f79 | note | INSPECTION/TEST METHOD: Verify
17a0d83e-4437-5701-bb3a-0e31c2428873 | note | RECORD OF CONFORMITY: This ITP Signed off
988758e9-b45c-5e41-9d56-42ce0380fb9b | note | IP
60900e8e-49b7-58bb-8199-dad13e1460b6 | note | RESPONSIBILITY: Site Engineer
257187b3-ef1d-5724-8390-58508b79a3a2 | textbox | DATE:
8e3231bf-0873-5346-baca-0f87c011441a | section | 3 - Aggregate
928a5bda-8c16-515b-838e-4904b562f88c | checkpoint | 3.1 Aggregate Specification
409f8992-43e7-5e93-861e-f77c29bb7a04 | note | FREQUENCY: Each lot
c30f97fa-dafa-5065-a8b0-9445b289af1a | note | ACCEPTANCE CRITERIA: Aggregate shall comply with sections:
01275b30-471f-5aff-a012-5c2ae2c5eae2 | note | ○ 801 - Source Rock for the Production of Crushed Rock and Aggregates
7bafd573-5462-5f9e-b93b-1845887f5842 | note | ○ 831 - Aggregate for Sprayed Bituminous Surfacing
1fe2945f-87b2-52ea-b3aa-16e8bddd7a68 | note | REFERENCE DOCUMENTS: Cl 408.11 (a)
0136ead0-675d-554a-abae-7d4c1b665c56 | note | INSPECTION/TEST METHOD: Verify
eb181efa-d320-58c1-bdcc-dedaefdc2c81 | note | RECORD OF CONFORMITY: This ITP Signed off
475941aa-6fe0-509d-9c68-65fdf517a34b | note | IP
d6c4ce3c-de22-5244-93f0-cf5aee4e7575 | note | RESPONSIBILITY: Site Engineer
54cb9396-dc42-57b3-a179-8700b0e977e8 | textbox | DATE:
dcea322a-a0fa-5ffe-8b1b-941b578abbcd | checkpoint | 3.2 Aggregate Precoating
1b4797c5-8577-5166-ab05-b86f1daf2adb | note | FREQUENCY: Each lot
dcbe1837-ba0b-5a6a-ac7a-b848e5ce49b4 | note | ACCEPTANCE CRITERIA: Supply plant precoated aggregate or field precoated aggregate.
bfcb9e73-be82-5d8a-98eb-cab6a871bf37 | note | ○ Aggregate precoating shall be undertaken using a purpose-built item of plant to apply to the precoating material in a controlled manner that produces a uniform coating.
18302b0a-1087-5615-8637-d675b956a587 | note | REFERENCE DOCUMENTS: Cl 408.11 (b)
cad554cb-c312-5773-a146-994df0489de8 | note | INSPECTION/TEST METHOD: Verify
b2711e48-db7f-52f4-906b-fb62e927fed2 | note | RECORD OF CONFORMITY: This ITP Signed off
6be7bcb2-11e9-52d3-b4b3-e16f124064bb | note | IP
3729010d-09d0-5e2c-9a30-5e6b4bb66bad | note | RESPONSIBILITY: Site Engineer
99457a04-7c78-5c88-b42a-bf133fb9a5fd | textbox | DATE:
5cb25a71-d7ad-5696-acfc-bb368b706d63 | checkpoint | 3.3 Removal of loose aggregate
fdf35e8a-cee6-5006-888b-9a505f509569 | note | FREQUENCY: Each lot
6ff4b59c-8a46-59d4-8d57-82467e75312a | note | ACCEPTANCE CRITERIA: All areas – within 8 hours of sealing as it is mfreeway and AADT is greater than 5000, as per table 408.141, unless otherwise agreed with the Superintendent.
e43927f7-37b2-5edb-87e4-7e2f8e6e0566 | note | ○ For seal of nominal size ≥ 10mm, < 40 loose stones/m2 to remain after removal of loose aggregate. For seal of nominal size ≤ 7mm, < 60 loose stones/m2 to remain after.
eec4bba6-6aa0-5801-9381-699c5193b8cc | note | REFERENCE DOCUMENTS: Table 408.141
adc14994-0fe1-521c-9f57-3a8ae7ee7b9d | note | INSPECTION/TEST METHOD: Verify
fd16ccdb-4483-57cb-91e8-135781daa3a7 | note | RECORD OF CONFORMITY: This ITP Signed off
0dd748fd-afed-581f-8b2c-6072aa6a7391 | note | IP
a1414623-275c-5f70-86be-569bbb1dd3d9 | note | RESPONSIBILITY: Site Engineer
aa29d1a8-57c0-59b4-b95c-f4436b1aa784 | textbox | DATE:
2307a9ad-63b5-50b1-89aa-dbcbb656688f | section | 4 - Asphalt Placement
34da61f7-4ab4-585e-b6d8-2d821c710bd0 | checkpoint | 4.1 Tack Coat
a65fdddb-f186-5c75-9ecd-671e414e029a | note | FREQUENCY: Prior to commencing paving
b5386b4a-8cfb-5d25-8c3b-aeac45f65447 | note | ACCEPTANCE CRITERIA: Tack coat shall consist of a bituminous based binder. From 1 July 2022 only trackles stack coat will be permitted. The contractor shall submit the details of the trackless tack coat proposed to be used in the works
730b960c-e673-5c62-981e-9f34626a2ad8 | note | REFERENCE DOCUMENTS: Cl 407.08 (d) AS2150 11
d486e7ed-53a4-5dca-aa55-e69a61efa8ab | note | INSPECTION/TEST METHOD: Verify
8224b50f-5eaa-54a0-a984-21e2a49901cf | note | RECORD OF CONFORMITY: Hold Point Release
20f72ccb-5aa7-5cd9-9a75-9055e9585807 | note | HP
564728d0-14a0-50a1-aefd-97b36e437bcd | note | RESPONSIBILITY: FH Engineer/ Superintendent
1f411913-a82e-572f-b9c8-ef79f6878144 | textbox | DATE:
722c5f36-9065-5447-964e-cba70ff36443 | signoff | AUTHORITY HOLDPOINT
40d99f78-eb1a-5aa2-8ea8-a6c1da0589c5 | checkpoint | 4.2 Application of Tack Coat
ee32ab3d-94f8-5583-8600-e2d9bed033c9 | note | FREQUENCY: Prior to Asphalt placement
24b0403c-1e49-5ee3-bc9c-fcbd29770704 | note | ACCEPTANCE CRITERIA: A tack coat shall be applied to all asphalt, concrete or sprayed seals on which asphalt is to be placed. The tack coat shall achieve an effective bond between the asphalt and the underlying layer.
8a39381e-0891-5b26-ade5-f06544279c92 | note | REFERENCE DOCUMENTS: Cl 407.19
3588daed-02f8-51fb-8eae-8c85524bd895 | note | INSPECTION/TEST METHOD: Visual Inspection
40758950-1591-5541-a736-af19df04725b | note | RECORD OF CONFORMITY: This ITP Signed off
b481bb9c-b77b-57a4-b792-b15eb3b7dd34 | note | IP
3b828970-eb7c-5ea5-9123-c4ee0e16ce00 | note | RESPONSIBILITY: FH Engineer / QAV
70ceef2a-2bc8-5fa1-8253-c7c392c23fe2 | textbox | DATE:
84834d1b-bcea-5161-8937-05e2abdb296f | checkpoint | 4.3 Commencement of Asphalt Placement
5f716c6b-b952-5dd8-9295-7db2f3720dfa | note | FREQUENCY: Prior to commencing Paving
c54b0000-0a9e-5920-ac85-e139ea59ac88 | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until approval to proceed is obtained from the Superintendent
cb82779c-8231-5cf4-98b0-fd1195238a30 | note | REFERENCE DOCUMENTS: Cl 407.23
1b1d2a5e-d6d9-52a7-96eb-632d5402a91b | note | INSPECTION/TEST METHOD: Verify
8ae00f78-a72e-5f28-b135-364cac8f2a3d | note | RECORD OF CONFORMITY: Hold Point Release
8e2d64a2-f919-5956-b2c2-fa7580669966 | note | HP
723551ff-b226-5e4d-8493-2bc33960c7da | note | RESPONSIBILITY: FH Engineer / QAV
3f65f2fe-1446-5c9c-9441-c4750e236489 | textbox | DATE:
7c8f61d8-52b5-5b91-944a-94b45b7268f9 | signoff | AUTHORITY HOLDPOINT
f3288ed8-8a3f-5401-8599-f5d980882918 | checkpoint | 4.4 Delivery of Mix
cdb511e5-85c2-5735-b73a-24078af4f389 | note | FREQUENCY: Each load
9f1d77a1-9562-5ff0-9335-daaf71993f89 | note | ACCEPTANCE CRITERIA: Asphalt delivered to site, which is segregated, has been overheated, is too cold, contains separated binder, uncoated particles or which does not comply with the Specification shall be removed from the site.
5832f869-9849-5ac8-9bab-23d8c105d7f0 | note | REFERENCE DOCUMENTS: Cl 407.20 (a)
272268e9-126b-52a4-9774-1bf7b76ef087 | note | INSPECTION/TEST METHOD: Visual Inspection
b925e12f-d0e5-5b4f-a8bd-c54806df30e6 | note | RECORD OF CONFORMITY: Delivery Docket /Asphalt Traceability Sheet
4bea0bb0-4fbc-585f-8e10-19804d0faba1 | note | IP
dd41aaed-1e4a-5f65-8591-62284a07370a | note | RESPONSIBILITY: FH Foreman / FH Engineer
cdb2c198-abe6-543f-af1c-26a726b7ab39 | textbox | DATE:
089aa06e-2322-56d2-8be4-0a9595298838 | checkpoint | 4.5 Layer Thickness and Scale of Level
6e9f889a-426b-5999-8061-00563c15c2d0 | note | FREQUENCY: Regularly during paving
65cb4411-a391-5193-b37f-7eac2b9b0c91 | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness and Scale for Level as specified on drawings or specifications
e75e28a7-9957-5d97-902d-8db6105f56c8 | note | REFERENCE DOCUMENTS: Cl 407.30 Drawings
ebfade17-a8fa-591f-a158-a5a55b6b5764 | note | INSPECTION/TEST METHOD: Verify
d4590917-e2f9-5db2-90a3-2d46e51e0403 | note | RECORD OF CONFORMITY: Dips using ruler or dip stick
34dcc745-49df-57cd-b0ff-b2f5f5e8daac | note | IP
6014951a-dd34-531a-a8ab-3a293309de81 | note | RESPONSIBILITY: FH Foreman / FH Engineer
dfc6211b-d607-5e92-baf5-e052b9279967 | textbox | DATE:
61825577-b5c8-527b-98e7-942529a0941d | checkpoint | 4.6 Paver Stoppages
32ff8f3a-79c6-5ec5-bf29-ef6add24ad4a | note | FREQUENCY: If paver stops
139efe57-5a3d-5a72-b0be-9547d7f99629 | note | ACCEPTANCE CRITERIA: If the paver is required to stop and asphalt in front of the screed cools to below 120°C , a transverse joint shall be constructed.
07852e78-ccb9-5fae-820d-035f35adaa71 | note | ○ Hand spreading shall only be used for small areas where it is not practical to use a paver
418c02b4-9087-5def-a8b8-0f181cdd66fc | note | REFERENCE DOCUMENTS: Cl 407.25
dbdecf46-716c-5a5c-b795-31dff8c27c77 | note | INSPECTION/TEST METHOD: Verify
669949af-7c3a-5272-8219-f8b29d27a67e | note | RECORD OF CONFORMITY: Thermometer
d3ffa807-d281-540a-82d4-4a579e3b3a3a | note | IP
b235ab88-8043-541f-9400-0a9618d3caa9 | note | RESPONSIBILITY: FH Foreman / FH Engineer
17aa0131-70d3-5ebc-be82-ffaa98710e4a | textbox | DATE:
88ae6d3d-e406-56dd-899b-af8160a823e0 | checkpoint | 4.7 Surface Finish of Wearing Course
d81605b1-659b-554d-a75e-c3bd60e9d435 | note | FREQUENCY: During paving and after final roll
28a5aebd-375f-5901-88dc-daf9336179c4 | note | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
1a86ab8b-a169-50cd-adac-f78f0645e19f | note | REFERENCE DOCUMENTS: Cl 407.29 (i)
10b924dc-c87b-53b3-be23-b15646389931 | note | INSPECTION/TEST METHOD: Visual Inspection
e33b5707-9d00-5071-bd60-ac71f6bbbe8c | note | RECORD OF CONFORMITY: This ITP signed off
9886536b-020b-59f1-a6f0-c6daa3028145 | note | IP
8996b184-36f8-5f6e-b8bf-8b47182aa94f | note | RESPONSIBILITY: FH Foreman / FH Engineer
4d99f5ef-433b-58fc-8704-93ee0b7779dd | textbox | DATE:
482f6f29-be0f-55ee-91f9-586fcc721f45 | checkpoint | 4.8 Kerb and Channel
b35775f7-86c3-5bb3-95da-a9f9e8e6cc54 | note | FREQUENCY: During paving and after final roll
02232edc-90b5-588e-8aa2-cab26d5de7da | note | ACCEPTANCE CRITERIA: Where asphalt is placed against kerb and channel the surface at the edge of the wearing course shall be either flush with or not more than 5mm above the lip of the channel.
33b9f353-113d-5ae1-ab35-77732ea4f804 | note | REFERENCE DOCUMENTS: Cl 407.29 (ii)
aedd8625-f1eb-5eb4-a02e-361bd7f0ce50 | note | INSPECTION/TEST METHOD: Visual Inspection
5d25bdb3-dd9f-5fde-a7f1-17846f5dc6b0 | note | RECORD OF CONFORMITY: This ITP signed off
39b92f6d-bd8c-5fee-93d7-93a88f1e2862 | note | IP
db6723a6-5067-511e-85bb-a320ad785e79 | note | RESPONSIBILITY: FH Foreman / FH Engineer
dcd81be7-581f-5080-ae76-06261c064e1c | textbox | DATE:
8ffec652-9c3e-574e-ba71-5f83f20f18b6 | checkpoint | 4.9 Alignment of layers not placed against concrete edge
f0a53d2d-0aac-599b-b3fd-b652d47dc8fb | note | FREQUENCY: During paving and at completion of work
385ee71b-b869-5e0e-abc2-4a83c8c8905a | note | ACCEPTANCE CRITERIA: Where asphalt is not placed against a concrete edging, the edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designated offset from centreline or design line. Within these tolerances, the rate of change of offset of the edge of layer shall not be greater than 25mm in 10 m.
63e041af-977f-5a67-ae68-f01def5952ab | note | REFERENCE DOCUMENTS: Cl 407.29 (iv) Drawings
f1a2f71e-dd11-53cf-bd00-d8b27f3ec6a0 | note | INSPECTION/TEST METHOD: Visual Inspection
9fb298b7-342f-5e01-b264-9cecdc792ad1 | note | RECORD OF CONFORMITY: This ITP signed off
5f38a854-5cd2-5479-a728-8ab9278287f5 | note | IP
184fd4fd-e473-5c50-8af3-6d06e2c7eccf | note | RESPONSIBILITY: FH Foreman / FH Engineer
f66462fb-97d0-53c7-ba8a-1a175d426320 | textbox | DATE:
6a4bf608-566d-505f-adba-80d8a44189a8 | checkpoint | 4.10 Width of layers not placed against concrete edge
8e0c5cb2-581b-5f20-9f75-6fe80e29d84e | note | FREQUENCY: During paving and at completion of work
d65294f3-ed63-5dcf-b6e7-a78f0cd6f044 | note | ACCEPTANCE CRITERIA: Where asphalt placement is not placed against a concrete edging, the width of asphalt layers shall not be less than the design or specified width of layer by more than 50mm or greater than the design or specified width by more than 100mm. The average width over any 300 m shall not be less than the design or specified width.
6b0f009e-8e55-56da-9f22-926da0653a95 | note | REFERENCE DOCUMENTS: Cl 407.29 (v)
03c1b870-2d1f-5530-b4cc-713a6b896d84 | note | INSPECTION/TEST METHOD: Visual Inspection
15df499a-9899-530e-8e14-608c432b7cb3 | note | RECORD OF CONFORMITY: This ITP signed off
c51270e7-b129-5169-8b79-b4ab2d4a258a | note | IP
d771e430-931f-59dc-82a9-c0c2e1aac47d | note | RESPONSIBILITY: FH Foreman / FH Engineer
3b53eb72-16fe-56b7-93e9-0e0ffcec1942 | textbox | DATE:
ec23590b-344d-5521-b978-7ef2ed8bd6cc | section | 5 - Spray Sealing
f286bbf8-9d97-5ec6-b185-97b852bd6bbb | checkpoint | 5.1 Rates of Application
5f84fe9d-a5b6-576d-bc84-94fb555a672f | note | FREQUENCY: Each lot
8c4ea38b-d5d5-5c26-a2ba-c905b0851e9d | note | ACCEPTANCE CRITERIA: Hold Point
b1b285ed-2fdc-5a52-953b-4f257ff75421 | note | ○ At least one week prior to the commencement of work, the Contractor shall submit the initial design rates of application for bituminous material, aggregate, and rates for pre-treatment for review by the Superintendent.
03fdea3f-81d0-58b4-bb3b-5c11dc73417d | note | REFERENCE DOCUMENTS: Cl 408.13 (a)
086ff9cc-099a-52c8-8327-63b9e93c440a | note | INSPECTION/TEST METHOD: Verify
cffb0f02-2138-5457-9d97-18b3a5646202 | note | RECORD OF CONFORMITY: Signed ITP
674981aa-44ad-53f9-a718-3b8ab810806e | note | HP
cdd67014-9d8d-579a-b340-d26ea3e4239f | note | RESPONSIBILITY: Site Engineer / QAV
dbf1650b-4d78-569b-b4c8-c6a93c7b829a | textbox | DATE:
439a9070-29c2-515e-8b5e-02f83d43edd8 | signoff | AUTHORITY HOLDPOINT
cdf33fff-ca47-505a-9cb6-d4f537c83011 | checkpoint | 5.2 Surface Pre-treatment
bd17fb53-822f-59dd-93ee-3c12a6545f30 | note | FREQUENCY: Each lot
ae6aab2b-7a70-55d6-833a-b7d08636ebeb | note | ACCEPTANCE CRITERIA: Surface pre-treatments to correct variable surface texture shall be allowed for and carried out as part of the works to meet the requirements of Surface Texture and Aggregate Loss specified in Tables 408.152 and 408.153.
5a913b29-193d-5f4d-aa93-309842894867 | note | REFERENCE DOCUMENTS: Cl 408.13 (b)
94f26fcb-bd05-5b0c-b837-9acfb80b9e88 | note | INSPECTION/TEST METHOD: Verify
0d79a9de-5e98-5d05-9e95-195d887a6d46 | note | RECORD OF CONFORMITY: Signed ITP
54f65954-21b4-5c83-b09c-1db3ac3a296f | note | IP
b5e3ffb8-124d-5f7a-a472-c9d9a3edaecd | note | RESPONSIBILITY: Site Engineer
94cf1a23-528c-5c6e-b4d5-0e963f3d2860 | textbox | DATE:
f356bd3b-0b61-595d-a417-592c6acba555 | checkpoint | 5.3 Calibration of Bitumen Sprayer
a7a7f7b9-820a-5278-b153-96b8675fa0eb | note | FREQUENCY: Prior to commencing works
7a17069a-c0f0-5de0-9b90-f0eac27f8a2a | note | ACCEPTANCE CRITERIA: All sprayers used for application of bituminous materials shall have a current Certificate of Calibration showing compliance with Austroads Test Methods AGPT-T530, and AGTP-T536 and renewed every 12 months.
928c899f-c3d6-5a0a-b7f1-ff1aef402809 | note | REFERENCE DOCUMENTS: Cl 408.07
80ace55b-750b-5f99-bac4-fc20df6732e7 | note | INSPECTION/TEST METHOD: Verify
dc39c35d-1fd5-5abb-af59-717f52a15061 | note | RECORD OF CONFORMITY: Signed ITP
d78c04bd-3e87-53d8-929a-edc9c88accc0 | note | IP
8fb2c2db-f175-5765-a356-869be64d02b0 | note | RESPONSIBILITY: Site Engineer
4f536d50-c0a8-5a67-9932-98210f2a1d74 | textbox | DATE:
942556dd-cfbd-527a-9166-36e0c82e964a | checkpoint | 5.4 Commencement of seal works
f562b4b1-d8f8-5cbc-a2f6-3645c3b63b34 | note | FREQUENCY: Prior to commencing works
8b2d5324-38a1-5096-adc3-463af65b9f24 | note | ACCEPTANCE CRITERIA: Hold Point
9b766401-8e06-5ea8-801e-43c2af7db175 | note | ○ Work shall not commence until the Contractor & Superintendent have agreed that the road or pavement surface is fit and ready for surfacing no more than 24 hours prior to the works occuring. For Periodic Resurfacing and Maintenance Works this includes patching and other preparatory works, and for the Initial Seals on Construction Projects the requirements of Standard Section 310 shall be satisfied.
344867b4-3647-5223-8472-f9f627cc6290 | note | REFERENCE DOCUMENTS: Cl 408.04
2785a4a0-1604-5940-b2a6-001a6ffd42af | note | INSPECTION/TEST METHOD: Verify
671fe475-64bf-56e3-9aef-99bfb4243a1c | note | RECORD OF CONFORMITY: Signed ITP
25a7d4a3-93a0-5ead-a524-a9906f883bb6 | note | HP
9b4da1c7-711a-5c56-9ec9-b3a5d1f5294d | note | RESPONSIBILITY: Site Engineer / QAV
d23b2a61-9e39-59fe-9cd6-a154d0529f05 | textbox | DATE:
d1efc9b8-663d-58bc-a382-fef2ad89d373 | signoff | AUTHORITY HOLDPOINT
e76dc21a-5bf1-5faf-bdd4-1fe378438a8e | checkpoint | 5.5 Commencement of seal works
b4715000-a8a2-5996-ba45-0ad30e929c5c | note | FREQUENCY: Prior to commencing works
ef25f30d-809c-5005-a782-9e4b12938d8e | note | ACCEPTANCE CRITERIA: Hold Point
e36a7f43-4ac6-50ac-aefd-fe5e797654b3 | note | ○ Written confirmation of the works that will be undertaken the following day and obtain agreement from the superintendent to any variation in the design rates of appliaction to those provided under clause 408.13(a).
9178cd20-5f7d-5674-a46a-18b2b05b82a8 | note | REFERENCE DOCUMENTS: Cl 408.04
e7313a36-68fe-5731-887f-f29412962135 | note | INSPECTION/TEST METHOD: Verify
c0061154-726e-50a2-8533-9ab6b0fed83b | note | RECORD OF CONFORMITY: Signed ITP
b7d02f6e-544d-5841-bf54-fe1a34710649 | note | HP
0fc4b798-5c8b-5aa4-8815-d9b1d6f37f76 | note | RESPONSIBILITY: Site Engineer / QAV
54523495-fb2d-5403-b6df-9dba68e7d688 | textbox | DATE:
9e0f2267-17ce-56b3-a38f-b0fd7c8f38ba | signoff | AUTHORITY HOLDPOINT
f425a4fa-288f-5770-85d2-5fe710c4dfcb | checkpoint | 5.6 Records
c1a87c42-88ea-5944-9de3-3cd8d744a6e4 | note | FREQUENCY: Each lot
18f96529-d3be-5ada-b494-a152719c1daf | note | ACCEPTANCE CRITERIA: Job completion report using the proforma included as Attachment A to Section 408, or an equivlant proforma as approved by the Superintendent, completed and submitted within 7 days of completion of sealing each job.
0198bef7-cd06-5e0f-ac5d-c45a665b93be | note | REFERENCE DOCUMENTS: Cl 408.17
342cf8ff-eae5-570b-96aa-dbc069408af6 | note | INSPECTION/TEST METHOD: Verify
731cab83-c598-5722-b7ed-4a1995d65b0d | note | RECORD OF CONFORMITY: Signed ITP
1abafca9-147b-52a7-b54b-4a1ab89f11d1 | note | IP
765aee05-9034-5b5b-98e1-ee6d5978e833 | note | RESPONSIBILITY: Site Engineer / QAV
061265c5-9e57-5484-a40a-d58c45ad87d9 | textbox | DATE:
0aa3a348-6db5-5833-b333-7fcfcad73528 | checkpoint | 5.7 Binder application rates
d3e1ca09-d818-554c-ac23-f6f8ba61cfff | note | FREQUENCY: Each lot
39adec4c-fe8d-5fa0-ba58-2dfd378ad495 | note | ACCEPTANCE CRITERIA: The Contractor shall produce evidence to show that the actual rate of application complies with the design rates of application. Variation between the actual rates and the design rates will be assessed in accordance with Table 408.151.
5c2048fc-674f-5d68-9628-907befa52cbf | note | REFERENCE DOCUMENTS: Cl 408.15 (a)
0abfa414-beb5-5166-bac5-564a23b42966 | note | INSPECTION/TEST METHOD: Verify
cfeda4d2-2a3d-5f94-8c93-84f49a023e3f | note | RECORD OF CONFORMITY: Signed ITP
2a5ce10b-fd14-5b89-a2a0-792453fb4d21 | note | IP
c247ffcc-ec71-5d50-b495-44f1bce8b42a | note | RESPONSIBILITY: Site Engineer
4c1ba79d-581f-5f1d-b99c-fb79d8f67e7e | textbox | DATE:
376c676b-ed21-5778-a1dc-6d3ddf0c8ee4 | checkpoint | 5.8 Surface Texture
e9b6449d-4d66-5aa2-9010-5ad8b4a98357 | note | FREQUENCY: Each lot
1536a972-b827-57d8-92a2-be4f560c4445 | note | ACCEPTANCE CRITERIA: Acceptance of work for surface texture and surface enrichment shall be based on visual assessment, or tested in accordance with VicRoads Test Method RC 317.01 and assessed in accordance with Table 408.152 if required by the Superintendent
a923d297-8585-564a-acb3-a77f9f619540 | note | REFERENCE DOCUMENTS: Cl 408.15 (b)
bd60abd5-01bf-5015-a235-5d7312d0edee | note | INSPECTION/TEST METHOD: Verify
73c2d937-f12b-5c63-b8d2-41de0e422382 | note | RECORD OF CONFORMITY: Signed ITP
a586ac26-33bb-5768-a8c4-6400a756798d | note | IP
27c1c61b-8413-5f0f-85be-a9ed3c20c0b5 | note | RESPONSIBILITY: Site Engineer
1c8c4ba9-a2d6-52f9-a743-5ab592c22a2f | textbox | DATE:
9a5aeec8-7828-584e-9084-9a5ea6c08077 | checkpoint | 5.9 Aggregate retention
6a54524d-a7c5-513b-8b40-971042fa03ad | note | FREQUENCY: Each lot
f5e6002a-40c8-57a9-ac0d-7443ce76f984 | note | ACCEPTANCE CRITERIA: Acceptance of work for aggregate retention shall be based on visual assessment, or tested in accordance with the VicRoads Test Method RC 317.03 and assessed in accordance with Table 408.153 if required by the Superintendent.
6732653c-aa51-5b50-9c3f-22318879cfb6 | note | REFERENCE DOCUMENTS: Cl 408.15 (c)
3831de35-205b-5721-8ffd-ed4489694877 | note | INSPECTION/TEST METHOD: Verify
48325a31-353b-5f34-8f02-8af66222cff8 | note | RECORD OF CONFORMITY: Signed ITP
98a17834-5673-5dd6-b753-3a66122b3985 | note | IP
55cb68ef-402b-54ad-a190-5c3c75039682 | note | RESPONSIBILITY: Site Engineer
b0e9b3f7-ecf1-5512-9f35-9eec67e290b3 | textbox | DATE:
0c3edd80-de3b-5ac2-9147-2be8a29762e6 | checkpoint | 5.10 Visual Uniformity
112685cf-3476-544d-8eaf-92ae56c1f294 | note | FREQUENCY: Each lot
d8232232-3caa-591d-a941-2e9fd6871f5e | note | ACCEPTANCE CRITERIA: Provide a surface with uniform colour, texture and consistent appearance
3f59cb67-7f2a-554c-bb61-2e17a1beafd9 | note | REFERENCE DOCUMENTS: Cl 408.15 (d)
404b9113-cd47-52d3-8ad3-9cd4c92f1b3b | note | INSPECTION/TEST METHOD: Verify
c266668d-e05b-5c82-ad4d-0fca065577b6 | note | RECORD OF CONFORMITY: Signed ITP
0d5a11cf-bd72-5e9f-be60-64779641ef28 | note | IP
d478320a-4506-5e84-8e4e-dc3e8906e756 | note | RESPONSIBILITY: Site Engineer
91fcc253-a25f-5353-9d5c-dc2bffa7139e | textbox | DATE:
5d372536-5ff0-5860-864c-67310663d3f9 | checkpoint | 5.11 Maintenance of seals
aac2a3d7-c24f-5e61-bd2d-d80a0863190a | note | FREQUENCY: Each lot
dbfc9156-510f-51be-8cf9-8a0294190834 | note | ACCEPTANCE CRITERIA: Hold Point
6223e4da-55be-5e39-a505-8c2b822e98ea | note | ○ The contractor shall be responsible for the monitoring and maintenance of seals from the time of application until the end of the defects liability period. The Contractor shall advise the Superintendent in writing of the proposed treatment to effect the above work before undertaking the work
becb4177-5452-57c9-ba91-fce39a9312b4 | note | REFERENCE DOCUMENTS: Cl 408.16
1af9c469-af8b-503f-9ce0-a3ec2b4359b8 | note | INSPECTION/TEST METHOD: Verify
fa35f33c-6c9b-5e90-aabe-91449bdc0c9f | note | RECORD OF CONFORMITY: Signed ITP
4414ec9c-d694-5a78-8b8f-bee710120748 | note | HP
c4c2c245-826e-578f-92d1-622afb36fb65 | note | RESPONSIBILITY: FH Engineer / Spray Supervisor / Superintendent
a3733765-8c92-5c4f-a54a-82ea0cdaa8c4 | textbox | DATE:
19269890-529c-573f-9ad7-d12c7d87c554 | signoff | AUTHORITY HOLDPOINT
62a72039-9427-5a9a-ab13-59ee778863e6 | checkpoint | 5.12 Maintenance of seals
6f16bed2-52f0-5870-a0ae-d3ed6832a7e2 | note | FREQUENCY: Each lot
3971561e-5075-5b78-9a2b-68a0fd2769f2 | note | ACCEPTANCE CRITERIA: The Contractor shall obatin the agreement of the Superintendent of the proposed treatment before undertaking the work.
d21f2bf7-ae5b-5d03-b658-440e1873e216 | note | REFERENCE DOCUMENTS: Cl 408.16
45f17edb-35c4-5748-9464-3d041c162656 | note | INSPECTION/TEST METHOD: Verify
2ff0f647-7e0f-56f3-ba24-9bedf9989b3f | note | RECORD OF CONFORMITY: Signed ITP
fe5b92f1-2e8e-5377-8e6a-925ad7e5ab93 | note | HP
9dedb990-17b3-51bf-b3ac-382cd01e2fab | note | RESPONSIBILITY: FH Engineer / Spray Supervisor / Superintendent
2208c765-b17f-5885-9bc6-af5de52ab904 | textbox | DATE:
6477687a-c323-5ea5-bea6-da88060f7459 | signoff | AUTHORITY HOLDPOINT
ddaa6927-dfb1-5e8b-a844-c0e33779ef10 | section | 6 - Testing
dff9bb81-61b5-5377-83fa-b6bd0bb636e1 | checkpoint | 6.1 Compaction of Asphalt layers
8b613938-1d09-5e7c-afae-18aaeec33685 | note | FREQUENCY: Per Lot
2aa9b1fc-6bf1-5acf-a5f8-ffb0d4ec78a0 | note | ACCEPTANCE CRITERIA: For layers <= 50mm, if characteristic density ration is:
042e016e-baf5-5b29-ba03-c5555aa52ed0 | note | • 95.0% or more - Accept Lot
14492da3-2760-5fa0-8cac-15d159240e6a | note | • 94.9% to 93.0% - Lot may be accepted at reduced rate
f6006e49-31ee-5856-8335-067139ac4844 | note | ○ For layers >= 50mm, if characteristic density ratio is:
2276849f-85bb-53f9-9e5b-b3b2813ec5eb | note | • 96.0% or more - Accept lot
149e3403-ce25-555a-b0cb-04782994d764 | note | • 94% to 95.9% Lot may be accepted at reduced rate
50620cb6-5c86-512f-86c1-48b66330f5ed | note | REFERENCE DOCUMENTS: Cl 407.27 Table 407.271 Cl 173.04
625c0c51-3bdb-504e-a21f-ee12d18d9f9d | note | INSPECTION/TEST METHOD: Verify
492ff300-fb86-53d1-a52e-e4eec40e5596 | note | RECORD OF CONFORMITY: Test Report
3bac5176-ab79-5647-a4fe-9a80055496a0 | note | TP
6ab1c57f-d805-5185-b03d-dea1b81d5999 | note | RESPONSIBILITY: FH Engineer/ Lab Technician
0c49ce3d-e7cb-5e68-be0e-11b750d169e6 | textbox | DATE:
9e28d996-d93c-522e-baa8-d9332efde8a7 | checkpoint | 6.2 Level Conformance for Asphalt layers
1190961f-51a0-51a3-a20c-6e6780a17856 | note | FREQUENCY: Per 4,000m2 at completion of work
f178bdc5-c0d9-574e-b4af-af561c33a026 | note | ACCEPTANCE CRITERIA: Individual departures from design not to exceed ±5mm with a standard deviation of ±8mm (Scale B)
e9739a65-9506-55ca-a5b2-8eacad31dcd5 | note | REFERENCE DOCUMENTS: Cl 407.29 Table 407.293
01533929-71b2-5e8d-a73a-2efc9cf9f829 | note | INSPECTION/TEST METHOD: Verify
18d3f177-7624-55b6-95d7-32784a5c0aa3 | note | RECORD OF CONFORMITY: Visual match existing / This ITP signed off
07a6058e-9260-5949-953b-7eff16ee2eb8 | note | SCP
e2e8d870-8bd4-5a15-afb9-63435371e2f4 | note | RESPONSIBILITY: FH Engineer/ Surveyor
320257c7-5005-5849-b62e-71f7c6683bf4 | textbox | DATE:
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
e187866e-0c32-5b43-880a-d83cc2fbc9d9 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
56a217b4-ddad-5e85-88fd-c5e0bd2345ac | textbox | Print Name:
3eef27a2-367b-5785-a22e-5f2839bfcab3 | textbox | Position:
8d2cf711-2dfb-5f96-ae97-47a7a04e4300 | textbox | Date:
a0c663c6-4171-59c1-b168-9abeb4fc1adc | signoff | Add Signature
7281e952-e25e-5f7a-8275-1d8852b4c162 | checkpoint-no-value | Table 407.171 Minimum Pavement Temperatures Prior to Laying Asphalt
5b520a18-4ad3-530b-b716-d3f298e68c86 | note | Asphalt Type ¦¦ Intermediate or Base Courses ¦¦ Wearing Course
e1cd95aa-ea07-558c-810b-379b0cd8eaed | note | – – – – – – – – – –
15422762-5a70-557e-b88c-e9e30ca1224b | note | All asphalt with a specified binder class of C170 or C320 ¦¦ 5°C ¦¦ 10°C
382350f2-2766-51b5-b540-21798a253ea7 | note | All asphalt with a specified binder class of C600 or containing a PMB ¦¦ 10°C ¦¦ 15°C
257cd6fa-4cfb-5ddd-8e41-bf4e4778f616 | checkpoint-no-value | Table 407.271 Limits for Characteristic Density Ratio (Six Tests)
48f4a7a1-9986-5819-8a84-2ce4085b8e0a | note | For layers less than 50 mm thick
a563e88b-e508-5639-937a-eaddfb96ab6f | note | Characteristic Value of the Density Ratio (Rc) ¦¦ Assessment
6371cbdb-ccf9-5b55-951d-7f0a6e582a29 | note | – – – – – – – – – –
d7f96ffd-de69-525e-9c69-638eff1ed499 | note | 95.0% or more ¦¦ Accept lot subject to no other nonconformances raised for the lot
bbb271d3-860f-5573-a7c8-6f82ae7518b0 | note | 94.9% to 93.0% ¦¦ Lot may be accepted at a reduced rate calculated by P = 15 Rc - 1325
01b3efc7-3979-52f3-8cbb-df1db2f047d0 | note | 92.9% or less ¦¦ Remove and replace asphalt
1dd463f8-bc26-507c-a3e8-c07713bc9d4b | note | – – – – – – – – – –
f286ba01-e0d4-5415-8236-fefd007827a1 | note | For layers 50 mm thick or greater
932ed2ca-a16b-559d-a991-e6b53898578c | note | Characteristic Value of the Density Ratio (Rc) ¦¦ Assessment
1b867551-991c-5e35-8e48-1b48163c022e | note | – – – – – – – – – –
8fd94fc9-1f80-5759-9f80-a2d3f621aea8 | note | 96.0% or more ¦¦ Accept lot subject to no other nonconformances raised for the lot.
27658de0-cc04-515b-8514-acab4d5136a9 | note | 95.9% to 94.0% ¦¦ Lot may be accepted at a reduced rate calculated by P = 15 Rc - 1340
b050102b-1f56-51c1-8725-3e67e6d31557 | note | 93.9% or less ¦¦ Remove and replace asphalt
b90812aa-fa7c-5133-a34a-ca1483c0d113 | checkpoint-no-value | Table 407.292 Minimum Number of Level Measurements per Lot
f51aa531-a3be-5a07-8700-f21de0ff1bb7 | note | Scale of Surface Level Measurement ¦¦ Minimum Number of Measurements Per Lot
87bfc630-aeed-56e6-823c-8052ea2a2914 | note | – – – – – – – – – –
15a594a0-c6b9-573c-b231-570caf7e02ee | note | Scale A ¦¦ 80
b69a9018-e555-5e57-9a01-29c393df7702 | note | Scale B ¦¦ 40
87ecdfc5-859e-5063-91fd-95b71aec18fe | checkpoint-no-value | Table 407.293 Mean Surface Level Tolerances for the Sub-base and Pavement Courses
2d55fa64-fa8b-5414-8e10-7ae7c12b9507 | note | Granular or Cement Treated Subbase: x̅ Range (mm) / Max. S (mm) ¦¦ Asphalt Layers: x̅ Range (mm) / Max. S (mm)
f90c28df-ab4d-567d-a611-d3a21fee77da | note | – – – – – – – – – –
b75f9568-f711-5a17-a837-7b3c94f4ced0 | note | Scale of Surface Level Measurement: Scale A
fe1a7e1f-e83b-504d-8fcd-382ce450df81 | note | +4 to -8 / 8 ¦¦ ±5 / 8
24727a43-e762-54da-b740-db8d52707016 | note | – – – – – – – – – –
156389ab-8d87-5f2e-9cb0-c97dc351d9c7 | note | Scale of Surface Level Measurement: Scale B
f74d5df0-aa62-50b0-bf98-872a2ec3b499 | note | +6 to -12 / 13 ¦¦ ±8 / 10
79de996b-f4c4-5765-b017-3b02c7a88f42 | note | – – – – – – – – – –
338c0242-5fda-5dde-bd09-d3ca0e681cc9 | note | Notes on Table 407.293
4657958d-2460-5648-999d-a2af996534c5 | note | x̅ is the mean value of all level readings taken in the lot (a negative value designates a measured departure below the design level and positive value designates a surface level above the design level)
e3d38d3e-4f0c-5275-bf4a-5ad589fb7a43 | note | S is the standard deviation of all level readings taken in the lot.
8f564eba-4531-55ec-932c-ede59be540ac | checkpoint-no-value | Table 408.141 Maximum Time Limit for Removal of Loose Aggregate
0b1d1e64-c84b-5a3f-bd58-4f0c7447902f | note | Traffic Volume (AADT) * ¦¦ Maximum Time Limit
2624a167-395f-5565-b330-550d57f586d7 | note | – – – – – – – – – –
2762a61b-0249-5c76-b74a-055b35cb5a04 | note | >5000 and all Freeways ¦¦ Within 8 hours of sealing
94d8eba2-a020-5f10-998b-bd55099340ef | note | >2000 to 5000 ¦¦ Within 24 hours of sealing
73adb0c9-42bf-5f84-a18d-0a99292d733f | note | >500 to 2000 ¦¦ Within 48 hours of sealing
1e3bfd21-5d2f-5c80-95d3-4a6e8ec3f8d0 | note | <500 ¦¦ Within 5 days of sealing
8c2c8610-e80a-5756-80ae-48a9fc9fbbd4 | checkpoint-no-value | Table 408.152 Surface Texture Requirements
333bcb96-7887-5b8f-8f23-0d44d75586bc | note | SINGLE/SINGLE TREATMENTS
980e54f1-0a52-5901-9c55-778cd1ce6398 | note | Mean Texture Depth (mm)
30c1ae94-7e0b-5404-8950-f010ac48255d | note | Size 5 :: Size 7 :: Size 10 :: Size 14 ¦¦ Action Required
690facc9-e3e9-543a-845c-418e1354014c | note | – – – – – – – – – –
cdb99ded-7e4f-507b-bad1-7d5b9079a233 | note | Treatment: Seals (All Types) (1)
ac3d4354-53d6-5239-81d0-5b9870b65f2c | note | 1.0 to 1.6 :: 1.3 to 1.8 :: 1.5 to 2.5 :: 2.0 to 4.0 ¦¦ Accept
48f5b95a-d0c2-5659-95f8-647e579daea7 | note | 0.8 to 1.0 or 1.6 to 1.8 :: 1.2 to 1.3 or 1.8 to 2.0 :: 1.3 to 1.5 or 2.5 to 3.0 :: 1.7 to 2.0 or 4.0 to 4.5 ¦¦ The Superintendent may require rectification of the works or elect to reduce payment for the lot by $1.00/m^2
539a6c00-96b6-5d7c-9b34-9478c4a00888 | note | < 0.8 or > 1.8 :: < 1.2 or > 2.0 :: < 1.3 or > 3.0 :: < 1.7 or > 4.5 ¦¦ Work to be rectified
8710dd4c-a77d-5a95-bb8c-23a09592f686 | note | – – – – – – – – – –
bf9acd3a-624c-522b-9240-e3056d7b23b4 | note | Treatment: Initial Seals (2)
ead9ca90-3d65-525e-82eb-ec8139474570 | note | N/A :: 1.0 to 2.0 :: 1.2 to 3.0 :: N/A ¦¦ Accept
4f066559-de8b-50a6-92e3-6fb2b1fd734a | note | N/A :: < 1.0 or > 2.0 :: < 1.2 or > 3.0 :: N/A ¦¦ Work to be rectified
2c7328f1-95b6-56ef-a674-7ff09ac8bfb1 | note | – – – – – – – – – –
f9991294-310c-5dee-8982-b3ea18b239d6 | note | Treatment: Surface Enrichment (1)
f5ce8ec6-ae5e-528c-9ea2-bda540de282e | note | N/A :: N/A :: 0.8 :: 0.8 ¦¦ Accept
c94d8789-803d-52ed-b04f-1e425b0de4b1 | note | N/A :: N/A :: < 0.8 :: < 0.8 ¦¦ Work to be rectified
11dc0293-b814-51d7-99e2-9a2577750af9 | note | – – – – – – – – – –
3a7b05cf-8ffb-5c5e-a8fd-217120a2ffac | note | DOUBLE/DOUBLE TREATMENTS
6a820f0d-7294-51cd-ba4c-b875b00b3687 | note | Mean Texture Depth (mm)
bd4a0a5a-9c55-5ec2-ad8a-027668950082 | note | Size 10/5 :: Size 10/7 :: Size 14/5 :: Size 14/7 :: Size 20/7 ¦¦ Action Required
bc5589e0-e00d-5a1a-8ebd-87bd935bf0d4 | note | – – – – – – – – – –
523de091-9403-5344-a334-ead2a0df670f | note | Treatment: Seals (All Types) (1)
e22f0e9a-c516-5a5b-a0cd-563c8adbaf2d | note | 1.3 to 2.1 :: 1.3 to 2.2 :: 1.3 to 2.4 :: 1.3 to 2.4 :: 1.4 to 2.5 ¦¦ Accept
ccd69a9c-5172-50e9-a78d-dc738b336ebe | note | 1.2 to 1.3 or 2.0 to 2.3 :: 1.2 to 1.3 or 2.1 to 2.4 :: 1.2 to 1.3 or 2.4 to 2.7 :: 1.2 to 1.3 or 2.4 to 2.7 :: 1.3 to 1.4 or 2.5 to 2.8 ¦¦ The Superintendent may require rectification of the works or elect to reduce payment for the lot by $1.00/m^2
fa65ecf7-ef45-569f-a218-e8869fd7fae6 | note | < 1.1 or > 2.3 :: < 1.1 or > 2.4 :: < 1.2 or > 2.7 :: < 1.2 or > 2.7 :: < 1.3 or > 2.8 ¦¦ Work to be rectified
b302f73e-c360-5a4e-b345-75b0ff070857 | note | – – – – – – – – – –
d080db5f-9e1f-539f-b64e-b7ec13631258 | note | Treatment: Initial Seals (2)
ad6a61ac-cec9-5f90-9734-2804530311d6 | note | 1.0 to 2.0 :: 1.0 to 2.0 :: N/A :: N/A :: N/A ¦¦ Accept
10d18ac4-14e3-555e-837a-dbc8a0ed4530 | note | < 1.0 or > 2.0 :: < 1.0 or > 2.0 :: N/A :: N/A :: N/A ¦¦ Work to be rectified
0e80b2d3-dfb1-58bd-a89a-d55bc3923030 | note | – – – – – – – – – –
1f4b42dd-5972-5fa3-8351-3b2c95a7e55e | note | Notes:
f8b03e2c-8fcf-5929-9e9a-e7587cad93c0 | note | (1) Surface texture measurements for sprayed seals and surface enrichment may be undertaken at any time during the Defects Liability Period, but final acceptance of works is not affected until the end of the Defects Liability Period.
1d352828-1919-581c-b66d-9d8cf145f521 | note | (2) Surface texture measurements for initial seals shall be undertaken between 10 and 15 weeks after placement. If tests are not undertaken in this period and later test results require the works to be rectified, the later test results are to be used for acceptance of the works.
cd7b550c-7c3d-5200-a2c0-025ed5af7300 | checkpoint-no-value | Table 408.153 Assessment of Aggregate Retention
659116e6-2339-5c1d-b0b5-69e76b47b264 | note | Degree of Aggregate Stripping ¦¦ Action Required
350b575c-9693-5886-b2dc-ed58c44238a1 | note | – – – – – – – – – –
696d5fc0-56b9-5e69-86a2-e1608804f3f8 | note | 0 to 2 ¦¦ Accept
22713e3d-9a5f-5bc7-b00e-f074042a87f6 | note | 3 to 5 ¦¦ Work to be re-tested within one month prior to the end of the Defects Liability Period. If the Degree of Aggregate Stripping has increased since it was last tested, the work shall be rectified before the end of the Defects Liability Period.
05f5326f-5f94-5703-85be-e129af22fdae | note | Greater than 5 ¦¦ Work shall be rectified within 5 days.
c98588a5-c3d4-565a-a8bb-c60778f2a886 | note | – – – – – – – – – –
b46346fe-5eb7-5eb5-89de-1f9b888ab7da | note | Note: Aggregate retention measures may be undertaken at any time during the Defects Liability Period, but final acceptance of works is not affected until the end of the Defects Liability Period.
e36fb361-b0c3-5111-8f03-c7af452c7543 | checklist | ITP - Unbound Flexible Pavement Construction Rev0 | itp | ITP - Unbound Flexible Pavement Construction
56f12a57-1e96-5877-8041-0f0eb46d12c8 | section | 1 - Preliminary Works
8cd47aa7-19e4-55e7-9939-09ffbf3c7b11 | checkpoint | 1.1 Check for correct documentation
c6398249-f9a9-5b90-972b-75222a199fb5 | note | FREQUENCY: Prior to commencing any activity
7059cf4c-6bb0-52c2-920b-79d5989ef903 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
944b5e0f-b16a-5d8a-afe2-8379cdf3612d | note | – using the correct and complete set of drawings
7c77b366-01c1-527b-8dd6-f1e5d5caa6c8 | note | – all drawings are the latest revision
41fe83c5-7661-5abd-8e40-50bc46026657 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
7d0b3fef-f0a4-5248-b90a-81ad39c587fa | note | INSPECTION/TEST METHOD: Visual inspection
07a479d1-fff8-5981-a6ca-fad5f9a36c14 | note | RECORD OF CONFORMITY: This ITP signed
d2942df1-1654-5e9c-9743-6b24960fcf3b | note | HP*
09277241-96fa-554f-b6a7-c026fa07037a | note | RESPONSIBILITY: Site Engineer
43e340cf-d9f0-5c48-b07d-cff316c654c3 | textbox | DATE:
d449b8cf-898e-5370-baf3-dd4ee4fe4f96 | checkpoint | 1.2 Material Classification
fc6dd005-d61a-569e-81d7-577f048c2354 | note | FREQUENCY: Prior to commencing works
f089999a-7820-5c1e-9d3d-40b15c03bb87 | note | ACCEPTANCE CRITERIA: Hold Point:
ce1908b2-f873-5bb8-81d4-ad93506392d5 | note | ○ All crushed rock proposed for use shall be current registered mixes in accordance with VicRoads RC500.02 and conform to specified requirements applicable to that class of product
af70da0c-9fe8-5457-a633-65f98987b4c9 | note | REFERENCE DOCUMENTS: 812.04 VicRoads RC500.02
321cb2e4-4ae8-5d24-bbd1-ab60b687e4ef | note | INSPECTION/TEST METHOD: Document Review
ea260407-6f9d-59de-a829-d30a6df8163a | note | RECORD OF CONFORMITY: This ITP signed
d32a18a4-64ae-5d60-b950-78a9c07d0a72 | note | AP
ed4c045c-f5e6-5c60-aa72-eca5d5ff9882 | note | RESPONSIBILITY: Site Engineer / QAV
ee6d705c-0f90-5e05-bbf4-37f54d46aa92 | textbox | DATE:
75521530-3b3d-5f1c-94af-bbaacaccc991 | checkpoint | 1.3 Implementation of all measures and controls
5be76739-6a07-5892-b885-1f0ecf8dc319 | note | FREQUENCY: Prior to commencing works
ebc6632f-6d02-5e47-98b0-a388d04474ad | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP`
a7719349-47a2-50a5-8968-837f8113c45f | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
df875b8a-a9c8-5b08-9072-a443035905c5 | note | INSPECTION/TEST METHOD: Visual Inspection
e88471aa-8398-51dd-a349-18b535df9b3d | note | RECORD OF CONFORMITY: This ITP signed
a625da13-f862-523e-bddd-5bd89070ca11 | note | HP*
7cabfe0b-7c0a-5662-a03d-52230f7eac9c | note | RESPONSIBILITY: Site Engineer
a7aadbc8-1b6f-53e9-a731-f827f9f39821 | textbox | DATE:
3ca0a106-d7b2-5ce2-a462-605891139018 | checkpoint | 1.4 Plant and Equipment
80039990-616f-5ef9-bd12-03364b275bfb | note | FREQUENCY: Prior to commencing works
fc609099-3e50-5ea0-8132-30c4898d0e8d | note | ACCEPTANCE CRITERIA: Plant and equipment used in the Works are appropriate to achieve specification requirements and is inducted
e7c02c2f-e278-55e6-a14e-26190e4aa8ab | note | REFERENCE DOCUMENTS: N/A
8be7150b-f17d-5f77-ac77-41dfe016f964 | note | INSPECTION/TEST METHOD: Visual Inspection
fbb1d845-cc7a-5f33-aee9-acca5ceb0c45 | note | RECORD OF CONFORMITY: This ITP signed
8d148387-f206-54ee-8a95-9099b20bdf7e | note | IP
c7e23a8d-0f06-5d6e-8d17-c8deadc2340c | note | RESPONSIBILITY: Site Engineer
34649f6e-caab-535f-8514-4995e8db2978 | textbox | DATE:
b2c17757-337a-5ba5-8bf8-5c53302c17e3 | section | 2 - Placement
df4d8ebe-adc0-58bb-adf8-9df6e547cda5 | checkpoint | 2.1 The commencement of construction of base and subbase
4e9f8aaa-f949-5709-8910-e3c4cea8be76 | note | FREQUENCY: Prior to placing subbase
a4fbea7c-e65c-5ebb-9b1b-77d91da9af69 | note | ACCEPTANCE CRITERIA: Underlying ITP signed off
b282747b-ec75-596b-91ef-21a224f0682a | note | ○ Identifying and removing soft areas to a minimum of 200mm depth. Underlying layer shall be clean of all foreign matter. The edges of previously placed materials shall be watered. Proof roll underlying layer prior to commencing
86c270eb-ffc7-56de-b2bb-50fec93e2291 | note | REFERENCE DOCUMENTS: Drawings
aaf06cc1-caea-5713-9ba8-0e7572cb0736 | note | INSPECTION/TEST METHOD: Verify
ae74e797-daa3-533b-a53a-85f679f6ad0a | note | RECORD OF CONFORMITY: This ITP signed
f0cf0231-ae4c-5620-9db5-28284986e8c6 | note | IP
e1a89533-0751-5914-965f-8f3d98ca7f7b | note | RESPONSIBILITY: Site Engineer
d4140099-5157-5ff1-94be-26890d34aca4 | textbox | DATE:
b438f38f-9925-584f-9c80-af0a21fabade | checkpoint | 2.2 Delivery Dockets
cc46f891-9d18-5dc9-9805-b68472995528 | note | FREQUENCY: Each lot
a774fb6d-0b43-56c7-b5e4-c935d10b539b | note | ACCEPTANCE CRITERIA: Where material is scheduled for measurement by loose volume in delivery vehicles or by mass, a delivery docket for each load shall be issued to the Superintendent at the point of delivery.
2afc10e1-d093-5372-b236-9c8983a6f0fc | note | REFERENCE DOCUMENTS: –
e09f9600-55b6-5e26-af24-a175f7bc833b | note | INSPECTION/TEST METHOD: Verify
520fb827-fe31-5f92-94fe-a0dd5c51ac48 | note | RECORD OF CONFORMITY: This ITP signed
b9968940-7ce9-52aa-a42b-30f122cba730 | note | IP
aff6a056-a24e-5f4b-a7ff-6c53a104f8d8 | note | RESPONSIBILITY: Site Engineer
72a1a068-e1cc-5340-94e1-3e6499b74f07 | textbox | DATE:
aaf1c964-0de4-5230-8ec9-90bac16fdf12 | checkpoint | 2.3 Layer Thickness
6eac5ed2-6abd-52d7-86ca-03d94b198dad | note | FREQUENCY: Each layer
31e059ed-5b40-5cc8-96cf-89f8fa60a28f | note | ACCEPTANCE CRITERIA: Material is to be compacted to the overall thickness shown in the drawings (dependent on pavement type), subbase not less than the specified thickness by more than 15 mm
dd5d6cc5-e380-5c29-b4c9-242c74650510 | note | REFERENCE DOCUMENTS: Drawings and 304.06(c)
ca984352-e0cc-57cb-9a97-0f14f1a93ab5 | note | INSPECTION/TEST METHOD: Visual and Measure
c446ec31-cec3-503b-a872-e4b567b2cf5f | note | RECORD OF CONFORMITY: This ITP signed
698385e8-3334-56a0-adb0-66ecb2ff6f5e | note | IP
074334de-3f36-5052-9edb-467ea1d745ed | note | RESPONSIBILITY: Site Engineer
79d378db-835a-5418-83f8-a109840942fd | textbox | DATE:
fe0087fd-9d99-5049-a942-da3d2aecde1e | checkpoint | 2.4 Conformity with Drawing
54fa00dd-9f39-5f9a-a245-10f69844497c | note | FREQUENCY: Each lot
17c663bd-3c66-5f7f-9a4f-3d871d6ad1a8 | note | ACCEPTANCE CRITERIA: Width of each side of the pavement shall not be less than the specified offset width or more than 50 mm outside the specified offset width when measured at right angles from the centre line or design line.
868b1643-2735-5779-8c3c-478e0e6e0f76 | note | ○ Where pavement is to be constructed to the lip level of kerb and channel, it shall be constructed flush with the lip of the channel or not more than 5 mm above.
7e2d7735-3f29-5944-b3d6-36b26e209b9c | note | ○ Any material that has been compacted and then trimmed from the compacted surface to conform
eedb79b0-97f5-5cbf-a7a9-f80e5689f8e7 | note | REFERENCE DOCUMENTS: –
2e86c5fd-1b9b-5013-a00c-f31889eaf003 | note | INSPECTION/TEST METHOD: Verify
d40db8a3-08d9-5085-9f6d-0f0ace372779 | note | RECORD OF CONFORMITY: This ITP signed
bcb92259-9972-5060-8d80-a7611f61990a | note | IP
aee7cedd-1174-5234-8339-83223877cc65 | note | RESPONSIBILITY: Site Engineer
4d44e8c9-3781-50cf-bbaa-3bd72653654f | textbox | DATE:
4dc97c3b-ac61-5cb3-b8e0-151b03336db8 | checkpoint | 2.5 Jointing
d68ae229-c194-5d98-8b7e-f3c85b3ded73 | note | FREQUENCY: Each lot
4fddde64-4cd2-563e-881d-c80e775d4d15 | note | ACCEPTANCE CRITERIA: (a) material shall be spread in such a manner as to minimise the number of joints
1b6961eb-ccfa-5c04-8faa-646ab647d4a8 | note | (b) transverse joints shall be offset from one layer to the next by not less than 2m
e141124e-9a20-5265-9717-dd4ccf33e583 | note | (c) longitudinal joints shall be offset from one layer to the next by not less than 150mm.
447dd349-f271-5b3e-b56c-5e8efcb64ea3 | note | (e) longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane.
0cf9b080-5bca-5bd4-a346-109f48181b82 | note | REFERENCE DOCUMENTS: 304.07
d19dee21-c426-5ace-b3b2-c2200d024e86 | note | INSPECTION/TEST METHOD: Visual Inspection
709904d0-96dd-507f-a561-47d295fe70af | note | RECORD OF CONFORMITY: This ITP signed
0d6d803c-451a-5702-9a5f-ce3b259af846 | note | IP
1a9f6968-6fe6-59bb-bfc9-fa3bc664016b | note | RESPONSIBILITY: Site Engineer
528e6720-8b61-5cdb-8c5c-5064575ddae1 | textbox | DATE:
5145022f-ae73-58b1-8629-bba74142f27e | section | 3 - Testing and Conformance
cfe0a29c-d34c-5c24-a78c-c6a958a83923 | checkpoint | 3.1 Determine Testing Scale & Initial testing frequency
263cfe93-cbbd-5b70-ac54-faad9e8acc41 | note | FREQUENCY: Prior to Testing
da8d8119-5be5-5ab3-943f-935980eadaef | note | ACCEPTANCE CRITERIA: Where testing is specified in Clause 304.10(c) or (d) and Clause 304.12 requires it to be Scale B, the first lot of each pavement course shall be tested for post-compaction grading and PI.
4c199292-4184-5b85-97e3-14445dc04789 | note | ○ If the first lot each pavement course satisfies the specified post compaction requirements in Clause 304.10(a) and (b), as applicable, no further post-compaction testing will be required for that pavement course.
2b487ca8-e9a2-5401-8246-054cbfbe537d | note | REFERENCE DOCUMENTS: Table 204.161 304.10 (c or d) 304.10 (a) 304.10 (b)(ii) Table 304.101 Table 304.103 304.11 (c) (ii)
5cc9a097-8c18-5a58-be70-971888f98ecc | note | INSPECTION/TEST METHOD: Document Review/ Site Inspection
b50d4367-1b53-5ade-a5f6-254ac013e69c | note | RECORD OF CONFORMITY: This ITP signed
aff8812a-8ff0-55fe-bc27-c96a95ea6b2d | note | AP
1a0bd384-a5c5-53bc-9f1d-d7c6ca9382d3 | note | RESPONSIBILITY: Site Engineer
0176cbcd-99e8-537b-8fd7-f3edcf412e7e | textbox | DATE:
0fc1c96e-06da-5d4a-9415-fa9410bbda3d | checkpoint | 3.2 Post Compaction Testing
30ae342a-a3a5-5415-aa5b-4c0d0d496404 | note | FREQUENCY: Each Lot 304.10 (a) & (b)
21f3a830-0846-5991-93bc-0d64171ea097 | note | ACCEPTANCE CRITERIA: If the first lot does not meet the requirements specified in Clause 304.10(a) and (b), the Contractor shall then seek approval from the Superintendent before work proceeds.
be8dd27d-9481-5e06-b613-1f7d1abf045c | note | REFERENCE DOCUMENTS: 304.11 (c) (ii)
c4e92739-ed57-55ce-a42e-670b1d1a1835 | note | INSPECTION/TEST METHOD: PI
03ec4906-5c74-5c39-8195-598bde180831 | note | RECORD OF CONFORMITY: This ITP sIgned
7b6aac28-26bb-5ad1-bfca-295aeb63cb62 | note | HP
948e4d24-5e2a-571e-8c94-edd1b189e8a9 | note | RESPONSIBILITY: Site Engineer
c4bfbc42-f363-55df-867b-65edc36ea524 | textbox | DATE:
bfdc3ade-3a20-5d39-bd24-08101103981c | signoff | AUTHORITY HOLDPOINT
3e4abe6d-9aee-5722-9069-2cd9902cbc63 | checkpoint | 3.3 Test Rolling
07b3bea1-936d-536c-839a-c02e9e4bc087 | note | FREQUENCY: Each lot
84c3a2cc-c606-565f-9b97-ee279ae5791d | note | ACCEPTANCE CRITERIA: Hold Point:
20d6b12c-b4ac-558e-98f5-f6d0eaf260a5 | note | ○ All pavement layers shall be compacted to withstand rolling and shall be test rolled in accordance with Section 173, prior to acceptance of the layer.
860cced8-badc-54de-a54b-39b5f299f660 | note | REFERENCE DOCUMENTS: 304.08
0df7e326-5f4a-5f96-afed-df3896f321f9 | note | INSPECTION/TEST METHOD: Test Roll
305f5e2f-ef60-5eab-bc5b-79609d46033e | note | RECORD OF CONFORMITY: This ITP signed
efda61f8-1ebe-5f40-b9e2-d60f338228c8 | note | HP
ecb52887-b4dc-597c-a126-66074b351422 | note | RESPONSIBILITY: Site Engineer / QAV
41e0aca4-8316-52b1-967c-c849ef8c8068 | textbox | DATE:
68eb34f8-aaa5-5556-88b0-012859a6a9a6 | signoff | AUTHORITY HOLDPOINT
c32000f8-1164-5a24-8e98-73afe3a47cfa | checkpoint | 3.4 Compaction Testing
9dbd9700-9122-5db1-a115-b8379562b35e | note | FREQUENCY: Every Lot, Every second lot (reduced frequency)
ba3ec50c-62ce-5695-8879-49b8ae3b8372 | note | ACCEPTANCE CRITERIA: The calculation of density ratio shall be based on tests performed using Modified compactive effort. The work shall be assessed for compliance with Scale B requirements for testing and acceptance of compaction as specified in the table below
1a5b0d93-0043-561e-8fc7-f261eff11635 | note | – – – – – – – – – –
4daf1fcb-aae4-5230-94f8-8955baaa124d | note | Characteristic Density Ratio % (six tests)
3002809b-f761-57b3-a9a9-b7a2a0646513 | note | Lower Subbase Layers ¦¦ Upper Subbase Layers ¦¦ Base Layers: Layer directly beneath the Bituminous Surfacing ¦¦ Base Layers: Other Layers
d74db173-addd-5edb-bb97-f355c03014e5 | note | – – – – – – – – – –
5a500729-49db-545e-96f0-949b58bb54d3 | note | ○ Compaction Scale: A
c955d89f-5d55-5cec-82c2-4eead873f294 | note | Not less than 98.0 ¦¦ Not less than 98.0 ¦¦ Not less than 100.0 ¦¦ Not less than 99.0
d16ea8c7-2516-5cb7-a0e1-650299e2dfa5 | note | ○ Compaction Scale: B
3cd1696b-b375-5fec-b3a8-ab205a35a138 | note | Not less than 97.0 ¦¦ Not less than 97.0 ¦¦ Not less than 98.0 ¦¦ Not less than 98.0
61535c46-d4c2-5e17-9e4f-6929990d4144 | note | – – – – – – – – – –
3719158d-6419-5dab-bca0-6d4a66cba4ca | note | REFERENCE DOCUMENTS: 304.08 Table 304.061 304.11 (b) Table 304.111
656bb10f-9ebf-549c-9852-0e900ba2814c | note | INSPECTION/TEST METHOD: Test point
67b1d0b1-6bdb-59c2-bfa2-5e47d414c470 | note | RECORD OF CONFORMITY: This ITP signed
f1103766-7281-5955-b805-2bd3abf5c7ab | note | TP
8b22f1a4-0b42-54a9-b085-97eb8032e52a | note | RESPONSIBILITY: Site Engineer
05fa1039-a5c1-5822-8ed9-880a5036fa0a | textbox | DATE:
e38f1f36-47be-51d7-bb91-c3b0873378ef | checkpoint | 3.5 Post Compaction Testing
dd59006c-624d-5edf-befc-ba59abe3e988 | note | FREQUENCY: Refer to table 304.111 for various minimum frequency or testing for Grading and PL
01f81722-e8d4-5d72-bd5a-4dd1c032b851 | note | ACCEPTANCE CRITERIA: If specified in Clause 304.10(c) or Clause 304.10(d), following completion of compaction, material shall be tested for post-compaction grading or Plasticity Index (PI) at the frequency specified in Clause 304.11 for the appropriate Scale of Testing specified in Clause 304.12(a).
54e0cf80-de51-5d25-930c-adcba71077d6 | note | REFERENCE DOCUMENTS: 304.10 Table 304.101
cc6b4909-b0c1-5ac5-a1d4-330eb42bf1fa | note | INSPECTION/TEST METHOD: Test point
3a237fa5-95e4-5a2f-8208-d2fd50ad2fce | note | RECORD OF CONFORMITY: This ITP signed
dc87989a-3362-5630-870f-7d244b2e1ee2 | note | TP
8ee674bb-b5a9-5d26-a7b1-adbb15f56129 | note | RESPONSIBILITY: Site Engineer
447aeb45-de7f-544c-b77d-02982eb0bf42 | textbox | DATE:
f700622d-8137-51da-93f5-2c69138e21db | checkpoint | 3.6 Shape
d07fdb02-5ef9-5746-a5e2-331239b97b11 | note | FREQUENCY: Each lot
de22be02-a053-5d76-86fc-301a71a9708a | note | ACCEPTANCE CRITERIA: Layer to be finished to a smooth and uniform surface and after compaction shall have no point deviation > 8mm from 3m straight edge. The subbase shall also not be less than the specified thickness by more than 15mm
ddfadaf0-7d61-5391-9498-9cdf966b0be5 | note | REFERENCE DOCUMENTS: 304.06(b, d, i) Drawings Table 304.062
ba8c5b67-8ea3-553c-9ec9-41abb88f58dc | note | INSPECTION/TEST METHOD: Survey
f76cf3af-9562-5c04-ab11-e970a876b4f1 | note | RECORD OF CONFORMITY: This ITP signed
90c4de1b-4571-5807-a642-239b212b1d1e | note | IP
3575f03e-0ce9-5bc6-8119-c0a213e18eaf | note | RESPONSIBILITY: Site Engineer
0b0ff9e8-d416-571e-afb0-d92628950151 | textbox | DATE:
7bd6111c-78fa-5cd8-9028-0fb8f58b3779 | checkpoint | 3.7 Completed Surface Level Compliance
0aa2bd2a-34f1-5c30-b8b8-05caeabca202 | note | FREQUENCY: Each lot
f9c5f478-f3ce-5ead-874a-1d0412399ee5 | note | ACCEPTANCE CRITERIA: Each level measurement shall be taken at random locations over the area of the lot in accordance with the VicRoads Test Method and the number of measurements taken within each lot shall not be less than the number specified in Table 304.061.
6c1d4f5e-9be7-58e4-b99a-d14b8310fa2c | note | ○ The mean and standard deviation of the departures from the design surface level for the pavement courses at their respective levels within each lot shall meet the requirements of Table 304.062.
026cdf10-366f-5496-aab0-a2e81edcc59b | note | – – – – – – – – – –
f77675c7-65d6-58e8-bfdf-433328bd23bb | note | Table 304.062 Surface Level Tolerances for the Pavement Courses
33f9d3af-6e84-51ca-920e-03b7fd0703e3 | note | – – – – – – – – – –
5e0c1834-002a-5598-8b40-9854fcf657bf | note | Scale of Level Measurement: Scale A
a15039f9-c693-5ca2-b8ba-2ffc9a3bbc41 | note | Lower Subbase: x̅ Range (mm) ¦¦ Max. S (mm)
c32486b3-d1ea-5eb8-9c3c-8b1b427ef9f8 | note | +6 to -10 ¦¦ 10
d37b4f76-a47d-5e2d-90fe-49d3695d9aa1 | note | Upper Subbase: x̅ Range (mm) ¦¦ Max. S (mm)
47079b0f-132d-5fb7-99ae-b36d362b54e1 | note | +4 to -8 ¦¦ 8
6631f63e-10c7-5155-9d5b-4983b21d64a8 | note | Base: x̅ Range (mm) ¦¦ Max. S (mm)
1f68c3b6-fdab-5b2d-91c6-2f8f73c5bc4c | note | ±5 ¦¦ 8
048b0dd8-fc41-5f97-97f5-dfb9df96e0fb | note | – – – – – – – – – –
392c4098-d766-58c0-a17d-fb9622b80db2 | note | Scale of Level Measurement: Scale B
07ed34ad-3485-51c6-9614-73861ace54c3 | note | Lower Subbase: x̅ Range (mm) ¦¦ Max. S (mm)
062719f7-a023-5694-b25a-b1f9f5645040 | note | +8 to -16 ¦¦ 15
fc509d74-151c-5cbf-bf31-67c9988b8f74 | note | Upper Subbase: x̅ Range (mm) ¦¦ Max. S (mm)
bce9f6a0-014a-5738-95a4-b94b98f77149 | note | +6 to -12 ¦¦ 13
610bc85a-3c3a-5872-a423-4a2ab7db77d1 | note | Base: x̅ Range (mm) ¦¦ Max. S (mm)
707a3243-1908-54e1-91ae-7931bd9db429 | note | ±8 ¦¦ 10
de1d4d7a-182f-5584-b90f-eaa6960ce16e | note | – – – – – – – – – –
3447661a-bce4-5631-9078-eb20fecbc44d | note | Notes:
2c2465e7-ce7c-58cd-844e-118c99b7c3c2 | note | 1. x̅ is the mean value of all level readings taken in the lot
3b8139c2-9e57-5b10-a546-61dce40ac35b | note | 2. S is the standard deviation of all level readings taken in the lot
b5a5a575-a1d4-5520-b0a9-2ccf5d0661ff | note | 3. A negative value designates a measured departure below the design level and positive value designates a surface level above the design level
20d66477-c45f-533c-82de-7182b725158b | note | – – – – – – – – – –
f9bee490-a9de-57de-8848-ce722ec6628a | note | REFERENCE DOCUMENTS: 304.06(b) Drawings Table 304.062
4df09d3b-8546-5165-a0c0-c926d762c7eb | note | INSPECTION/TEST METHOD: Survey
4a56aac2-1e67-57be-9da4-6be616bb3860 | note | RECORD OF CONFORMITY: This ITP signed
880b3681-c876-5ae1-83c2-f2d211ac67ed | note | SCP
23642d29-01c8-56bb-a65f-1bca9ba0cc0b | note | RESPONSIBILITY: Site Engineer
3a335967-9944-5ec1-818d-53cd63b1e12a | textbox | DATE:
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
21d373ec-67ab-5fec-a321-00686c690984 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
c9b5e644-645d-58fd-bcd5-3949105bbf75 | textbox | Print Name:
00d9fafa-a140-59a0-b067-e2de40e77c69 | textbox | Position:
4f5689f7-baad-5983-9a4b-1f1d3ca57c6c | textbox | Date:
a0c663c6-4171-59c1-b168-9abeb4fc1adc | signoff | Add Signature
f0dc6815-a506-5c61-968b-b5ee0266d8a4 | checkpoint-no-value | Table 204.161 Schedule for Surface Tolerance, Material Properties and Compaction Testing
d8b47f00-a0f4-5849-9882-252a242ec2b9 | note | Road Name ¦¦ Chainage/Location ¦¦ Scale of Surface Level Measurement (A, B or C) ¦¦ Scale of Material Property Testing (A or B) ¦¦ Scale of Compaction (A, B or C)
02ec9a7e-fc7f-5081-a8c0-f013297bbbac | note | – – – – – – – – – –
ca85cf57-337d-56f9-b238-76b5aac8ab0c | note | Bruny Island Main Road ¦¦ Within Limits of Works ¦¦ B ¦¦ B ¦¦ B
42089e81-a44f-5676-90bf-0b23a906fd51 | checkpoint-no-value | Table 304.081 Acceptance Limits for Scale A and Scale B Standards of Compaction
88377ef5-ba52-5edd-9418-b51dad45b4f6 | note | Characteristic Density Ratio % (six tests)
46e3b38c-9a30-54ed-abf5-d3eac22af680 | note | Lower Subbase Layers ¦¦ Upper Subbase Layers ¦¦ Base Layers: Layer directly beneath the Bituminous Surfacing ¦¦ Base Layers: Other Layers
0efb62e8-9904-53ab-b428-0a8c8969f1f4 | note | – – – – – – – – – –
5382a076-a98a-5ddf-a590-692d28d153fb | note | Not less than 98.0 ¦¦ Not less than 98.0 ¦¦ Not less than 100.0 ¦¦ Not less than 99.0
cc58adf2-d6d8-5f09-9661-0005fa605354 | note | Not less than 97.0 ¦¦ Not less than 97.0 ¦¦ Not less than 98.0 ¦¦ Not less than 98.0
792a3c8d-d3eb-54bb-a992-d86aa261b4d2 | checkpoint-no-value | Table 304.101 Post-Compaction Grading Requirements for Crushed Materials
807659ab-79a9-5700-aba9-adf9a22d30d3 | note | Post-Compaction Grading Limits (% Passing by Mass)
279c0a74-6577-59b0-b019-2962e5584211 | note | – – – – – – – – – –
912ee43e-d807-5b5b-a7ae-9398516d8a1d | note | Class 1 or Class 2 Crushed Rock
52cd748e-556d-56c8-af46-36ab34224603 | note | Crushed Scoria Base
ee5fce6f-2678-5d6d-91fd-f85afe468d2e | note | Class CC2 Crushed Concrete
1973547b-a835-54ca-b6c2-46f930424445 | note | – – – – – – – – – –
194284a6-7605-5c91-aa88-4686ff7a626c | note | Sieve Size ¦¦ Nominal Size (mm): 20
997f9db3-475e-58ff-945c-4af30840155f | note | – – – – – – – – – –
ed77b85d-ca7c-56c9-8808-9d2ff1ad1e6c | note | 53.0 ¦¦ -
2086ed57-3486-5587-8371-8cf543b86ce3 | note | 37.5 ¦¦ -
e4c6f2c7-a5d7-531a-bd1d-a26e42753cc1 | note | 26.5 ¦¦ 100
385c8fd6-55e9-55bb-9219-5dfb6ebd5dd5 | note | 19.0 ¦¦ 95 - 100
fc81f893-47e9-5932-8077-7626c5cc3c30 | note | 13.2 ¦¦ 78 - 92
3e45e2a3-2280-5523-a160-e5792a8bbc0e | note | 9.5 ¦¦ 63 - 83
54ed646b-ef10-5d73-80e0-1f9226299761 | note | 4.75 ¦¦ 44 - 64
066d039e-fb5c-5c2f-9e1f-fb9632b5fc6f | note | 2.36 ¦¦ 30 - 49
052a2c75-1c76-5cdd-834f-a3c0f1b2366a | note | 0.425 ¦¦ 14 - 23
8493c17b-f077-5935-aa9a-c47ca1260135 | note | 0.075 ¦¦ 6 - 12
bf73e1bb-7687-5a06-91ce-7461db9fe937 | note | – – – – – – – – – –
23dac730-5f5c-555f-a0de-d3ac84df6edd | note | Class 3 Crushed Rock
817909f8-02d6-5226-9f1e-1b0b2b30d74c | note | Crushed Scoria Upper Subbase
32aba97b-8482-58ee-b168-514eef83834d | note | Crushed Concrete Class CC3
670dead9-d291-5ebc-8f40-23c183dd4a06 | note | – – – – – – – – – –
f35db539-59cf-5c00-b28f-f38744d68e52 | note | Sieve Size ¦¦ Nominal Size (mm): 20 ¦¦ Nominal Size (mm): 40
0fed80de-dd2b-56af-beaa-939c1f0877b1 | note | 53.0 ¦¦ - ¦¦ 100
4af3a435-9e11-5ace-9d11-960f2a2b1043 | note | 37.5 ¦¦ - ¦¦ 95 - 100
5bf2c8c7-4b47-5664-86d0-4cb155aa8efc | note | 26.5 ¦¦ 100 ¦¦ 75 - 95
c990ec9a-128c-575a-900f-f4002731b075 | note | 19.0 ¦¦ 95 - 100 ¦¦ 64 - 90
1afde101-d0aa-557b-b72a-d56855131063 | note | 13.2 ¦¦ 75 - 95 ¦¦ -
f0bf9028-608b-5553-ba57-179f6c02c9d0 | note | 9.5 ¦¦ 60 - 90 ¦¦ 42 - 78
f730a9d4-3551-527d-b62e-d76457fa6501 | note | 4.75 ¦¦ 42 - 76 ¦¦ 27 - 64
11467642-ea32-58f1-972f-b109cfd3331c | note | 2.36 ¦¦ 28 - 61 ¦¦ 20 - 51
f24feb09-9f58-51b0-9965-f8a03535a194 | note | 0.425 ¦¦ 14 - 29 ¦¦ 10 - 24
35dc2c90-1cdd-56a1-b01d-3c1a38472471 | note | 0.075 ¦¦ 6 - 14 ¦¦ 6 - 13
acf8222d-b598-56ca-ada9-dd0582d13823 | checkpoint-no-value | Table 304.103 Post-Compaction Requirements for Plasticity Index
797c815e-71cf-5cd8-a154-24b5f5cc711f | note | Material ¦¦ Plasticity Index: Minimum ¦¦ Plasticity Index: Maximum
6adea1b3-3ebf-5536-b8b8-a2965a49d4e7 | note | – – – – – – – – – –
9e1499fd-652e-5d67-b8ba-1eeb0c27bedb | note | Class 1 Crushed Rock ¦¦ 0 ¦¦ 6
37b6606c-9226-5a30-89be-1e9b78381bb5 | note | Class 2 Crushed Rock ¦¦ 0 ¦¦ 6
d8a1d67c-331f-5854-ab3f-1c95136557e7 | note | Class 3 Crushed Rock ¦¦ 0 ¦¦ 10
cc080cf1-f108-57c8-8c8a-ebaf3ca4c73a | checkpoint-no-value | Table 304.111 Maximum Lot Size and Minimum Frequency of Testing for Compaction, Post-compaction Grading and PI (after passing the minimum number of qualifying lots)
cc1f4f67-1111-5547-83ee-7b3531e9e326 | note | Maximum Allowable Lot Size for a Single Layer of Work ¦¦ Minimum Frequency of Testing for Compaction ¦¦ Minimum Frequency of Testing for Scale A Post-compaction Grading ¦¦ Minimum Frequency of Testing for Scale A Post-compaction PI
ff2d1dc2-88e9-5635-bb6f-777e8c922eb7 | note | – – – – – – – – – –
bedb68c2-cb6f-5652-8e74-d9aa4850e1ee | note | Pavement Layer: Upper Base Layer
7cd72f2a-b880-5e20-a8a9-c687ddf577c2 | note | The lesser of 4000 m^2 or one day's production ¦¦ One per 2 lots ¦¦ One per 2 lots ¦¦ One pair per 4 lots
46448bbf-9f79-5f31-81ca-469153dc82ab | note | – – – – – – – – – –
e9bb861d-ecbc-50d7-ad56-472aaa6e4fbc | note | Pavement Layer: Lower Base Layer
6db442f3-759e-5b0c-b33e-bdb8bff0ee37 | note | The lesser of 4000 m^2 or one day's production ¦¦ One per 2 lots ¦¦ One per 2 lots ¦¦ One pair per 8 lots
8372acab-c6ef-519d-bcd2-f6cf4c5f1aca | note | – – – – – – – – – –
ee3f152c-c1b9-58dc-8be3-d00b9cd893c6 | note | Pavement Layer: Upper Subbase
265b7f11-eeab-5ce8-8d77-bcf92d8ea010 | note | The lesser of 4000 m^2 or one day's production ¦¦ One per 2 lots ¦¦ One per 4 lots ¦¦ One pair per 8 lots
cfe666f5-660d-5416-8686-2ef7c9925f51 | note | – – – – – – – – – –
d5471046-aa28-5f95-84b4-cfeb69d17af3 | note | Pavement Layer: Lower Subbase
8ac8721b-cdb9-519d-a967-f981af5c4e25 | note | The lesser of 4000 m^2 or one day's production ¦¦ One per 2 lots ¦¦ – ¦¦ –
3dd62ed5-51de-58bc-b419-5347c252b539 | checkpoint-no-value | Table 310.032 Testing Schedule for Pavement Dryback and Embedment
c96c9ce0-23f5-5cc0-b1d9-8afcdb7d2ef0 | note | Road ¦¦ Location/Chainage ¦¦ Testing Scale
129fa04d-cb86-52f9-95d3-e0764218a863 | note | – – – – – – – – – –
b383fe65-622f-5f96-bbeb-4f62ab298773 | note | Bruny Island Main Road ¦¦ Within the limits of works ¦¦ B