## Enabling Works
ITP - Albany Bus Layovers
Enabling Works - Footpath, Kerb and channel, Pram Crossing, Vehicle Crossing, and Berm
Number | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | Hold Point | Records | Onsite Responsibility
Survey - Set out
1 | Site Set out | Surveyor | Surveyor | Everysite | Site Set out as per construction plan provided with GPS location and 2D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable. | Inprocess Inspection | Onsite records/photos | Site Engineer
Kerb and Channel
2 | Kerb & Channel | QA FORM | TDM Technical Standards - KC0001, KC0030, KC0031 | Everysite | Kerb & Channel to be laid using precast hand-laid on compacted minimum 300mm GAP65 sub base with CIV > 25. Concrete 20MPa @28 Days | Inprocess Inspection | Clegg Sheet, photos. Concrete Plant Docket | Site Engineer
3 | Channel Level | QA FORM | TDM Technical Standards - KC0001 | Everysite | Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match new road level. Channel grade to follow long-sections provided in IFC set. | Inprocess Inspection | FH channel QA sheet/photos | Site Engineer
Footpath
4 | Concrete Footpaths | QA FORM | TDM Technical Standards - FP0001 | 10m Intervals | Basecourse - 100mm Gap40 min. thickness Clegg CIV > 12 (frequency every 3m or minimum 4 spots per pour - excluding PX) Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 black oxide with broom finish | Inprocess Inspection | Clegg Sheet, photos. Concrete Plant Docket | Site Engineer
Pram Crossing
5 | Service Covers and Street Furniture | Visual | AT Contract Specification 14000 | Everysite | Service covers to be adjusted to new surface levels. Ensure no damage is done to street furniture in the vicinity while carrying out works. | Inprocess Inspection | Nil | Site Engineer
Grass Berm
6 | Grass Berms | Visual | ATCOP Section 12 Footpaths and Pedestrian Facilities | Everysite | 100mm thick layer of compacted approved quality topsoil, free of weeds and stones and sowed with grass seeds. | Inprocess Inspection | Photos | Site Engineer
Wooden Bollard
7 | Wooden Bollard & chain fence | Visual | TDM Technical Standards - FE0012 | Everysite | 150mm post and 2500 spacing connected with chains. Post 600mm inground with 75mm thick around and 150 thick at top collar with rebar. | Inprocess Inspection | Photos | Site Engineer
Timber boardwalk
8 | Timber board walk | Visual | TES Design drawing RD-001 REVA | Everysite | 150mm x 50mm H5 Timber Blocking 200mm x 100mm H5 Timber Bearer 250mm x 75mm H5 Timber joists 490mm centres. 150mm x 50mm rough sawn H5 Timber decking with non-slip geogrid M16 Bolts Marine Grade stainless steel expansion bolts into concrete rain garden wall | Inprocess Inspection | Photos/dockets | Site Engineer
Asbuilts
9 | As built information | Drawings |  | Every Site | As built drawings | In Process Inspection | Asbuilt records | Site Engineer & PM
10 | RAMM DATA | RAMM DATA SHEET |  | Every Site | RAMM SHEET | In Process Inspection | RAMM Sheet | Site Engineer & PM
ITP APPROVAL
Prepared By |  | Ajithkumar Ayyanar | Initial | AA |  | Date:
Approving Delegate |  | Denny Jeong | Initial | DJ |  | Date:

## Stormwater Drainage
ITP - Albany Bus Layovers
Stormwater Drainage
Number | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | Hold Point | Records | Onsite Responsibility
Design
1 | Design | Survey Setout | Issued for Construction Drawings | Each site | Setout Pipe Alignment and catchpit locations and with inlet & outlet points and inverts as required to construct to design | Inprocess Inspection | IFC Drawings | Site Engineer
Material Compliance
2 | Material Compliance - Pipe | Visual Inspection | Drawings and Dockets | Prior to construction | Pipe shall be Check for freshly formed pipes and return if required 1) DN225 Class 3 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 4) Prefabricated concrete Manhole/cesspit shall be in accordance with TDM Standards/SWCOP | Inprocess Inspection | Photos/Dockets | Site Engineer
3 | Subsoil Pipes | Visual Inspection | TDM Technical Standards - RD0010 | Prior to construction | Subsoil pipe should have punched holes and filtersok Depth to be 375mm from subgrade level to invert of pipe or as possible to achieve invert of subsoil pipe to be above soffit level of outlet pipe in the downsteam cesspit. 50mm bedding. Backfilled with scoria 30/10 or similar approved product. | Inprocess Inspection | Photos/Dockets | Site Engineer
4 | Catchpit/manhole | Visual Inspection | TDM Technical Standards - RD0025, RD0026, RD0027 and SWCoP - drawing SW05 revision 2 | Prior to construction | No Damage or cracks- Material should compliance with TDM standard | Inprocess Inspection | Photos/Dockets | Site Engineer
5 | Kassel kerb drainage pit/grate | Visual Inspection | as per supplier (busck) guidelines | Prior to construction | No Damage or cracks- Material should compliance with TDM standard | Inprocess Inspection | Photos/Dockets | Site Engineer
Construction
6 | Construction | Trench Profile - Width | SWCOP | Daily / as trenching takes place. Different depth methodology | Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing. provide a minimum of 100mm bedding below each pipe | Inprocess Inspection | Visual Inspection, Measurement | Site Engineer
7 | Construction | Bedding for Concrete Pipe Laying & Manhole & Cesspit | Placing and compaction of Bedding Material. | Inspected continuously during placing and compaction of Bedding Material. | Bedding & Pipe surround material to be GAP7 or GAP 20 or alternate material CIV>25 TDM Technical Standard RD0010, RD0025, RD0026, & RD0027 & SWCoP - drawing SW05 revision 2, to be followed | Inprocess Inspection | Visual Inspection Photos showing depths of trench and trench reinstatement Clegg Sheet | Site Engineer
8 | Construction | Trench Backfill - Placing & Compacting | Placing and compacting of Trench Backfill Material | Throughout Trench Backfilling operation. | Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm TDM Technical Standard RD0010, RD0025, RD0026, & RD0027 & SWCoP - drawing SW05 revision 2, to be followed | Inprocess Inspection | Visual Inspection | Site Engineer
9 | Construction | Subsoil | Trench, install, bedding and backfill TDM Technical Standard RD0010 | Throughout Trench Backfilling operation. | Depth to be 375mm from subgrade level to invert of pipe or as possible to achieve invert of subsoil pipe to be above soffit level of outlet pipe in the downsteam cesspit. 50mm bedding. Backfilled with scoria 30/10 or similar approved product. | Inprocess Inspection | Visual Inspection Photos showing depths of trench and trench reinstatement | Site Engineer
Asbuilts
10 | As built information | Drawings |  | Every Site | As built drawings | In Process Inspection | Asbuilt records | Site Engineer & PM
11 | RAMM DATA | RAMM DATA SHEET |  | Every Site | RAMM SHEET | In Process Inspection | RAMM Sheet | Site Engineer & PM
ITP APPROVAL
Prepared By |  | Ajithkumar Ayyanar | Initial | AA |  | Date:
Approving Delegate |  | Denny Jeong | Initial | DJ |  | Date:

## Signage
ITP - Albany Bus Layovers
Site Location |  |  | Albany Bus Layovers
Signage
Number | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | Hold Point | Records | Onsite Responsibility
Site Set Out
1 | Site Set out | Surveyor | Surveyor | Everysite | Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable. Alternatively like for like | Mandatory HOLD POINT - | Survey Receipt | Site Engineer
Materials
2 | Signs/Belisha Disk | QA FORM | TDM Technical Standards | Every site | All signs to looking in excellent condition. Signs to have good reflection and visibility. NO scratches or markings. All signs to match with construction drawings provided by designers. | Inprocess Inspection | Dockets/Photos | Site Engineer
3 | Pole, Impact recovery post and Ground Socket | QA FORM | TDM Technical Standards | Every site | Check for underground service before installtion. All poles and post to be looking in excellent conditon with end caps - 3m long. Ground socket to be 60mm dia, 600mm deep with grouted screw or pins. For Black and white pole 76mm dia and 600mm deep | Inprocess Inspection | Dockets/Photos | Site Engineer
Construction
4a | Ground Socket | QA FORM | TDM Technical Standards | Each Socket | The dug out hole to be 300mm wide and 600mm deep. 20Mpa concrete with 50mm cover at bottom to be used for installing socket. The sockets to have 50mm reveal at top and smooth finish of concrete around the socket. | Inprocess Inspection | Dockets/Photos with tape measurement | Site Engineer
4b | Pole and Impact recovery post | QA FORM | TDM Technical Standards | Each Post or pole | All poles to inserted into the socket after the concrete curing. And, the screw or pins to be used to prevent thr pole rotation. The impact recovery post installed on the island infill surface after curing period by drilling and using Dyna bolts. The bolts are tightned sufficent to prevent rotation | Inprocess Inspection | Dockets/Photos | Site Engineer
5 | Signs/Belisha Disk | QA FORM | TDM Technical Standards | Each Sign | All the sign/Belisha disk to be fixed with the pole or post with ARC brackets and tightened adequately. | Inprocess Inspection | Dockets/Photos | Site Engineer
Asbuilts
6 | As built information | RAMM DATA SHEET |  | Every Site | As built drawings and Ramm Sheets Completed | In Process Inspection | Asbuilt records | Supervisor and Engineer
ITP APPROVAL
Prepared By |  |  | Initial |  |  | Date:
Approving Delegate |  |  | Initial |  |  | Date:

## Pavement Widening
Cornerstone Drive Pavement Widening Excavate 650mm 425mm ATAP65 65mm AC14HF (Revised Design Thickness) 105mm AC20 (Revised Design Thickness) 55mm AC14 (Revised Design Thickness)
Project Name: |  | ERAA Albany Bus Layovers |  |  |  | Design Report . | TES Drawing R5-002 Revision A
ITP Prepared By: |  | Daeyoung Jeong - FH |  | Date: | 2025-02-10 | Peer Review By:
No. | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | TYPE | RECORDS (Responsibility) | ONSITE RESPONSIBILITY | CONTRACT MANAGER SIGNOFF
Excavation
1 | Identification and location of shallow services | Measure depth of cover to utility services | Trained contractor staff | Two measures per service (each side of the road) | Services sufficently deep to avoid damage. Otherwise consider relocation or concrete cap | Mandatory HOLD POINT Designer Signoff Required | Marked up sheet | Project Engineer | Designer Signoff
2 | Milling / Cut to Waste Existing Pavement Area = 650mm or match adjacent existing pavement depth to avoid water ponding | Survey As-built / Stringline | Survey As-built / Stringline | 10m each lane | +0 / -20mm to design level | Mandatory HOLD POINT Designer Signoff Required | Survey As-built / Stringline sheet | Project Engineer | Designer Signoff
3 | Subgrade | No unacceptable subgrade materials after excavation | Visual Inspection | NA | Free of detritius and loose material | Inprocess Inspection | Photos | Project Engineer
Undercutting Contingency
4 | Contingency Weak / Soft Spot | Scala Pentrometer tests | Design Report | At 10m intervals in each lane | Subgrade CBR ≥ 3.5 If CBR < 3.5 but ≥ 2, Excavate further 200mm and place a bidim A29 geotextile on subgrade and replace with GAP65 subbase | Mandatory HOLD POINT Designer Signoff Required | Marked up drawing | Project Engineer | Designer Signoff
5 | Contingency Weak / Soft Spot | Survey As-built / Stringline | Survey As-built / Stringline | 10m each lane | +0 / -20mm No trafficking of the excavated subgrade | Mandatory HOLD POINT Designer Signoff Required | Survey As-built / Stringline sheet | Project Engineer | Designer Signoff
6 | Subgrade | No unacceptable subgrade materials after excavation | Visual Inspection | NA | Free of detritius and loose material | Inprocess Inspection | Photos | Project Engineer
AT AP65
7 | ATAP65 (material) | No non-compliant results | Material test results | Once | Compliance with AT Series 800 Specification for the Supply of Aggregates | Contractor Records | Testing Results | Project Engineer
8 | ATAP65 (Compaction) | Density Testing | Clegg Testing | 5m grids | CIV > 27. to be compacted in 150mm layers | Mandatory HOLD POINT Designer Signoff Required | Testing Results | Project Engineer | Designer Signoff
9 | ATAP65 (Level Tolerance) Backfill areas to bring up levels to -225mm below FSL | Survey As-built / Stringline | Survey As-built / Stringline | 10m each lane | +0 / -20mm No trafficking of the excavated subgrade | Mandatory HOLD POINT Designer Signoff Required | Survey As-built / Stringline sheet | Project Engineer | Designer Signoff
10 | ATAP65 (Surface finish) | N/A | Visual Inspection | NA | Free of detritius and loose material | Inprocess Inspection | Photos | Project Engineer
11 | ATAP65 (Deflection Testing) | N/A | Benkleman Beam Deflection Testing | NA | Target Deflection: Maximum Deflection = 1.6mm 90th Percentile Deflection = 1.4mm | Mandatory HOLD POINT Designer Signoff Required | Test Report | Project Engineer | Designer Signoff
Emulsion (Concrete and AC layer)
12 | Heavy Tack coat and blinding | CAT60 cationic emulsion or approved alternative | Visual Inspection | each lot | Hand spray tack coat emulsion (residual bitumen 0.6L/m2) Blinding mix or milling max 5mm depth | Inprocess Testing | Photos | Project Engineer
Structural Asphalt (65mm AC14HF & 105mm AC20)
13 | AC14HF & AC20 | Mix Design | Sign-off by Designer | Prior to starting | Sign-off by Designer | Mandatory HOLD POINT Designer Signoff Required | Mix Design Report | Project Engineer | Designer Signoff
14 | AC14HF & AC20 | Check weather reports | Check weather reports | Daily | No fog, rain or wet surface. Base temp ≥ 7o C | Inprocess Testing | AC check sheet | Project Engineer
15 | AC14HF & AC20 | Ensure previous layer is broomed clean | Visual | Prior to starting | Free of detritius and loose material | Inprocess Testing | AC check sheet | Project Engineer
16 | AC14HF & AC20 | Production tests | Grading, binder content, max density, temp | As per M/10 | NZTA M/10 | Inprocess Testing | Lab test | Project Engineer
17 | AC14HF & AC20 | Surface finish inspection | Visual inspection by the Engineer | Each lot | Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate. | Inprocess Testing | Inspection sheet | Project Engineer
18 | AC14HF & AC20 | Density testing | NDM | Every 10m each lane staggerd | Air voids to meet NZTA M/10:2020 | Inprocess Testing | Inspection sheet | Project Engineer | Auckland Transport Signoff
19 | AC14HF | Survey As-built / Stringline | Survey As-built / Stringline | 10m each lane | Thickness no less than 65mm Height discrepancy +/- 5mm | Inprocess Testing | Survey As-built / Stringline sheet | Project Engineer
20 | AC20 | Survey As-built / Stringline | Survey As-built / Stringline | 10m each lane | Thickness no less than 105mm Height discrepancy +/- 10mm | Inprocess Testing | Survey As-built / Stringline sheet | Project Engineer
21 | AC14HF & AC20 | Density testing | Cores air voids | Minimum 8 mat cores & 3 joint cores Location to be jointly agreed with the Engineer on-site and be outside of wheelpath | Air voids to meet NZTA M/10:2020 | Mandatory HOLD POINT Auckland Transport Signoff Required | RFI response | Project Engineer | Auckland Transport Signoff
22 | AC14HF & AC20 | Thickness | Cores depth | Minimum 8 mat cores & 3 joint cores Location to be jointly agreed with the Engineer on-site and be outside of wheelpath | Target thickness 170mm (no less than 170mm thickness for AC14HF and AC20 combined) | Mandatory HOLD POINT Auckland Transport Signoff Required | Core test report | Project Engineer | Auckland Transport Signoff
Asphalt Surfacing - 55mm AC14
23 | Shape of road | 3m straight edge | NZTA M/10 spec | At joints and any other areas of concern | Irregularities < 5mm under straight edge | Inprocess Inspection | Check sheet | Project Engineer
24 | Temperature Limitations | Temperature | Contract Spec / M10 Spec | Every Site | Asphalt not to be paved when foggy or raining, or placed on a wet surface or when temperature is below the base temperature limitations of 10 Degree | Inprocess Inspection | Asphalt QA | Project Engineer
25 | Surface Preparation | Visual | NZTA M/10 spec | Every Site | Swept clean; all necessary measures to prevent ponding prior to any surfacing | Inprocess Inspection | Visual | Project Engineer
26 | Asphalt Production Tests for AC14 | Production Tests | Grading, binder content, max density, temp | As per M/10 | NZTA M/10 | Laboratory Testing | IANZ Lab | Project Engineer
27 | AC14 - Layer thickness - 50mm compacted depth | Insitu | Contract Spec / NZTA M10 Spec | Continuous | 55 mm minimum and 60 mm maximum compacted depth Final asphalt level to be 5mm proud of lip of channel | Mandatory HOLD POINT Auckland Transport Signoff Required | Asphalt QA | Project Engineer | Auckland Transport Signoff
28 | AC14 | Density testing | NDM | Every 10m each lane staggerd | NZTA M/10 | Mandatory HOLD POINT Auckland Transport Signoff Required | RFI response | Project Engineer | Auckland Transport Signoff
29 | AC14 (Deflection Testing) | N/A | Benkleman Beam Deflection Testing | NA | Target Deflection: Maximum Deflection = 1.0mm 90th Percentile Deflection = 0.8mm | Mandatory HOLD POINT Designer Signoff Required | Test Report | Project Engineer | Designer Signoff
No. | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | TYPE | RECORDS (Responsibility) | ONSITE RESPONSIBILITY | CONTRACT MANAGER SIGNOFF
30 | Reinstatement of Linemarking and RRPM's & Apply Joint sealing | Visual | Visual inspection | Every site | Visual inspection | Inprocess Inspection | Photos | Project Engineer
APPROVALS
Approved by Project Engineer : |  | Ryan Simon |  | Signature: RS |  | Date: | 2025-02-10
Approved by Contract Manager : |  | Daeyoung Jeong |  | Signature: DJ |  | Date: | 2025-02-10
Approved by Client Rep : |  |  |  | Signature: |  | Date: