## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Pavement Widening | itp |  |  |  |  | ITP - Albany Bus Layovers - Pavement Widening
section | Excavation
checkpoint | 1 - Identification and location of shallow services
label | VERIFICATION ACTIVITY: Measure depth of cover to utility services
label | METHODS OR REFERENCE: Trained contractor staff
label | FREQUENCY: Two measures per service (each side of the road)
label | ACCEPTANCE CRITERIA: Services sufficently deep to avoid damage.
label | ○ Otherwise consider relocation or concrete cap
label | TYPE: Mandatory HOLD POINT Designer Signoff Required
label | RECORDS (Responsibility): Marked up sheet
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF: Designer Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Milling / Cut to Waste Existing Pavement Area = 650mm or match adjacent existing pavement depth to avoid water ponding
label | VERIFICATION ACTIVITY: Survey As-built / Stringline
label | METHODS OR REFERENCE: Survey As-built / Stringline
label | FREQUENCY: 10m each lane
label | ACCEPTANCE CRITERIA: +0 / -20mm to design level
label | TYPE: Mandatory HOLD POINT Designer Signoff Required
label | RECORDS (Responsibility): Survey As-built / Stringline sheet
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF: Designer Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Subgrade
label | VERIFICATION ACTIVITY: No unacceptable subgrade materials after excavation
label | METHODS OR REFERENCE: Visual Inspection
label | FREQUENCY: NA
label | ACCEPTANCE CRITERIA: Free of detritius and loose material
label | TYPE: Inprocess Inspection
label | RECORDS (Responsibility): Photos
label | ONSITE RESPONSIBILITY: Project Engineer
section | Undercutting Contingency
checkpoint | 4 - Contingency Weak / Soft Spot
label | VERIFICATION ACTIVITY: Scala Pentrometer tests
label | METHODS OR REFERENCE: Design Report
label | FREQUENCY: At 10m intervals in each lane
label | ACCEPTANCE CRITERIA: Subgrade CBR ≥ 3.5
label | ○ If CBR < 3.5 but ≥ 2, Excavate further 200mm and place a bidim A29 geotextile on subgrade and replace with GAP65 subbase
label | TYPE: Mandatory HOLD POINT Designer Signoff Required
label | RECORDS (Responsibility): Marked up drawing
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF: Designer Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Contingency Weak / Soft Spot
label | VERIFICATION ACTIVITY: Survey As-built / Stringline
label | METHODS OR REFERENCE: Survey As-built / Stringline
label | FREQUENCY: 10m each lane
label | ACCEPTANCE CRITERIA: +0 / -20mm
label | ○ No trafficking of the excavated subgrade
label | TYPE: Mandatory HOLD POINT Designer Signoff Required
label | RECORDS (Responsibility): Survey As-built / Stringline sheet
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF: Designer Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Subgrade
label | VERIFICATION ACTIVITY: No unacceptable subgrade materials after excavation
label | METHODS OR REFERENCE: Visual Inspection
label | FREQUENCY: NA
label | ACCEPTANCE CRITERIA: Free of detritius and loose material
label | TYPE: Inprocess Inspection
label | RECORDS (Responsibility): Photos
label | ONSITE RESPONSIBILITY: Project Engineer
section | AT AP65
checkpoint | 7 - ATAP65 (material)
label | VERIFICATION ACTIVITY: No non-compliant results
label | METHODS OR REFERENCE: Material test results
label | FREQUENCY: Once
label | ACCEPTANCE CRITERIA: Compliance with AT Series 800 Specification for the Supply of Aggregates
label | TYPE: Contractor Records
label | RECORDS (Responsibility): Testing Results
label | ONSITE RESPONSIBILITY: Project Engineer
checkpoint | 8 - ATAP65 (Compaction)
label | VERIFICATION ACTIVITY: Density Testing
label | METHODS OR REFERENCE: Clegg Testing
label | FREQUENCY: 5m grids
label | ACCEPTANCE CRITERIA: CIV > 27. to be compacted in 150mm layers
label | TYPE: Mandatory HOLD POINT Designer Signoff Required
label | RECORDS (Responsibility): Testing Results
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF: Designer Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - ATAP65 (Level Tolerance) Backfill areas to bring up levels to -225mm below FSL
label | VERIFICATION ACTIVITY: Survey As-built / Stringline
label | METHODS OR REFERENCE: Survey As-built / Stringline
label | FREQUENCY: 10m each lane
label | ACCEPTANCE CRITERIA: +0 / -20mm
label | ○ No trafficking of the excavated subgrade
label | TYPE: Mandatory HOLD POINT Designer Signoff Required
label | RECORDS (Responsibility): Survey As-built / Stringline sheet
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF: Designer Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - ATAP65 (Surface finish)
label | VERIFICATION ACTIVITY: N/A
label | METHODS OR REFERENCE: Visual Inspection
label | FREQUENCY: NA
label | ACCEPTANCE CRITERIA: Free of detritius and loose material
label | TYPE: Inprocess Inspection
label | RECORDS (Responsibility): Photos
label | ONSITE RESPONSIBILITY: Project Engineer
checkpoint | 11 - ATAP65 (Deflection Testing)
label | VERIFICATION ACTIVITY: N/A
label | METHODS OR REFERENCE: Benkleman Beam Deflection Testing
label | FREQUENCY: NA
label | ACCEPTANCE CRITERIA: Target Deflection:
label | ○ Maximum Deflection = 1.6mm
label | ○ 90th Percentile Deflection = 1.4mm
label | TYPE: Mandatory HOLD POINT Designer Signoff Required
label | RECORDS (Responsibility): Test Report
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF: Designer Signoff
holdpoint | AUTHORITY HOLDPOINT
section | Emulsion (Concrete and AC layer)
checkpoint | 12 - Heavy Tack coat and blinding
label | VERIFICATION ACTIVITY: CAT60 cationic emulsion or approved alternative
label | METHODS OR REFERENCE: Visual Inspection
label | FREQUENCY: each lot
label | ACCEPTANCE CRITERIA: Hand spray tack coat emulsion (residual bitumen 0.6L/m2)
label | ○ Blinding mix or milling max 5mm depth
label | TYPE: Inprocess Testing
label | RECORDS (Responsibility): Photos
label | ONSITE RESPONSIBILITY: Project Engineer
section | Structural Asphalt (65mm AC14HF & 105mm AC20)
checkpoint | 13 - AC14HF & AC20
label | VERIFICATION ACTIVITY: Mix Design
label | METHODS OR REFERENCE: Sign-off by Designer
label | FREQUENCY: Prior to starting
label | ACCEPTANCE CRITERIA: Sign-off by Designer
label | TYPE: Mandatory HOLD POINT Designer Signoff Required
label | RECORDS (Responsibility): Mix Design Report
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF: Designer Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 - AC14HF & AC20
label | VERIFICATION ACTIVITY: Check weather reports
label | METHODS OR REFERENCE: Check weather reports
label | FREQUENCY: Daily
label | ACCEPTANCE CRITERIA: No fog, rain or wet surface. Base temp ≥ 7o C
label | TYPE: Inprocess Testing
label | RECORDS (Responsibility): AC check sheet
label | ONSITE RESPONSIBILITY: Project Engineer
checkpoint | 15 - AC14HF & AC20
label | VERIFICATION ACTIVITY: Ensure previous layer is broomed clean
label | METHODS OR REFERENCE: Visual
label | FREQUENCY: Prior to starting
label | ACCEPTANCE CRITERIA: Free of detritius and loose material
label | TYPE: Inprocess Testing
label | RECORDS (Responsibility): AC check sheet
label | ONSITE RESPONSIBILITY: Project Engineer
checkpoint | 16 - AC14HF & AC20
label | VERIFICATION ACTIVITY: Production tests
label | METHODS OR REFERENCE: Grading, binder content, max density, temp
label | FREQUENCY: As per M/10
label | ACCEPTANCE CRITERIA: NZTA M/10
label | TYPE: Inprocess Testing
label | RECORDS (Responsibility): Lab test
label | ONSITE RESPONSIBILITY: Project Engineer
checkpoint | 17 - AC14HF & AC20
label | VERIFICATION ACTIVITY: Surface finish inspection
label | METHODS OR REFERENCE: Visual inspection by the Engineer
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate.
label | TYPE: Inprocess Testing
label | RECORDS (Responsibility): Inspection sheet
label | ONSITE RESPONSIBILITY: Project Engineer
checkpoint | 18 - AC14HF & AC20
label | VERIFICATION ACTIVITY: Density testing
label | METHODS OR REFERENCE: NDM
label | FREQUENCY: Every 10m each lane staggerd
label | ACCEPTANCE CRITERIA: Air voids to meet NZTA M/10:2020
label | TYPE: Inprocess Testing
label | RECORDS (Responsibility): Inspection sheet
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff
checkpoint | 19 - AC14HF
label | VERIFICATION ACTIVITY: Survey As-built / Stringline
label | METHODS OR REFERENCE: Survey As-built / Stringline
label | FREQUENCY: 10m each lane
label | ACCEPTANCE CRITERIA: Thickness no less than 65mm
label | ○ Height discrepancy +/- 5mm
label | TYPE: Inprocess Testing
label | RECORDS (Responsibility): Survey As-built / Stringline sheet
label | ONSITE RESPONSIBILITY: Project Engineer
checkpoint | 20 - AC20
label | VERIFICATION ACTIVITY: Survey As-built / Stringline
label | METHODS OR REFERENCE: Survey As-built / Stringline
label | FREQUENCY: 10m each lane
label | ACCEPTANCE CRITERIA: Thickness no less than 105mm
label | ○ Height discrepancy +/- 10mm
label | TYPE: Inprocess Testing
label | RECORDS (Responsibility): Survey As-built / Stringline sheet
label | ONSITE RESPONSIBILITY: Project Engineer
checkpoint | 21 - AC14HF & AC20
label | VERIFICATION ACTIVITY: Density testing
label | METHODS OR REFERENCE: Cores air voids
label | FREQUENCY: Minimum 8 mat cores & 3 joint cores
label | ○ Location to be jointly agreed with the Engineer on-site and be outside of wheelpath
label | ACCEPTANCE CRITERIA: Air voids to meet NZTA M/10:2020
label | TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required
label | RECORDS (Responsibility): RFI response
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 22 - AC14HF & AC20
label | VERIFICATION ACTIVITY: Thickness
label | METHODS OR REFERENCE: Cores depth
label | FREQUENCY: Minimum 8 mat cores & 3 joint cores
label | ○ Location to be jointly agreed with the Engineer on-site and be outside of wheelpath
label | ACCEPTANCE CRITERIA: Target thickness 170mm (no less than 170mm thickness for AC14HF and AC20 combined)
label | TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required
label | RECORDS (Responsibility): Core test report
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff
holdpoint | AUTHORITY HOLDPOINT
section | Asphalt Surfacing - 55mm AC14
checkpoint | 23 - Shape of road
label | VERIFICATION ACTIVITY: 3m straight edge
label | METHODS OR REFERENCE: NZTA M/10 spec
label | FREQUENCY: At joints and any other areas of concern
label | ACCEPTANCE CRITERIA: Irregularities < 5mm under straight edge
label | TYPE: Inprocess Inspection
label | RECORDS (Responsibility): Check sheet
label | ONSITE RESPONSIBILITY: Project Engineer
checkpoint | 24 - Temperature Limitations
label | VERIFICATION ACTIVITY: Temperature
label | METHODS OR REFERENCE: Contract Spec / M10 Spec
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: Asphalt not to be paved when foggy or raining, or placed on a wet surface or when temperature is below the base temperature limitations of 10 Degree
label | TYPE: Inprocess Inspection
label | RECORDS (Responsibility): Asphalt QA
label | ONSITE RESPONSIBILITY: Project Engineer
checkpoint | 25 - Surface Preparation
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: NZTA M/10 spec
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: Swept clean; all necessary measures to prevent ponding prior to any surfacing
label | TYPE: Inprocess Inspection
label | RECORDS (Responsibility): Visual
label | ONSITE RESPONSIBILITY: Project Engineer
checkpoint | 26 - Asphalt Production Tests for AC14
label | VERIFICATION ACTIVITY: Production Tests
label | METHODS OR REFERENCE: Grading, binder content, max density, temp
label | FREQUENCY: As per M/10
label | ACCEPTANCE CRITERIA: NZTA M/10
label | TYPE: Laboratory Testing
label | RECORDS (Responsibility): IANZ Lab
label | ONSITE RESPONSIBILITY: Project Engineer
checkpoint | 27 - AC14 - Layer thickness - 50mm compacted depth
label | VERIFICATION ACTIVITY: Insitu
label | METHODS OR REFERENCE: Contract Spec / NZTA M10 Spec
label | FREQUENCY: Continuous
label | ACCEPTANCE CRITERIA: 55 mm minimum and 60 mm maximum compacted depth
label | ○ Final asphalt level to be 5mm proud of lip of channel
label | TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required
label | RECORDS (Responsibility): Asphalt QA
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 28 - AC14
label | VERIFICATION ACTIVITY: Density testing
label | METHODS OR REFERENCE: NDM
label | FREQUENCY: Every 10m each lane staggerd
label | ACCEPTANCE CRITERIA: NZTA M/10
label | TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required
label | RECORDS (Responsibility): RFI response
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 29 - AC14 (Deflection Testing)
label | VERIFICATION ACTIVITY: N/A
label | METHODS OR REFERENCE: Benkleman Beam Deflection Testing
label | FREQUENCY: NA
label | ACCEPTANCE CRITERIA: Target Deflection:
label | ○ Maximum Deflection = 1.0mm
label | ○ 90th Percentile Deflection = 0.8mm
label | TYPE: Mandatory HOLD POINT Designer Signoff Required
label | RECORDS (Responsibility): Test Report
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF: Designer Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 30 - Reinstatement of Linemarking and RRPM's & Apply Joint sealing
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: Visual inspection
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Visual inspection
label | TYPE: Inprocess Inspection
label | RECORDS (Responsibility): Photos
label | ONSITE RESPONSIBILITY: Project Engineer
section | APPROVALS
checkpoint | ITP Approval
label | Approved by Project Engineer: Ryan Simon
label | Approved by Contract Manager: Daeyoung Jeong
textbox | Approved by Client Rep:
checklist | ITP - Signage | itp |  |  |  |  | ITP - Albany Bus Layovers - Signage
section | Site Set Out
checkpoint | 1 - Site Set out
label | VERIFICATION ACTIVITY: Surveyor
label | METHODS OR REFERENCE: Surveyor
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
label | ○ Alternatively like for like
label | HOLD POINT: Mandatory HOLD POINT -
label | RECORDS: Survey Receipt
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | AUTHORITY HOLDPOINT
section | Materials
checkpoint | 2 - Signs/Belisha Disk
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: All signs to looking in excellent condition. Signs to have good reflection and visibility. NO scratches or markings. All signs to match with construction drawings provided by designers.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Dockets/Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3 - Pole, Impact recovery post and Ground Socket
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Check for underground service before installtion. All poles and post to be looking in excellent conditon with end caps - 3m long. Ground socket to be 60mm dia, 600mm deep with grouted screw or pins. For Black and white pole 76mm dia and 600mm deep
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Dockets/Photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | Construction
checkpoint | 4a - Ground Socket
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards
label | FREQUENCY: Each Socket
label | ACCEPTANCE CRITERIA: The dug out hole to be 300mm wide and 600mm deep. 20Mpa concrete with 50mm cover at bottom to be used for installing socket. The sockets to have 50mm reveal at top and smooth finish of concrete around the socket.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Dockets/Photos with tape measurement
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 4b - Pole and Impact recovery post
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards
label | FREQUENCY: Each Post or pole
label | ACCEPTANCE CRITERIA: All poles to inserted into the socket after the concrete curing. And, the screw or pins to be used to prevent thr pole rotation.
label | ○ The impact recovery post installed on the island infill surface after curing period by drilling and using Dyna bolts. The bolts are tightned sufficent to prevent rotation
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Dockets/Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 5 - Signs/Belisha Disk
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards
label | FREQUENCY: Each Sign
label | ACCEPTANCE CRITERIA: All the sign/Belisha disk to be fixed with the pole or post with ARC brackets and tightened adequately.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Dockets/Photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | Asbuilts
checkpoint | 6 - As built information
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | METHODS OR REFERENCE:
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
section | ITP APPROVAL
checkpoint | ITP Approval
textbox | Prepared By:
textbox | Approving Delegate:
checklist | ITP - Stormwater Drainage | itp |  |  |  |  | ITP - Albany Bus Layovers - Stormwater Drainage
section | Design
checkpoint | 1 - Design
label | VERIFICATION ACTIVITY: Survey Setout
label | METHODS OR REFERENCE: Issued for Construction Drawings
label | FREQUENCY: Each site
label | ACCEPTANCE CRITERIA: Setout Pipe Alignment and catchpit locations and with inlet & outlet points and inverts as required to construct to design
label | HOLD POINT: Inprocess Inspection
label | RECORDS: IFC Drawings
label | ONSITE RESPONSIBILITY: Site Engineer
section | Material Compliance
checkpoint | 2 - Material Compliance - Pipe
label | VERIFICATION ACTIVITY: Visual Inspection
label | METHODS OR REFERENCE: Drawings and Dockets
label | FREQUENCY: Prior to construction
label | ACCEPTANCE CRITERIA: Pipe shall be
label | Check for freshly formed pipes and return if required
label | 1) DN225 Class 3 RCRRJ pipes AS/NZS 4058
label | 2) All Concrete RCRRJ pipes to be fitted with Rubber rings
label | 3) Pipes shall have product certification (ISO Type 5) to AS/NZS 4058
label | 4) Prefabricated concrete Manhole/cesspit shall be in accordance with TDM Standards/SWCOP
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos/Dockets
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3 - Subsoil Pipes
label | VERIFICATION ACTIVITY: Visual Inspection
label | METHODS OR REFERENCE: TDM Technical Standards - RD0010
label | FREQUENCY: Prior to construction
label | ACCEPTANCE CRITERIA: Subsoil pipe should have punched holes and filtersok
label | ○ Depth to be 375mm from subgrade level to invert of pipe or as possible to achieve invert of subsoil pipe to be above soffit level of outlet pipe in the downsteam cesspit.
label | ○ 50mm bedding.
label | ○ Backfilled with scoria 30/10 or similar approved product.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos/Dockets
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 4 - Catchpit/manhole
label | VERIFICATION ACTIVITY: Visual Inspection
label | METHODS OR REFERENCE: TDM Technical Standards - RD0025, RD0026, RD0027 and SWCoP - drawing SW05 revision 2
label | FREQUENCY: Prior to construction
label | ACCEPTANCE CRITERIA: No Damage or cracks- Material should compliance with TDM standard
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos/Dockets
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 5 - Kassel kerb drainage pit/grate
label | VERIFICATION ACTIVITY: Visual Inspection
label | METHODS OR REFERENCE: as per supplier (busck) guidelines
label | FREQUENCY: Prior to construction
label | ACCEPTANCE CRITERIA: No Damage or cracks- Material should compliance with TDM standard
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos/Dockets
label | ONSITE RESPONSIBILITY: Site Engineer
section | Construction
checkpoint | 6 - Construction
label | VERIFICATION ACTIVITY: Trench Profile - Width
label | METHODS OR REFERENCE: SWCOP
label | FREQUENCY: Daily / as trenching takes place. Different depth methodology
label | ACCEPTANCE CRITERIA: Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing. provide a minimum of 100mm bedding below each pipe
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Visual Inspection, Measurement
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 7 - Construction
label | VERIFICATION ACTIVITY: Bedding for Concrete Pipe Laying & Manhole & Cesspit
label | METHODS OR REFERENCE: Placing and compaction of Bedding Material.
label | FREQUENCY: Inspected continuously during placing and compaction of Bedding Material.
label | ACCEPTANCE CRITERIA: Bedding & Pipe surround material to be GAP7 or GAP 20 or alternate material
label | ○ CIV>25
label | ○ TDM Technical Standard RD0010, RD0025, RD0026, & RD0027 & SWCoP - drawing SW05 revision 2, to be followed
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Visual Inspection, Photos showing depths of trench and trench reinstatement, Clegg Sheet
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 8 - Construction
label | VERIFICATION ACTIVITY: Trench Backfill - Placing & Compacting
label | METHODS OR REFERENCE: Placing and compacting of Trench Backfill Material
label | FREQUENCY: Throughout Trench Backfilling operation.
label | ACCEPTANCE CRITERIA: Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
label | ○ TDM Technical Standard RD0010, RD0025, RD0026, & RD0027 & SWCoP - drawing SW05 revision 2, to be followed
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Visual Inspection
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 9 - Construction
label | VERIFICATION ACTIVITY: Subsoil
label | METHODS OR REFERENCE: Trench, install, bedding and backfill
label | ○ TDM Technical Standard RD0010
label | FREQUENCY: Throughout Trench Backfilling operation.
label | ACCEPTANCE CRITERIA: Depth to be 375mm from subgrade level to invert of pipe or as possible to achieve invert of subsoil pipe to be above soffit level of outlet pipe in the downsteam cesspit.
label | ○ 50mm bedding.
label | ○ Backfilled with scoria 30/10 or similar approved product.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Visual Inspection, Photos showing depths of trench and trench reinstatement
label | ONSITE RESPONSIBILITY: Site Engineer
section | Asbuilts
checkpoint | 10 - As built information
label | VERIFICATION ACTIVITY: Drawings
label | METHODS OR REFERENCE:
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Site Engineer & PM
checkpoint | 11 - RAMM DATA
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | METHODS OR REFERENCE:
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: RAMM SHEET
label | HOLD POINT: In Process Inspection
label | RECORDS: RAMM Sheet
label | ONSITE RESPONSIBILITY: Site Engineer & PM
section | ITP APPROVAL
checkpoint | ITP Approval
label | Prepared By: Ajithkumar Ayyanar
label | Approving Delegate: Denny Jeong
checklist | ITP - Enabling Works - Footpath, Kerb and channel, Pram Crossing, Vehicle Crossing, and Berm | itp |  |  |  |  | ITP - Albany Bus Layovers - Enabling Works - Footpath, Kerb and channel, Pram Crossing, Vehicle Crossing, and Berm
section | Survey - Set out
checkpoint | 1 - Site Set out
label | VERIFICATION ACTIVITY: Surveyor
label | METHODS OR REFERENCE: Surveyor
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 2D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Onsite records/photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | Kerb and Channel
checkpoint | 2 - Kerb & Channel
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - KC0001, KC0030, KC0031
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Kerb & Channel to be laid using precast hand-laid on compacted minimum 300mm GAP65 sub base with CIV > 25. Concrete 20MPa @28 Days
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Clegg Sheet, photos. Concrete Plant Docket
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3 - Channel Level
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match new road level. Channel grade to follow long-sections provided in IFC set.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH channel QA sheet/photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | Footpath
checkpoint | 4 - Concrete Footpaths
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - FP0001
label | FREQUENCY: 10m Intervals
label | ACCEPTANCE CRITERIA: Basecourse - 100mm Gap40 min. thickness
label | ○ Clegg CIV > 12 (frequency every 3m or minimum 4 spots per pour - excluding PX)
label | ○ Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 black oxide with broom finish
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Clegg Sheet, photos. Concrete Plant Docket
label | ONSITE RESPONSIBILITY: Site Engineer
section | Pram Crossing
checkpoint | 5 - Service Covers and Street Furniture
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: AT Contract Specification 14000
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Service covers to be adjusted to new surface levels. Ensure no damage is done to street furniture in the vicinity while carrying out works.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Nil
label | ONSITE RESPONSIBILITY: Site Engineer
section | Grass Berm
checkpoint | 6 - Grass Berms
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones and sowed with grass seeds.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | Wooden Bollard
checkpoint | 7 - Wooden Bollard & chain fence
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: TDM Technical Standards - FE0012
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: 150mm post and 2500 spacing connected with chains.
label | ○ Post 600mm inground with 75mm thick around and 150 thick at top collar with rebar.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | Timber boardwalk
checkpoint | 8 - Timber board walk
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: TES Design drawing RD-001 REVA
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: 150mm x 50mm H5 Timber Blocking
label | ○ 200mm x 100mm H5 Timber Bearer
label | ○ 250mm x 75mm H5 Timber joists 490mm centres.
label | ○ 150mm x 50mm rough sawn H5 Timber decking with non-slip geogrid
label | ○ M16 Bolts Marine Grade stainless steel expansion bolts into concrete rain garden wall
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos/dockets
label | ONSITE RESPONSIBILITY: Site Engineer
section | Asbuilts
checkpoint | 9 - As built information
label | VERIFICATION ACTIVITY: Drawings
label | METHODS OR REFERENCE:
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Site Engineer & PM
checkpoint | 10 - RAMM DATA
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | METHODS OR REFERENCE:
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: RAMM SHEET
label | HOLD POINT: In Process Inspection
label | RECORDS: RAMM Sheet
label | ONSITE RESPONSIBILITY: Site Engineer & PM
section | ITP APPROVAL
checkpoint | ITP Approval
label | Prepared By: Ajithkumar Ayyanar
label | Approving Delegate: Denny Jeong