## ITP-003
|  |  | Inspection and Test Plan - Concrete Construction | [7 empty] | Document # ITP-008
Revision : 1
Client: |  | VIVA Energy |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | VIVA Slip Lane |  | Structural Concrete Construction (Pit Protection Slab) |  | Name: | Jonathan Rau | Name: | Jonathan Rau |  | Name: | Greg Grima
Contract No: |  | II00829C-ERW-001 |  | Specifications: VicRoads Standard Specification - Section 610, 611 and 614
|  |  |  | Structure / Component: Concrete Construction |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: CCP Precast, 78 Forest St, Colac East VIC 3250 |  | Date : | 2025-03-28 | Date : | 2025-03-28 |  | Date : | 2025-03-28
Lot No: | 1 |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are using the correct, complete and most uptodate revision of the design drawings. | Drawings and drawing registers | Visual inspection | ITP Signed | HP* | Project Engineer/ Site Foreman | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP | QMP, TMP, JSEA, SWMS, WP | Visual inspection | ITP Signed | HP* | Project Engineer/ Site Foreman | N/A |  | N/A
1.3 | Materials |  | Prior to commencing any activity | The manufacturer shall submit the concrete mix design details for review by the Superintendent not less than 4 weeks prior to the placement of concrete. This shall include full details of the proposed methods of curing. Manufacturers and suppliers of steel reinforcement materials must be in posession of a current certificate of approval, issued by the ACRS. Reinforcement shall be checked upon delivery and placed on timbers adjacent to site fixing. Manufacturer to specify brand of lifting lugs to be used prior to installation. Lifting lugs to be checked for good condition. Ensure that materials on-site are sufficient for the completion of works. | Design Drawings, VR Section 610 & 611 | Document Review | ITP Signed, Test Certificates, Material Data Sheets. | HP | Project Engineer/ Superintendent | N/A |  | N/A
2 | Construction Works
2.1 | Placement of Steel Reinforcement |  | Each Lot | Ensure steel reinforcement complies with the relevant specification and design drawings. Reinforcement placement shall be coordinated with formwork/mould erection such that is can be placed to the correct size, location, diameter, number and spacing as shown on the drawings. Steel reinforcement shall be supplied in the full lengths shown on the drawings. Alternatively, and where directed by the Superintendent, the Contractor shall splice the bars by lapping. In lapped splices, the reinforcements shall be placed in contact and the specified cover shall be maintained. The lap shall be long enough to develop the full strength of the reinforcement and unless shown on the drawings shall be not less than the tensile or compressive development length determined in accordance with AS 5100.5, Cl 13.1. Ensure reinforcement to be embedded shall be free of mortar, oil, dirt, rust, grease, paint, tar or any other contaminants. Ensure 50mm cover on all steel reinforcement unless noted otherwise on the design drawings. Lifting lugs to be set in formwork as per the manufacturer of the lifting lugs specifications. | Design Drawings, VR Section 611, AS 5100.5, Cl 13.1. | Visual inspection | ITP Signed | HP | Project Engineer/ Superintendent | N/A |  | N/A
2.2 | Formwork/Mould |  | Each Lot | Formwork/mould, including supporting systems, shall be constructed in a fashion that ensures the specified quality of concrete finish is achieved. Forms shall be clean and free of majore surface defects. Formwork/mould shall be constructed and shall be sufficient stiffness to tolerate the rate of concrete placement and high frequency vibration, and shall be of uniform stiffness to avoid causing varying vibration aplitudes over the formwork surfaces during compaction of concrete. All corners shall have 12 x 12 mm fillets or chamfers unless noted otherwise. Formwork/mould shall not be placed in locations where steel reinforcement and other fixtures cannot be inspected and/or will be left open until inspections have been completed. | VR Section 614 | Visual inspection | ITP Signed / Certificate of Compliance - Formwork Inspection | HP | Project Engineer | N/A |  | N/A
2.3 | Placement of Concrete |  | Each Lot | Ensure concrete being used for Pit Protection Slab complies with the relevant specification and design drawings. Ensure that the dimensions, reinforcement and embedments have been checked against the specifciation and design drawings. Air and concrete temperatures shall be recorded. Concrete shall only be placed under the following conditions: - Air temperature 5 to 35 deg C. - Concrete temperature 10 to 30 deg C. Measured Air Temperature: Measured Concrete Temperature: Concrete shall be placed from a height not exceeding 2m. Concrete pumping shall be used where access is restricted. Prior to the commencement of placing concrete by pumping, the initial discharge of concrete shall be pumped to waste until a consistent workable mix is discharged. In continuous concrete pours the maximum time lag between truck loads on site shall not exceed 60 minutes. | VR Section 610 | Visual inspection | ITP Signed | HP | Project Engineer/ Superintendent | N/A |  | N/A
2.4 | Removal of Formwork/mould |  | Each Lot | Formwork/mould shall not be disturbed or adjusted during the concreting operation and shall remain in position and undisturbed until the minimum removal times given in VicRoads Table 610.251 have elapsed, after completion of the placing of concrete. | VR Section 610.25 | Visual inspection | ITP Signed | HP* | Project Engineer | N/A |  | N/A
2.5 | Curing |  | Each Lot | Ensure the method and period of curing is in accordance with specifications outlined in VR 610. | VR Section 610.23 | Visual inspection | ITP Signed | HP* | Project Engineer | N/A |  | N/A
2.6 | Dimensional Tolerances |  | Each Lot | Dimensional tolerances shall be checked against the requirements in accordance with specications agreed with the client. The concrete shall be inspected for quality of finish and compliance with the surface class requirements. | VR Section 610.47 | Visual inspection | ITP Signed | HP* | Project Engineer | N/A |  | N/A
3 | Quality Control Testing
3.1 | Concrete Testing |  | Prior to commencing any activity | All concrete shall be sampled and tested in accordance with AS 1012. The minimum number of test samples shall be in accordance with Table 610.161 in the VicRoads Standard. | VR Section 610.16 | Test Point | ITP Signed | HP* | Project Engineer | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.