## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [6 empty] | Document # ITP-01
Revision : 1
Client: |  | Ballarat City Council |  | Construction Process: | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Gillies Rd (Jubilee to Millers Rd) |  | Subgrade Preperation | Name: | Jarvis Gleeson | Name: |  |  | Name:
Contract No: |  |  |  | Specifications:
|  |  |  | Structure / Component: | Signed : | J.GLEESON | Signed : |  |  | Signed :
|  |  |  | Location: | Date : | 2025-03-28 | Date : |  |  | Date :
Lot No: |  |  | Lot Details: |  |  |  |  | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Inspection / Test Method | Acceptance Criteria | Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | Date
1 | Construction Works
1.01 | Site clearing & preperation |  | Visual Inspection; removal of vegetation, debris, and organic matter | Surface must be free of vegetation and debris; organic content <5% | Visual check; field sampling if required | Daily field report/Photos | IP | Site Engineer | N/A
1.02 | Subgrade grading verification |  | Check final grading and crossfall for drainage | Slope and crossfall as per design specifications | Surveying equipment | Survey reports | IP | Site Engineer | N/A
1.03 | Moisture content testing |  | Measure natural moisture content (NMC) | NMC within +/- of optimum moisture content (OMC) | calibrated moisture meter | moisture logs | IP | Site Engineer | N/A
1.05 | Proof rolling |  | Load bearing assessment using a proof roll test | No deflections, pumping, or soft spots, uninform bearing capacity | Loaded water cart or roller; visual and manual measurement | Field test results/photos | IP | Site Engineer | N/A
COMMENTS |  | _______________________________________________________________________________________________________________________________________________________________ ________________________________________________________________________________________________________________________________________________________________
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: | [5 empty] | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent