## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [6 empty] | Document # ITP-02
Revision : 1
Client: |  | Ballarat City Council |  | Construction Process: | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Gillies Rd (Jubilee to Millers Rd) |  | Red Dredge Application | Name: | Jarvis Gleeson | Name: |  |  | Name:
Contract No: |  |  |  | Specifications:
|  |  |  | Structure / Component: | Signed : | J.GLEESON | Signed : |  |  | Signed :
|  |  |  | Location: | Date : | 2025-03-26 | Date : |  |  | Date :
Lot No: |  |  | Lot Details: |  |  |  |  | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Inspection / Test Method | Acceptance Criteria | Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | Date
1 | Construction Works
1.01 | Material delivery and verification |  | Verify red dredge quality and source certification | Red dredge conforms to design specifications | Supplier certification review; visual check | Delivery dockets, certification documents | IP | Site Engineer | N/A
1.02 | Equipment calibration check |  | Verification of mixing and application equipment calibration | Equipment calibrated and within acceptable tolerances | Calibration log review; instrument checks | Calibration certificates | IP | Site Engineer | N/A
1.04 | Blending process |  | Visual inspection of blending uniformity | even distribution of red dredge in the subgrade | Field observation; test pits | Daily field logs/photos | IP | Site Engineer | N/A
1.05 | Sieve analysis |  | Laboratory test of particle size distribution | Results conform to design gradation requirements | Collect representative samples; laboratory sieving | Lab report | IP | Site Engineer | N/A
1.06 | Hydrometer analysis |  | Laboratory test for clay content (<0.002mm) | Clay content within specified limits (<15%) | Collect sampls; Hydrometer test | Lab report | IP | Site Engineer | N/A
1.07 | Atterberg limits |  | Laboratory test for plasticity (Liquid and plastic limits) | Limits within accpetable design ranges | Sample collection; Lab testing | Lab report | IP | Site Engineer | N/A
1.08 | Moisture content testing |  | Field measurements of NMC | Moisture content within OMC range | Moisture meter measurment | Moisture logs | IP | Site Engineer | N/A
1.09 | Organic content testing |  | Loss on ignition test | Organic content <5% | Laboratory testing | Lab report | IP | Site Engineer | N/A
1.1 | Final Sign Off |  | Sign off from superintendent/ terra-3000 representative | Above ITP | Review works methodology and confirm it has been followed | This ITP | HP | Superintendent |  | N/A
COMMENTS |  | _______________________________________________________________________________________________________________________________________________________________ ________________________________________________________________________________________________________________________________________________________________
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: | [5 empty] | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent