## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [6 empty] | Document # ITP-03
Revision : 1
Client: |  | Ballarat City Council |  | Construction Process: | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Gillies Rd (Jubilee to Millers Rd) |  | Terra 3000 Stabilization | Name: | Jarvis Gleeson | Name: |  |  | Name:
Contract No: |  |  |  | Specifications:
|  |  |  | Structure / Component: | Signed : | J.GLEESON | Signed : |  |  | Signed :
|  |  |  | Location: | Date : | 2025-03-26 | Date : |  |  | Date :
Lot No: |  |  | Lot Details: |  |  |  |  | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Inspection / Test Method | Acceptance Criteria | Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | Date
1 | Construction Works
1.01 | Material Preparation & Dilution |  | Verify dilution rate (1:20 with water) | Correct dilution per supplier guidelines | Field observation; on site dilution check | Field logs; supplier documentation | IP | Site Engineer | N/A
1.02 | Ambient conditions check |  | Monitor ambient tempreture and humidity | Within acceptable range for Terra-3000 application | Weather report; field log | Weather log; field notes | IP | Site Engineer | N/A
1.04 | Application and blending process |  | Visual inspection of application and blending | Even and thorough mixing of Terra-3000 into the subgrade. | Visual inspection; core sampling | Daily field log/Photos | IP | Site Engineer | N/A
1.05 | blending depth verification |  | Check consistency of mix depth across the subgrade | Full depth achieved as per design | Core sampling/Manual Depth measurement | Field measurement records | IP | Site Engineer | N/A
1.06 | Moisture content testing |  | Field measurement of NMC post Terra-3000 application | NMC within target range (aligned to OMC) | Moisture meter mesurement | Moisture logs | IP | Site Engineer | N/A
1.07 | Compaction testing |  | Field density test of stabilized layer | Achieve or exceed required dry density | Nuclear density guage or sand cone test | Compaction testing | IP | Site Engineer | N/A
1.08 | Uniformity and consistency check |  | Visual and physical inspection for uniform stabilization | Consistent appearance and texture throughout the area | Field inspection | Field inspection logs | IP | Site Engineer | N/A
1.09 | Final Sign Off |  | Sign off from superintendent/ terra-3000 representative | Above ITP | Review works methodology and confirm it has been followed | This ITP | HP | Superintendent |  | N/A
COMMENTS |  | _______________________________________________________________________________________________________________________________________________________________ ________________________________________________________________________________________________________________________________________________________________
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: | [5 empty] | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent