## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [6 empty] | Document # ITP-05
Revision : 1
Client: |  | Ballarat City Council |  | Construction Process: | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Gillies Rd (Jubilee to Millers Rd) |  | Shoulder & Drainage Rehabilitation | Name: | Jarvis Gleeson | Name: |  |  | Name:
Contract No: |  |  |  | Specifications:
|  |  |  | Structure / Component: | Signed : | J.GLEESON | Signed : |  |  | Signed :
|  |  |  | Location: | Date : | 2025-03-28 | Date : |  |  | Date :
Lot No: |  |  | Lot Details: |  |  |  |  | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Inspection / Test Method | Acceptance Criteria | Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | Date
1 | Construction Works
1.01 | Site preparation |  | Visual inspection | Area cleared of debris, esisting conditions recorded | Site walkthrough | Daily site report/Photos | IP | Site Engineer | N/A
1.02 | Swale drain excavation |  | Depth, width & slope check | Excavation to design depth, width & gradient | Design drawings and survey | Survey report | IP | Site Engineer | N/A
1.03 | subgrade preparation |  | Proof rolling | No excessive movement, pumping, or deflection | Observational assessment | Photos | IP | Site Engineer | N/A
1.04 | Swale drain formation |  | grading and shaping | Drain profile and slopes meet design | Design drawings | Survey report | IP | Site Engineer | N/A
1.05 | Compaction of drain base |  | Density testing | Minimum specified density | AS 1289.5.1.1 | Compaction test report | IP | Site Engineer | N/A
1.06 | Topsoil placement (if required) |  | Visual inspection & material test | Topsoil meets grading and organic content specifications | AS 4419 | Material test report | IP | Site Engineer | N/A
1.07 | Vegetation establishment (if required) |  | Visual check | Vegetation coverage as per specifications | Design Drawings/Seeding specs | Site report/photos | IP | Site Engineer | N/A
1.08 | Shoulder material placement |  | Visual & grading test | Material conforms to specifications | Material specifications | Delivery dockets | IP | Site Engineer | N/A
1.1 | Final Inspection |  | Walkthrough & drainage function test | No defects, positive drainage flow achieved | Site walkthrough | This ITP | HP | Superintendent |  | N/A
COMMENTS |  | _______________________________________________________________________________________________________________________________________________________________ ________________________________________________________________________________________________________________________________________________________________
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: | [5 empty] | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent