## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 1.01 - Subgrade Preparation | itp |  |  |  |  | 1.01 - Subgrade Preparation Rev1
section | 1 - Construction Works
checkpoint | 1.01 - Site clearing & preperation
label | INSPECTION / TEST METHOD - Visual Inspection; removal of vegetation, debris, and organic matter
label | ACCEPTANCE CRITERIA - Surface must be free of vegetation and debris; organic content <5%
label | METHOD - Visual check; field sampling if required
label | RECORD OF CONFORMITY - Daily field report/Photos
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.02 - Subgrade grading verification
label | INSPECTION / TEST METHOD - Check final grading and crossfall for drainage
label | ACCEPTANCE CRITERIA - Slope and crossfall as per design specifications
label | METHOD - Surveying equipment
label | RECORD OF CONFORMITY - Survey reports
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.03 - Moisture content testing
label | INSPECTION / TEST METHOD - Measure natural moisture content (NMC)
label | ACCEPTANCE CRITERIA - NMC within +/- of optimum moisture content (OMC)
label | METHOD - calibrated moisture meter
label | RECORD OF CONFORMITY - moisture logs
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.05 - Proof rolling
label | INSPECTION / TEST METHOD - Load bearing assessment using a proof roll test
label | ACCEPTANCE CRITERIA - No deflections, pumping, or soft spots, uninform bearing capacity
label | METHOD - Loaded water cart or roller; visual and manual measurement
label | RECORD OF CONFORMITY - Field test results/photos
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | 1.02 - Red Dredge Application & Blending | itp |  |  |  |  | 1.02 - Red Dredge Application & Blending Rev1
section | 1 - Construction Works
checkpoint | 1.01 - Material delivery and verification
label | INSPECTION / TEST METHOD - Verify red dredge quality and source certification
label | ACCEPTANCE CRITERIA - Red dredge conforms to design specifications
label | METHOD - Supplier certification review; visual check
label | RECORD OF CONFORMITY - Delivery dockets, certification documents
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.02 - Equipment calibration check
label | INSPECTION / TEST METHOD - Verification of mixing and application equipment calibration
label | ACCEPTANCE CRITERIA - Equipment calibrated and within acceptable tolerances
label | METHOD - Calibration log review; instrument checks
label | RECORD OF CONFORMITY - Calibration certificates
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.04 - Blending process
label | INSPECTION / TEST METHOD - Visual inspection of blending uniformity
label | ACCEPTANCE CRITERIA - even distribution of red dredge in the subgrade
label | METHOD - Field observation; test pits
label | RECORD OF CONFORMITY - Daily field logs/photos
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.05 - Sieve analysis
label | INSPECTION / TEST METHOD - Laboratory test of particle size distribution
label | ACCEPTANCE CRITERIA - Results conform to design gradation requirements
label | METHOD - Collect representative samples; laboratory sieving
label | RECORD OF CONFORMITY - Lab report
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.06 - Hydrometer analysis
label | INSPECTION / TEST METHOD - Laboratory test for clay content (<0.002mm)
label | ACCEPTANCE CRITERIA - Clay content within specified limits (<15%)
label | METHOD - Collect sampls; Hydrometer test
label | RECORD OF CONFORMITY - Lab report
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.07 - Atterberg limits
label | INSPECTION / TEST METHOD - Laboratory test for plasticity (Liquid and plastic limits)
label | ACCEPTANCE CRITERIA - Limits within accpetable design ranges
label | METHOD - Sample collection; Lab testing
label | RECORD OF CONFORMITY - Lab report
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.08 - Moisture content testing
label | INSPECTION / TEST METHOD - Field measurements of NMC
label | ACCEPTANCE CRITERIA - Moisture content within OMC range
label | METHOD - Moisture meter measurment
label | RECORD OF CONFORMITY - Moisture logs
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.09 - Organic content testing
label | INSPECTION / TEST METHOD - Loss on ignition test
label | ACCEPTANCE CRITERIA - Organic content <5%
label | METHOD - Laboratory testing
label | RECORD OF CONFORMITY - Lab report
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.10 - Final Sign Off
label | INSPECTION / TEST METHOD - Sign off from superintendent/ terra-3000 representative
label | ACCEPTANCE CRITERIA - Above ITP
label | METHOD - Review works methodology and confirm it has been followed
label | RECORD OF CONFORMITY - This ITP
label | HP
label | RESPONSIBILITY - Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | 1.03 - Terra-3000 Stabilization | itp |  |  |  |  | 1.03 - Terra-3000 Stabilization Rev1
section | 1 - Construction Works
checkpoint | 1.01 - Material Preparation & Dilution
label | INSPECTION / TEST METHOD - Verify dilution rate (1:20 with water)
label | ACCEPTANCE CRITERIA - Correct dilution per supplier guidelines
label | METHOD - Field observation; on site dilution check
label | RECORD OF CONFORMITY - Field logs; supplier documentation
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.02 - Ambient conditions check
label | INSPECTION / TEST METHOD - Monitor ambient tempreture and humidity
label | ACCEPTANCE CRITERIA - Within acceptable range for Terra-3000 application
label | METHOD - Weather report; field log
label | RECORD OF CONFORMITY - Weather log; field notes
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.04 - Application and blending process
label | INSPECTION / TEST METHOD - Visual inspection of application and blending
label | ACCEPTANCE CRITERIA - Even and thorough mixing of Terra-3000 into the subgrade.
label | METHOD - Visual inspection; core sampling
label | RECORD OF CONFORMITY - Daily field log/Photos
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.05 - blending depth verification
label | INSPECTION / TEST METHOD - Check consistency of mix depth across the subgrade
label | ACCEPTANCE CRITERIA - Full depth achieved as per design
label | METHOD - Core sampling/Manual Depth measurement
label | RECORD OF CONFORMITY - Field measurement records
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.06 - Moisture content testing
label | INSPECTION / TEST METHOD - Field measurement of NMC post Terra-3000 application
label | ACCEPTANCE CRITERIA - NMC within target range (aligned to OMC)
label | METHOD - Moisture meter mesurement
label | RECORD OF CONFORMITY - Moisture logs
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.07 - Compaction testing
label | INSPECTION / TEST METHOD - Field density test of stabilized layer
label | ACCEPTANCE CRITERIA - Achieve or exceed required dry density
label | METHOD - Nuclear density guage or sand cone test
label | RECORD OF CONFORMITY - Compaction testing
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.08 - Uniformity and consistency check
label | INSPECTION / TEST METHOD - Visual and physical inspection for uniform stabilization
label | ACCEPTANCE CRITERIA - Consistent appearance and texture throughout the area
label | METHOD - Field inspection
label | RECORD OF CONFORMITY - Field inspection logs
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.09 - Final Sign Off
label | INSPECTION / TEST METHOD - Sign off from superintendent/ terra-3000 representative
label | ACCEPTANCE CRITERIA - Above ITP
label | METHOD - Review works methodology and confirm it has been followed
label | RECORD OF CONFORMITY - This ITP
label | HP
label | RESPONSIBILITY - Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | 1.05 - Shoulder & Drainage Rehabilitation | itp |  |  |  |  | 1.05 - Shoulder & Drainage Rehabilitation Rev1
section | 1 - Construction Works
checkpoint | 1.01 - Site preparation
label | INSPECTION / TEST METHOD - Visual inspection
label | ACCEPTANCE CRITERIA - Area cleared of debris, esisting conditions recorded
label | METHOD - Site walkthrough
label | RECORD OF CONFORMITY - Daily site report/Photos
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.02 - Swale drain excavation
label | INSPECTION / TEST METHOD - Depth, width & slope check
label | ACCEPTANCE CRITERIA - Excavation to design depth, width & gradient
label | METHOD - Design drawings and survey
label | RECORD OF CONFORMITY - Survey report
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.03 - subgrade preparation
label | INSPECTION / TEST METHOD - Proof rolling
label | ACCEPTANCE CRITERIA - No excessive movement, pumping, or deflection
label | METHOD - Observational assessment
label | RECORD OF CONFORMITY - Photos
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.04 - Swale drain formation
label | INSPECTION / TEST METHOD - grading and shaping
label | ACCEPTANCE CRITERIA - Drain profile and slopes meet design
label | METHOD - Design drawings
label | RECORD OF CONFORMITY - Survey report
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.05 - Compaction of drain base
label | INSPECTION / TEST METHOD - Density testing
label | ACCEPTANCE CRITERIA - Minimum specified density
label | METHOD - AS 1289.5.1.1
label | RECORD OF CONFORMITY - Compaction test report
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.06 - Topsoil placement (if required)
label | INSPECTION / TEST METHOD - Visual inspection & material test
label | ACCEPTANCE CRITERIA - Topsoil meets grading and organic content specifications
label | METHOD - AS 4419
label | RECORD OF CONFORMITY - Material test report
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.07 - Vegetation establishment (if required)
label | INSPECTION / TEST METHOD - Visual check
label | ACCEPTANCE CRITERIA - Vegetation coverage as per specifications
label | METHOD - Design Drawings/Seeding specs
label | RECORD OF CONFORMITY - Site report/photos
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.08 - Shoulder material placement
label | INSPECTION / TEST METHOD - Visual & grading test
label | ACCEPTANCE CRITERIA - Material conforms to specifications
label | METHOD - Material specifications
label | RECORD OF CONFORMITY - Delivery dockets
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.10 - Final Inspection
label | INSPECTION / TEST METHOD - Walkthrough & drainage function test
label | ACCEPTANCE CRITERIA - No defects, positive drainage flow achieved
label | METHOD - Site walkthrough
label | RECORD OF CONFORMITY - This ITP
label | HP
label | RESPONSIBILITY - Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP