## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Floor Preparation
section | Details
checkpoint | Check area clear of all other trades and their materials
checkpoint | Grind Floor
checkpoint | Are there any cracks that require remediation?
checkpoint | Remediate cracks
checkpoint | Apply feather coat, Sanded, Edges
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Damtec | [5 empty] | Damtec (Level 1)
section | Details
checkpoint-no-status | N/A for Lvl 1
checklist | Vinyl Installation
section | Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Check if prep is to an acceptable standard
checkpoint | Check walls are acceptable for vinyl coving
section | Installation
checkpoint | Confirm direction as per cutting plan
checkpoint | Glue out floors
checkpoint | Install damtec
checkpoint | Check damtec is suitabe to install vinyl over
checkpoint | Glue out floors
checkpoint | Install vinyl
checkpoint | Roll with heavy roller to secure bond and elimate bubbles
checkpoint | Weld joins
checkpoint | Wipe down the floor to remove adhesive residue or dust
checkpoint | Check if stairs are ready for nosings
checkpoint | Install nosings
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Report for inspection
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Carpet Tile Installation
section | Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Check floor if prep is required
checkpoint | Measure area
section | Installation
checkpoint | Confirm carpet tile pattern direction/layout
checkpoint | Glue out floors
checkpoint | Install carpet tiles
checkpoint | Tiles are cut flush to skirtings
checkpoint | Install trims as applicable
checkpoint | All tiles are sitting correctly (no tiles lifting)
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Clean any excess glue
checkpoint | Report for inspection
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Carpet Installation
section | Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Check floor if prep is required
section | Installation
checkpoint | Install carpet including smoothedge and underlay as applicable
checkpoint | Install trims as applicable
checkpoint | Smoothedge nails not protruding through carpet
checkpoint | All temporary nails removed
checkpoint | All strands cut off
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Report for inspection
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Stair Installation
section | Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Check floor if prep is required
checkpoint | Measure nosings
section | Installation
checkpoint | Confirm area is ready to install nosings
checkpoint | Install nosings
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Report for inspection
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL