## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Floor Preparation
section | Details
checkpoint | Check area clear of all other trades and their materials
checkpoint | Grind Floor
checkpoint | Are there any cracks that require remediation?
checkpoint | Remediate cracks
checkpoint | Apply feather coat, Sanded, Edges
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Vinyl Installation (Basic)
section | Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Check floor for U3 (3mm variance over 3m)
checkpoint | Check wall for smoothness where coving
checkpoint | Measure area
checkpoint | Acclimatise vinyl / vinyl planks what is required for job
section | Installation
checkpoint | Confirm vinyl / vinyl planks layout direction
checkpoint | Confirm coving location/type as applicable
checkpoint | Glue out floors
checkpoint | Install vinyl / vinyl planks as required
checkpoint | Install coving & capping/sealant as applicable
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Clean any excess glue
checkpoint | Report for inspection
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Wall Vinyl Installation
section | Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Check walls are prepared to a Level 4 finish with a seal coat
checkpoint | Measure area
checkpoint | Acclimatise vinyl
section | Installation
checkpoint | Confirm wall vinyl direction as per cutting plan
checkpoint | Confirm wall vinyl type as per finishes schedule
checkpoint | Glue out wall
checkpoint | Install wall vinyl
checkpoint | Install coving & capping/sealant as applicable
checkpoint | Weld joins
checkpoint | Wipe down the wall to remove adhesive residue or dust
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Report for inspection
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Carpet Tile Installation (Basic)
section | Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Check floor if prep is required
checkpoint | Measure area
section | Installation
checkpoint | Confirm carpet tile pattern direction/layout
checkpoint | Confirm flotex carpet pattern direction/layout as applicable
checkpoint | Glue out floors
checkpoint | Install carpet tiles
checkpoint | Install flotex carpet as applicable
checkpoint | Install trims as applicable
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Clean any excess glue
checkpoint | Report for inspection
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Stair Installation
section | Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Measure area, stairs and nosings as required
checkpoint | Acclimatise vinyl / carpet / carpet tiles if required
section | Installation
checkpoint | Confirm layout direction if acquired for stairs
checkpoint | Install vinyl / carpet / carpet tiles as required
checkpoint | Install nosings - check the correct profile is used
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Clean any excess glue
checkpoint | Report for inspection
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL