## Sheet1
1 | Identification and location of shallow services | Measure depth of cover to utility services | Trained contractor staff | Two measures per service (each side of the road) | Services sufficently deep to avoid damage. Otherwise consider relocation or concrete cap | Mandatory HOLD POINT Designer Signoff Required | Marked up sheet | Project Engineer | Designer Signoff | 1 - Identification and location of shallow services | VERIFICATION ACTIVITY: Measure depth of cover to utility services | METHODS OR REFERENCE: Trained contractor staff | FREQUENCY: Two measures per service (each side of the road) | ACCEPTANCE CRITERIA: Services sufficently deep to avoid damage. Otherwise consider relocation or concrete cap | TYPE: Mandatory HOLD POINT Designer Signoff Required | RECORDS (Responsibility): Marked up sheet | ONSITE RESPONSIBILITY: Project Engineer | CONTRACT MANAGER SIGNOFF: Designer Signoff | 1 - Identification and location of shallow services
VERIFICATION ACTIVITY: Measure depth of cover to utility services
METHODS OR REFERENCE: Trained contractor staff
FREQUENCY: Two measures per service (each side of the road)
ACCEPTANCE CRITERIA: Services sufficently deep to avoid damage. Otherwise consider relocation or concrete cap
TYPE: Mandatory HOLD POINT Designer Signoff Required
RECORDS (Responsibility): Marked up sheet
ONSITE RESPONSIBILITY: Project Engineer
CONTRACT MANAGER SIGNOFF: Designer Signoff