## Sheet1
1 | Site Set out | Surveyor | Surveyor | Everysite | Site Set out as per construction plan provided with GPS location and 2D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable. | Inprocess Inspection | Onsite records/photos | Site Engineer | 1 - Site Set out | VERIFICATION ACTIVITY: Surveyor | METHODS OR REFERENCE: Surveyor | FREQUENCY: Everysite | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 2D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable. | HOLD POINT: Inprocess Inspection | RECORDS: Onsite records/photos | ONSITE RESPONSIBILITY: Site Engineer | 1 - Site Set out
2 | Kerb CHAR(AMP) Channel | QA FORM | TDM Technical Standards - KC0001, KC0030, KC0031 | Everysite | Kerb CHAR(AMP) Channel to be laid using precast hand-laid on compacted minimum 300mm GAP65 sub base with CIV > 25. Concrete 20MPa @28 Days | Inprocess Inspection | Clegg Sheet, photos. Concrete Plant Docket | Site Engineer | 2 - Kerb CHAR(AMP) Channel | VERIFICATION ACTIVITY: QA FORM | METHODS OR REFERENCE: TDM Technical Standards - KC0001, KC0030, KC0031 | FREQUENCY: Everysite | ACCEPTANCE CRITERIA: Kerb CHAR(AMP) Channel to be laid using precast hand-laid on compacted minimum 300mm GAP65 sub base with CIV > 25. Concrete 20MPa @28 Days | HOLD POINT: Inprocess Inspection | RECORDS: Clegg Sheet, photos. Concrete Plant Docket | ONSITE RESPONSIBILITY: Site Engineer | VERIFICATION ACTIVITY: Surveyor
3 | Channel Level | QA FORM | TDM Technical Standards - KC0001 | Everysite | Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match new road level. Channel grade to follow long-sections provided in IFC set. | Inprocess Inspection | FH channel QA sheet/photos | Site Engineer | 3 - Channel Level | VERIFICATION ACTIVITY: QA FORM | METHODS OR REFERENCE: TDM Technical Standards - KC0001 | FREQUENCY: Everysite | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match new road level. Channel grade to follow long-sections provided in IFC set. | HOLD POINT: Inprocess Inspection | RECORDS: FH channel QA sheet/photos | ONSITE RESPONSIBILITY: Site Engineer | METHODS OR REFERENCE: Surveyor
4 | Concrete Footpaths | QA FORM | TDM Technical Standards - FP0001 | 10m Intervals | Basecourse - 100mm Gap40 min. thickness Clegg CIV > 12 (frequency every 3m or minimum 4 spots per pour - excluding PX) Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 black oxide with broom finish | Inprocess Inspection | Clegg Sheet, photos. Concrete Plant Docket | Site Engineer | 4 - Concrete Footpaths | VERIFICATION ACTIVITY: QA FORM | METHODS OR REFERENCE: TDM Technical Standards - FP0001 | FREQUENCY: 10m Intervals | ACCEPTANCE CRITERIA: Basecourse - 100mm Gap40 min. thickness Clegg CIV > 12 (frequency every 3m or minimum 4 spots per pour - excluding PX) Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 black oxide with broom finish | HOLD POINT: Inprocess Inspection | RECORDS: Clegg Sheet, photos. Concrete Plant Docket | ONSITE RESPONSIBILITY: Site Engineer | FREQUENCY: Everysite
5 | Service Covers and Street Furniture | Visual | AT Contract Specification 14000 | Everysite | Service covers to be adjusted to new surface levels. Ensure no damage is done to street furniture in the vicinity while carrying out works. | Inprocess Inspection | Nil | Site Engineer | 5 - Service Covers and Street Furniture | VERIFICATION ACTIVITY: Visual | METHODS OR REFERENCE: AT Contract Specification 14000 | FREQUENCY: Everysite | ACCEPTANCE CRITERIA: Service covers to be adjusted to new surface levels. Ensure no damage is done to street furniture in the vicinity while carrying out works. | HOLD POINT: Inprocess Inspection | RECORDS: Nil | ONSITE RESPONSIBILITY: Site Engineer | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 2D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable.
6 | Grass Berms | Visual | ATCOP Section 12 Footpaths and Pedestrian Facilities | Everysite | 100mm thick layer of compacted approved quality topsoil, free of weeds and stones and sowed with grass seeds. | Inprocess Inspection | Photos | Site Engineer | 6 - Grass Berms | VERIFICATION ACTIVITY: Visual | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities | FREQUENCY: Everysite | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones and sowed with grass seeds. | HOLD POINT: Inprocess Inspection | RECORDS: Photos | ONSITE RESPONSIBILITY: Site Engineer | HOLD POINT: Inprocess Inspection
7 | Wooden Bollard CHAR(AMP) chain fence | Visual | TDM Technical Standards - FE0012 | Everysite | 150mm post and 2500 spacing connected with chains. Post 600mm inground with 75mm thick around and 150 thick at top collar with rebar. | Inprocess Inspection | Photos | Site Engineer | 7 - Wooden Bollard CHAR(AMP) chain fence | VERIFICATION ACTIVITY: Visual | METHODS OR REFERENCE: TDM Technical Standards - FE0012 | FREQUENCY: Everysite | ACCEPTANCE CRITERIA: 150mm post and 2500 spacing connected with chains. Post 600mm inground with 75mm thick around and 150 thick at top collar with rebar. | HOLD POINT: Inprocess Inspection | RECORDS: Photos | ONSITE RESPONSIBILITY: Site Engineer | RECORDS: Onsite records/photos
8 | Timber board walk | Visual | TES Design drawing RD-001 REVA | Everysite | 150mm x 50mm H5 Timber Blocking 200mm x 100mm H5 Timber Bearer 250mm x 75mm H5 Timber joists 490mm centres. 150mm x 50mm rough sawn H5 Timber decking with non-slip geogrid M16 Bolts Marine Grade stainless steel expansion bolts into concrete rain garden wall | Inprocess Inspection | Photos/dockets | Site Engineer | 8 - Timber board walk | VERIFICATION ACTIVITY: Visual | METHODS OR REFERENCE: TES Design drawing RD-001 REVA | FREQUENCY: Everysite | ACCEPTANCE CRITERIA: 150mm x 50mm H5 Timber Blocking 200mm x 100mm H5 Timber Bearer 250mm x 75mm H5 Timber joists 490mm centres. 150mm x 50mm rough sawn H5 Timber decking with non-slip geogrid M16 Bolts Marine Grade stainless steel expansion bolts into concrete rain garden wall | HOLD POINT: Inprocess Inspection | RECORDS: Photos/dockets | ONSITE RESPONSIBILITY: Site Engineer | ONSITE RESPONSIBILITY: Site Engineer
9 | As built information | Drawings |  | Every Site | As built drawings | In Process Inspection | Asbuilt records | Site Engineer CHAR(AMP) PM | 9 - As built information | VERIFICATION ACTIVITY: Drawings | METHODS OR REFERENCE: | FREQUENCY: Every Site | ACCEPTANCE CRITERIA: As built drawings | HOLD POINT: In Process Inspection | RECORDS: Asbuilt records | ONSITE RESPONSIBILITY: Site Engineer CHAR(AMP) PM | 2 - Kerb CHAR(AMP) Channel
10 | RAMM DATA | RAMM DATA SHEET |  | Every Site | RAMM SHEET | In Process Inspection | RAMM Sheet | Site Engineer CHAR(AMP) PM | 10 - RAMM DATA | VERIFICATION ACTIVITY: RAMM DATA SHEET | METHODS OR REFERENCE: | FREQUENCY: Every Site | ACCEPTANCE CRITERIA: RAMM SHEET | HOLD POINT: In Process Inspection | RECORDS: RAMM Sheet | ONSITE RESPONSIBILITY: Site Engineer CHAR(AMP) PM | VERIFICATION ACTIVITY: QA FORM
METHODS OR REFERENCE: TDM Technical Standards - KC0001, KC0030, KC0031
FREQUENCY: Everysite
ACCEPTANCE CRITERIA: Kerb CHAR(AMP) Channel to be laid using precast hand-laid on compacted minimum 300mm GAP65 sub base with CIV > 25. Concrete 20MPa @28 Days
HOLD POINT: Inprocess Inspection
RECORDS: Clegg Sheet, photos. Concrete Plant Docket
ONSITE RESPONSIBILITY: Site Engineer
3 - Channel Level
VERIFICATION ACTIVITY: QA FORM
METHODS OR REFERENCE: TDM Technical Standards - KC0001
FREQUENCY: Everysite
ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match new road level. Channel grade to follow long-sections provided in IFC set.
HOLD POINT: Inprocess Inspection
RECORDS: FH channel QA sheet/photos
ONSITE RESPONSIBILITY: Site Engineer
4 - Concrete Footpaths
VERIFICATION ACTIVITY: QA FORM
METHODS OR REFERENCE: TDM Technical Standards - FP0001
FREQUENCY: 10m Intervals
ACCEPTANCE CRITERIA: Basecourse - 100mm Gap40 min. thickness Clegg CIV > 12 (frequency every 3m or minimum 4 spots per pour - excluding PX) Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 black oxide with broom finish
HOLD POINT: Inprocess Inspection
RECORDS: Clegg Sheet, photos. Concrete Plant Docket
ONSITE RESPONSIBILITY: Site Engineer
5 - Service Covers and Street Furniture
VERIFICATION ACTIVITY: Visual
METHODS OR REFERENCE: AT Contract Specification 14000
FREQUENCY: Everysite
ACCEPTANCE CRITERIA: Service covers to be adjusted to new surface levels. Ensure no damage is done to street furniture in the vicinity while carrying out works.
HOLD POINT: Inprocess Inspection
RECORDS: Nil
ONSITE RESPONSIBILITY: Site Engineer
6 - Grass Berms
VERIFICATION ACTIVITY: Visual
METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
FREQUENCY: Everysite
ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones and sowed with grass seeds.
HOLD POINT: Inprocess Inspection
RECORDS: Photos
ONSITE RESPONSIBILITY: Site Engineer
7 - Wooden Bollard CHAR(AMP) chain fence
VERIFICATION ACTIVITY: Visual
METHODS OR REFERENCE: TDM Technical Standards - FE0012
FREQUENCY: Everysite
ACCEPTANCE CRITERIA: 150mm post and 2500 spacing connected with chains. Post 600mm inground with 75mm thick around and 150 thick at top collar with rebar.
HOLD POINT: Inprocess Inspection
RECORDS: Photos
ONSITE RESPONSIBILITY: Site Engineer
8 - Timber board walk
VERIFICATION ACTIVITY: Visual
METHODS OR REFERENCE: TES Design drawing RD-001 REVA
FREQUENCY: Everysite
ACCEPTANCE CRITERIA: 150mm x 50mm H5 Timber Blocking 200mm x 100mm H5 Timber Bearer 250mm x 75mm H5 Timber joists 490mm centres. 150mm x 50mm rough sawn H5 Timber decking with non-slip geogrid M16 Bolts Marine Grade stainless steel expansion bolts into concrete rain garden wall
HOLD POINT: Inprocess Inspection
RECORDS: Photos/dockets
ONSITE RESPONSIBILITY: Site Engineer
9 - As built information
VERIFICATION ACTIVITY: Drawings
METHODS OR REFERENCE:
FREQUENCY: Every Site
ACCEPTANCE CRITERIA: As built drawings
HOLD POINT: In Process Inspection
RECORDS: Asbuilt records
ONSITE RESPONSIBILITY: Site Engineer CHAR(AMP) PM
10 - RAMM DATA
VERIFICATION ACTIVITY: RAMM DATA SHEET
METHODS OR REFERENCE:
FREQUENCY: Every Site
ACCEPTANCE CRITERIA: RAMM SHEET
HOLD POINT: In Process Inspection
RECORDS: RAMM Sheet
ONSITE RESPONSIBILITY: Site Engineer CHAR(AMP) PM