## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Job Details
section | Details
checkpoint | Site Info
text | Site Address
text | Builders Details
text | Project Managers Details
text | Site Managers Details
checkpoint | Latest drawings (attached or referenced)
checkpoint | Scope of Works Attached
checkpoint | Additional Pre-Start Docs (attached or referenced)
checklist | Prestart OH&S Documents
section | Details
checkpoint | All Pre-start OH&S Documentation Completed, Reviewed & Attached
label | Public Liability and Work Cover Insurances
label | Company Safety Plan
label | SWMS & MSDS (Attached below)
label | Additional Prestart OH&S Documents
checklist | Toolbox meeting
section | Details
checkpoint | Toolbox meeting completed & Specific Document(s) attached
text | Date
text | Site Address
text | Toolbox meeting topic
text | Toolbox Item 1 - (Add any resolutions below item)
text | Toolbox Item 2 - (Add any resolutions below item)
text | Toolbox Item 3 - (Add any resolutions below item)
text | Toolbox Item 4 - (Add any resolutions below item)
checkpoint | Toolbox meeting pdf attached (Add below)
label | Broad Air takes safety seriously and we encourage all persons representing the company to speak up if something is not right. If you find yourself unsure about something when it comes to safety, ASK! There is no such thing as a stupid question.
checkpoint | Sign Off – By signing this page you acknowledge your attendance of this toolbox meeting and your co-operation with our policies & procedures
holdpoint | Click to 'Add' signature's of each attendee
checklist | Variation (21/05/2020)
section | Details
checkpoint | Variation Details Complete (Pass once inputted)
text | Variation Name
text | Variation Description
text | Materials & labour breakdown (Names, Hours & Material(s)/Quantities)
text | Acknowledgement (Who requested the work to be done)
text | Signature/Reference Mail (Who to send the variation too)
checkpoint | Supporting Documentation (Attached or Referenced)
label | Add Photos/Comments of variation work below
checkpoint | Variation Sign-Off - Click to Add signatures below
button | Broad Air Representative Signature Added below | Yes, No
button | Builder Representative Signature Added below | Yes, No
holdpoint | Click to Add Signatures of Wilson & Builder's Representative
checklist | Incident Report - Checklist
section | Injured Workers Details
checkpoint | Injured Worker
text | Name of Employer of injured Person(s) (If any):
text | Business address of Person/Organisation in charge of the equipment:
text | Full name of Employee:
text | Date of Birth:
button | Sex: | Female, Male
text | Residential address and telephone number (if known):
text | Occupation of Employee:
section | Incident Details
checkpoint | Incident
text | Date of Birth:
text | Place/Location where incident occurred:
text | Work/activity being performed at time of incident and equipment being used:
text | Brief description of incident:
text | Treatment given/action taken at the time of the incident: (Attach Statements below)
text | Name of Witnesses or Name of Person(s) who first attended the scene: (Attach Statements below)
text | Action taken/intended, if any, to prevent recurrence of the incident:
label | Add diagram or picture of incident below
section | Treatment Details
checkpoint | Details
button | Did the injury necessitate loss of time? | No, Yes
label | If "Yes" selected
text | Name the clinic/medical centre attended:
label | Attach WorkCover Certificate of Capacity (Attach below)
button | Was an ambulance required? | No, Yes
button | Was the incident reported to WorkSafe Victoria? | No, Yes
label | If "Yes" selected
text | WorkSafe Incident notification number is:
section | Form Details
checkpoint | Details of Person submitting this form
text | Name:
text | Position/Title:
text | Date:
button | Type of Injury (Filled out by OHS Manager): | LTI, MTI, FAI