## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | ITP - Foam Bitumen Stabilisation - Material testing Rev 0 | itp | ITP - Foam Bitumen Stabilisation - Material testing |  | 6881fdb7-6c08-4ad8-90bd-1b9c4ffd247f
| section | 1.0. AGGREGATE AND BINDER OPTIMISATION / ACCEPTANCE TESTING / DESIGN and DRAWINGS
| checkpoint | 1.01 - AP40 Basecourse Aggregates used for overlay (if applicable)
2be96bb7-6c0c-5926-ac1b-ca0c880debba | note | Notes:
6b60cde3-a076-52c2-82cb-df72348a8c74 | note | ○ H = Hold point up to approval of Optimisation Testing
b8d9dc26-c68a-59c8-b140-84cb741e195a | note | ○ M = Monitor during production
44cb94e2-5deb-581d-9fdf-7decd2b94643 | note | Detail of Activity / Test - Crushing Resistance
a67ddada-b7d7-59f0-a839-8eb6538b623a | note | Action (Hold, Monitor, Witness) - H
abe27d99-e116-52e8-8500-ca71c2c91d9a | note | Minimum Test Frequency - 1 per 10,000 m3
1004da4d-d78a-5f86-a8b7-167c3ea963db | note | Inspection / Test method - NZS4407:3.10
835c398d-d1f2-5be2-972e-393135dfe6d8 | note | Acceptance Criteria - < 10% passing 2.36mm sieve at 130kN
bdd2553f-368c-5c42-90cb-7da4b2340459 | note | Record documents (QCP - Quality Control Portal) - IANZ report
358f516b-6ef8-56fc-a67e-819b6ce0c527 | note | Responsibility - Contractor
af8d10bb-b98c-5920-bf44-ba976690ee0b | note | Designer - A
8f75bd8f-5beb-5835-8727-0dcad67ca5d7 | note | Eng. Rep - I
dff76d2c-7bc4-5932-87ac-3a15feddf510 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.02 - AP40 Basecourse Aggregates used for overlay (if applicable)
4ffc1667-558d-5388-9a19-c25608ca297a | note | Notes:
5208cf25-d715-5648-b791-86dbcaf71eac | note | ○ H = Hold point up to approval of Optimisation Testing
3a938b9d-195f-5759-9869-f515bac7f3ea | note | ○ M = Monitor during production
9ac6ef2d-185e-5a2a-9c4e-4e0bfe5f9a86 | note | Detail of Activity / Test - Weathering Quality Index
831d9244-bb0d-5074-97b5-5b8ba2437ef0 | note | Action (Hold, Monitor, Witness) - H
36bacb34-47e9-506d-ba36-ea0b6a0c7e1f | note | Minimum Test Frequency - 1 per 10,000 m3
1ea0bfbc-c0bd-51d3-927a-712a8ff6869e | note | Inspection / Test method - NZS4407:3.11
8ff42178-5bad-5583-8443-e087b12c236c | note | Acceptance Criteria - AA, AB, AC, BA, BB, CA
e6ce47ce-3640-5558-b8f8-c90f901c4b1c | note | Record documents (QCP - Quality Control Portal) - IANZ Report
9f301995-af5d-599b-af26-6391a3c266d1 | note | Responsibility - Contractor
221c93a4-bdf9-5933-a11f-1992e3cc3311 | note | Designer - A
b7b87438-fb95-5e7c-aef0-894e66d5b883 | note | Eng. Rep - I
7630fb3e-7c51-5c6f-9373-4d8af63dd6e9 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.03 - AP40 Basecourse Aggregates used for overlay (if applicable)
7cef6196-93cb-5f10-85df-2deb45cb78cd | note | Notes:
41fa4727-9d24-56c1-b832-be570278357d | note | ○ H = Hold point up to approval of Optimisation Testing
3c555323-b2d0-5dbe-99c3-1390e979a593 | note | ○ M = Monitor during production
0c225179-17fe-572b-bd00-5aa340f45ce6 | note | Detail of Activity / Test - Calfornia Bearing Ratio (CBR)
3f7d1555-d69b-5bce-a03c-3ad6330875fd | note | Action (Hold, Monitor, Witness) - H
e5432fe0-047f-5ee2-9369-f3331185303c | note | Minimum Test Frequency - 1 per 10,000 m3
f95a00e1-b939-5c44-8fc2-43512b8cb33f | note | Inspection / Test method - NZS4402:4.1.3, NZS4407:3.15
aaf1f638-37d5-52f9-9d05-6c3727fca140 | note | Acceptance Criteria - Compaceted using NZ Vibe Hammer, 4-day soaked CBR ≥ 80%
839a0cbd-512c-5aad-8a6c-a24d2001a0ea | note | Record documents (QCP - Quality Control Portal) - IANZ Report
1fedaadb-0da6-54c7-9f88-564f09fcad4c | note | Responsibility - Contractor
d0919354-e816-596d-9c14-30a0531d1316 | note | Designer - A
f1c7cfb3-4f9b-518f-93e0-df4835143364 | note | Eng. Rep - I
06b309dc-9592-56ff-bacf-833d4cc24188 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.04 - AP40 Basecourse Aggregates used for overlay (if applicable)
29fcdce0-c389-5938-b623-1485fbcbba1e | note | Notes:
c4a5d39d-1721-5084-8ae0-791b9f28fe02 | note | ○ H = Hold point up to approval of Optimisation Testing
dc8f0e98-f62f-5ce8-ab9b-860ef99ece95 | note | ○ M = Monitor during production
61a25e50-cf99-5f27-be64-bb170fd19e4f | note | Detail of Activity / Test - Quality of Fines, either PI or SE or CI
a79f631f-322f-5335-b815-87d8d8e8918b | note | Action (Hold, Monitor, Witness) - H
82269d80-64b8-576f-8a68-b08f83f06e69 | note | Minimum Test Frequency - 1 per 1,000 m3
6dfe5250-37a9-5a4c-8629-42d16901527f | note | Inspection / Test method - NZS4407:3.4 - PI, NZS4407:3.5 - CI
c8042915-cf0c-5795-8a82-e189f07b399f | note | Acceptance Criteria - PI ≤ 5, CI ≤ 3
f5d8e078-c06b-5ec4-8238-7e433a310a72 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
fdfae6bf-3aeb-5d04-a63d-727e80ee607f | note | Responsibility - Contractor
7479c61b-713f-517c-abf5-761e0c5db5a1 | note | Project Specific Notes / Instructions - NZTA M04: 2024
ebe7da54-3c7a-5966-936d-b20cc790048e | note | ○ AP40 - Class 2
48518c5f-8864-5ac2-a828-d00caab28b47 | note | ○ PI and CI applies
36dd4c22-363b-59bf-a5cc-63d880ce3898 | note | Designer - A
50322dbc-73d3-5fb5-848d-1d329bf73e05 | note | Eng. Rep - I
32d3bbe7-7e78-523e-8559-ec0722529793 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.05 - AP40 Basecourse Aggregates used for overlay (if applicable)
0c8e92c7-7ed4-5e55-a6b1-c094cbfd809f | note | Notes:
5670b73e-8239-5ed4-975d-67de0012093e | note | ○ H = Hold point up to approval of Optimisation Testing
55f8240c-d2f9-5723-87b6-cc644a7b53f6 | note | ○ M = Monitor during production
ba53d257-936c-5200-9d7f-47ba0c1ae8cd | note | Detail of Activity / Test - Broken Faces Content
ff907705-dc70-5ab8-9370-466ce9e07338 | note | Action (Hold, Monitor, Witness) - H
61e0549e-a006-5b26-8501-fda74e9e538c | note | Minimum Test Frequency - 1 per 1,000 m3
68257f0d-71d4-5a88-b80e-3aabe1d9cce6 | note | Inspection / Test method - NZS4407:3.14
7d2908e5-c9cb-5b64-b3e9-333ee71491ef | note | Acceptance Criteria - ≥ 70% more than two broken faces on aggregates between 37.5mm and 4.75mm
1b96b731-05a8-5032-97b2-201415efc3b0 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
b691630f-ad4a-5d35-8a1b-39fa1398989a | note | Responsibility - Contractor
36088737-964a-5328-a9fb-81c5ee27000e | note | Project Specific Notes / Instructions - Waived if aggregate is from crushed hard rock quarry
e39af9a5-5302-5b14-85e4-3c63e757e768 | note | Designer - A
7608746f-7cfc-51fe-b885-4f448dccf5dc | note | Eng. Rep - I
2f4ff281-89e9-53bf-9ffc-bfb352ad1ffe | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.06 - AP40 Basecourse Aggregates used for overlay (if applicable)
330c3d66-c883-57af-98a4-2d261d85644a | note | Notes:
1cac7bad-f3a4-55fc-89c0-668808964e8b | note | ○ H = Hold point up to approval of Optimisation Testing
6d32ce48-c6f8-5c7c-82ca-0b3cb2dbc346 | note | ○ M = Monitor during production
3360b542-c969-5a28-9f98-80bd0c1e68a0 | note | Detail of Activity / Test - Particle Size Distribution
b8815777-d2c8-5db3-abb5-57a9320d1306 | note | Action (Hold, Monitor, Witness) - H
968e708b-f84e-569a-9a61-3d609440e0e1 | note | Minimum Test Frequency - 1 per 1,000 m3
e15ec36a-d3cd-5293-b4a8-8564744661dd | note | Inspection / Test method - NZS4407:3.8.1
aaa5a23e-c000-5d21-acc0-f98f5a181e30 | note | Acceptance Criteria - NZTA M04:2024-Class 2
1c59c933-0ade-5e3b-878d-10e94d0c2c4f | note | ○ Class 2 in Table 12 for PSD
9bf9f95d-3d07-57f6-914f-767b0adb961a | note | ○ Table 13 for shape control
df88dd2a-a737-5ca3-a67b-171d6c5abb55 | note | Record documents (QCP - Quality Control Portal) - IANZ report
d4c03406-3f39-5ed4-bbdc-b09b08d7f07c | note | Responsibility - Contractor
98119672-b744-502f-b9c1-c400e8fd798f | note | Designer - A
0bdab5ea-76d5-50de-8520-17b36a370269 | note | Eng. Rep - I
101f5f10-b192-5239-b8eb-8e8a82e01502 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.07 - Optimisation of Stabilising Agent(s)
c59cb70f-a542-5d0f-ac29-4bde8dc67a53 | note | Detail of Activity / Test - Blend Particle Size Distribution
e40a9819-80f4-5c76-bc58-8fc8f4f07a40 | note | Action (Hold, Monitor, Witness) - H
a76fc138-9412-5945-8caf-01a3e81813b9 | note | Minimum Test Frequency - 1 per 1,000 m3
3c7cfd20-f8e8-52fc-bc2f-f7388661b91b | note | Inspection / Test method - NZS4407:3.8.1
5d9d3997-c568-5166-8d5d-115b1ea8df4c | note | Acceptance Criteria - Check if average of existing (from TPs) and any overlay will meet the ideal FBS / BE grading.
6ed90226-d0d2-51c2-9269-886ed53b0c95 | note | Record documents (QCP - Quality Control Portal) - Report using IANZ Reports for AP40 and TP PSDs
ce2e495a-de60-5618-9cb8-b09f40f19297 | note | Responsibility - Designer
a6bea5a2-5454-56ec-ada1-96031f36b355 | note | Project Specific Notes / Instructions - Designer to advise if "average" blend is acceptable.
af2c082e-4053-5eab-9356-9c3c75d88c3c | note | Designer - R
cd0edee6-a0be-521a-a4d7-1a19b180149c | note | Eng. Rep - A
c81e4e7b-2b17-5be5-8e37-94bbfe9136a5 | note | Contractor - I
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.08 - Optimisation of Stabilising Agent(s)
b8e9cf8c-b981-546b-bf0a-e0e00d0d04e4 | note | Detail of Activity / Test - Indirect Tensile Strength, ITS
d3a8fcd3-444d-5d5d-bd54-bb0e37dc4f51 | note | Action (Hold, Monitor, Witness) - H
3c804a95-cc5c-540a-8881-6de58d0482aa | note | Minimum Test Frequency - 1 Optimisation test per aggregate type
74cbca82-d97a-5a9e-9ed3-3a454bd13b3d | note | Inspection / Test method - NZTA T/19: 2020
d0ab84cd-8747-5223-8a47-6edef0ef086e | note | Acceptance Criteria - Testing at 1mm/min:
6b36fd4d-306e-5241-9486-0be75b963fa1 | note | – BSM Dry ITS: 175 kPa to 400 kPa
d80eeca7-92f0-58bb-b447-2cfd4bff2890 | note | – BSM Soaked ITS: 150 kPa to 350 kPa
4be42e74-757e-51cb-ad97-62f97ba94f74 | note | ○ Testing at 50.8mm/min:
1aa46efc-7ec9-5e20-930e-dcaf9776fe55 | note | – BSM Dry ITS: 210 kPa to 480 kPa
9f9249ad-db95-5dcf-bfb1-65d999187cae | note | – BSM Soaked ITS: 180 kPa to 450 kPa
8a27c126-f71d-554c-b0ba-e7aa44571343 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
37996d42-76c0-5a62-b6b9-4aa8f47d0d61 | note | Responsibility - Designer
61007cb8-3a85-57c9-8445-0c9fac31e3dc | note | Project Specific Notes / Instructions - Designer to advise on binder content(s)
8a7d9996-331d-560b-931f-1ff888c72da0 | note | ○ Note that the min.design ITS is as per T/19 Notes + 25kPa to ensure that the min.ITS values are obtained in the field
da00eef4-6cd9-5740-8650-6434740c164c | note | Designer - R
b6b33a87-f49c-55cf-b58d-d8dee93fdf8c | note | Eng. Rep - A
ccdbf693-802a-52fa-aa75-dad9369ec8b3 | note | Contractor - I
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.09 - Optimisation of Stabilising Agent(s)
a43eccaf-f3b5-5d54-b3aa-1ccc10dab72a | note | Detail of Activity / Test - Unconfined Compressive Strength, UCS
5163e712-a786-51e3-8069-17a32cc042ea | note | Action (Hold, Monitor, Witness) - H
d5033425-d998-5db1-b0a2-91fcc6156d5d | note | Minimum Test Frequency - 1 Optimisation test per aggregate type
1a3d7d3f-eba9-526a-8968-99f14d19ccae | note | Inspection / Test method - CCNZ / NPTG / CETANZ Industry Guide
dd908091-e0ec-5756-8afa-58542f7f37a8 | note | Acceptance Criteria - UCS limits set by the design engineeer
d10f92e6-d951-5ffd-89f1-c2eca2332b5d | note | Record documents (QCP - Quality Control Portal) - IANZ Report
32f5c099-7e9f-5928-beaf-b35549621023 | note | Responsibility - Designer
ef8b71cf-6267-503d-86cf-eaa6b44ac946 | note | Project Specific Notes / Instructions - Designer to advise on binder content(s)
d44724e7-6631-5725-b128-f939d46f2d8e | note | ○ Note that the min.design ITS is as per T/19 Notes + 25kPa to ensure that the min.ITS values are obtained in the field
00c77a89-1741-5e69-a3dd-73078bdc2a38 | note | Designer - R
710e85aa-f817-508b-88f6-bccf0ac0a3bc | note | Eng. Rep - A
d32b622a-c529-583a-9105-bc0b874eab64 | note | Contractor - I
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.10 - Optimisation of Stabilising Agent(s)
5102cd68-90d2-5f9c-a82c-5880b9f96ac9 | note | Detail of Activity / Test - Modified Maximum Dry Density
2696df96-953a-5fd3-8a6b-698ca7ec44ff | note | Action (Hold, Monitor, Witness) - H
3cabd14b-f360-537d-b6f2-2ce15f9bc54e | note | Minimum Test Frequency - At Optimised Binder selection
9a915276-6433-5acc-ac28-a72f5029b9db | note | Inspection / Test method - NZS 4402.4.1.3
aaa84404-cd28-52ec-b0af-cb3219e22549 | note | Acceptance Criteria - To determine target density
beb493d0-25c7-5ada-ae3f-0d2a808d7a2d | note | Record documents (QCP - Quality Control Portal) - IANZ Report
ca37069a-6583-5821-a55e-4a2005c6c0bb | note | Responsibility - Designer
c2bd7448-1fc6-5d5e-aae3-f798e9e64b2f | note | Project Specific Notes / Instructions - Required before Stabilisation comences
2ee64c4e-f5ed-5bb8-87b1-d7b60069103c | note | Designer - R
7e0c8a3b-73f2-58af-9bc4-ba5b86cb8f11 | note | Eng. Rep - A
d32f49b2-7cf0-5a4f-8cad-2563797a760e | note | Contractor - I
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
eafcf5ad-e777-5b4a-b855-eb62fa796eb8 | textbox | Contractor's Rep Name:
28925e9f-edf1-5c44-b410-ed24b68961b4 | textbox | Engineer's Rep. Name:
9d58d381-e766-5776-9b99-cbc21798a670 | date | Date:
| signoff | Add Signature
| checklist | ITP - Foam Bitumen Stabilisation - Pre Treatments Rev 0 | itp | ITP - Foam Bitumen Stabilisation - Pre Treatments |  | 7dbd1865-b28c-4130-812d-582981eecfe7
| section | 2.0. BEFORE BITUMEN STABILISATION STARTS
| checkpoint | 2.01 - Setout section
9986ba90-c19e-53d7-b6d6-543561667f35 | note | Detail of Activity / Test - Install offset pegs / check geometric model; record centreline, edge line or mark out stabilisation extents from existing line marking
d42cc76d-8c2c-5f25-9fdb-b5a43a1d8d6a | note | Action (Hold, Monitor, Witness) - H
50fd8f32-62cf-51f6-ac17-c53fbd7cbc91 | note | Minimum Test Frequency - Prior to each section
04e2fb85-c450-58d6-b7f8-ba471b0d3495 | note | Inspection / Test method - Survey
d59bd00e-cbe4-5658-8e55-bc7191d452b2 | note | Acceptance Criteria - Document existing furniture
aebf6bc9-949e-510f-b1b0-f77b7dcd0b8e | note | Record documents (QCP - Quality Control Portal) - Electronic survey files
c2209223-fd6f-5f44-bf2b-643faf798da6 | note | Responsibility - Contractor
b35cdc80-4ade-57cf-be0b-80128ce338e5 | note | Eng. Rep - I
62925157-f9bd-5bd5-a326-d480d3964f1b | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.02 - Pre-hoe, shape and proof roll
e86205a7-3a5e-544d-af31-274cae7c83d3 | note | Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting
f225cb08-9cb7-55b8-bb68-3f285d265540 | note | Action (Hold, Monitor, Witness) - H
67e775ab-3697-554b-b93b-f667e659c874 | note | Minimum Test Frequency - Prior to stabilisation per section
2a715791-f618-5cf4-8e44-9adb1da04d7d | note | Inspection / Test method - Use grader's machine control and inspect shape
75aa2875-41ba-5425-a3bb-96b3f8541b25 | note | Record documents (QCP - Quality Control Portal) - N/A
336b9167-5e70-5cfb-8da8-3cd9ebbed80a | note | Responsibility - Stabilising Contractor
baf45511-898a-5660-b3d4-b5bde1ce1ab1 | note | Project Specific Notes / Instructions - Intention is to carry out only minor correction (eg.2% to 3%). Any major shape corrections to be identified prior to site establishment and included in the site specific methodology statement
79cf8e45-e680-530a-acf3-fc6b8913857d | note | Eng. Rep - A
8bdaa2e4-5a90-5288-9f3c-f2b88eb85969 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.03 - Pre-hoe, shape and proof roll
67c09e5e-9f7c-52f5-98c5-36988159ee07 | note | Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting
a17a2f57-8250-5e9a-b9ee-ac5b932b2df6 | note | Action (Hold, Monitor, Witness) - H
e7e1b973-5f2a-5cd1-acac-b3548f626313 | note | Minimum Test Frequency - Prior to stabilisation per section
a95a23a8-7cac-51b7-b6f9-b216b30c979a | note | Inspection / Test method - Visual check or Vibratory Roller's response meter
ffa7385d-50db-511e-8b9f-ac59b0ab7d5b | note | Record documents (QCP - Quality Control Portal) - Stabilising Contractor confirm no obvious soft areas found
eeddcd5e-3b16-5d6d-930f-e74bec2e70b2 | note | Responsibility - Stabiliisng Contractor
5df9f9d4-d87f-5c6e-8aaa-0be95a4e724c | note | Project Specific Notes / Instructions - Any soft spots identified by visual means or that show up as significantly different to be raised with the ER for further instructions
54bd17e1-1b4d-5bfa-8423-e5bac4204f8b | note | Eng. Rep - A
a81a7ab6-3421-5636-a0a6-8e93a855df89 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.04 - Overlay and check levels
c3a51bfa-7a87-5b34-aa78-c70890ac5204 | note | Detail of Activity / Test - Supply, pre-compact and trim to line and level with NZTA M/4 AP40
0dedecaa-21cd-544e-99ed-5d5975f77bd0 | note | Action (Hold, Monitor, Witness) - H
b8165694-2c15-5b3d-8eaf-48aa667ab772 | note | Minimum Test Frequency - Prior to stabilisation per section
b9f35ebb-3655-5dde-98f0-4125773fa528 | note | Inspection / Test method - Survey
ec63e4c3-2d36-5cd6-b5ea-fbc5b713aee2 | note | Acceptance Criteria - As per NZTA Z/16
12bfcd31-7c74-5183-8aff-28f67e4b0602 | note | Record documents (QCP - Quality Control Portal) - Check with Grader and visual inspection
dcb2dd0e-2ac6-5a20-b5e6-ede5308ee183 | note | Responsibility - Stabilising Contractor with Main Contractor
bb4cca72-5c2c-5035-8201-71bc1f7e659c | note | Project Specific Notes / Instructions - This is the last opportunity to check items before adding the FB. Assess items such as (but not limited to):
ce01f28a-f4a2-5de6-ad2d-32e02eb1f21e | note | ○ overlay aggregate quality / consistency
b936cdfe-c3f4-5cff-9f95-0ee6d44746c3 | note | ○ moisture content
e871f201-2d14-5b09-9f6e-82eea378ac1d | note | ○ any concerns with shape and tie in
5dcc2e8a-2d26-576d-842a-48702c0e13cc | note | ○ etc.
070cd3b7-1635-521c-846e-ff3a7653b6ac | note | Eng. Rep - I
96baf954-914a-57c5-9e8b-313ff02458f3 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.05 - Production Plan
76f59c41-311e-581a-8b1b-dd5c9ed7ea45 | note | Detail of Activity / Test - Plan showing cut lines and sequencing of works
e7906efa-ddc0-52da-878e-f63410b4190c | note | Action (Hold, Monitor, Witness) - M
62ea7800-71a8-55f1-bdc0-08b361da46d4 | note | Minimum Test Frequency - Prior to each section
0b8692db-a34a-58c0-87eb-7217b37eb3d3 | note | Inspection / Test method - Daily Report
4a287c83-bd50-5cb0-a027-002df82957b9 | note | Acceptance Criteria - Points covered in NZTA B/5
55727680-c289-50b5-b90e-07c662c7358e | note | Record documents (QCP - Quality Control Portal) - Daily Production Plan
427b4c64-6026-5795-81a5-166b003a0572 | note | Responsibility - Stabilising Contractor
6de6d099-8cf1-55e7-a226-d8c7d249080f | note | Eng. Rep - I
ad938dbf-33c6-5ee1-bc7c-3f2580b9f3aa | note | Contractor - R
| checkpoint | 2.06 - Weather conditions
94a8494b-4611-523b-8d5f-9556f4f0f48a | note | Detail of Activity / Test - Material behind stabiliser
49b413bd-1f38-57bd-8b09-c5dc1a11d4cb | note | Action (Hold, Monitor, Witness) - M
a05c3c2a-259d-5cb1-ad20-35cd69a7a6f5 | note | Minimum Test Frequency - Prior to spreading
032335e2-0ddc-50c3-9cfc-50a20d093877 | note | Inspection / Test method - Measurement
855375d1-b20d-58ad-8661-69722cc8466a | note | Acceptance Criteria - Material after stabilisation: BE: > 20°C, FB: > 20°C and Ambient: >5 deg.C
96591bb9-0bdc-581c-ab5d-9e8532d41112 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
42c9858d-a7b9-5759-affe-21572797c178 | note | Responsibility - Stabilsing Contractor
1cf331a1-e0f3-5e59-8912-49f1540d173c | note | Eng. Rep - I
9ce8b4aa-82e1-5cda-aad1-2462a229d753 | note | Contractor - R
| checkpoint | 2.07 - Weather conditions
95afe829-ba6a-5103-8fa4-4a63eb70799e | note | Detail of Activity / Test - Wind
903f870f-4a2f-566a-8bd8-2262cb3ad0ca | note | Action (Hold, Monitor, Witness) - M
243d794a-1c49-5ce6-b8f5-7dd96a1f04a6 | note | Minimum Test Frequency - Prior to spreading cement or lime
436132fa-8cd6-5a42-8eab-e738fcbb4d53 | note | Inspection / Test method - Local weather stations
1bfd41a2-aceb-5cb0-bf9e-55d41aaa3536 | note | Acceptance Criteria - Wind speed < 25 km/hr
c6ebe69c-e1a9-51e7-b108-ce4e3572ea8a | note | Record documents (QCP - Quality Control Portal) - Daily work Log
ff4869f0-0170-56ea-ac93-81cd5ed0cc53 | note | Responsibility - Stabilsing Contractor
4c3a01ce-64c8-52f3-aebc-7eefa9828f4d | note | Eng. Rep - I
d67dc5b9-d092-5d10-88ca-4c6819cee583 | note | Contractor - R
| checkpoint | 2.08 - Weather conditions
eeaad781-0670-5b7f-95c4-0725f4f9d5f9 | note | Detail of Activity / Test - Rain
6188abfc-b30c-5917-bd35-1e68adf69acc | note | Action (Hold, Monitor, Witness) - M
fb3efee1-5757-56fc-a0c2-4eef41fae75a | note | Minimum Test Frequency - Prior to spreading cement or lime
ed17b307-d3e2-551b-b84f-a528f2711e91 | note | Inspection / Test method - Local weather stations
fe1b3d84-c770-5e93-b9ee-98365b9396be | note | Acceptance Criteria - No spreading of cement / lime if it is raining or likely to rain before these can be mixed in with the material
b5de423e-d17e-5057-8bd4-a4d84426bb5f | note | Record documents (QCP - Quality Control Portal) - Daily work Log
ce0093e0-5dd5-5181-9743-74f21eed2f54 | note | Responsibility - Stabilsing Contractor
2347a084-6f03-5185-9f2e-100b9d472ce1 | note | Eng. Rep - I
6ff3cae9-eca3-59ac-87df-147e16998594 | note | Contractor - R
| checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
dec22408-23ba-52f0-ac47-94c4efe99291 | textbox | Contractor's Rep Name:
5297358a-d7fd-53d9-a3f4-60f28620cbc5 | textbox | Engineer's Rep. Name:
f587f3d4-b7fa-5105-bf17-8e59fbf7dd05 | date | Date:
| signoff | Add Signature
| checklist | ITP - Foam Bitumen Stabilisation - Post FBS testing Rev 0 | itp | ITP - Foam Bitumen Stabilisation - Post FBS testing |  | ce1d9b1e-9d89-47f8-9128-6b6367389dfb
| section | 4.0. Testing and Sgnoff
| checkpoint | 4.01 - Finished Pavement
96c1be4c-60c1-5af3-b10e-3ab1676e1599 | note | Detail of Activity / Test - Crossfall
303ee57f-7e45-5ed3-b9af-e69ff1d41927 | note | Action (Hold, Monitor, Witness) - H
e427087e-3806-5b1c-9a5d-696fdc1a6d8a | note | Minimum Test Frequency - every 20m
cd26945e-6c83-5332-9c4c-a4838a29ddac | note | Inspection / Test method - Measurement
d783f69d-f1d9-5fa4-bb5c-07d2402ba2b3 | note | Acceptance Criteria - ± 0.5% of specified crossfall measure 2m apart
6f3b24d5-e97c-5132-a9c9-b049e9d8f82f | note | Record documents (QCP - Quality Control Portal) - Survey
f99fdda2-79d3-5b01-94b9-579976d2a95a | note | Responsibility - Stabilising Contractor
1af74a00-ece8-5248-92d0-32e6ac4951fe | note | Eng. Rep - A
c288a246-2924-55f4-95db-dfabd4a429b5 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.02 - Finished Pavement
fb854560-f217-52d6-98bc-32e4bcaaf74f | note | Detail of Activity / Test - Stabilised width
6656ef11-04a7-5799-a0e0-84f9bd6e32fd | note | Action (Hold, Monitor, Witness) - H
be250ba6-823a-5bfd-9178-52044238cf01 | note | Minimum Test Frequency - 1 every 20m
0e59090d-6e7f-530d-bdae-0dd73ade6a95 | note | Inspection / Test method - Measurement
0a254045-5eaf-5241-a10c-375498b3e064 | note | Acceptance Criteria - -20mm, +100mm
7090634a-fd50-50b8-bab0-1381ebc1db90 | note | Record documents (QCP - Quality Control Portal) - Survey
df2a1356-65af-5d6f-8693-2fc9168375fd | note | Responsibility - Stabilising Contractor
5d696d34-0140-5877-87a0-5115d0fd463e | note | Eng. Rep - A
b2e1d640-6df6-5fda-a61e-72cc41705be7 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.03 - Finished Pavement
689d31fa-bccd-5568-825a-0ae6c72bc43c | note | Detail of Activity / Test - Surface Shape
737b2d76-73da-5158-86dd-102d50866d30 | note | Action (Hold, Monitor, Witness) - H
42e8bdea-ec00-56a0-a1ad-2f5be8abdc86 | note | Minimum Test Frequency - every 20m
1fe05709-b8e2-5a0d-80aa-4f5d5ba95b5e | note | Inspection / Test method - Measurement
6f9d14b2-46f4-50a8-af67-f8ccbb08df5d | note | Acceptance Criteria - < 10mm using 3m straight edge
3a0cd3d7-d49b-51c7-993b-605c78daad95 | note | Record documents (QCP - Quality Control Portal) - Survey
ae285b78-4acb-5d7f-8a07-512b1b10c016 | note | Responsibility - Stabilising Contractor
5a1bcd6d-e926-575b-9cc2-3691eab78352 | note | Project Specific Notes / Instructions - Only required if the visual inspection appears unsatisfactory
de955122-cb8e-510e-b716-0a18c6c9d246 | note | Eng. Rep - A
5dba1616-d55b-59d7-ab96-8cc6f7917e80 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.04 - Finished Pavement
0305029f-b78f-5ca7-9764-0e97885dc83c | note | Detail of Activity / Test - Surface Levels
8aa1d9c0-9856-5df4-8538-bdfbe4f21ed6 | note | Action (Hold, Monitor, Witness) - H
759311f6-505c-5d77-96a6-1a6fe0697e9e | note | Minimum Test Frequency - every 20m
6878214a-d5fb-5076-9855-6e8cf72854e7 | note | Inspection / Test method - Measurement
7fce1301-1f40-51fe-a9e1-fbd8e8bcb9e2 | note | Acceptance Criteria - -5mm, +15mm
b64790f4-39d8-58bd-9edb-0e75a248f2aa | note | Record documents (QCP - Quality Control Portal) - Survey
6a648ff2-1886-5207-84a3-9241ef3d88ac | note | Responsibility - Stabilising Contractor
7b0581f2-8f3e-561d-846c-5ddcbd87db02 | note | Eng. Rep - A
65b376ea-59cc-5737-82e8-a2b775df8de2 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.05 - Finished Pavement
689509f4-e511-5e09-ac74-9d2f562b6e7e | note | Detail of Activity / Test - Surface Finish
d6b1ee2c-44be-51c8-b99f-f3c7f784dc91 | note | Action (Hold, Monitor, Witness) - H
b9b7073b-f7a1-5587-ad70-46d0bde008ca | note | Minimum Test Frequency - Per Lot
7a1944e0-55bc-5927-98d3-2a902006222a | note | Inspection / Test method - Visual
0dd6c5ef-9088-5d24-a462-201fc044e19d | note | Acceptance Criteria - 1. Larger aggregate held in pace with a matrix of smaller aggregate
7be3d1f7-24f2-521e-b391-f315b69acacd | note | 2. Smaller aggregate held in place by fine material
eb34b168-bb56-57b7-a5df-618af16be619 | note | 3. matrix does not displace under normal trafficking and/or sweeping
7e34500f-4af4-5b88-b4d7-f0feaff4ef18 | note | Record documents (QCP - Quality Control Portal) - Survey
813c4773-95ab-5454-9ab4-2187fb2fc493 | note | Responsibility - Stabilising Contractor
0127748e-d36e-5a17-b62e-65ae51c4dabd | note | Project Specific Notes / Instructions - ER to be present at pre-seal inspection
c93da31d-8d3a-50d8-80ca-7a6e81a8df9b | note | Eng. Rep - A
a96b2e46-0455-5146-9e8b-5e388fe6e83b | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.06 - Finished Pavement
9e3201ae-a942-5a4a-bcdc-cc5db18ab0e5 | note | Detail of Activity / Test - Roughness
a4dac419-ac24-55c2-91bb-a00aa183ee37 | note | Action (Hold, Monitor, Witness) - H
969d6d55-4d71-57a3-8fab-fa4a935e7bd6 | note | Minimum Test Frequency - Before Sealing
5f431c6e-7e0a-516a-88c4-d43fd57e4bf2 | note | Inspection / Test method - TNZ TM 7003 v1
64247a25-5e34-5e9d-b060-1b068b66c40c | note | Acceptance Criteria - 100m rolling average ≤ 75 counts/km
9ead2cea-2a9d-5541-85b9-d9a319465190 | note | Record documents (QCP - Quality Control Portal) - Test Certificate
90feccc1-bc12-58b2-a483-3c45bdb5c05a | note | Responsibility - Contractor
404d4612-81e0-5ada-a4f4-804699b11957 | note | Eng. Rep - A
8d42ca14-67de-5863-81ff-3359bc06b541 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.07 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover)
f609e5f4-9f21-55c8-b5e6-639809885834 | note | Detail of Activity / Test - Clegg Impact Value
92e7565d-1fd8-5053-847c-d54c76d98e2e | note | Action (Hold, Monitor, Witness) - H
bf7182e8-0fc7-5ff4-98d1-8c309ffec07e | note | Minimum Test Frequency - 5 per 1000m2
73f414f4-2e9b-577c-aa4b-ac38e12dfc88 | note | Acceptance Criteria - CIV ≥ 50
55d07aa6-d51e-5913-b811-c769595ff291 | note | Record documents (QCP - Quality Control Portal) - CIV form - ConQA
253faca2-8fa0-5aa4-9231-f9c540774c71 | note | Responsibility - Stabilising Contractor
67f393de-03f0-5dc9-8598-ed1458f07db0 | note | Designer - I
5879cfc6-f54d-52c5-b49d-f3d183065cde | note | Eng. Rep - A
0f952d34-1784-50da-aa2b-075ba33b4205 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.08 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover)
769bf83c-afac-5518-b734-3e1645cca1b6 | note | Detail of Activity / Test - Degree of Saturation, DOS
78924db4-f33a-55d2-a996-12e95566b576 | note | Action (Hold, Monitor, Witness) - M
d9a4e6a0-2ae7-52ef-a2e4-cc560cb00456 | note | Minimum Test Frequency - 5 per 1000m2
34e02569-7033-530d-8cce-7fabf520a176 | note | Inspection / Test method - NZS 4407.4.2.2 and DOS calculation in NZTA B/5
694b0f07-07f5-5775-9203-3a9a312c270f | note | Acceptance Criteria - aim for DOS ≤ 80%
2e4568b6-fd36-5651-b47b-a2f6f3de5434 | note | Record documents (QCP - Quality Control Portal) - IANZ report
ca99d6c1-6f9e-5151-82f9-a787a0209250 | note | Responsibility - Contractor
b21f3d7c-8b55-53ae-95a3-dfe29ae193c8 | note | Project Specific Notes / Instructions - Report only
15b4fda8-ff06-574c-8fcf-0c65172d6d85 | note | Designer - I
98d6f31a-0228-5574-863f-64f0dba48ad7 | note | Eng. Rep - A
87c8315e-cfe7-5c49-8f09-e73acd65a55b | note | Contractor - R
| checkpoint | 4.09 - Pavement Layer Signoff
59db984f-18fc-5bbb-8c93-c40efc20b576 | note | Detail of Activity / Test - Assessment of all test results for conformity
3ff8f330-7dd1-5612-97cd-f61cb88f8986 | note | Action (Hold, Monitor, Witness) - H
24c5f4fa-69a4-5b90-9f12-ec06abc3a504 | note | Minimum Test Frequency - Each Lot
b08eb498-07a5-559b-b196-aece4f631eb7 | note | Inspection / Test method - Site Inspection
95857bec-9882-52ee-ae71-eecd084b9079 | note | Acceptance Criteria - Reporting of any non-conforming results to Designer via NCR
40ea1a6d-5e3b-5a16-bf7c-5fb88d319f6c | note | Record documents (QCP - Quality Control Portal) - NCR
ec6aacfb-7a40-5e84-945f-4617db91e072 | note | Responsibility - Engineers Representative
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
c70b3a1f-4316-5bc1-b043-c02bb00899ab | textbox | Contractor's Rep Name:
d0b10919-6ee0-51a3-9ab1-5ce99b85cec7 | textbox | Engineer's Rep. Name:
89b0e04a-acb2-5690-9d09-1ed07e8437e9 | date | Date:
| signoff | Add Signature
| checklist | ITP - Foam Bitumen Stabilisation - FBS operation Rev 0 | itp | ITP - Foam Bitumen Stabilisation - FBS operation |  | 4216c747-4808-4716-ab13-9261e9574f94
| section | 3.0. BITUMEN STABILISATION OPERATION
| checkpoint | 3.01 - Production Plan
18f80137-e68d-5f5c-8e3c-ca8dd218f646 | note | Detail of Activity / Test - Plan showing cut lines and sequencing of works
63f62e1a-54de-5249-8342-5bfc793549b4 | note | Action (Hold, Monitor, Witness) - M
e515b63a-06f1-5a2a-819a-21de548e0da6 | note | Minimum Test Frequency - Prior to each section
8ba08741-6723-598e-8a1d-6729427c1e68 | note | Inspection / Test method - Daily Report
b7e509d1-a886-5812-a8f7-42034fc3db88 | note | Acceptance Criteria - Points covered in NZTA B/5
a7590362-aa7b-5de6-948e-b44b1989843c | note | Record documents (QCP - Quality Control Portal) - Daily Production Plan
32c71017-990a-5bf5-9de7-a9d04804cf76 | note | Responsibility - Stabilising Contractor
f7475d00-f999-571b-8ab6-29815cf4cdfc | note | Designer -
4bf3096c-f23b-548c-846d-4e08d38db8c2 | note | Eng. Rep - I
09355c40-6154-535d-a995-37d28d98a948 | note | Contractor - R
| checkpoint | 3.02 - Weather conditions
bf1c6484-4b5e-599c-aff6-4722bd752707 | note | Detail of Activity / Test - Material behind stabiliser
cdf1b233-2a1d-5c1a-b9c7-dd1bcb655c44 | note | Action (Hold, Monitor, Witness) - M
d838f44e-9a10-5cb5-b979-fd669fb2bab8 | note | Minimum Test Frequency - Prior to spreading
98a45d6b-e562-5ecd-8240-2dbf96931769 | note | Inspection / Test method - Measurement
4d534a52-1dc6-57b6-950e-bad9018476bc | note | Acceptance Criteria - Material after stabilisation: BE: > 20°C, FB: > 20°C and Ambient: >5 deg.C
8786e057-2936-5946-b99d-128744a666e4 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
c1c867d9-57ac-5da8-8439-1f5e91066b83 | note | Responsibility - Stabilsing Contractor
91eb24c6-8534-57ff-b400-7787c152518a | note | Designer -
04bdeb91-8204-5121-a78c-9fd9e57f7678 | note | Eng. Rep - I
c8c8c6d2-2d9a-5978-87e0-392a05228f96 | note | Contractor - R
| checkpoint | 2.07 - Weather conditions
9255db96-2df0-5fc4-919a-6424bfc78c63 | note | Detail of Activity / Test - Wind
f22f8524-43dd-5f8f-b417-136e8ffa5aab | note | Action (Hold, Monitor, Witness) - M
f6234824-4928-5d75-aedf-7c99101bfe98 | note | Minimum Test Frequency - Prior to spreading cement or lime
e262af5f-9d8d-5b2d-ada6-ebcb322dca50 | note | Inspection / Test method - Local weather stations
5e3fbcac-d352-59fe-b537-6d9b4966cef5 | note | Acceptance Criteria - Wind speed < 25 km/hr
1d78ceb9-6e31-5c53-89ff-cdbb31a7db45 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
5aef50e8-cbb7-5a16-a362-1d1db4d9b89d | note | Responsibility - Stabilsing Contractor
97770fd8-30f1-5601-a5f9-153470d59368 | note | Designer -
5c6b9215-5943-5ccd-acb7-57ba5020552b | note | Eng. Rep - I
28355262-de83-5a0d-b325-40df4aacdeeb | note | Contractor - R
| checkpoint | 2.08 - Weather conditions
3b794877-a84b-54cf-86fd-87a89688ddbd | note | Detail of Activity / Test - Rain
26b4d3f9-9704-5640-809b-7c837883e26a | note | Action (Hold, Monitor, Witness) - M
e4dd5ad0-7a3f-58a2-9707-2d02a96332e5 | note | Minimum Test Frequency - Prior to spreading cement or lime
7bf939e6-39e4-53a9-8246-e21f9ccc898f | note | Inspection / Test method - Local weather stations
c62bca29-645b-569f-96ba-3bd3961f6e0e | note | Acceptance Criteria - No spreading of cement / lime if it is raining or likely to rain before these can be mixed in with the material
26a6ec8d-2d6c-5ffa-96a7-65dd831857a3 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
c3084073-454a-5df3-b6c1-ed5878fb6d32 | note | Responsibility - Stabilsing Contractor
7c1a7ddd-ce91-5097-8355-e0884688f705 | note | Designer -
21c67299-4991-5c32-b249-dc198fba966f | note | Eng. Rep - I
2399a71f-aec1-5630-b5c3-98c8fe71bbb5 | note | Contractor - R
| checkpoint | 3.01 - Stabilising Agents
ac012d0f-bb6d-5169-83a2-b0b2697666db | note | Detail of Activity / Test - Lime (if applicable - check PI delete otherwise)
e1443abc-af96-511e-be52-d2836221060e | note | Action (Hold, Monitor, Witness) - M
77224abf-986a-5b72-b5bf-f69505300d0e | note | Minimum Test Frequency - Per Batch
f26257c9-178c-5f01-9457-a072cf4425f9 | note | Inspection / Test method - TNZ M/15
0a0e3602-94e2-5d9e-b763-12297219ae7d | note | Acceptance Criteria - Conform to Specification
7574459d-092f-5a22-ba4d-29708eee3e85 | note | Record documents (QCP - Quality Control Portal) - Certificate in contractor's site folder
0e0304e3-d493-5a75-ad79-5b12cdcdabcb | note | Responsibility - Stabilising Contractor
d5374282-76f1-59a4-bdd6-335179be4766 | note | Designer -
e8659cf5-25dc-50ec-bedb-f450048094f6 | note | Eng. Rep - I
86a9969f-f5cc-534a-ba0c-fae22a39a84d | note | Contractor - R
| checkpoint | 3.02 - Stabilising Agents
57ef5a5f-ab5c-588e-b27b-80f51be2dc01 | note | Detail of Activity / Test - Cement, GP
9096ced6-64c6-5b6f-9575-25131ca6e6b9 | note | Action (Hold, Monitor, Witness) - M
25a6395a-c35a-5f75-9680-e5b9a3cdd15c | note | Minimum Test Frequency - Per Batch
27010c02-9c84-5dab-9661-64ebadcbf27b | note | Inspection / Test method - NZS 3122
eb97da68-39c0-50b3-afbc-b6d59a4d8224 | note | Acceptance Criteria - Conform to Specification
0fdc453b-3b12-5ee2-a5bd-eec4e5b79cdd | note | Record documents (QCP - Quality Control Portal) - Certificate in contractor's site folder
33bd8979-8bcf-5fd9-bbd1-75a043292645 | note | Responsibility - Stabilising Contractor
670e0309-9409-5ea3-8f65-682ea97b4fde | note | Designer -
a8b69bd1-2bae-5440-9692-db15d5c5e051 | note | Eng. Rep - I
332ae894-bb5b-5ac5-bc24-8357d5082de6 | note | Contractor - R
| checkpoint | 3.03 - Stabilising Agents
4788fa12-5a60-5fb7-a6d2-064b9fcfcbe3 | note | Detail of Activity / Test - Bitumen (130/150)
7fb8e18c-949c-51ad-8d22-e78b78c8ec45 | note | Action (Hold, Monitor, Witness) - M
163cb6c7-e495-565a-9481-8c9ad5beed16 | note | Minimum Test Frequency - Per Batch
7ba0e458-8ec0-5f01-bea9-97d47ef6f5e1 | note | Inspection / Test method - M/1
523e76e3-a4db-5cdd-b1ed-0e226b960d90 | note | Acceptance Criteria - Conform to Specification
f45f8321-7e38-5e03-b1bb-fdbba563ac7b | note | Record documents (QCP - Quality Control Portal) - Certificate in contractor's site folder
c44ee264-6945-5ad7-a465-b15c9b41e725 | note | Responsibility - Stabilising Contractor
ab299b4d-b18d-5b50-9a5e-b1f8cdefcee1 | note | Designer -
ec1d330a-2c28-501f-a77f-8c317478100a | note | Eng. Rep - I
2e1f689d-e116-534a-8de0-dbf7c83486db | note | Contractor - R
| checkpoint | 3.04 - Spreading of powdered stabilising agent (Cement / Lime)
ebdb1c69-d01e-542a-af29-cd00411caf01 | note | Detail of Activity / Test - Place 1m2 canvas or 0.5m x 0.5m trays along spreader run
665587d1-b012-5647-8432-1169cb2afaf7 | note | Action (Hold, Monitor, Witness) - M
8533d432-e1b2-5c15-b878-ef3a8320e208 | note | Minimum Test Frequency - every 400 m2, every 150m for a 2.4m width
9cef32df-05e5-5425-9134-7f9fd809a187 | note | Inspection / Test method - Weigh mat or tray
aee8a673-c0dc-59b5-b3f8-bb8c5cbb09b1 | note | Acceptance Criteria - ± 0.5kg/m2 of specified rate
83e4c2fc-c068-5a10-b192-d0ac196c3388 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
89ceb06f-fee8-5bb4-86c0-307e7d9a6b2e | note | Responsibility - Stabilising Contractor
93f088f5-fc9c-5369-a12c-1751ae58df14 | note | Designer -
29cd1974-c2da-5922-baa2-88a4cbc5bac9 | note | Eng. Rep - I
c7f4d48b-4d9a-5019-b34b-d5df5e927170 | note | Contractor - R
| checkpoint | 3.05 - Spreading of powdered stabilising agent (Cement / Lime)
721b9694-e710-5062-a80a-2c1a80b7e893 | note | Detail of Activity / Test - Compare area spread with weight used for each spreader load
39bdd341-c01e-55b9-afeb-4829d9188ed0 | note | Action (Hold, Monitor, Witness) - M
898403a8-f1ab-5ede-b6b3-be8830b07c14 | note | Minimum Test Frequency - On-going measurement by computer/load cells
cd0ea3a3-dc21-5660-94b5-e5700441918e | note | Inspection / Test method - Measurement each run
eb69fde7-e6dd-5ded-9fa7-6a546d982673 | note | Acceptance Criteria - ± 2.5% of specified rate
ce11192f-f779-5859-8e34-89eb156ba096 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
f007fd1b-4641-5084-ae1a-e95076be6a89 | note | Responsibility - Stabilising Contractor
42802bee-c58c-5872-a616-2f19e1393d2a | note | Designer -
9dae86dc-7376-5177-8d7f-5f509797a55f | note | Eng. Rep - I
58ed924f-d949-5ef1-8aa7-c5bbfe1fdaff | note | Contractor - R
| checkpoint | 3.06 - Injection of bituminous stabilising agent (FBS or BE)
940f8bac-e707-5c09-921d-bfc2384abc8c | note | Detail of Activity / Test - Flow meter and operator's display readings
cbc6c9a2-98ec-5d4a-9fcc-c8405a95e72c | note | Action (Hold, Monitor, Witness) - M
ba0a952b-8b1e-5900-b5d8-c96c58f6f379 | note | Minimum Test Frequency - Continous monitoring by the operator and the grounds person
612965e8-1945-55f3-bbbe-1bd8f3e3f032 | note | Inspection / Test method - Visual display reading
f1bae931-f2bb-5e7a-8290-8f5e3f8b6929 | note | Acceptance Criteria - ± 5% of specified rate
3dae57ad-629a-57de-8d75-41d373c95675 | note | Record documents (QCP - Quality Control Portal) - N/A
330630e0-7f68-5251-b816-28e36f0f854e | note | Responsibility - Stabilising Contractor
a092c365-e7e3-5f3d-8b5a-2e4183ebdebf | note | Designer -
b54dc74d-7779-5a9c-9438-9cc5cc5bf1b8 | note | Eng. Rep - I
b6370a95-48c9-50fd-bbcb-9b46560931af | note | Contractor - R
| checkpoint | 3.07 - Injection of bituminous stabilising agent (FBS or BE)
9320143c-0558-5fc9-b7ce-999549f52ac5 | note | Detail of Activity / Test - Compare tonnes used (from the stabiiser's PCU) with the measured area
cdaa59eb-ff58-5585-9e21-f93edc3474f3 | note | Action (Hold, Monitor, Witness) - M
160259bd-88e0-5a5d-8e1b-0cd57f49e9ad | note | Minimum Test Frequency - Record usage from PCU at the end of each run
dcc6f9b6-b9aa-5d01-80cf-c58c86534daf | note | Inspection / Test method - Record readings at the end of each run
4ab0a6de-ddff-53b9-9f23-8157df54b886 | note | Acceptance Criteria - ± 3% of specified rate
1dfd94d0-9320-5f6a-80c8-ff72b3a184e8 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
ec833f0c-252d-5576-bb29-ceee63c7e41d | note | Responsibility - Stabilising Contractor
2a11dc50-dd23-5b3f-9ddc-6fb243d17ffc | note | Designer -
4cf0a763-56b8-51d8-ad8c-2948b0ef7a15 | note | Eng. Rep - I
8347c761-20a3-5dbe-8303-aee196d54d13 | note | Contractor - R
| checkpoint | 3.08 - Injection of bituminous stabilising agent (FBS or BE)
2dd6d971-5a56-5978-950f-dca62e4477fa | note | Detail of Activity / Test - Compare tonnes used (from delivery docket) with measured area
16513ca9-3a36-5c1c-ad9f-fc4e6ea26e51 | note | Action (Hold, Monitor, Witness) - M
72ff0555-6dcd-5757-938b-2bba4c86928e | note | Minimum Test Frequency - For each bitumen tanker load
907e172b-62c4-5a34-90f8-8f3027a798d7 | note | Inspection / Test method - Dip bitumen tanker before and after
02bd6f9e-f851-5293-bb90-ff3fdddcdb03 | note | Acceptance Criteria - ± 2.5% of specified rate
3918916f-6cd1-5ae7-bcea-bb3743346dac | note | Record documents (QCP - Quality Control Portal) - Daily work Log
a4612f46-baf9-5726-9e84-32d33c073036 | note | Responsibility - Stabilising Contractor
c370c5a3-0d90-57ab-b163-9c5e8b8c0f63 | note | Designer -
69da0d7f-161a-5500-aa0d-84e1220a9e45 | note | Eng. Rep - I
53afbbac-fe02-58e7-aee1-0862280ba0aa | note | Contractor - R
| checkpoint | 3.09 - Injection & Mixing of Water
9164c521-fc99-5ef6-918b-143af100a014 | note | Detail of Activity / Test - In-situ Stabilisation process
eeb9939d-2e3e-5bd3-80b4-ce465bcff4b6 | note | Action (Hold, Monitor, Witness) - M
9077b394-9922-5c18-8188-434f7faee5bc | note | Minimum Test Frequency - On-going visual assessment
85f12cce-8a44-5d29-9303-933b7c6baad0 | note | Inspection / Test method - Visual and hand squeeze test
1d7be9ec-bc16-57fc-b2ae-e020b7a190d2 | note | Acceptance Criteria - Mixed material free of pockets or streaks. Overlaps minimum of 150mm
a2d59421-dee9-58d9-b74d-466dcc535607 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
081cdd09-0532-5be3-ad5f-145b1451c3e7 | note | Responsibility - Stabilising Contractor
2f21695c-9723-5024-902f-905de6f88c5e | note | Designer -
b4fc1109-2dd0-51ae-8355-6b154724a956 | note | Eng. Rep - I
40df0563-2e8c-5cf5-a35c-280d40772c0a | note | Contractor - R
| checkpoint | 3.10 - Depth of stabilisation
430efee4-866e-5c94-95ff-c2b89438033a | note | Detail of Activity / Test - Depth of stabilisation
e73d659d-a765-5b9f-8431-4c3482cd6067 | note | Action (Hold, Monitor, Witness) - M
318b605b-00c5-533d-bfa9-9abfdfc91ac2 | note | Minimum Test Frequency - Every 200m
dd1e137a-4bad-5474-8907-e3e2c2988ead | note | Inspection / Test method - Measurement
b0642379-449f-5949-89b9-b42debbc1ba7 | note | Acceptance Criteria - +15mm / -5mm from specified depth
43a3ff64-86db-5034-a083-78cb508d0002 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
7f4b1954-163c-51fd-91da-4363d2284609 | note | Responsibility - Stabilising Contractor
1e362fc9-9321-5456-b612-bb532c0946f2 | note | Designer -
4a236261-8177-5f5a-b552-b774d90ab1ae | note | Eng. Rep - I
50774958-11af-5df4-b8cf-f823fb6197aa | note | Contractor - R
| checkpoint | 3.11 - FBS material
46ddfceb-e2dc-5285-bef1-5d42bbff8e5f | note | Detail of Activity / Test - Stabilised material strength - ITS
aba067f2-10d9-5920-9874-263c29977d4a | note | Action (Hold, Monitor, Witness) - M
9eddfadb-2bf8-55e1-b56d-864742308805 | note | Minimum Test Frequency - 3 soaked ITS + 3 dry ITS per Lot or when the material changes
9302794f-4594-5093-a1dc-020f08e22296 | note | Inspection / Test method - NZTA T/19N: 2020
243da002-7e36-5e35-88d7-d6a5361beda8 | note | Acceptance Criteria - Testing at 1mm/min:
a12c0c0a-c8ef-5ae4-8c5d-234cd28ade6b | note | – BSM Dry ITS: 150 kPa to 400 kPa
ad0ef415-126e-5b68-9b35-f156f5ecbda3 | note | – BSM Soaked ITS: 120 kPa to 350 kPa
3e92d676-8338-58c8-afeb-d3b2f94af728 | note | ○ Testing at 50.8mm/min:
0c75f157-1187-5bda-a8fe-e2dc77d687e3 | note | – BSM Dry ITS: 180 kPa to 450 kPa
dcd870d0-d701-54aa-8c7e-f95f2be36e84 | note | – BSM Soaked ITS: 150 kPa to 420 kPa
fd85fda4-7d45-5544-8430-b728d11602c2 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
bbb9674e-69f1-5c83-9126-4d55f4da1ef0 | note | Responsibility - Stabilising Contractor
6bfcaeac-1fab-5138-b203-6cffa1ba0cfe | note | Project Specific Notes / Instructions - ITS briquettes to be produced on site if travel time to lab > 30 minutes.
3194d33e-6103-5de6-b860-6d56d9eb56bb | note | Designer - I
44d1196c-c8e6-5363-9096-2a74ac38df9a | note | Eng. Rep - A
85966a30-6d1b-5449-a6ef-c17c4500b91f | note | Contractor - R
| checkpoint | 3.12 - Compaction
94df43cc-3457-5f64-9a9c-9b7c901de1dc | note | Detail of Activity / Test - Plateau Density Test
97c1bfc2-fe8d-5f3e-b0f0-5efdc97cc65d | note | Action (Hold, Monitor, Witness) - H
ce2ba0b4-32ec-5c6f-a084-6e613a485634 | note | Minimum Test Frequency - On first day per site and then 1 per 10,000m2 unless material or anvil conditions change
619a2e82-8961-53ac-b044-885cf1ea6e39 | note | Inspection / Test method - Draft NZTA T/24 (Aug-2024)
8cfac5bb-cd9f-54ca-94db-717ae8f9debe | note | Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD
fda27670-4486-58fe-9106-9305fa135f94 | note | Record documents (QCP - Quality Control Portal) - Field PDT sheet photos into ConQA for ER and Pavement designer to assess. IANZ report when processed.
46fabe8f-2536-512b-b496-67468c67d8df | note | Responsibility - Stabilising Contractor
b38976f3-013d-5de3-a279-68d125e3211c | note | Project Specific Notes / Instructions - If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER
aff8f298-738e-59f2-8515-b4da5176d8d3 | note | Designer - I
337ccb98-0115-561f-8b36-affafc83a401 | note | Eng. Rep - A
bfa39a51-afb0-59a1-9454-0fa170473a11 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.13 - Compaction
895ffb88-e626-5b90-ae93-29cb6d7b2e5f | note | Detail of Activity / Test - Maximum Dry Density
dd87a4f8-5552-563b-b16b-c77ebc9dbefa | note | Action (Hold, Monitor, Witness) - M
135ee69a-60d5-5818-b118-62e6b8e39b42 | note | Minimum Test Frequency - On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes
8f33c499-ffe7-508b-a7c4-d1db3d998c16 | note | Inspection / Test method - NZS 4402.4.1.3
6a862b84-251b-5649-8fa7-97c714e2aa62 | note | Acceptance Criteria - For analysis of DoC
2c1efbd0-5101-5e99-8226-3234f2dd5ee1 | note | ○ To be done at the sampled MC, at hand squeze test MC and 1% above the hand squeeze test on site
1c711be7-0074-50c3-96dd-6cc129d50e92 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
04f668bf-4e54-5c14-9dce-09bba300c67a | note | Responsibility - Stabilising Contractor
1f04e8eb-0cf1-5d60-be40-ad0335c75f2a | note | Project Specific Notes / Instructions - MDD briqutte to be produced on site if travel time to lab > 30 minutes
2def514a-7ca6-5f8d-a5f4-e3a14069e43a | note | ○ Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out.
4b5f73eb-1e11-5297-b682-04741336cb04 | note | Designer - I
8eff42b5-fbe8-58db-bb8b-9fad6c1d48ab | note | Eng. Rep - A
602aa6ca-e822-5916-b1fe-be624525db29 | note | Contractor - R
| checkpoint | 3.14 - Compaction
ea7c2f8b-85da-5cae-9a2b-bed429949bcb | note | Detail of Activity / Test - Degree of Compaction (DoC)
a06659eb-2a21-5e7d-a1ea-5224ac7e6dc6 | note | Action (Hold, Monitor, Witness) - H
d2be0f71-255f-5330-a37e-665929025a42 | note | Minimum Test Frequency - 5 per 1,000m2
24996e1d-2b67-5194-baa0-e8735f9c7167 | note | Inspection / Test method - NZS 4407.4.2.1 (DT full stabilising depth)
51d15499-b0f0-5b14-bcce-1578834a3321 | note | Acceptance Criteria - Average DoC ≥ 98%, Minimum DoC ≥ 95%
3c856d1e-d8a6-58b2-b2e3-48939a227795 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
cb326d81-f1c7-5b33-a680-19e6a606be28 | note | Responsibility - Stabilising Contractor
a31fbe3f-f80c-5432-8e27-9459b5a67caa | note | Designer - I
204779c9-1ab2-509b-8cdd-8f485e24b9e4 | note | Eng. Rep - A
845e8c38-421b-52ea-b999-778ed3d695b5 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.15 - Finished Pavement
3341277a-b4b3-561f-8658-179e8fd5cb68 | note | Detail of Activity / Test - Crossfall
e9a895e0-6b41-5fc6-8a88-9177c684224e | note | Action (Hold, Monitor, Witness) - H
7533eee9-76f2-5151-9fb6-dfcc6337d55c | note | Minimum Test Frequency - every 20m
6dc44e3d-d532-5be9-98e4-5899ae5e3909 | note | Inspection / Test method - Measurement
beadaebc-79f1-5cff-851f-42b43eac10c2 | note | Acceptance Criteria - ± 0.5% of specified crossfall measure, 2m apart
37e91b38-7dcf-59fe-b954-a80690ce95b0 | note | Record documents (QCP - Quality Control Portal) - Survey
20c79d50-f981-5bb3-a2d9-a9150fc5c4d3 | note | Responsibility - Stabilising Contractor
06e4afab-d678-5812-b818-23640b895b13 | note | Designer -
15742fa1-c27a-5ab2-a809-ab1acae8953b | note | Eng. Rep - A
49059814-c02f-5015-9cb4-7ca703ecb14f | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.16 - Finished Pavement
d49f6bda-531d-5d5c-976e-9998bd98966d | note | Detail of Activity / Test - Stabilised width
6a47d5c8-6757-58ee-8948-e35bb6753458 | note | Action (Hold, Monitor, Witness) - H
5d2041b0-83d9-5d13-8f38-1dbbca399549 | note | Minimum Test Frequency - 1 every 20m
61abf257-1e26-5af9-a26f-1d55b482bfdd | note | Inspection / Test method - Measurement
eef53334-6a28-54cf-9b78-21641f2abd1b | note | Acceptance Criteria - -20mm, +100mm
961a9cb7-b411-53ca-878c-92a6e5225f85 | note | Record documents (QCP - Quality Control Portal) - Survey
0cea34c6-dfca-52af-821b-8f4960470a59 | note | Responsibility - Stabilising Contractor
bb7a6dbe-20c2-5ce9-ae8f-e196ecd2ff7a | note | Designer -
31f7eaa9-9ec8-5d89-a0cd-fc4d002e29e3 | note | Eng. Rep - A
7a96c7ec-a11d-5311-b14c-967b2fc94329 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.17 - Finished Pavement
d895b294-310d-548b-9d60-d08cf8fda856 | note | Detail of Activity / Test - Surface Shape
29b71316-aee7-5208-84b4-e15c965db1a8 | note | Action (Hold, Monitor, Witness) - H
740fae6e-c7e1-5249-a367-86855ee48d63 | note | Minimum Test Frequency - every 20m
c0a76551-d2f3-5205-a577-1e6635d6a5f7 | note | Inspection / Test method - Measurement
32137c7e-f583-5a8a-a43b-4dec3754ec31 | note | Acceptance Criteria - < 10mm using 3m straight edge
37890296-bdf4-5691-8f45-f8e3b6397a55 | note | Record documents (QCP - Quality Control Portal) - Survey
007ba64a-2530-5278-8046-76ed34c820cf | note | Responsibility - Stabilising Contractor
04f6f856-53da-51d4-bfaa-b8d8580b6e63 | note | Project Specific Notes / Instructions - Only required if the visual inspection appears unsatisfactory
26795058-fb90-5081-849f-375fcb1295b0 | note | Designer -
40955c7e-d139-576f-a2f6-ef346c6dc2e1 | note | Eng. Rep - A
b865a8b1-08ca-519a-93ad-c6a603141f23 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.18 - Finished Pavement
4fcf577e-f510-55fb-b0e0-afc44c322321 | note | Detail of Activity / Test - Surface Levels
ed961cbc-b31d-584c-bf0e-768369dada5c | note | Action (Hold, Monitor, Witness) - H
78bb4a81-ccdb-535f-b456-d18c106cd6b6 | note | Minimum Test Frequency - every 20m
f26b8f41-e061-5ab7-a2e3-2fd7e2fe85f9 | note | Inspection / Test method - Measurement
58d12bc3-9afe-5967-bed8-b284b14604b7 | note | Acceptance Criteria - -5mm, +15mm
9b9d1c25-3050-5c65-8dff-674de58a9f9b | note | Record documents (QCP - Quality Control Portal) - Survey
a080c344-db83-5016-9905-85b969b1a4d2 | note | Responsibility - Stabilising Contractor
a144b90d-3bcd-5e4f-bd6e-008fd10cf030 | note | Designer -
f2e9cbb1-235f-5dd6-84ef-3faa49bba8c0 | note | Eng. Rep - A
757f8df6-b4ae-5798-8405-3c88b8df644e | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.19 - Finished Pavement (1)
7574ace1-ee8d-5fc4-b73d-926644ad7bd0 | note | Detail of Activity / Test - Surface Finish
6560992d-a663-5bf8-9066-3e22d9eb55ad | note | Action (Hold, Monitor, Witness) - H
b46a5eb0-191e-5540-90f7-44017555ce96 | note | Minimum Test Frequency - Per Lot
8fe352f6-6628-5b68-b5e8-7af2f422b700 | note | Inspection / Test method - Visual
43c76510-6e25-5abd-9cee-aee7781cdf68 | note | Acceptance Criteria - 1. Larger aggregate held in pace with a matrix of smaller aggregate
3a9bf5aa-638a-507b-ace2-afbc5057ab55 | note | 2. Smaller aggregate held in place by fine material
a440c61e-c137-5043-88e1-422e078d0bfa | note | 3. matrix does not displace under normal trafficking and/or sweeping
b6a9defe-3663-5239-9dbc-e9cd2e6a6570 | note | Record documents (QCP - Quality Control Portal) - Survey
e1355051-4842-52ce-a52b-d702d9267c9f | note | Responsibility - Stabilising Contractor
29e43e32-5c06-5038-b2fa-0698dff7b4c3 | note | Project Specific Notes / Instructions - ER to be present at pre-seal inspection
d1f1fd88-e33d-5ea3-8076-e85360550a6c | note | Designer -
9d296bc6-693a-567e-a0b4-a4c760747bf9 | note | Eng. Rep - A
73b0adb0-829c-51c3-970f-96f14e9f6851 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.19 - Finished Pavement (2)
3ff2d1b4-e61e-5fbd-894b-82b3b79cd277 | note | Detail of Activity / Test - Roughness
d4bb4b3f-4a1d-56e7-8a0b-f6fa88af1ebc | note | Action (Hold, Monitor, Witness) - H
e9e1fd48-c4b1-5b2c-9be9-ebc0408c5964 | note | Minimum Test Frequency - Before Sealing
97b8036b-7a73-5e33-9e99-fcbda9cee2da | note | Inspection / Test method - TNZ TM 7003 v1
e78c7545-da5b-51af-bc67-90f6f3c2b720 | note | Acceptance Criteria - 100m rolling average ≤ 75 counts/km
6f4604c0-e93d-5ead-a777-15fdeca97a45 | note | Record documents (QCP - Quality Control Portal) - Test Certificate
d774cdee-6f0e-56b2-a43b-e1621a0a33eb | note | Responsibility - Contractor
5727f324-08ff-5e76-9164-d2ac39399f07 | note | Designer -
e8b927c6-cbf9-5adb-8cc7-c58d619270a3 | note | Eng. Rep - A
67cf6972-dac2-5adc-9181-e0591436be23 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover)
279a365b-eb80-5950-8b33-18400b76f6bb | note | Detail of Activity / Test - Clegg Impact Value
9ccbea11-2515-51b6-b136-0310bc9c1773 | note | Action (Hold, Monitor, Witness) - H
0d398692-c5db-5cb8-89e8-8dad889b3e49 | note | Minimum Test Frequency - 5 per 1000m2
2f454144-5322-5840-8b1a-9e6308c59667 | note | Acceptance Criteria - CIV ≥ 50
bd73bf20-b534-5666-9df9-a13d92368c17 | note | Record documents (QCP - Quality Control Portal) - CIV form - ConQA
3a1d5b3b-5040-5666-a36e-5dc27cdd0564 | note | Responsibility - Stabilising Contractor
9322bdb9-2f67-5cac-9cfd-5df2e99c2af9 | note | Designer - I
87b0d417-32cb-5566-9a04-cb4b936b8bd9 | note | Eng. Rep - A
8907282d-39fe-5149-8657-f7b421b9e6a5 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.21 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover)
076f6efb-1864-5aaa-b943-39404e4dc85c | note | Detail of Activity / Test - Degree of Saturation, DOS
7513f3ed-f9ac-5c1e-a55c-b08777cdd7a9 | note | Action (Hold, Monitor, Witness) - M
b12a852c-f85c-564a-8140-54251915d391 | note | Minimum Test Frequency - 5 per 1000m2
4bc976ad-567d-58db-9d01-ce89e5c7c727 | note | Inspection / Test method - NZS 4407.4.2.2 and DOS calculation in NZTA B/5
770a66a2-4b4e-5ade-a53a-49fa580e620c | note | Acceptance Criteria - aim for DOS ≤ 80%
c038888e-0ba7-524f-90e7-10f82f6f0348 | note | Record documents (QCP - Quality Control Portal) - IANZ report
1e36d244-7c1f-5908-b258-d0c17461c8e4 | note | Responsibility - Contractor
025eca51-65aa-5d1e-b0a3-249a203ec500 | note | Project Specific Notes / Instructions - Report only
83003806-b015-58b5-92f8-9896692fb120 | note | Designer - I
5dd4b705-ce13-554f-9a3c-dec1e8853a3e | note | Eng. Rep - A
b71769bc-6331-566c-bb51-a56302930a33 | note | Contractor - R
| section | 4.0. FINAL SIGN OFF
| checkpoint | 4.01 - Pavement Layer Signoff
5503c545-236c-5086-9a2a-9ef8d175585a | note | Detail of Activity / Test - Assessment of all test results for conformity
4cda2e35-5625-549c-b4fc-12ac2e38420a | note | Action (Hold, Monitor, Witness) - H
05c24fd8-63d0-51ea-b750-f41ea2aff2ae | note | Minimum Test Frequency - Each Lot
cf4e5707-f2b2-54a6-9074-2e298233362c | note | Inspection / Test method - Site Inspection
dc58bba4-4e49-59d6-80c9-ca31437f9093 | note | Acceptance Criteria - Reporting of any non-conforming results to Designer via NCR
4948c31e-6e15-59b6-b3b5-dc80229427ec | note | Record documents (QCP - Quality Control Portal) - NCR
94af590f-f1d6-53d3-adeb-80ed6538f71a | note | Responsibility - Engineers Representative
ebe24c54-1388-5b5b-8d9e-d8bed8aba77c | note | Designer -
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
9f467806-3159-5af2-b225-c579ce379a68 | textbox | Contractor's Rep Name:
9175d3c1-8949-512c-87ba-fbc4f3ac627a | textbox | Engineer's Rep. Name:
6d81d04d-d8d1-5ae3-8178-e344ab519238 | date | Date:
| signoff | Add Signature