## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DTM-ITP-006- Unbound Flexible Pavement Construction | itp |  |  |  |  | DTM-ITP-006- Unbound Flexible Pavement Construction Rev0
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | Reference Documents - IFC Drawings
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 1.2 - Material Mix Design
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mixes RC500.02 as listed in Section 175.
label | Reference Documents - 812.04, VicRoads RC500.02
label | Inspection/Test Method - Document Review
label | Record of conformity - Crushed Rock Registration, This ITP signed
label | HP
label | Responsibility - Site Engineer / QAV
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Material Quality
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Material complies with the Class 4 specification for crushed rock
label | Reference Documents - 812, Table 812.121
label | Inspection/Test Method - Measure
label | Record of conformity - Test Results
label | IP
label | Responsibility - Site Engineer
date | Date Completed:
section | 2 - Placement
checkpoint | 2.1 - Layer Thickness
label | Frequency - Each layer
label | Acceptance Criteria - In addition to complying with pavement layer surface tolerances specified in Clause 304.06(b), the following tolerances shall apply to the thickness of any pavement layer:
label | (i) the subbase course shall be not less than the specified thickness by more than 15 mm;
label | (ii) the base course shall be not less than the specified thickness by more than 10 mm and the average thickness of base over every 100 m section, over the full carriageway width, shall be not less than the specified thickness;
label | (iii) the combined thickness of subbase and base courses shall be not less than the specified thickness by more than 15 mm.
label | Reference Documents - Drawings and 304.06(c)
label | Inspection/Test Method - Visual and Measure
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 2.2 - Jointing
label | Frequency - Each lot
label | Acceptance Criteria - The layout of joints shall conform to the following requirements:
label | (a) material shall be spread in such a manner as to minimize the number of joints;
label | (b) for all pavement layers, transverse joints in adjoining paver runs shall be offset by not less than 2 m;
label | (c) transverse joints shall be offset from one layer to the next by not less than 2 m;
label | (d) longitudinal joints shall be offset from one layer to the next by not less than 150 mm;
label | (e) longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane.
label | Reference Documents - 304.07
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 2.3 - Test Rolling
label | Frequency - Each lot
label | Acceptance Criteria - All pavement layers shall be compacted to withstand rolling and shall be test rolled in accordance with Section 173, prior to acceptance of the layer.The Contractor shall provide for the Superintendent to be present during all test rolling.
label | Reference Documents - 304.08
label | Inspection/Test Method - Test Roll
label | Record of conformity - Witness Point
label | HP
label | Responsibility - Site Engineer / QAV
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Testing and Conformance
checkpoint | 3.1 - Determine Testing Scale & Initial testing frequency
label | Frequency - Prior to Testing
label | Acceptance Criteria - Scale B - The first lot of each material type shall be tested to demonstrate compliance with the material property requirements specified in Clause 204.04. Where the first lot of each material type satisfies the material property requirements in, no further testing will be required unless changes are observed or where directed by the Superintendent.
label | Reference Documents - 204.161
label | ○ 304.08 (a)
label | ○ 304.11 (b)
label | ○ 304.11 (c)(iii)
label | ○ Table 304.111
label | ○ Table 304.121
label | Inspection/Test Method - Document Review/ Site Inspection
label | Record of conformity - Signed ITP
label | AP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 3.2 - Compaction Testing
label | Frequency - Every Lot, Every second lot (reduced frequency)
label | Acceptance Criteria - Minimum Characteristic Density Ratio (CDR) of not less than 97% (subbase) for Scale B, using Modified compaction effort. Material during compaction shall have a moisture content of not less than 85% of optimum.
label | Reference Documents - 304.081, 304.11 (b), Table 304.111
label | Inspection/Test Method - Test point
label | Record of conformity - This ITP signed off; Test reports
label | TP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 3.5 - Completed Surface Level Compliance
label | Frequency - Each lot
label | Acceptance Criteria - Layer to be finished to a smooth and uniform surface and after compaction shall conform within the following limits:
label | ○ Shape: no point deviation > 8mm from 3m straight edge in any direction
label | ○ Surface level tolerances: As per table 304.062 below
label | – 40 measurements per lot (Scale B - Davey Street, Macquarie Street, Southern Outlet)
label | Reference Documents - 304.06, IFC Drawings Table 304.062
label | Inspection/Test Method - Survey
label | Record of conformity - This ITP signed off; Survey Report
label | TP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 3.6 - Pavement Dryback and Embedment
label | Frequency - Prior to sealing works (only for uppermost layer below asphalt)
label | Acceptance Criteria - Scale A - The uppermost pavement layer after preparation of the surface and prior to sealing shall be allowed to dry back so the moisture content of the layer meets the requirements of Table 310.031 for each test lot. Also, pavement embedment shall be assessed by Ball Penetration testing when required as detailed in Table 310.031
label | Reference Documents - 310.03, Table 310.031
label | Inspection/Test Method - Review
label | Record of conformity - Test Results
label | TP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
holdpoint | Add Signature