## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | ITP-171-STR-SSB-Post and Panel RW-Piling and Steel post installation Rev 1 | itp | ITP-171-STR-SSB-Post and Panel RW-Piling and Steel post installation |  | 14f7f739-a33c-4452-8ac1-15630ee3ba65
| section | Referenced Documentation
| checkpoint | Referenced Documentation
7140b100-c3b1-50ea-b735-c0492424df85 | note | Document Title: ITP-171-STR-SSB-Post and Panel RW-Piling and Steel post installation
b5a36515-3de6-5e8c-ae1e-b2892a1a5ebf | note | ITP Description: SSB-Post and Panel RW-Piling and Steel post installation
bfe8b5c0-6076-5274-a11b-ad7af79a1567 | note | Discipline (e.g. CIV/STR/RAIL): 171-STR
9a8df709-cd89-54cc-888b-be5dd0701e25 | note | Revision Number: 1
1e009a7e-a356-519c-bf33-e8c053e4fd91 | note | Revision Date: 29/05/2024
0f5cfda5-14fd-5b2c-abf0-ea42f54a7330 | note | ITP created by: Victor Mira
8b1cf9bb-0759-5561-9116-6426a1d20906 | note | ITP approved for use by: Victor Mira
48cc6efc-4f72-5859-82c6-7b695ed73ad2 | note | 1.1 Non Dependent
4b2d4d68-fab0-51bc-810f-107236c623bd | note | Reference: VicRoads Section VR 606 July 2017
6c2c79bc-ef2f-5d5a-923b-d6b82acf0b94 | note | 1.2 Non Dependent
49013930-edd6-5b87-a44e-43b0c31feb6e | note | Reference: VicRoads Section VR 610
30599074-7c21-57cf-beb0-acde7295d50b | note | 1.3 Non Dependent
d93a748b-7a09-5f2f-ae68-c6ea4944dacb | note | Reference: VicRoads Section VR 611
41fb889a-790c-5b44-9784-dc6274d29e67 | note | 1.4 Non Dependent
9e4ae9a4-87fb-571e-afed-b3fa095a21be | note | Reference: AS2159-2009
ec4378bf-7ffb-599d-b6ce-6b82e1d63c66 | note | 1.5 Non Dependent
065a6145-00a0-52ed-9a66-5d77579908e5 | note | Reference: VicRoads Section 630
4dc4958b-dffb-58b4-b7d9-76e5399b4eb4 | note | 1.6 Non Dependent
60d93e04-8a50-5224-a30f-3ff6741e5bb2 | note | Reference: AS2159-2009
| section | Preliminaries - Materials
| checkpoint | 2.1 Concrete Mix
4d01fde1-df6c-5797-9959-97a486034266 | note | REFERENCE: VR 610.07 Table VR 610.071
ed0e169b-01b0-5258-b707-b41ac5f13377 | note | – – – – – – – – – – – – – – – – –
45660aa8-09e4-5fe4-83cc-13978c6e364f | note | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
e440e2ba-151b-5dc3-b27e-436c11b25144 | note | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
204c4921-b8b0-5bb1-b48d-86eca8390a59 | textbox | Enter: TeamBinder Material Approval number
7efde954-f89c-5fcf-9737-2d4ee4d069f8 | note | – – – – – – – – – – – – – – – – –
acf2dbea-f147-5437-985b-652f7c65593f | note | METHOD: Document Review
a4ebef05-450e-5c8c-8453-a4e5fe64967e | note | – – – – – – – – – – – – – – – – –
ac48882c-8cdc-5b2a-bc50-de3a2f4129b2 | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
165776ce-885b-50f8-80d3-801283712003 | note | – – – – – – – – – – – – – – – – –
6b913a7b-6dd9-5644-a09d-178d6d6233c7 | note | CATEGORY: HP
cc777502-3599-5449-b01b-61a6af62329f | note | – – – – – – – – – – – – – – – – –
e9828e8c-cdf6-52cb-a725-6664fe54af73 | note | RESPONSIBILITY: Nominated Authority
80c1e2c4-002d-5fa3-a6b5-e723a0e3d366 | note | – – – – – – – – – – – – – – – – –
e983ef49-eb9e-55cf-bcb6-4dff9e57ea86 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
f0bc8dfb-1a2a-5bf8-b138-fbda53cb9463 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 ACRS Certification (for Reinforcement)
a1306511-a7e4-5059-be1f-1850ec69d2e5 | note | REFERENCE: VR 611.05 (a)
f664906a-0074-5804-b05a-a1810f37ac41 | note | – – – – – – – – – – – – – – – – –
44c774f2-dbcf-5622-a77a-0e7a6ffd34b3 | note | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
22e49f5d-cc11-5f87-b43a-168ad86fffd6 | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g. 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
7bd8f8d2-b348-5454-aaab-8033170b7d64 | textbox | Enter: TeamBinder Material Approval number
a5b44336-7085-5070-8e44-5ecb57ab83ca | note | – – – – – – – – – – – – – – – – –
5ce904d5-a25d-54f8-9bfc-fb5197b1a608 | note | METHOD: Document Review
174659b0-1a9f-5faf-adbe-18f7e9dc3acb | note | – – – – – – – – – – – – – – – – –
f293f669-5ab4-5b92-b088-5e2dda292b03 | note | FREQUENCY: Once for each supplier, 14 days of award of contract
6b31b6dc-d7cf-5aed-8c9c-16e90df5c6c4 | note | – – – – – – – – – – – – – – – – –
f5bb3c33-40f0-5015-8075-7ec24415d920 | note | CATEGORY: HP
f5f2f0ff-a4f3-51b3-bbe0-7afed80bfa45 | note | – – – – – – – – – – – – – – – – –
3ce22be3-f9d1-5794-8c6c-d5c8ee52fa8a | note | RESPONSIBILITY: Nominated Authority
9b7ce79d-5950-5dbe-bcd4-ef7000eddf48 | note | – – – – – – – – – – – – – – – – –
7368ddbb-2cbd-57c9-b3b9-0082bd806eaa | note | VERIFYING DOCUMENTS: This ITP
9b155f05-478b-5f07-bd98-db59675d1497 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 Bar Chairs/Aspros/wheels Certification
e75ef907-3f3b-5b75-9463-4f03f8060199 | note | REFERENCE: VR 610.26 (a)
1b0ea237-c34d-56fe-baa0-7fc48328bedf | note | – – – – – – – – – – – – – – – – –
4638bd85-948e-5bf5-b17f-252c9b425975 | note | ACCEPTANCE CRITERIA: Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
ec5c04eb-e89c-509c-8d90-b4067fc80449 | note | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
2b845e8d-4e8c-5414-9b3a-789a5a76abdc | note | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
65d7e147-7185-5907-a7d8-a32d8a47dc4a | textbox | Enter: TeamBinder Material Approval number
98396374-2d72-50aa-b4df-166320a3e811 | note | – – – – – – – – – – – – – – – – –
4d155396-ee5c-5fb7-b8d5-e517546ac791 | note | METHOD: Document Review
f6fc7b6a-6557-5969-aa77-ddb69ec5f2fa | note | – – – – – – – – – – – – – – – – –
08478185-3947-56c1-91da-6ba40f1e6d58 | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
4664b749-92a6-56d0-9f38-85b296e68684 | note | – – – – – – – – – – – – – – – – –
05da2a88-f06d-5cf2-9d9c-d8f0dd310afb | note | CATEGORY: HP
81457136-660a-517c-9635-60826cbc0736 | note | – – – – – – – – – – – – – – – – –
61b53150-dee2-5437-ae1b-7314f70ad678 | note | RESPONSIBILITY: Nominated Authority
6f40b961-4175-57dc-936e-a63caa95c920 | note | – – – – – – – – – – – – – – – – –
c13e5734-70e4-58a5-8cfc-665bc13b27ad | note | VERIFYING DOCUMENTS: This ITP
c66e313c-ff10-53f9-9295-b58badffb647 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 Steel Post
3a696e59-4384-5b6d-8d82-96c3f45d676f | note | REFERENCE: 630
d330c328-0070-5d3a-81a4-4988ae34b07a | note | – – – – – – – – – – – – – – – – –
20cad741-733c-539f-b71c-9313e8c0868a | note | ACCEPTANCE CRITERIA: Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component.
6a46ffce-6de1-59d5-adb4-3a954f0476ba | note | Typically this consists of but is not limited to:
51e1d173-c9fe-50dc-b304-3ef297486e6e | note | i. Certificate of Compliance
0af4f554-e8ce-5b40-9063-ccbb92859bd9 | note | ii. Completed ITP
f9d2075c-3c37-56cc-9180-588bf4ffeb57 | note | iii. Weld Procedure Specifications
a4f511cc-96e9-5732-9671-c51bfc817307 | note | iv. Weld Procedure Qualifications
fc696e01-bd64-5cde-a87e-efc9eae045fe | note | v. Welder Qualifications
b073615d-c6ea-5d65-a02d-a55f4b065a94 | note | vi. Material Certificates and traceability
c97d888b-15f2-5fbd-9f72-1655fed40b60 | note | vii. Quality Assurance check sheets
31ac30f6-7261-5abd-9820-c1bdc7cf3173 | note | viii. Welding Consumable batch certificates
e6f9ac8f-1010-5650-8dfe-0d45b925f0f5 | note | ix. Coating certificate(s)
32d4b54c-6029-5318-83e7-52b5b73e9bc8 | note | x. Non-destructive Testing (NDT) Reports
762c979a-48a9-5486-a26d-1b1a46dc01f9 | note | xi. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
fc512458-7141-55bc-81eb-3216df17002c | textbox | Enter: TeamBinder MDR Lot number
dd1de0c3-c647-5104-bdaf-a1c6a7f70d78 | note | – – – – – – – – – – – – – – – – –
0f6d3265-1ae6-554f-b9f2-1246bb1827ec | note | METHOD: Document Review
42d5c766-ede0-5eb2-a22c-cbeb1d075a2e | note | – – – – – – – – – – – – – – – – –
28909ae8-de28-54f1-ab59-1a727f04a4d1 | note | FREQUENCY: For Each Element
ebd565d6-377c-5a80-b92e-a5371b1c4c3d | note | – – – – – – – – – – – – – – – – –
bc27519e-349e-568d-82fd-f8e64db8ae12 | note | CATEGORY: HP
66d1ff0a-fff2-5c34-9186-5a08a4e8b121 | note | – – – – – – – – – – – – – – – – –
3ca3c407-fc2f-50e3-bea2-b78a47afb6a6 | note | RESPONSIBILITY: Nominated Authority
d214910d-6ce5-52ff-9a2c-e1a4c1b26e66 | note | – – – – – – – – – – – – – – – – –
927c3f06-5cb3-536b-aea4-ba1afdf98242 | note | VERIFYING DOCUMENTS: This ITP
9aeb307b-45cc-5e56-9a34-6637e5f791e0 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Preliminaries - Procedures & Documentation
| checkpoint | 3.1 Piling Operations Work Procedure
2b52d7a4-d599-5a3f-90be-7f50f3298056 | note | REFERENCE: VR 606.03 (a)
71e4f91f-a5b3-579b-9ef3-0062babfc700 | note | – – – – – – – – – – – – – – – – –
ae913888-0907-5a57-8756-172378cbac0e | note | ACCEPTANCE CRITERIA: Piling operations work procedure to be submitted for review to the Nominated Authority.
ef296558-7d8c-5ea7-8617-47e47c710cca | textbox | Enter: TeamBinder Approval number
4c79b510-fe23-5522-b45b-990bd3e813dd | note | – – – – – – – – – – – – – – – – –
b11a64cb-263f-577e-b202-f2ee22678da2 | note | METHOD: Document Review
60e67c4b-6e28-5c7d-a6d4-ea638375eb6f | note | – – – – – – – – – – – – – – – – –
0e10947b-3028-5381-ac18-0b7045f8fe24 | note | FREQUENCY: Once, 4 weeks prior to the commencement of piling
c9f934bc-1d51-5512-891d-551451d3c8bc | note | – – – – – – – – – – – – – – – – –
032d3f8e-c780-54eb-9551-65573e468c05 | note | CATEGORY: HP
3240c919-db6a-5bd1-bbad-aff00a6c7911 | note | – – – – – – – – – – – – – – – – –
ff42f41e-875a-5426-af91-f1e68eaf1df7 | note | RESPONSIBILITY: Nominated Authority
539cccee-efcf-5299-b957-197869e9f54d | note | – – – – – – – – – – – – – – – – –
ff920fb6-fc5d-5fd5-8288-388544101dd0 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
442a967b-e016-579a-be4c-d155debff5dd | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 Pre-qualified Pile Testing Consultant
c26dbb76-cdcb-5b58-97a2-56cf0be746ed | note | REFERENCE: VR 606.07
307d6d08-cf00-5972-b992-3496c8c77f01 | note | – – – – – – – – – – – – – – – – –
cd8fe6ea-13c1-56cb-9f4d-58e9d63f6451 | note | ACCEPTANCE CRITERIA: All testing shall be undertaken by a Vicroads pre-qualified consultant who is independent of the piling contractor.
a6558e30-fc1f-5505-880d-6c5c17413109 | note | ○ Details of the consultant to be submitted for review to the Nominated Authority.
82bf37dc-1eee-5b0c-960e-0dae3078f47c | textbox | Enter: TeamBinder Approval number
d46c4d00-bbfc-5cf5-9f23-43c3edfbbc81 | note | – – – – – – – – – – – – – – – – –
ac4fca68-296e-5f90-bf6a-9dac5e2a4061 | note | METHOD: Document Review
7cd656c5-4226-551f-9048-d074e506c34b | note | – – – – – – – – – – – – – – – – –
88de1d14-ed3a-578f-8f3b-737d8e5b7ea8 | note | FREQUENCY: Once, two weeks prior to testing
859fa1ea-d146-5ce5-8f29-07095a435c78 | note | – – – – – – – – – – – – – – – – –
646615a9-5539-50a2-a388-3a2dfc028229 | note | CATEGORY: HP
184f7512-3325-532a-ade3-029beb2a5572 | note | – – – – – – – – – – – – – – – – –
dc8fc8ef-c516-59ab-b852-7206f76e20cf | note | RESPONSIBILITY: Nominated Authority
a4e9ef1d-442f-56fe-ba6b-398c8e41dc00 | note | – – – – – – – – – – – – – – – – –
96666436-912f-57b1-b724-ebf04e81a9d6 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
5a103932-2147-5405-908b-096f430315ce | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Pre-construction Activities
| checkpoint | 4.1 IFC Drawings
e15f48b3-3044-564f-b1e6-ed98309b95b8 | note | REFERENCE: MRPA Quality Management Plan
6868a5ec-9848-52ba-b653-3fddd04d258a | note | – – – – – – – – – – – – – – – – –
7b71ad5d-9961-513e-ac7d-939ae1388f77 | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on TeamBinder)
7eb928d2-ef6e-533b-9ed6-5de1215e2d6c | note | – – – – – – – – – – – – – – – – –
745393f9-1cd1-581a-b7f0-eb73f1b1de50 | note | METHOD: Document Review
b673b002-e60a-507a-8449-7626fec3e34a | note | – – – – – – – – – – – – – – – – –
c5f8db7d-50b3-5b82-a27c-dd1def3e8002 | note | FREQUENCY: Prior to starting Works and at regular intervals
0afd4ed6-b376-5604-acce-f5f776454a18 | note | – – – – – – – – – – – – – – – – –
3ccf6d39-e5ed-5d03-a8e1-992a8c1782a9 | note | CATEGORY: HP*
71434425-4ff9-507c-ad77-add02a4df2c8 | note | – – – – – – – – – – – – – – – – –
4f13e597-fb5d-5be5-9150-8d56ead96f78 | note | RESPONSIBILITY: All
57a54c4e-f38a-5668-b547-cd77515d44e3 | note | – – – – – – – – – – – – – – – – –
00bac684-a8c7-537b-98c7-8afb7f1968b6 | note | VERIFYING DOCUMENTS: This ITP
4f1fc353-d8ec-5d8b-b9fb-b7aab4b7fee7 | date | Date Completed:
| checkpoint | 4.2 Survey Set-out
382a811e-5864-5ecd-b10f-45b33bb394ee | note | REFERENCE: IFC Drawings VR 606.08 (a - c)
60fb1aed-9d53-5254-83cb-9b7402f3804f | note | – – – – – – – – – – – – – – – – –
574567ac-daed-53d0-bfb1-3dde29c506b7 | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
4c6b6199-cdcc-534f-b0d3-4b1887c2b8ce | note | Attach: Lot Map, Marked drawing to indicate the location of piles in the Lot
30c1f699-4669-5ba4-a723-92112570b9a7 | note | – – – – – – – – – – – – – – – – –
d17f8307-eb2f-5b29-8aed-96029b439ec0 | note | METHOD: Measure, Visual
9c1badc0-1286-5a8b-a7d9-4c01da17cd72 | note | – – – – – – – – – – – – – – – – –
8056dd1f-548d-5ce0-bfba-16d31e5999f5 | note | FREQUENCY: Each pile
f7117a85-3320-597a-b2dd-cc86f7ad09e0 | note | – – – – – – – – – – – – – – – – –
77805517-86f0-51d1-bd95-681b60374f1e | note | CATEGORY: IP
f4e6d03f-2730-5f69-971b-ab9920de03f1 | note | – – – – – – – – – – – – – – – – –
81515dc9-813b-5ccb-8b96-a51ed75ce02c | note | RESPONSIBILITY: Surveyor, SE
2feedf07-287f-5aea-a131-acab1dba5e5d | note | – – – – – – – – – – – – – – – – –
36ae7eb4-1557-5a84-a101-85545ecc77bf | note | VERIFYING DOCUMENTS: This ITP
0ae8f736-415b-51e0-a96d-efaf17e9f4bb | date | Date Completed:
| checkpoint | 4.3 Protection of Adjacent Piles
2869b4ae-fcbd-513e-ae46-f6153985e8d2 | note | REFERENCE: VR 606.04
a155a8d4-261f-5569-867f-47255c7d45bc | note | – – – – – – – – – – – – – – – – –
e3561f02-83e4-5199-86bb-8fa42abf4678 | note | ACCEPTANCE CRITERIA: Pile construction shall not:
08a7f770-cff8-55c5-b908-995c6b2f033c | note | i. result in damage to adjacent newly cast piles due to ground vibration.
b7f4057c-dcfc-576b-8b0d-89166f680dd1 | note | ii. commence within 2.5m clear distance from newly cast piles if that pile concrete strength <15MPa
4b9b25da-cd14-534f-a187-3283007da12b | note | iii. involve driving or create significant vibration within 9m until that pile strength ≥15MPa and set for a minimum of 24 hours
f1dc81ac-afd7-5256-b86f-b49a9aacb54b | note | – – – – – – – – – – – – – – – – –
8f2f98d5-cb37-5c72-81f2-6726788e89ae | note | METHOD: Measure, Visual
10b76026-a6ca-59e1-83c9-16c1b24a0b12 | note | – – – – – – – – – – – – – – – – –
cbd1e818-ba12-5e5a-879e-f2e92236b422 | note | FREQUENCY: Each pile
0110935a-fc51-5869-a59e-aca8c603b8ec | note | – – – – – – – – – – – – – – – – –
858bdeea-e8dd-5a43-9ca0-d590385b09d8 | note | CATEGORY: HP*
e1b34ee0-2635-597d-9b9b-ef372ea03dad | note | – – – – – – – – – – – – – – – – –
68705dc0-4dab-5d42-9c8a-292f392f356c | note | RESPONSIBILITY: SPE/PE
c0e72493-f6d7-5c26-88de-d32a224fc6ed | note | – – – – – – – – – – – – – – – – –
301e7bb5-fa48-51d2-ae39-a34ec13c22a9 | note | VERIFYING DOCUMENTS: This ITP
f9f77b81-9f01-5fa5-97e6-63ff7a241038 | date | Date Completed:
| checkpoint | 4.4 Steel Post Material Inspection
fe156f90-243e-5741-a58c-e9f459be3b44 | note | REFERENCE: IFC Drawings
d155614b-ec87-518c-8b7f-130316ad9516 | note | – – – – – – – – – – – – – – – – –
7d99e472-6e30-5974-a8d4-761349bf241c | note | ACCEPTANCE CRITERIA: General inspection of structural steel elements for:
1a59105c-cd5a-588e-bae0-136ac6ae9d8e | note | – Damage & distortion, twist
e58b500a-8655-5a33-8d65-7da192ac168f | note | – Defect to the coating.
49c213aa-0259-5efd-9695-f692769ba51f | note | – Defects to welding between bearing plates and the profile
421978e4-5f0d-5293-bbdc-5c6ace4cef00 | note | – – – – – – – – – – – – – – – – –
b2de9571-0e50-5300-bef1-00586488409f | note | METHOD: Visual
5f3e4e41-acff-5e59-a028-e3624361eb07 | note | – – – – – – – – – – – – – – – – –
a8dee5d1-3f6f-554b-8529-643887ba851b | note | FREQUENCY: Each delivery
339c6929-3313-5156-bb9a-1e01ca9ce47e | note | – – – – – – – – – – – – – – – – –
a4b132ff-d4ca-58a1-8ddb-9e30a56409ea | note | CATEGORY: IP
9014f903-4f8c-5f15-bbba-dbd60da5aec6 | note | – – – – – – – – – – – – – – – – –
bd8dad89-39b3-5f24-b8b9-2223aedb5c11 | note | RESPONSIBILITY: SE/PE
bf876baf-73d9-5401-9336-ee1f13ff504a | note | – – – – – – – – – – – – – – – – –
e853e839-7cb2-5be4-9ce9-8fae05cff4c0 | note | VERIFYING DOCUMENTS: This ITP
53fcc659-a7c5-5e10-9740-825fdc0513d6 | date | Date Completed:
| checkpoint | 4.5 Steel Post Material - Correct post
10713a82-c2a4-584f-9c5c-aba95e911d42 | note | REFERENCE: IFC Drawings
44e0f7c8-49c4-516f-88db-19d22a8a32f9 | note | – – – – – – – – – – – – – – – – –
02287c80-c479-5afe-ba6d-306233a2c8e7 | note | ACCEPTANCE CRITERIA: For each post:
1e37c07a-0fc4-527d-bfa9-187080b870fa | note | – Check the profile of steel post (Type and Size)
c99646f3-f0e9-53b7-8d36-16cc01f55f1a | note | – Check the length
701c4b45-b7f7-56b6-8a66-35f012f118eb | note | – Check the Bearing plates number
de3524f7-602f-5788-b0d6-ee324ae63ef9 | note | – – – – – – – – – – – – – – – – –
14db8f2b-4db2-5d9a-8a09-d46f0ab88c68 | note | METHOD: Visual, Measure
938c6ba7-5277-5762-ac0a-cc1d99c8aa01 | note | – – – – – – – – – – – – – – – – –
2562ba4a-7b02-5385-ab43-01538330e7cf | note | FREQUENCY: Each Element
67c1fd4e-85ef-599a-ac77-10343dc26402 | note | – – – – – – – – – – – – – – – – –
e3b411af-0cf1-58e8-ac3c-7c386bc527ea | note | CATEGORY: IP
6c9ae534-d243-585b-b54c-2ed7f90b4b8a | note | – – – – – – – – – – – – – – – – –
aca245df-752d-5fa9-9678-3461517317b0 | note | RESPONSIBILITY: SE/PE
1172b581-73c0-56da-8200-d2af5985f700 | note | – – – – – – – – – – – – – – – – –
3c0917d7-39a9-5449-89b0-a04f33e70d94 | note | VERIFYING DOCUMENTS:
09c412fe-5c32-5c34-8039-cae1e1269b17 | date | Date Completed:
| section | Construction Activities
| checkpoint | 5.1 Reinforcement - Inspection
| note | REFERENCE: IFC Drawings
| note | 611.06
| note | 611.09
| note | 611.10
| note | 611.11
| note | 611.12
| note | – – – – – – – – – – – – – – – – –
| note | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
| note | ○ Projecting reinforcement is the correct length and location.
| note | ○ Splice lengths achieve the minimum length and are in contact for this length.
| note | ○ The reinforcement surface condition is free from dirt, debris and damage.
| note | ○ Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
| note | ○ The resulting reinforcement cage securely held with sufficient ties (or tacks) to limit displacement or deformation during handling.
| note | – – – – – – – – – – – – – – – – –
| note | METHOD: Measure, Visual
| note | – – – – – – – – – – – – – – – – –
| note | FREQUENCY: Each pile
| note | – – – – – – – – – – – – – – – – –
| note | CATEGORY: IP
| note | – – – – – – – – – – – – – – – – –
| note | RESPONSIBILITY: Foreman, SE/PE/SPE
| note | – – – – – – – – – – – – – – – – –
| note | VERIFYING DOCUMENTS: This ITP
| date | Date Completed:
| checkpoint | 5.2 Boring Operations (Bored Piles)
64463eef-7f0e-5152-a52e-e63e137313e9 | note | REFERENCE: IFC Drawings VR 606.03 (a)
3b0128f2-2271-584d-a48b-36fc6d3c88b4 | note | – – – – – – – – – – – – – – – – –
bfe64dfa-9bba-508f-80e2-e7b76865ac17 | note | ACCEPTANCE CRITERIA: Boring performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
a3bf4a23-76a7-5f2b-9044-a5b68ef19667 | note | ○ Excavation clean and de-watered (where applicable) for inspection.
06be78e8-1867-5d11-b7c7-b73930f56e5e | note | ○ Excavated material to be disposed of as appropriate to maintain a clean site.
d3d4f165-48d8-5274-b5ed-e710329ea45d | note | – – – – – – – – – – – – – – – – –
eca18119-61ee-5c6d-a8f0-9776b83cfb50 | note | METHOD: Measure, Visual
baba1778-c8ed-51cc-9580-866305ccbc38 | note | – – – – – – – – – – – – – – – – –
6f3789db-9665-5e72-bbf6-2c4125d2fdd6 | note | FREQUENCY: Each pile
9df92a5a-ba26-52d8-9588-6c1aed133c17 | note | – – – – – – – – – – – – – – – – –
137936fc-a8ee-50c1-ade7-4a8431d0957d | note | CATEGORY: IP
1e90f30e-9cc6-583f-a9c8-96e6f4019e21 | note | – – – – – – – – – – – – – – – – –
37894879-aec6-5944-af04-eb4a04ea6e67 | note | RESPONSIBILITY: Surveyor, SE/PE
00604b07-708d-56c0-8160-0af4cce350de | note | – – – – – – – – – – – – – – – – –
21eeee03-f5a1-5fcd-aafb-e32f02f8857e | note | VERIFYING DOCUMENTS: This ITP
c1242fa2-f679-5a09-b427-9f31e3190653 | date | Date Completed:
| checkpoint | 5.3 Augering Operations (CFA Piles)
| note | REFERENCE: IFC Drawings 607.04
| note | – – – – – – – – – – – – – – – – –
| note | ACCEPTANCE CRITERIA: Augering performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
| note | ○ The augering shall be in once continuous operation with boring rate, penetration rate and torque monitored and recorded through-out the entire process.
| note | ○ Where piles are founded on rock, they shall extend into the rock at a depth shown on the IFC Drawings.
| note | – – – – – – – – – – – – – – – – –
| note | METHOD: Measure, Visual
| note | – – – – – – – – – – – – – – – – –
| note | FREQUENCY: Each pile
| note | – – – – – – – – – – – – – – – – –
| note | CATEGORY: IP
| note | – – – – – – – – – – – – – – – – –
| note | RESPONSIBILITY: Surveyor, SE/PE/SPE
| note | – – – – – – – – – – – – – – – – –
| note | VERIFYING DOCUMENTS: This ITP
| date | Date Completed:
| checkpoint | 5.4 Inspection of Pile Excavation (Bored Piles)
85368da5-a0e4-505b-8ca1-8ac6603df827 | note | REFERENCE: VR 606.05
517d3240-2140-5f2e-b3fd-8e7933feeaa2 | note | – – – – – – – – – – – – – – – – –
16577933-8fb9-50e6-9bd6-778746c04810 | note | ACCEPTANCE CRITERIA: Pile walls and base to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
a8579572-90ff-50c8-91cc-1ce1434691e6 | note | Attach: Geotechnical Field Sheet or Report
d7cb0187-e94e-5052-bff9-2642b55bdde1 | note | – – – – – – – – – – – – – – – – –
bb1fe919-32e8-5605-b2a0-82cd5ebad42c | note | METHOD: Measure, Visual
5862d057-7dc8-51d1-ab8e-45272981473a | note | – – – – – – – – – – – – – – – – –
36c47ba5-99ec-5605-af00-7417b8a4e3ad | note | FREQUENCY: Each pile
9726b9b6-f3bd-567c-b38d-119984f8b0ff | note | – – – – – – – – – – – – – – – – –
658c91a3-670c-5706-bfd3-376c0f6a1007 | note | CATEGORY: HP
8cc10b7f-6283-5f51-84b4-b8db13a7933d | note | – – – – – – – – – – – – – – – – –
5e86cb93-ad05-5128-a413-2f72b1e12931 | note | RESPONSIBILITY: Geotechnical Engineer
2a7e8a8b-5aa3-5886-bc94-7a2d2137bec9 | note | – – – – – – – – – – – – – – – – –
36891f8e-2ae7-585c-bbb7-879de3cceb20 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
6903b545-f9b6-56c9-9134-c1ba09ac0fb1 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.5 Inspection of Excavated Material (CFA Piles)
| note | REFERENCE: 607.04
| note | – – – – – – – – – – – – – – – – –
| note | ACCEPTANCE CRITERIA: Excavated material to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
| note | Attach: Geotechnical Field Sheet or Report
| note | – – – – – – – – – – – – – – – – –
| note | METHOD: Measure, Visual
| note | – – – – – – – – – – – – – – – – –
| note | FREQUENCY: Each pile
| note | – – – – – – – – – – – – – – – – –
| note | CATEGORY: HP
| note | – – – – – – – – – – – – – – – – –
| note | RESPONSIBILITY: Geotechnical Engineer
| note | – – – – – – – – – – – – – – – – –
| note | VERIFYING DOCUMENTS: ConQA Hold Point Release
| date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.6 Increase in Depth Beyond Design
| note | REFERENCE: 607.04 (a - d) Piling Operations Work Procedure
| note | – – – – – – – – – – – – – – – – –
| note | ACCEPTANCE CRITERIA: Where increasing the pile depth beyond the levels shown on the IFC Drawings is necessary, follow the approved work procedure and obtain confirmation from the geotechnical engineer that the newly bored depth has achieved the required design capacity.
| note | ○ A full account of the changes shall be submitted for approval to the Nominated Authority:
| note | Attach: Geotechnical Engineer's Acceptance of the New Pile Depth
| note | – – – – – – – – – – – – – – – – –
| note | METHOD: Measure, Document Review
| note | – – – – – – – – – – – – – – – – –
| note | FREQUENCY: Where applicable
| note | – – – – – – – – – – – – – – – – –
| note | CATEGORY: HP
| note | – – – – – – – – – – – – – – – – –
| note | RESPONSIBILITY: Geotechnical Engineer
| note | – – – – – – – – – – – – – – – – –
| note | VERIFYING DOCUMENTS: ConQA Hold Point Release
| date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.7 Reinforcement - Placement (Bored Piles)
239b1518-d78c-5847-a5c4-719c404bc77b | note | REFERENCE: IFC Drawings
117e3712-a140-5778-ba26-6c253fd1556c | note | ○ VR 611.06
34d1bdee-a54e-553f-8750-9c6864e52db5 | note | ○ VR 611.09
a90a3be6-1732-5e91-b4cc-302202fcaebf | note | ○ VR 611.10
653efdb7-796f-5fd6-9a4e-b460488b4f04 | note | ○ VR 611.11
5e90495e-7484-56db-bb93-ab6326c6e891 | note | ○ VR 611.12
94aa25e2-5b2e-50d7-a3c8-54f3e29fd0d1 | note | ○ VR 606.06 (a)
3b9e51d5-071e-5239-885e-f79ef87cce52 | note | – – – – – – – – – – – – – – – – –
63d8d4b9-706c-5439-a909-280a8f1b2f43 | note | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
9c823025-7f91-56a9-bb2c-a48f57eecada | note | ○ Projecting reinforcement is the correct length and location.
345064fb-28e5-5243-a466-746f793acd51 | note | ○ Splice lengths achieve the minimum length and are in contact for this length.
ac35d507-2280-5979-8565-55b768ac062b | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
6ba45e03-3042-5dcd-ace2-4787ee3220bb | note | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
7fb2edd7-4b77-5e8b-abd8-905d39245e48 | note | ○ Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
07e60652-ae90-526d-b59a-6866242130a4 | note | – – – – – – – – – – – – – – – – –
02cfbed7-04cd-5681-a22a-c2349379f1e4 | note | METHOD: Measure, Visual
207605d5-b399-5320-bffb-0d9bb1d3dc9d | note | – – – – – – – – – – – – – – – – –
ba1e3d82-731f-5ca5-be05-7d926aa6e3d3 | note | FREQUENCY: Each pile
1885385a-b93b-5db6-9c05-cd827d4d1959 | note | – – – – – – – – – – – – – – – – –
b72453a0-f34e-50e2-bbb8-9a711fc15dd5 | note | CATEGORY: IP
5e2a7821-ef4e-5619-9fd0-e92fd5c4cce5 | note | – – – – – – – – – – – – – – – – –
ffa4182a-a4b6-50d9-ba61-f4146969b5a4 | note | RESPONSIBILITY: Foreman, SE/PE
60e00d43-673f-551d-b873-31dc8dc9ace0 | note | – – – – – – – – – – – – – – – – –
2ab608f1-48b6-5674-9d48-c3d9cae21af0 | note | VERIFYING DOCUMENTS: This ITP
e58a5383-3b7f-546b-ac99-e03e7462f39f | date | Date Completed:
| checkpoint | 5.8 Cast-in Items-Steel post
2755dacb-2475-54a8-bef2-e3bebb9cfe64 | note | REFERENCE: IFC Drawings
ba8e822b-9535-5141-9774-4af8beb1cdb4 | note | VR 610.46 (a), Table VR 610.462
fc51d21a-ffbe-5a1e-8097-b5a8654e07bf | note | VR 610.47 (a), Table VR 610.472
deba91d1-4fe3-54fa-aabc-7f9829c65a5e | note | – – – – – – – – – – – – – – – – –
b9292f24-3dcd-50b2-a776-a8508582e187 | note | ACCEPTANCE CRITERIA: For each post:
a601757e-a826-5114-98a2-b4288ca91bae | note | – Check the profile of steel post (Type and Size)
1853042a-3de4-55fa-b5d7-2c6846b34fb7 | note | – Check the length
454b0e1f-bfe2-5a33-8599-3008404f519a | note | – Check the Bearing plates
1862e553-fe6e-541b-851b-0fe4d25b4354 | note | – – – – – – – – – – – – – – – – –
77d0fad8-8b6b-56ff-bdc9-73448bee56e6 | note | METHOD: Measure, Visual
99f8c40e-0718-56a5-b7cf-0f0770044543 | note | – – – – – – – – – – – – – – – – –
ace41e41-e4b9-502d-88db-dfbd0ac635ab | note | FREQUENCY: Where applicable, each pile
90ced542-5126-5b5c-ade8-80da9d46db6f | note | – – – – – – – – – – – – – – – – –
b7c79e12-4c4d-503d-8eda-c62e61a1273a | note | CATEGORY: IP
fb8198e2-2d66-5dbf-96a6-baf0ed9ec858 | note | – – – – – – – – – – – – – – – – –
15c3a258-cb56-547a-9a1b-2914aea6de41 | note | RESPONSIBILITY: Foreman, SE/PE
1fafc9f2-cae2-5777-a2fc-80e0fa7b6bba | note | – – – – – – – – – – – – – – – – –
050f3820-12e1-590e-b1fd-c8262788e357 | note | VERIFYING DOCUMENTS: This ITP
6d4e8341-5951-59cd-b629-eee7761ab47f | date | Date Completed:
| checkpoint | 5.9 Cast-in Items-Steel post installation
1d545ff2-b1e8-57a2-a3fa-8a106b3d043b | note | REFERENCE: IFC Drawings
fe40d45b-a931-5b3e-946d-69532ecaf9c1 | note | VR 610.46 (a), Table VR 610.462
b5a6ec51-2e41-5b9f-9fb7-75d9023218f9 | note | VR 610.47 (a), Table VR 610.472
61d9385d-ccf0-554b-9084-1e527cb62944 | note | – – – – – – – – – – – – – – – – –
321f7330-596e-55e9-b233-8df2c4b1829f | note | ACCEPTANCE CRITERIA: For each post:
30e82f82-bc34-5760-b4ec-cb2fc3e1858c | note | – Check the orientation/Rotation
5b97d3c3-ad8f-5fc6-894a-afb3dcf4a1d7 | note | – Check the Rake/Plumbness
f94afd17-c60c-558f-9665-49139845f14a | note | – Check the embedment and above ground height
09acf390-4599-5997-8abe-4f339155f3ab | note | – Check the level of bearing plates to accommodate for the panels to be installed horizontally
14037e15-7539-580c-83cd-d20349073a46 | note | – – – – – – – – – – – – – – – – –
e4d2f7d9-f65d-5992-bbc6-746c2093272e | note | METHOD: Measure, Visual
86024723-d82b-542c-b904-11f802ae59a0 | note | – – – – – – – – – – – – – – – – –
3bbfb51d-dd3d-569c-9dac-7ad93fc35234 | note | FREQUENCY: Where applicable, each pile
66d2153b-e264-513a-b9be-bfe6afa0d4d7 | note | – – – – – – – – – – – – – – – – –
7abaded4-a6fd-596e-ab74-77b2b8f46bb0 | note | CATEGORY: IP
f8ce6f28-24f1-5bf6-bed1-b38f221378e8 | note | – – – – – – – – – – – – – – – – –
a7dfe08d-9974-5686-bf9a-1dfbc42c7ca4 | note | RESPONSIBILITY: Foreman, SE/PE
7c56b5ec-d97a-5a70-a455-ae8f0a278e08 | note | – – – – – – – – – – – – – – – – –
aa0e929d-a02c-5062-be40-92316e0d17d7 | note | VERIFYING DOCUMENTS: This ITP
4f86e12d-e8e0-514b-aafe-5bbee42e4cb0 | date | Date Completed:
| checkpoint | 5.10 Pre-pour Inspection
3cf48b78-ba2c-5975-a1e5-0e6bbdad3169 | note | REFERENCE: IFC Drawings VR 610.18 (a) (ii) & (iii)
78be15d6-51c3-5fa6-9d80-5e1056721fe7 | note | – – – – – – – – – – – – – – – – –
333e42bd-03df-51a9-910e-089e45171c86 | note | ACCEPTANCE CRITERIA: Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
39d20eaa-950f-5d1a-ae0f-6a174e595ccf | note | ○ All foreign material has been completely removed from the excavation.
b1374d7e-b937-5e3c-bad3-1d4b428912f2 | note | – – – – – – – – – – – – – – – – –
d83919ef-a908-5cbd-a371-9b462df11486 | note | METHOD: Measure, Visual
ace6d1f5-a634-5f45-86dc-2b991f729b0d | note | – – – – – – – – – – – – – – – – –
4c74a63e-3f44-5b08-a90a-429193a95222 | note | FREQUENCY: Each pile
3860077e-9027-5112-937f-036e24675824 | note | – – – – – – – – – – – – – – – – –
1761344a-e0e7-5340-aa04-15c67c5f8f9d | note | CATEGORY: HP
0d31f4d8-a903-5b59-be37-117b679d4c83 | note | – – – – – – – – – – – – – – – – –
b2bb3971-1d17-5adc-9629-42683ab1bcb2 | note | RESPONSIBILITY: Nominated Authority
5dfae186-8796-5289-bcb4-f652001fe177 | note | – – – – – – – – – – – – – – – – –
f918decd-0e91-5d59-9cc4-d4a3820d416d | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
c5a7da07-578f-5b71-8843-4dcf2e39fc5b | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.11 Weather Conditions & Evaporation Limits
448a25ab-8153-5412-bf57-8f296d8f28c9 | note | REFERENCE: Hot and/or Cold Weather Concreting Procedure
1310a9d6-6c2b-52c3-8860-d919f26994e2 | note | VR 610.17
b8b9df02-a4d1-5b41-bd54-830bcd573ab2 | note | VR 610.17 (a) & (e)
6a7e27ed-65b2-544f-bce8-27a08a29cf1e | note | Table VR 610.171
ded4a581-f42d-5d67-8ded-8be71c1927a3 | note | – – – – – – – – – – – – – – – – –
f6a6dce0-8024-55db-ba33-08a1ac1175bb | note | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
54e820e8-d383-5a5b-975b-aeefcec9261f | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
4782fd62-d659-5b2b-ae10-31db44eaeac3 | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
1f168883-03ff-5985-a404-d0f83c3e9875 | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
05bcef1d-8672-55e8-9c92-3599987bb829 | note | Record: Required information on the Concrete Pour Record.
5cf03152-ce08-5da3-80f8-f2ffe7ed37b6 | note | – – – – – – – – – – – – – – – – –
e7e24418-9427-58e4-a02f-f593bd8bcf02 | note | METHOD: Measure, Visual
b87fd7b3-a7be-58e4-8b0d-4167b65cf11a | note | – – – – – – – – – – – – – – – – –
d6aa7779-87ca-570a-97a3-3f13a3b8dcbd | note | FREQUENCY: Each pile
b1ccc87d-5b9a-5678-8cc8-cb90f91ac09c | note | – – – – – – – – – – – – – – – – –
c94396c9-251f-50bf-ab46-b4ab16fbf2c0 | note | CATEGORY: IP
cbcfc5f9-31c0-58a0-8748-d1fed2954684 | note | – – – – – – – – – – – – – – – – –
ac90f665-c3ea-5356-999d-d4f1d17e9239 | note | RESPONSIBILITY: Foreman, SE/PE
cf713eaa-c132-53b9-9147-752a12620a83 | note | – – – – – – – – – – – – – – – – –
16e6d1b1-ba76-5bea-a472-4f81b66c3007 | note | VERIFYING DOCUMENTS: This ITP
f99735fd-9955-50f7-be81-6180324e9582 | date | Date Completed:
| checkpoint | 5.12 Concrete Testing - Sampling Frequency
966c9ee2-6535-557e-850d-82b0b721ee02 | note | REFERENCE: Site Sampling & Testing Procedure VR 610.16 (b) Table, VR 610.1, VR 61
1f4e1dd2-2653-5b77-a205-80f436119f88 | note | – – – – – – – – – – – – – – – – –
545e4c13-aa74-59da-8a54-b07d2f6184e3 | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
50b79361-51b4-5c53-b0da-5feea8999eaf | note | 0m³ to 10m³ = 1 sample
f9fef681-b6c6-5e0c-ac2e-780ff7ed7744 | note | 10m³ to 25m³ = 2 samples
195fb19b-95cd-5cdd-b2ee-3331ae77b6d2 | note | 25m³ to 50m³ = 3 samples
4c1ef7ed-9ea6-54c3-a49b-27101bdb9a04 | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
35bbd97e-ddce-51fc-9704-614ce95cca16 | note | ○ For each additional 50m³ and additional sample shall be taken.
e0f9cb1a-6062-5369-9e53-4d9cca9ab6ce | note | ○ Where the time interval between the end of discharge of one truckload of concrete and the beginning of discharge of the next truckload exceeds 45 minutes, the minimum number of test samples shall be one (1) per truckload of concrete
c29bc44d-f491-5ec0-bde9-7088622811f9 | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
d92b95a5-8c32-5110-a8d1-a1ff6a6fd57e | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
f79dfdb6-355a-5c0b-a0bf-8fc0f4829c78 | note | Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
3e4eb771-08c2-5c2d-8287-4d7a1d8173b8 | note | Record: Required information on the Concrete Pour Record.
e293a2b7-1d1f-5b6f-bcf1-1df5833d45c3 | note | – – – – – – – – – – – – – – – – –
ebce1f93-5a51-5cf3-a106-a228adcb4c03 | note | METHOD: Test
8e6cec3b-4446-55ed-84f8-9797d5bd6b9c | note | – – – – – – – – – – – – – – – – –
2a7bec0f-0184-5346-981f-3e81a1079ec3 | note | FREQUENCY: Each pile
91a70a6a-0f6e-55f0-9213-e948233780fc | note | – – – – – – – – – – – – – – – – –
e41dd3a4-b7b4-52bf-9545-92191b4a22a6 | note | CATEGORY: IP
7cceec54-7e4b-53ab-8164-8646323e3319 | note | – – – – – – – – – – – – – – – – –
775cbfb5-5aaa-5558-8a06-e2064b6b857c | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE
0d3f066d-bd8d-56fb-b0cc-80373a342154 | note | – – – – – – – – – – – – – – – – –
bd4de3d3-b00e-53d7-af3d-924414fb15ae | note | VERIFYING DOCUMENTS: This ITP
2b8d62fb-9265-5271-ba5a-168eeb1a9a7e | date | Date Completed:
| checkpoint | 5.13 Concrete Testing - Spread, Passability & Viscosity
0a22386a-c3a7-5087-af06-32a36722f7ee | note | REFERENCE: VR 610.13 (b)
8e93cd67-d97e-5aa5-a967-2bb0cddf1e39 | note | – – – – – – – – – – – – – – – – –
73f3f150-a35f-54cf-b84a-cb770f746cc9 | note | ACCEPTANCE CRITERIA: Spread range = 550mm to 750mm
5a36121e-630e-5b69-8a46-abbe68acae62 | note | ○ T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
35a7e0a1-8515-5630-bd7e-82296dc4fd4e | note | ○ Passability = ≤10mm (aggregate height differential)
210af2dc-b0d4-577d-8e68-9489a3119e15 | note | Record: Required information on the Concrete Pour Record.
60bd29b5-0bb5-5415-9f78-5a8ccf5db073 | note | – – – – – – – – – – – – – – – – –
43e73991-d161-51ac-8652-ea18a5992f94 | note | METHOD: Test
e800b447-0edf-55b4-ab5f-d8bda7a6198d | note | – – – – – – – – – – – – – – – – –
63085646-59cc-5cd4-94b7-464f3889a6b8 | note | FREQUENCY: Each sample of Self-compacting Concrete
12c01ed3-a487-57a5-903f-405632aef06d | note | – – – – – – – – – – – – – – – – –
de25ca48-8d9a-541e-88fc-28bf259721e2 | note | CATEGORY: IP
5e81bf42-bc0c-5843-9ae5-badc3ff380cb | note | – – – – – – – – – – – – – – – – –
1e8827b6-52bc-5e0d-ba84-c373f88f9c32 | note | RESPONSIBILITY: Concrete Tester
b1884462-9696-5151-b874-ed7a6ec20b5e | note | – – – – – – – – – – – – – – – – –
7e8ccb66-c000-5aed-8b52-7f5479e95385 | note | VERIFYING DOCUMENTS: This ITP
38476caf-d168-54cf-aaa1-4c14ef4e37b5 | date | Date Completed:
| checkpoint | 5.14 Concrete Testing - Compressive Strength Cylinders
6333830b-1c5e-59db-a4de-c0a0517d5ed2 | note | REFERENCE: Site Sampling & Testing Procedure VR 610.16
7d27840e-7e00-521d-ad5a-c43e2dad842c | note | – – – – – – – – – – – – – – – – –
61dc7057-2fbe-53db-8e9b-ea1ae7f3bba2 | note | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample.
79c0d5ab-4c6e-5597-8bf6-80000f140cc4 | note | Record: Required information on the Concrete Pour Record.
a7c05c3e-2aa2-583f-a953-4445afc66d7e | note | – – – – – – – – – – – – – – – – –
948c52ae-f2de-543d-8fac-8b7caf22d344 | note | METHOD: Test
d743a972-3468-5429-a8ab-fb4084e0afa3 | note | – – – – – – – – – – – – – – – – –
4aca3269-b415-591f-a5f6-2f5bac98b661 | note | FREQUENCY: Each sample
1ca5b41b-ddad-5a0f-9e6e-7f35537d46a8 | note | – – – – – – – – – – – – – – – – –
e50d8140-cd5a-5358-b2da-f8dbc927263d | note | CATEGORY: IP
62c886cf-1adf-54ed-8c85-d135e8c5773c | note | – – – – – – – – – – – – – – – – –
3ba86e0f-7449-554b-815e-9a887ace3d09 | note | RESPONSIBILITY: Concrete Tester
263bcbf4-990c-5a63-a8a4-229d4c83b98e | note | – – – – – – – – – – – – – – – – –
d4340efc-d79f-51f9-b399-3498e9480bf2 | note | VERIFYING DOCUMENTS: This ITP
92b7dd20-a40d-58bd-96d0-716448fb3526 | date | Date Completed:
| checkpoint | 5.15 Placement & Compaction (Dry or Wet Excavation Conditions)
68997334-aec8-5ef2-bbd2-99e2ebfde4b4 | note | REFERENCE:
f86343e5-720a-5781-ab0d-bbfe8928b38d | note | VR 610.18 (a) & (b)
e98853b1-a8ad-5096-953a-3a668b80781b | note | VR 610.18 (d) (i)
f875c851-3f31-5d6c-b424-8062e82b5a18 | note | VR 606.06 (a & b)
| note | 607.04
3745e9a1-63d0-5dd9-8d2f-a5af69533135 | note | – – – – – – – – – – – – – – – – –
6c600c4d-337e-58a9-831a-f4d68ee97cbd | note | ACCEPTANCE CRITERIA: Concrete shall be placed within 24 hours of excavation - where this has not been achieved, the internal wall & base of the excavation shall be cleaned to an additional depth of 25mm.
788c168d-2678-53b4-875a-e86ed01354f8 | note | ○ All concrete batches are traceable.
4e57e955-4d89-5e79-ad22-2325107e0f77 | note | ○ Concrete shall be placed through either a tremie pipe or concrete pump and not dropped freely from a height exceeding 2m.
7b915a41-3d97-5bf3-96fe-629960d2096e | note | ○ The initial discharge is pumped to waste until a consistent workable mix is discharged.
7a6285dd-d05f-5b8e-b452-04b1b703b7c7 | note | ○ The ends of the discharge pipe shall not be lifted off the base of the excavation until a 2m head is created, which shall be maintained until the completion of the pour.
300dcd15-ac67-52f4-be22-07507f787361 | note | ○ Where a casing is used, it shall be withdrawn with care and at a rate to ensure that the free surface of the concrete is at least 1.5m above the bottom of the casing.
ac0b9a2a-f0e0-5020-a6ec-1f5b8ef1ab63 | note | ○ Pile height is to be 300mm above the cut-off level (or 400mm in wet piles) to allow for breaking back of sound concrete.
24ccb69f-c94d-5ff4-9ba3-e61600929dbf | note | Record: Required information on the Concrete Pour Record.
5741c7c9-cc9f-5f16-bcfa-e630695666fc | note | Attach: Concrete Pour Record
711f7603-5afa-53d2-9381-ed8de029ea0f | note | Attach: Concrete Dockets
00f54863-975d-5900-8fec-a11eb584c3c6 | note | – – – – – – – – – – – – – – – – –
794e7f6e-77d5-5ac7-b5ca-c3ed989c96d3 | note | METHOD: Visual
a70ccff7-f704-5962-ac5c-29994d46a70e | note | – – – – – – – – – – – – – – – – –
899832b6-e93e-56a4-b1a9-4c905c330b52 | note | FREQUENCY: Each load
dd819fec-a9b7-56ce-9d55-4867b8497da5 | note | – – – – – – – – – – – – – – – – –
3ca61870-64df-52b7-a978-a586af064600 | note | CATEGORY: SP
dfd49709-7599-59c9-84fc-1a8e6c20516a | note | – – – – – – – – – – – – – – – – –
aa08d87c-09a3-5620-8b8e-25a69d4c5aa1 | note | RESPONSIBILITY: Foreman, SE/PE
e450e448-2f47-5b9c-a5d2-90995bf4d939 | note | – – – – – – – – – – – – – – – – –
533dec9f-dc20-5080-9552-7aa1bcbb3617 | note | VERIFYING DOCUMENTS:
2916ba73-825b-5015-b69f-917bcee8a1bb | date | Date Completed:
| checkpoint | 5.16 Reinforcement - Placement (CFA Piles)
| note | REFERENCE: IFC Drawings 607.04
| note | – – – – – – – – – – – – – – – – –
| note | ACCEPTANCE CRITERIA: The cage to descend into the plastic concrete under its self-weight - care to be taken to centralise the cage so that there is no dislodgement of excavated material contaminating the concrete.
| note | ○ Note: Vibration of the cage shall only be performed under approval from the Nominated Authority along with evidence that the vibration does not segregate the placed concrete.
| note | ○ If the cage cannot be positioned into its final level, the pile shall be rejected.
| note | – – – – – – – – – – – – – – – – –
| note | METHOD: Measure, Visual
| note | – – – – – – – – – – – – – – – – –
| note | FREQUENCY: Each pile
| note | – – – – – – – – – – – – – – – – –
| note | CATEGORY: IP
| note | – – – – – – – – – – – – – – – – –
| note | RESPONSIBILITY: Foreman, SE/PE/SPE
| note | – – – – – – – – – – – – – – – – –
| note | VERIFYING DOCUMENTS: This ITP
| date | Date Completed:
| checkpoint | 5.17 Surface Finishes-top of the piles
7424d6c0-dcde-5664-b202-da0b3afbeed0 | note | REFERENCE: IFC Drawings
2ff61f34-dd66-57da-b0dc-4f6bddec6cba | note | – – – – – – – – – – – – – – – – –
95f7c28a-701d-5980-9697-e6bf6ceecca0 | note | ACCEPTANCE CRITERIA: Surface finish as per IFC drawings.
4b4e6637-c79e-567a-b70d-e00ade3c4253 | note | ○ Provide nominal fall to top of the pile towards outward edge
fe01f8b1-8d9c-552f-99d1-96dcba06ebba | note | – – – – – – – – – – – – – – – – –
ed5081af-c643-57dd-afba-dde1a4494866 | note | METHOD: Visual
c0714e3b-8c55-5c20-9257-fbc35e97a805 | note | – – – – – – – – – – – – – – – – –
ebd4cdaa-7212-5a16-955e-4add9d30b095 | note | FREQUENCY: Each pile
eac981c9-a6a6-520e-9eff-9795f18d62fb | note | – – – – – – – – – – – – – – – – –
e9047e94-6df4-5b1d-9a10-5962734e960e | note | CATEGORY: IP
058c12b4-228a-53ec-be05-629e777af4b6 | note | – – – – – – – – – – – – – – – – –
d0e74042-ccbd-520b-8761-50909679db41 | note | RESPONSIBILITY: Foreman, SE/PE
0d05e758-e7aa-553a-95c4-39d99a03fbc3 | note | – – – – – – – – – – – – – – – – –
5164ced5-eb4d-5ab6-a1c1-397478541ee2 | note | VERIFYING DOCUMENTS: This ITP
5b24603c-dab6-57db-a350-8a30cc09918f | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.1 Compressive Strength Test Results
2b745e41-42f8-5bfc-b7a2-386636c9b0b9 | note | REFERENCE: IFC Drawings Table VR 610.05.051, VR 610.16 (g)
8be2cf52-ad45-5aad-a450-48d5ae58cbf8 | note | – – – – – – – – – – – – – – – – –
9a58bc40-0a71-5552-a3dd-ceae2a1d0c19 | note | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
ac28aee1-2c9e-57ca-b6ab-ea483f331eb3 | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
5e737474-82f9-5363-a36c-ad012af938ff | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
650bf853-ae0e-5161-bf14-ada0921f7326 | note | Attach: Compressive Strength Test Results
ccde3bec-e843-5af8-9c69-c5192231ad7d | note | – – – – – – – – – – – – – – – – –
6d72a8fc-6626-5bd1-b766-8609899df474 | note | METHOD: Document Review
79bca243-efaf-56a4-9fb3-4d8dc7e2204b | note | – – – – – – – – – – – – – – – – –
b9b26f3e-a70b-577b-a755-96609fdd55fe | note | FREQUENCY: Each cylinder
fc45a153-2067-52f9-a734-db868ebed8cd | note | – – – – – – – – – – – – – – – – –
9d74e5ac-70f6-59a5-bff6-df955f3356d4 | note | CATEGORY: IP
3bbd35ef-b412-5fb6-9c91-c1daecda7c5b | note | – – – – – – – – – – – – – – – – –
e5eacc17-7a70-5c4f-aa46-3fda3a0e821a | note | RESPONSIBILITY: SE/PE
aea4870b-4f7d-5810-a6c2-43190a66e891 | note | – – – – – – – – – – – – – – – – –
6d0f36d3-8e59-5afa-8c95-938189f6d989 | note | VERIFYING DOCUMENTS: This ITP
e3591bd9-8972-5216-94db-9c5b9107a602 | date | Date Completed:
| checkpoint | 6.2 Pile Integrity Testing
e20dcbe5-ea37-5162-bb5a-8dda4d0e4be3 | note | REFERENCE: VR 606.07 (a, d & e) AS2159 Clause 8.8
71ef47e7-817c-55e0-9e57-2dd5d97f7e12 | note | – – – – – – – – – – – – – – – – –
019f7858-cacd-5e45-bf00-0e03a7490003 | note | ACCEPTANCE CRITERIA: Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
8e784805-4859-5daa-b3fd-e44f2b20ce9d | note | ○ Cross-sectional area = ≥95%
7785bb29-21aa-51cd-b09d-a5dc997a5f91 | note | ○ If any test fails, all piles shall be tested.
0b9bc60e-79c0-5d92-aaa8-5a3fe2ae1aea | note | Attach: Pile Integrity Test Report
17d8f78f-f26d-5c47-a00e-0fee5418aadd | note | – – – – – – – – – – – – – – – – –
ad3d9dab-c025-5895-ba5f-fb20a0da0ab7 | note | METHOD: Document Review
43011c3a-60d9-55f5-95c8-0ae6240c35af | note | – – – – – – – – – – – – – – – – –
00778f2d-d587-5bc0-a0d2-675cb263bff0 | note | FREQUENCY: Piles #1 - #6.
596feca4-62fe-5fed-a8ac-c3109e560692 | note | ○ Reduced to 1 test per 3 piles if the first 6 tests pass
120744c0-4d16-5e42-a2cd-44fefddfb46e | note | – – – – – – – – – – – – – – – – –
590e2274-9315-5ea9-92b8-37b55ca0eb10 | note | CATEGORY: IP
1014b85f-3825-57ed-b31f-6766862c2b19 | note | – – – – – – – – – – – – – – – – –
1b20a77f-5047-5493-8126-ba84536afbb1 | note | RESPONSIBILITY: Testing Consultant, SE/PE
ec15426e-0043-5937-9db7-76783b3fdcd6 | note | – – – – – – – – – – – – – – – – –
7c477621-e0c0-5184-a2ee-2e1dcda14937 | note | VERIFYING DOCUMENTS: This ITP
27d8a8d9-0825-5482-b453-07c2b562a258 | date | Date Completed:
| checkpoint | 6.3 As-built Survey
c573d89a-2a5f-5cb1-9088-5ca79e1073fa | note | REFERENCE: IFC Drawings VR 606.08 (a - c), AS2159 Clause 7.2.2
99ad81d9-3b41-5eda-b5f8-10c08d081dd8 | note | – – – – – – – – – – – – – – – – –
dfee99f2-896f-5c12-a2f0-e09e478b57b5 | note | ACCEPTANCE CRITERIA: The following tolerances apply to piles:
b8a7e2e3-4fa5-55d0-b531-a7d8a102ed2f | note | i. Pile head plan location = ±75mm
9b3273b1-1d6a-553d-873a-0b4fbac686d9 | note | ii. Variance from vertical or rake = 1:100
f661dfb8-35be-58a1-91ec-6bcb9db9b2e7 | note | iii. Irregularities in straightness = 1:100
3833015b-ca10-5eb8-9bbb-912b71632b39 | note | iv. RL = ±25mm
36dfb5d8-2858-5bee-9200-664ba2e18676 | note | Attach: Survey As-builts / Survey Report
21f288fc-4ab9-5e7b-a57d-f6fe221ea7b1 | note | – – – – – – – – – – – – – – – – –
ae6feecd-2735-5a08-baec-206bd11eace9 | note | METHOD: Document Review
b9a42594-1dbb-534e-aaea-5ef488032a80 | note | – – – – – – – – – – – – – – – – –
b6cb0efc-4c99-5fbe-990f-5de8fdbf100f | note | FREQUENCY: Each pile
672a99e8-5f89-5671-8438-97c8643c2c8e | note | – – – – – – – – – – – – – – – – –
95f78443-915f-50d8-917c-babb333d047d | note | CATEGORY: IP
eb6abb7c-35b0-509d-9386-b0adbbf53571 | note | – – – – – – – – – – – – – – – – –
a32d1206-d779-5fb8-b8b0-2f7caa7a624c | note | RESPONSIBILITY: Surveyor, SE/PE
e3828f99-097d-50a8-a87b-1d487b8010d6 | note | – – – – – – – – – – – – – – – – –
180ec103-40c5-50c9-b26f-15893da27a44 | note | VERIFYING DOCUMENTS: This ITP
7b2e125e-7abd-540d-b7e0-ce6889b93242 | date | Date Completed:
| checkpoint | 6.4 Non-conformance Report (NCR) Closure
ecf501b4-a451-5ab0-b80c-0f80ed3f3200 | note | REFERENCE: MRPA Quality Management Plan
a808e1d0-363a-5598-a703-23f744876b68 | note | – – – – – – – – – – – – – – – – –
6026d9c9-a39c-5de6-83d7-3a034c75929b | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
cf96180d-b0fd-5b8d-9246-7e6636db66dd | note | – – – – – – – – – – – – – – – – –
d5aa3bcf-8e14-5af8-ba8e-ab06de6e2885 | note | METHOD: Document Review
807d93b0-e52f-5b26-a010-c0b586692e95 | note | – – – – – – – – – – – – – – – – –
9ff413df-3b9a-59f6-b2b8-8a5ae18acb01 | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
4a624b08-09a1-589d-b2c1-78a24f4935b0 | note | – – – – – – – – – – – – – – – – –
47cb1eda-754c-551f-bf28-14154fe6c8f6 | note | CATEGORY: HP*
1dcd8fcb-8bf3-569d-a9e2-629e3d1107df | note | – – – – – – – – – – – – – – – – –
c50a2439-6588-530b-82d8-e56b929c937a | note | RESPONSIBILITY: SE/PE
71d53156-62a9-58a5-8891-b5d5bed123f4 | note | – – – – – – – – – – – – – – – – –
840fd802-527d-5114-8916-d70fde293605 | note | VERIFYING DOCUMENTS: This ITP
b8da4c83-0251-59f4-8f03-c753add32f9e | date | Date Completed:
| checkpoint | Final Inspection
3277118f-7c80-50f0-9406-e3f0515c320d | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
81c0b322-3822-51c3-9663-06575f3ea9e0 | textbox | Name:
e1ae85d9-02b8-5896-8921-e9f66cabb5c0 | textbox | Position:
64b3748d-a9ec-5608-9746-4c5d43ad10c4 | date | Date Completed:
| signoff | Sign ITP