## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Shopfront Install |  |  |  |  | Yes | Shopfront Install | 038089ae-65b3-4ab0-8e3c-79810671bfea
checkpoint-group |  |  | section | Client Opening Handover
checkpoint-status |  |  | checkpoint | QA Handover Received
checkpoint-status |  |  | checkpoint | Pre-Start Checks
checkpoint-status |  |  | checkpoint | Area Clear For Install
checkpoint-status |  |  | checkpoint | Opening Correct
checkpoint-status |  |  | checkpoint | Waterproofing / Flashing Tape Installed
checkpoint-group |  |  | section | Installation Checks
checkpoint-status |  |  | checkpoint | Sill Pan / Support Bar Installed Correctly
checkpoint-status |  |  | checkpoint | Correct Packing
checkpoint-status |  |  | checkpoint | Frame Installed As Per SD's - RL / GL
checkpoint-status |  |  | checkpoint | Fixings as per SD's / Overseal Complete
checkpoint-status |  |  | checkpoint | PEF Backing Rod Installed
checkpoint-status |  |  | checkpoint | Airseals Complete - 6mm & 18mm Wide, 2:1 Ratio
checkpoint-status |  |  | checkpoint | Head & External Flashings Installed
checkpoint-status |  |  | checkpoint | Sliding Panel Adjustment (If Applicable)
checkpoint-group |  |  | section | Glazing Checks
checkpoint-status |  |  | checkpoint | Correct Setting Blocks Installed
checkpoint-status |  |  | checkpoint | Glass Installed - Correct Orientation
checkpoint-status |  |  | checkpoint | Glazing Beads & Wedge - Complete
checkpoint-group |  |  | section | Final Checks
checkpoint-status |  |  | checkpoint | Installation Rubbish Cleared / Trade Clean Joinery
checkpoint-status |  |  | checkpoint | Frame Installed Correctly
checkpoint-status |  |  | checkpoint | Window Functionally Correctly
checkpoint-status |  |  | checkpoint | Doors Operationing Correctly
checkpoint-status |  |  | checkpoint | Installer Confirms Installation Complete
checkpoint-group |  |  | section | Final Inspection & Handover
checkpoint-status |  |  | checkpoint | Handover Notes/Photos
checkpoint-no-status |  |  | checkpoint | Installation Project Manager Signoff
holdpoint |  |  | signoff | Add Signoff / Request Signature
checkpoint-no-status |  |  | checkpoint | Manufacturer Signoff
holdpoint |  |  | signoff | Add Signoff / Request Signature
checkpoint-no-status |  |  | checkpoint | Client Signoff
holdpoint |  |  | signoff | Add Signoff / Request Signature
checklist-sectioned |  |  | checklist | Site Inspection - |  |  |  |  | Yes | Site Inspection - | 71026393-dc22-4e63-9edd-587a50f988ce
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Details Complete (pass once relevant details are recorded below)
text | f38dec04-2a3d-5ccf-a08b-845ec29019be |  | textbox | Site/Location :
text | 77077d9e-3441-51cb-b7e9-59b8f7155c36 |  | textbox | Name of Inspector :
checkpoint-group |  |  | section | Site Control
checkpoint-status |  |  | checkpoint | Hazard Board and signage up-to-date
select | d4c92872-19e8-5375-b18b-502e422269a4 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Environmental plan - issues
select | e2795881-1bea-5989-9dc9-d12f22dfd8b9 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
text | f9e97007-9a23-5662-9b9c-c1e1e11c880d |  | textbox | Toolbox talk last date:
checkpoint-status |  |  | checkpoint | Safety inductions for all on-site
select | ad6f8b90-e7e2-56a7-a340-d6908d902b62 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Safety notice board current
select | c519dd25-6d27-5676-a7e3-88afe4982ebb |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-group |  |  | section | Site Facilities
checkpoint-status |  |  | checkpoint | Offices clean, adequate & good lighting
select | 98ce2840-891d-5622-bff2-36059e0534eb |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Smoko sheds - clean, portable water
select | 4458bf07-35ce-5e85-8604-e968e66a67e1 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Toilets - clean, washing water
select | c20dc337-921c-526c-af25-407441429725 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Tool /equipment sheds adequate
select | e46d6dc4-2252-53f0-a510-ad66676a6551 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-group |  |  | section | General Site Tidiness and Access ways
checkpoint-status |  |  | checkpoint | Clear, safe access to work areas
select | 0f1479c1-b118-5039-8617-2774c08b888c |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Stairways and accessways clear
select | 98939353-1dee-522c-ba2c-b5c8a225cdd8 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Hoardings /fence and gates secure
select | 2f135047-c310-5fdd-adae-653b9cc20878 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Loose materials secure from wind
select | d63e2b2a-097a-52e1-bdd2-9ad76ae4a3f6 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | House Keeping
select | 6a1a8a60-7bc4-56f9-a5e6-553803054fc7 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-group |  |  | section | Personal Safety Equipment
checkpoint-status |  |  | checkpoint | Signage displayed and legible
select | 6bdcb9b6-775f-5c08-b818-90df6fc90141 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Hardhats and boots being worn
select | 7583d653-f134-5614-b3b2-0f80983fc3d6 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Glasses /ear muffs /vests /masks used
select | 0ce17096-a0c8-5b62-af9e-c190b242560f |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Task specific PPE used
select | aff68f5d-a042-58e7-871b-cc2960dfbb77 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-group |  |  | section | First Aid/Fire Prevention
checkpoint-status |  |  | checkpoint | First Aid Box Available
select | d9381337-49bb-58d8-97cc-4b3dd01405b2 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Accident register
select | 0531f97a-706e-5757-b64d-54d5ec634634 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Fire Extinguishers
boolean | 2b28d3d8-df52-5499-9322-da74b94dbf94 |  | tickbox | Available
boolean | e2ab6daa-30d9-5cf1-8f95-a092b68910f9 |  | tickbox | Current (12mth)
boolean | 71d563e4-2b7a-5bb5-8644-8ffffd253679 |  | tickbox | Sufficient number
select | c4d93160-dddf-5581-ac89-bc079ffc0c87 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Evacuation
boolean | ac96a7af-7558-5daf-b920-d54f676dde53 |  | tickbox | Procedure current
boolean | 1d3b0fb6-1339-5f42-8bbf-5036cdcfaaac |  | tickbox | All emergencies incl
select | bf7a16bc-3575-5316-a4ea-e7105361bb27 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-group |  |  | section | Cranes/hoist/lifting equipment
checkpoint-status |  |  | checkpoint | Proper lift assessment plan done
select | f9ec01c1-117c-5a2a-a836-33dea6a7afe4 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Crane certification current
select | 6dd8462a-645e-5d57-8121-e6c88223445f |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Slings/chains certified
select | fc12b77f-23cf-56d1-a644-ed7c1e73c255 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Operator procedures in place
select | 4537e925-ed51-59fb-b645-ebbbc29d3935 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Inspections being done
select | fe6d8154-f349-56f7-a885-f16ab5a9b3ab |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Man cage available
select | 550fc2f6-83ce-5233-adc3-d45c3c06e019 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Emergency plan in place
select | fcdd3861-4da4-582a-9b7a-4a11dc19e17a |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-group |  |  | section | Tools and equipment
checkpoint-status |  |  | checkpoint | In good condition
select | 8fa40ff2-2709-5baf-befe-777579c7fe08 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Appropriate guards fitted
select | 09aebf40-6316-5b02-bf1f-a558215b643e |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Trained user
select | 25a08d78-f5af-5be1-93c5-800c8f4f2397 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-group |  |  | section | Excavations
checkpoint-status |  |  | checkpoint | Correctly Shored/Benched/Battered
select | ca779a54-8bc6-571d-90b4-092fe94ddccb |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Access/Egress Installed
select | 866e37af-0a01-579c-8631-f7ef6643f66a |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-group |  |  | section | Hot Works
checkpoint-status |  |  | checkpoint | Hot work permits being issued
select | c4bd3971-f424-5cdf-a99a-558cacd37cf5 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Fire extinguishers on hand
select | c6221943-d0b3-57e2-abd8-f996486fa51b |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Operators using PPE
select | 265f784d-a767-5508-a8e7-9b869cc89c0f |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-group |  |  | section | Electrical Equipment
checkpoint-status |  |  | checkpoint | Main board lockable /weatherproof
select | 05b0cbf9-a42d-50a0-b7d7-6693e9cb86d7 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Current tagged and damage-free leads
select | c716cb52-1176-5db1-8236-b48897851682 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Current tagged plant
select | 60469683-7fbf-5741-bd60-8d409e8c578c |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Current tagged lifeguards
select | 6ead7d45-5bbb-510d-a630-5ba01a69ed37 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Leads safely placed
select | 71748c9c-b919-5a60-a214-15dceaa3f2a6 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Equipment in good condition
select | d9a37dab-1d46-52a9-a8bc-f82d3125bbda |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Appropriate guards on equipment
select | 146bd8a4-1c99-5b7c-a8d9-3eeae93a10b7 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Adequate temporary lighting
select | d3af6e84-91cd-501c-844f-9cea667b1685 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-group |  |  | section | Chemicals
checkpoint-status |  |  | checkpoint | Correctly stored
select | adfff8a3-6f92-5217-bb95-8263cfb3fc33 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Safety Data Sheet (SDS) available
select | f148262c-1622-51fe-af2a-39d448c19d3a |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Operators using PPE
select | 28111be6-a6dd-5ac2-a53f-6aacc11aa275 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-group |  |  | section | P.A.T Tools
checkpoint-status |  |  | checkpoint | P.A.T tool WoF current and secure
select | 13befa68-caa5-55b1-90bd-8e0e3e2cb777 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Staff trained in tool use (SWPS)
select | 7ed4a65d-7a71-5ff9-9bad-4568278ad2c1 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | PAT signage on site
select | 5623ba44-c051-5376-877b-de6a25b31bce |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-group |  |  | section | Ladders
checkpoint-status |  |  | checkpoint | Good condition
select | bea4b8ae-2ba1-5de6-b326-da70cfe353f8 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Access Ladders secured top and bottom
select | 174c9b21-4f57-5db0-9320-96756b4bf7ea |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Stays and rungs undamaged
select | 21ba8db9-6f77-500f-b047-bfda24c3d036 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Working within weight limits
select | baf8549a-c6d3-58b7-8fe1-652c45db1e8e |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-group |  |  | section | Fall Hazards
checkpoint-status |  |  | checkpoint | Fall Hazards
select | c2cbfa59-f87f-5fbc-b888-0566be409c42 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Floor openings
select | 8519d021-b953-5e97-a480-3cc83333bbf0 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Lift shafts
select | df26740e-677e-539b-b746-f673e780160b |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Stairs
select | 6a8e5536-3b5d-5faa-a485-1c5fe6169a45 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-group |  |  | section | EWP
checkpoint-status |  |  | checkpoint | Clean, Deck Clear
select | 29d8fcc0-531f-501a-9ade-f830643b7a12 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Log complete
select | 96280e6c-1778-5a2f-b0b1-512ff9403ba1 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Exclusion in place
select | d9711d43-b951-5735-b6f6-268c11de5add |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-group |  |  | section | Signoff
checkpoint-status |  |  | checkpoint | Required people sent signoff request
holdpoint |  |  | signoff | Signoff
checklist-sectioned |  |  | checklist | Curtain Wall Install |  |  |  |  | Yes | Curtain Wall Install | 95785238-5abb-44cd-8427-02b50eff2dc6
checkpoint-group |  |  | section | Client Opening Handover
checkpoint-status |  |  | checkpoint | QA Handover Received
checkpoint-group |  |  | section | Pre-Start Checks
checkpoint-status |  |  | checkpoint | Area Clear / Tidy
checkpoint-status |  |  | checkpoint | Opening Correct
checkpoint-status |  |  | checkpoint | Waterproofing / Flashing Tape Installed
checkpoint-group |  |  | section | Installation Checks
checkpoint-status |  |  | checkpoint | Cast In Channel
checkpoint-status |  |  | checkpoint | Floor Brackets & Packing
checkpoint-status |  |  | checkpoint | Bottom Sill
checkpoint-status |  |  | checkpoint | Panel Brackets & Bolts
checkpoint-status |  |  | checkpoint | Panel Install
checkpoint-status |  |  | checkpoint | Soakers / Splices
checkpoint-status |  |  | checkpoint | Flood Testing
checkpoint-status |  |  | checkpoint | Fire & Smoke Mitigation
checkpoint-status |  |  | checkpoint | External Fins
checkpoint-status |  |  | checkpoint | Backing Rod & Airseals
checkpoint-group |  |  | section | Final Checks
checkpoint-status |  |  | checkpoint | Installation Rubbish Cleared / Trade Clean Joinery
checkpoint-status |  |  | checkpoint | Frame Installed Correctly
checkpoint-status |  |  | checkpoint | Window Functionally Correctly
checkpoint-status |  |  | checkpoint | Doors Operationing Correctly
checkpoint-status |  |  | checkpoint | Installer Confirms Installation Complete
checkpoint-group |  |  | section | Final Inspection & Handover
checkpoint-status |  |  | checkpoint | Handover Notes/Photos
checkpoint-no-status |  |  | checkpoint | Installation Project Manager Signoff
holdpoint |  |  | signoff | Add Signoff / Request Signature
checkpoint-no-status |  |  | checkpoint | Manufacturer Signoff
holdpoint |  |  | signoff | Add Signoff / Request Signature
checkpoint-no-status |  |  | checkpoint | Client Signoff
holdpoint |  |  | signoff | Add Signoff / Request Signature
checklist-sectioned |  |  | checklist | Seismic Install |  |  |  |  | Yes | Seismic Install | 9c74ce07-f344-440f-ab74-43fc4081eb51
checkpoint-group |  |  | section | Client Opening Handover
checkpoint-no-status |  |  | checkpoint | Date
date | 31300998-dba8-58ed-8475-130ad52b6df9 |  | date | QA Handover Received
checkpoint-group |  |  | section | Pre-Start Checks
checkpoint-status |  |  | checkpoint | Area Clear / Tidy
checkpoint-status |  |  | checkpoint | Opening Correct
checkpoint-status |  |  | checkpoint | Waterproofing / Flashing Tape Installed
checkpoint-group |  |  | section | Installation Checks
checkpoint-status |  |  | checkpoint | External Sill Flashings Installed
checkpoint-status |  |  | checkpoint | Subframe Assembled and Corners Oversealed
checkpoint-status |  |  | checkpoint | Subframe Installed as per SD's - RL/GL
checkpoint-status |  |  | checkpoint | Correct Packing - Sill/Jambs/Head
checkpoint-status |  |  | checkpoint | Subframe Critical Seals Complete
checkpoint-status |  |  | checkpoint | Module/s Installed & Rubbered Off
checkpoint-status |  |  | checkpoint | Fixings as per SD's / Overseals Complete
checkpoint-status |  |  | checkpoint | Locator Screws Completed
checkpoint-status |  |  | checkpoint | PEF Backing Rod Installed - Continous
checkpoint-status |  |  | checkpoint | Airseals Complete - 6mm & 18mm Wide, 2:1 Ratio
checkpoint-status |  |  | checkpoint | Head Flashings Installed
checkpoint-status |  |  | checkpoint | Sliding Panel Adjustment (If Applicable)
checkpoint-group |  |  | section | Final Checks
checkpoint-status |  |  | checkpoint | Installation Rubbish Cleared / Trade Clean Joinery
checkpoint-status |  |  | checkpoint | Frame Installed Correctly
checkpoint-status |  |  | checkpoint | Window Functioning Correctly
checkpoint-status |  |  | checkpoint | Doors Operating Correctly
checkpoint-status |  |  | checkpoint | Installer Confirms Installation Complete
checkpoint-group |  |  | section | Final Inspection & Handover
checkpoint-status |  |  | checkpoint | Handover Notes/Photos
checkpoint-status |  |  | checkpoint | Installation Project Manager Signoff
holdpoint |  |  | signoff | Add Signoff / Request Signature
checkpoint-status |  |  | checkpoint | Manufacturer Signoff
holdpoint |  |  | signoff | Add Signoff / Request Signature
checkpoint-status |  |  | checkpoint | Client Signoff
holdpoint |  |  | signoff | Add Signoff / Request Signature
checklist-flat |  |  | checklist | Prestart - Date: |  |  |  |  | Yes | Prestart - Date: | b9224d04-2d94-4378-bd93-ccaa08a27b76
checkpoint-status |  |  | checkpoint | Person/s in charge of site operations
checkpoint-status |  |  | checkpoint | Weather conditions
select | 91f915d3-8d2f-5f48-9732-f700c9f93576 |  | dropdown | Conditions | Sunny, Overcast, Cloudy, Rainy
checkpoint-status |  |  | checkpoint | Wind Conditions
select | 1519378c-e087-53c9-80c2-32efe15da9ca |  | dropdown | Conditions | Strong, Medium, Low, None
checkpoint-status |  |  | checkpoint | Meeting minutes
checkpoint-status |  |  | checkpoint | Safety minutes
checkpoint-status |  |  | checkpoint | Main contractor supplied minutes
checkpoint-status |  |  | checkpoint | Signatures of all attendees
holdpoint |  |  | signoff | Send signoff to all attendees
checklist-sectioned |  |  | checklist | Replacement Glazing |  |  |  |  | Yes | Replacement Glazing | cfd5207f-9e14-443f-be28-17b0d6428cfd
checkpoint-group |  |  | section | Pre-Start Checks
checkpoint-status |  |  | checkpoint | Photos of damaged item
checkpoint-status |  |  | checkpoint | Opening Preparation
checkpoint-status |  |  | checkpoint | Panel Reglazed Including Date
checkpoint-status |  |  | checkpoint | Replacement Glass Installation
checkpoint-status |  |  | checkpoint | Application Of Structural Sealant
checkpoint-status |  |  | checkpoint | Application Of Weather Sealant (External)
checkpoint-status |  |  | checkpoint | Application Of Weather Sealant (Internal)
checkpoint-group |  |  | section | Testing
checkpoint-status |  |  | checkpoint | Quality Assurance Testing
checkpoint-status |  |  | checkpoint | Structural Bite
checkpoint-status |  |  | checkpoint | Adhesion Pull Test
checkpoint-group |  |  | section | Final Checks
checkpoint-status |  |  | checkpoint | Installation Rubbish Cleared / Trade Clean Joinery
checkpoint-status |  |  | checkpoint | Protective Tapes / Plates
checkpoint-status |  |  | checkpoint | Any Panel Damage Noted
checkpoint-group |  |  | section | Final Inspection & Handover
checkpoint-status |  |  | checkpoint | Handover Notes/Photos
checkpoint-no-status |  |  | checkpoint | Installation Project Manager Signoff
holdpoint |  |  | signoff | Add Signoff / Request Signature
checkpoint-no-status |  |  | checkpoint | Manufacturer Signoff
holdpoint |  |  | signoff | Add Signoff / Request Signature
checkpoint-no-status |  |  | checkpoint | Client Signoff
holdpoint |  |  | signoff | Add Signoff / Request Signature
checklist-sectioned |  |  | checklist | Replacement Install |  |  |  |  | Yes | Replacement Install | d9ed0e28-dd3f-441b-9b5d-6c3e0bf037b0
checkpoint-group |  |  | section | Pre-Start Checks
checkpoint-status |  |  | checkpoint | Before Photos
checkpoint-status |  |  | checkpoint | Area Clear And Ready For Install
checkpoint-status |  |  | checkpoint | Replacement Joinery Made Correct (Size/Orientation)
checkpoint-group |  |  | section | Installation Checks
checkpoint-status |  |  | checkpoint | Opening Before Waterproofing Tape Applied
checkpoint-status |  |  | checkpoint | Opening Prepped / Waterproofing Tape Applied
checkpoint-status |  |  | checkpoint | Sill Pan / Support Bar Installed Correctly
checkpoint-status |  |  | checkpoint | Sill Pan End Dam Seals
checkpoint-status |  |  | checkpoint | Frame Installed Correctly / Correct Packing / Fixed Off
checkpoint-status |  |  | checkpoint | Expanda Foam / Sealant Applied
checkpoint-status |  |  | checkpoint | Head & External Flashings Installed
checkpoint-status |  |  | checkpoint | Sliding Panel Adjustments (If Applicable)
checkpoint-group |  |  | section | Glazing Checks
checkpoint-status |  |  | checkpoint | Correct Setting Blocks Installed
checkpoint-status |  |  | checkpoint | Glass Installed - Correct Orientation
checkpoint-status |  |  | checkpoint | Glazing Beads & Wedge - Complete
checkpoint-group |  |  | section | Final Checks
checkpoint-status |  |  | checkpoint | Internal Area Cleaned & Vaccumed
checkpoint-status |  |  | checkpoint | External Area Cleaned & Vaccumed
checkpoint-status |  |  | checkpoint | Joinery & Glass Cleaned
checkpoint-status |  |  | checkpoint | Frame Installed Correctly
checkpoint-status |  |  | checkpoint | Window Functionally Correctly
checkpoint-status |  |  | checkpoint | Door Operationing Correctly
checkpoint-status |  |  | checkpoint | After Photos
checkpoint-status |  |  | checkpoint | Installer Confirms Installation Complete
checkpoint-group |  |  | section | Manufacturer Notes
checkpoint-no-status |  |  | checkpoint | Manufacturing Notes
checkpoint-no-status |  |  | checkpoint | Hardware Notes
checkpoint-no-status |  |  | checkpoint | Glass Notes
checkpoint-no-status |  |  | checkpoint | Other Notes
checkpoint-group |  |  | section | Installation Signoff
checkpoint-no-status |  |  | checkpoint | Installer Signoff
holdpoint |  |  | signoff | Add Signoff / Request Signature
checkpoint-no-status |  |  | checkpoint | Project Manager Signoff
holdpoint |  |  | signoff | Add Signoff / Request Signature
checkpoint-no-status |  |  | checkpoint | Client Signoff
holdpoint |  |  | signoff | Add Signoff / Request Signature
checklist-sectioned |  |  | checklist | Standard Install |  |  |  |  | Yes | Standard Install | dddaf194-fc95-4b55-8ba0-5e491b82babb
checkpoint-group |  |  | section | Client Opening Handover
checkpoint-no-status |  |  | checkpoint | Date
date | cacf326e-a72f-5f9b-b8b7-d39fd6207d16 |  | date | QA Handover Received
checkpoint-status |  |  | checkpoint | Pre-Start Checks
checkpoint-status |  |  | checkpoint | Area Clear For Install
checkpoint-status |  |  | checkpoint | Opening Correct
checkpoint-status |  |  | checkpoint | Waterproofing / Flashing Tape Installed
checkpoint-group |  |  | section | Installation Checks
checkpoint-status |  |  | checkpoint | Sill Flashing / Sill Pan / Support Bar Installed Correctly
checkpoint-status |  |  | checkpoint | Correct Packing
checkpoint-status |  |  | checkpoint | Frame Installed As Per SD's - RL / GL
checkpoint-status |  |  | checkpoint | Fixings as per SD's / Overseal Complete
checkpoint-status |  |  | checkpoint | Cavity Prepped / Cleaned for Airseals (Primer/Cleaner)
checkpoint-status |  |  | checkpoint | PEF Backing Rod Installed
checkpoint-status |  |  | checkpoint | Airseals Complete - 6mm min, 18mm max, 2:1 Ratio
checkpoint-status |  |  | checkpoint | Head & External Flashings Installed
checkpoint-status |  |  | checkpoint | Sliding Panel Adjustment (If Applicable)
checkpoint-group |  |  | section | Installation Checks
checkpoint-status |  |  | checkpoint | Installation Rubbish Cleared / Trade Clean Joinery
checkpoint-status |  |  | checkpoint | Frame Installed Correctly
checkpoint-status |  |  | checkpoint | Window Functioning Correctly
checkpoint-status |  |  | checkpoint | Doors Operating Correctly
checkpoint-status |  |  | checkpoint | Installer (L/H) Confirms Installation Complete
checkpoint-group |  |  | section | Final Inspection & Handover
checkpoint-status |  |  | checkpoint | Handover Notes/Photos
checkpoint-status |  |  | checkpoint | Installation Project Manager Signoff
checkpoint-status |  |  | checkpoint | Manufacturer Signoff & Client Signoff
checklist-sectioned |  |  | checklist | Standard Install - WO Liners |  |  |  |  | Yes | Standard Install - WO Liners | e9358f53-c99c-47b0-b5e8-26b374362d7f
checkpoint-group |  |  | section | Client Opening Handover
checkpoint-status |  |  | checkpoint | QA Handover Received
checkpoint-status |  |  | checkpoint | Pre-Start Checks
checkpoint-status |  |  | checkpoint | Area Clear For Install
checkpoint-status |  |  | checkpoint | Opening Correct
checkpoint-status |  |  | checkpoint | Waterproofing / Flashing Tape Installed
checkpoint-group |  |  | section | Installation Checks
checkpoint-status |  |  | checkpoint | Sill Pan / Support Bar Installed Correctly
checkpoint-status |  |  | checkpoint | Correct Packing
checkpoint-status |  |  | checkpoint | Frame Installed As Per SD's - RL / GL
checkpoint-status |  |  | checkpoint | Fixings as per SD's / Overseal Complete
checkpoint-status |  |  | checkpoint | Cavity Prepped / Cleaned for Airseals (Primer/Cleaner)
checkpoint-status |  |  | checkpoint | PEF Backing Rod Installed
checkpoint-status |  |  | checkpoint | Airseals Complete - 6mm min, 18mm max, 2:1 Ratio
checkpoint-status |  |  | checkpoint | Head & External Flashings Installed
checkpoint-status |  |  | checkpoint | Sliding Panel Adjustment (If Applicable)
checkpoint-group |  |  | section | Glazing Checks
checkpoint-status |  |  | checkpoint | Correct Setting Blocks Installed
checkpoint-status |  |  | checkpoint | Glass Installed - Correct Orientation
checkpoint-status |  |  | checkpoint | Glazing Beads & Wedge - Complete
checkpoint-status |  |  | checkpoint | Sliding Panel Readjustment (If Applicable)
checkpoint-group |  |  | section | Installation Checks
checkpoint-status |  |  | checkpoint | Installation Rubbish Cleared / Trade Clean Joinery
checkpoint-status |  |  | checkpoint | Frame Installed Correctly
checkpoint-status |  |  | checkpoint | Window Functionally Correctly
checkpoint-status |  |  | checkpoint | Doors Operationing Correctly
checkpoint-status |  |  | checkpoint | Installer (L/H) Confirms Installation Complete
checkpoint-group |  |  | section | Final Inspection & Handover
checkpoint-status |  |  | checkpoint | Handover Notes/Photos
checkpoint-status |  |  | checkpoint | Installation Project Manager Signoff
checkpoint-status |  |  | checkpoint | Manufacturer Signoff & Client Signoff
checklist-sectioned |  |  | checklist | Accident & Incident Investigation Report |  |  |  |  | Yes | Accident & Incident Investigation Report | ed4bce36-ec40-4691-9edb-339472c2f300
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Details Completed
text | 15f94413-ec55-5ef0-ac67-4998f24be165 |  | textbox | Name of Investigator:
checkpoint-group |  |  | section | Particulars of Incident
checkpoint-status |  |  | checkpoint | Particulars of Incident Details Completed
select | f90a42cd-e28c-5bfa-97b1-6892c5415499 |  | dropdown | Day of Incident: | Monday,Tuesday,Wednesday,Thursday,Friday,Saturday,Sunday
text | 31710282-8c65-5913-ab13-a36be139ec92 |  | textbox | Time:
text | a5d12b0f-afbe-5edd-b676-e35e7186d68b |  | textbox | Project/Site:
date | b0ad0161-53a2-5847-a470-deb38baa4ea8 |  | date | Date Reported:
checkpoint-group |  |  | section | Injured Person Details
checkpoint-status |  |  | checkpoint | Injured Person Details Completed
text | d32b48d9-673b-59c4-9999-5b484bef212a |  | textbox | Name:
text | 2d4e7bcf-a8ac-574d-8742-379bf9236038 |  | textbox | Age:
text | 7c8cc198-829d-5eb8-948d-4c37725406f7 |  | textbox | Phone Number:
text | 6539f7dd-062f-56bf-8bdd-61374eeb713d |  | textbox | Address:
text | d7c2359a-1ca0-522d-b028-20781e9f116d |  | textbox | Reported date of incident:
text | 0015d520-dcdd-53a6-a643-58060b3b2028 |  | textbox | Length of employment:
text | 1f9dc550-fc8e-5e80-9074-2cfbece9d892 |  | textbox | Time on job:
checkpoint-status |  |  | checkpoint | Type Of Injury:
boolean | a749c653-e210-5331-886e-52158d5ac2c9 |  | tickbox | Strain/sprain
boolean | 10db75dc-898b-5c4e-b0c1-29ab6485ca5a |  | tickbox | Fracture
boolean | 54b8cd28-f49a-5831-a526-cfbb6b346028 |  | tickbox | Laceration/cut
boolean | a69d5189-a658-51f5-8a45-3ca4b560a3b0 |  | tickbox | Bruising
boolean | 79f97ee0-2ced-5f07-9429-aeb78aacfb2b |  | tickbox | Scratch/abrasion
boolean | d10fa848-7141-5926-adc5-b928df074406 |  | tickbox | Amputation
boolean | dc0887f1-570d-578b-8779-d2fbd1c2d8fa |  | tickbox | Burn scald
boolean | 7af61271-d5c3-57e0-9933-28a3f71d2d52 |  | tickbox | Dislocation
boolean | 35ee273a-e884-55f8-8da4-924bec931aa5 |  | tickbox | Internal
boolean | 4d232846-ea50-5a9d-af35-dea80adcc48f |  | tickbox | Foreign body
boolean | 0646fa6f-8579-56b7-a951-db65d265cbd8 |  | tickbox | Chemical reaction
boolean | 345ac57f-e30f-5654-8d2b-3694cff1efc1 |  | tickbox | Other
text | 6649a86a-8f7b-5320-b235-8ee4d4a82086 |  | textbox | If other please specify:
text | 260549a2-4294-5840-b1bd-42678c71714e |  | textbox | Injured Part of Body:
checkpoint-group |  |  | section | Damaged Property
checkpoint-status |  |  | checkpoint | Damaged Property Details Completed
text | e3e20ff6-6bdd-5a43-a6cd-a3d838088b7c |  | textbox | Property/material damaged:
text | bd09d359-6562-5052-8f65-b4ad94418675 |  | textbox | Nature of damage:
text | 79a7584d-4aba-51e1-9e9d-b60024fa600a |  | textbox | Object/substance inflicting damage:
checkpoint-group |  |  | section | Incident
checkpoint-status |  |  | checkpoint | Incident Details Complete
text | 1e32cb15-5f58-5204-a193-9586fcd3777c |  | textbox | Describe what happened (space overleaf for diagram – essential for all vehicle incidents):
checkpoint-group |  |  | section | Analysis
checkpoint-status |  |  | checkpoint | Analysis Details Completed
text | 0eb199ba-07c6-577d-8506-d2add0549bc4 |  | textbox | What were the causes (root and contributing causes) of the incident?
text | bffcc3a7-ee51-5b3f-a77a-04d5db7db8ec |  | textbox | Root causes – safety system failures:
text | 21b0d65c-06e1-57d0-90b7-b6590c7826a0 |  | textbox | Contributing causes – unsafe acts and conditions:
checkpoint-group |  |  | section | Prevention
checkpoint-status |  |  | checkpoint | Prevention Details Completed
text | 4d54f3d1-967b-5ed9-bb1e-597d66e6b038 |  | textbox | What action has or will be taken to prevent a recurrence? Tick items already actioned
boolean | df87164e-2b94-5205-b1b4-2b241a1b1130 |  | tickbox | Completed
text | ecf7ae8e-8615-5622-9171-8da6faaf26fc |  | textbox | By Whom:
text | 382852d2-1966-5fa8-808f-bc02c1304677 |  | textbox | When:
checkpoint-group |  |  | section | Treatment and Investigation of Incident
checkpoint-status |  |  | checkpoint | Treatment and Investigation of Incident Details Completed
text | ab598a20-b4f7-518f-8b0f-38b0aa37a9f7 |  | textbox | Treatment and Investigation of Incident :
text | 86b6e957-fbb2-5ac3-9275-4db95a46e03f |  | textbox | Name of person giving First Aid:
text | d2a87253-7d15-57f6-8dee-66fa00a2aaa9 |  | textbox | Doctor/Hospital:
text | a2a1da22-3b6c-5006-abbf-dccc37fc2860 |  | textbox | Incident investigated by:
date | edc64384-5500-5638-823e-e7c4920a842b |  | date | Date:
select | 8bf80dd1-39eb-528a-93c3-82a65c4a51b4 |  | dropdown | Worksafe NZ advised | Yes,No
date | f5e29e08-9eb2-5164-b966-f6926805757a |  | date | Date:
checkpoint-group |  |  | section | Signoff
checkpoint-status |  |  | checkpoint | Required people sent signoff request
holdpoint |  |  | signoff | Signoff
checklist-sectioned |  |  | checklist | Toolbox Meeting - |  |  |  |  | Yes | Toolbox Meeting - | ef074007-f4f9-475e-9626-ab836c70362c
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Details Complete (pass once all relevant details are inputted below)
text | e0e89e72-3dc3-5fab-8e97-dc9632279d26 |  | textbox | Office location:
label | 1360d50c-cbe6-5708-95e7-22c5d864ed91 |  | note | Who is running this meeting
text | 4dc736d5-9342-5f06-9af8-bf2aabb98d08 |  | textbox | Name:
text | d9315596-5afb-50ff-a5fd-59e9c7ec5b98 |  | textbox | Company:
text | 3f3713cd-5c65-57ad-80c9-808f31146f47 |  | textbox | Agenda items:
text | 4291f081-2169-59e9-9ba0-1f7cb131c043 |  | textbox | Theme of the week (topic for focus):
checkpoint-group |  |  | section | Health and safety issues
checkpoint-status |  |  | checkpoint | Relevant Issues recorded with appropriate actions and date
text | d829dddf-fe51-55bd-9824-7c9abfaa2343 |  | textbox | Issue raised from site safety inspection:
text | 6fccfd6d-c408-5844-8dd5-0cbb1dfa599f |  | textbox | Actions:
text | 4c231a6b-0d2c-5892-b2a0-9e6671f354a2 |  | textbox | By who and when:
checkpoint-status |  |  | checkpoint | Issues outstanding from previous briefings recorded with appropriate actions and date
text | cb82dd5c-6158-55cc-badd-a9fc3b69b1cc |  | textbox | Issues outstanding from previous briefings:
text | 3192db1d-1a44-5dfa-aad5-ffeb4a3a1d12 |  | textbox | Actions:
text | fdef4880-8432-54c3-b48f-99a6ab63e02f |  | textbox | By who and when:
checkpoint-status |  |  | checkpoint | 3. Employee-raised issues recorded with appropriate actions and date
text | 05c6fcb0-590e-5e00-a7c7-6ccd211263b1 |  | textbox | Employee-raised issues:
text | 1d623f5e-3801-5e45-bef3-296ed76df1ba |  | textbox | Actions:
text | cba5367f-b397-5230-bf33-94e8bbc91fa7 |  | textbox | By who and when:
checkpoint-status |  |  | checkpoint | 4. Positive safe-action observations recorded with appropriate actions and date
text | 400a8461-97bd-5a4a-8724-a35c9a883265 |  | textbox | Positive safe-action observations:
text | ae8560f0-f29b-5871-bee5-dadeab65bcd3 |  | textbox | Actions:
text | 45b674a3-a94c-5975-9ab6-13b2408646e0 |  | textbox | By who and when:
checkpoint-status |  |  | checkpoint | 5. Incidents or injuries recorded with appropriate actions and date
text | d9814afa-debd-5850-ba72-6e4958c6258b |  | textbox | Incidents or injuries:
text | 48795fcf-6859-5177-9d0a-2e0b97865e38 |  | textbox | Actions:
text | 8a9d1c9d-e813-5ea4-98a8-47c85ff5be32 |  | textbox | By who and when:
checkpoint-group |  |  | section | Job plans reviewed
checkpoint-status |  |  | checkpoint | Job/Task plan(s) reviewed & Action(s) recorded below
text | d3551bc7-3eaf-5489-9c1d-2272064bd445 |  | textbox | 1
text | 429e8955-de2a-5404-918f-ecdb68380f49 |  | textbox | 2
text | b3fc99e1-3ead-5a5a-aa87-a0b0bd248bd1 |  | textbox | 3
text | 5a0a38c1-b29c-5350-bb75-ef12223a84f2 |  | textbox | 4
text | bce29ab8-0476-52dd-810c-4e0c033fa89d |  | textbox | 5
text | 7e02f2ee-2b62-5f0f-b628-4b823087c99d |  | textbox | 6
checkpoint-group |  |  | section | Operational issues
checkpoint-status |  |  | checkpoint | Operational Item(s) & Action(s) recorded below
text | e234aa49-f4f9-5f1b-9059-d36daf74e47d |  | textbox | 1
text | a3604d01-5feb-52e1-b09e-fb62774b303b |  | textbox | 2
text | 2e899692-e123-5fe3-a24c-93c0faf99902 |  | textbox | 3
text | 93291ce5-ac6b-58a3-ac90-2bbc2aa4a200 |  | textbox | 4
text | 4de9c6b3-6357-5db4-9ba2-c14803653ded |  | textbox | 5
text | 5e08c959-2f12-58ba-9fa2-4faa7ad0a930 |  | textbox | 6
checkpoint-group |  |  | section | Other business
checkpoint-status |  |  | checkpoint | Other Business Item(s) & Action(s) recorded below
text | ba2e7629-2c8e-59f7-8a21-6758e3c61ff7 |  | textbox | 1
text | 0ead4f6c-a28e-56ce-8f77-7f712c833b30 |  | textbox | 2
text | f033a72b-31f5-596d-b261-4869198487ec |  | textbox | 3
text | d693b61e-2aed-5f7c-8434-4d792662a39a |  | textbox | 4
checkpoint-group |  |  | section | Attendees
checkpoint-status |  |  | checkpoint | Add name and Photo of attendees (pass once all attendees are recorded)
holdpoint |  |  | signoff | Send signoff request to all attendees
checkpoint-group |  |  | section | Review by management
checkpoint-status |  |  | checkpoint | Send to management to review?
holdpoint |  |  | signoff | Reviewed and signed off by management
checklist-sectioned |  |  | checklist | Standard Install W Liners |  |  |  |  | Yes | Standard Install W Liners | f6891922-78e9-4830-962e-3d6715cfbb21
checkpoint-group |  |  | section | Client Opening Handover
checkpoint-status |  |  | checkpoint | QA Handover Received
checkpoint-group |  |  | section | Pre-Start Checks
checkpoint-status |  |  | checkpoint | Area Clear For Install
checkpoint-status |  |  | checkpoint | Opening Correct
checkpoint-status |  |  | checkpoint | Waterproofing / Flashing Tape Installed
checkpoint-group |  |  | section | Installation Checks
checkpoint-status |  |  | checkpoint | Sill Pan / Support Bar Installed Correctly
checkpoint-status |  |  | checkpoint | Correct Packing
checkpoint-status |  |  | checkpoint | Frame Installed As Per SD's - RL / GL
checkpoint-status |  |  | checkpoint | Timber Framing In & Out Correct
checkpoint-status |  |  | checkpoint | Fixings as per SD's / Overseal Complete
checkpoint-status |  |  | checkpoint | Cavity Prepped / Cleaned for Airseals (Primer/Cleaner)
checkpoint-status |  |  | checkpoint | PEF Backing Rod Installed
checkpoint-status |  |  | checkpoint | Airseals Complete - 6mm min, 18mm max, 2:1 Ratio
checkpoint-status |  |  | checkpoint | Head & External Flashings Installed
checkpoint-status |  |  | checkpoint | Sliding Panel Adjustment (If Applicable)
checkpoint-group |  |  | section | Glazing Checks
checkpoint-status |  |  | checkpoint | Correct Setting Blocks Installed
checkpoint-status |  |  | checkpoint | Glass Installed - Correct Orientation
checkpoint-status |  |  | checkpoint | Glazing Beads & Wedge - Complete
checkpoint-status |  |  | checkpoint | Sliding Panel Readjustment (If Applicable)
checkpoint-group |  |  | section | Installation Checks
checkpoint-status |  |  | checkpoint | Installation Rubbish Cleared / Trade Clean Joinery
checkpoint-status |  |  | checkpoint | Frame Installed Correctly
checkpoint-status |  |  | checkpoint | Window Functionally Correctly
checkpoint-status |  |  | checkpoint | Doors Operationing Correctly
checkpoint-status |  |  | checkpoint | Installer (L/H) Confirms Installation Complete
checkpoint-group |  |  | section | Final Inspection & Handover
checkpoint-status |  |  | checkpoint | Handover Notes/Photos
checkpoint-status |  |  | checkpoint | Installation Project Manager Signoff
holdpoint |  |  | signoff | Manufacturer Signoff & Client Sign Off