## CLYDE NORTH PS - NEW ITPS
type | name | values
checklist | CLYDE NORTH PS - ITP - Main Civil Works Drainage
checkpoint | 5.01 Check Set out/ Conformity with Drawings
note | STAGE / FREQUENCY: Prior to commencement
note | RECORDS: N/a
note | SPECIFICATION / STANDARD: Latest drawing available
note | ACCEPTANCE CRITERIA:
note | – Datum point is marked in accessible area by Surveyor
note | – acceptable tolerances as per 701.05
note | INSPECTION / TEST PROC: N/a
note | INSPECTOR / APPROVER: Contractor Authorised Representative, Subcontractor Authorised Representative, Engineer, Foreman
note | HOLD OR WITNESS POINT: Witness
checkpoint | 5.02 Pipe work Materials
note | STAGE / FREQUENCY: Prior to commencement
note | RECORDS: Delivery Dockets
note | SPECIFICATION / STANDARD: N/a
note | ACCEPTANCE CRITERIA: Ensure pipe work is ready and client delivers pipe work to work zone
note | INSPECTION / TEST PROC: N/a
note | INSPECTOR / APPROVER: Contractor Authorised Representative, Subcontractor Authorised Representative, Engineer, Foreman
note | HOLD OR WITNESS POINT: Witness
checkpoint | 5.03 Excavation
note | STAGE / FREQUENCY: Prior & during construction
note | RECORDS: Visual & photo evidence
note
note | ACCEPTANCE CRITERIA:
note | – As per minimum horizontal clearances in table 701.101
note | INSPECTION / TEST PROC: Visual
note | INSPECTOR / APPROVER: Contractor Authorised Representative, Subcontractor Authorised Representative, Engineer, Foreman
note | HOLD OR WITNESS POINT: Witness
checkpoint | 5.04 Pipe Bedding
note | STAGE / FREQUENCY: Pit to Pit
note | RECORDS: Visual & photo evidence
note | SPECIFICATION / STANDARD: AS3500
note | ACCEPTANCE CRITERIA:
note | – Minimum bedding as per 701.11
note | – no less than 100mm bedding via vibration plate
note | INSPECTION / TEST PROC: Visual
note | INSPECTOR / APPROVER: Contractor Authorised Representative, Subcontractor Authorised Representative, Engineer, Foreman
note | HOLD OR WITNESS POINT: Witness
checkpoint | 5.05 Laying
note | STAGE / FREQUENCY: During construction
note | RECORDS: Visual & photo evidence
note | SPECIFICATION / STANDARD: AS3500
note | ACCEPTANCE CRITERIA:
note | – Rebate and socket ends of pipe sections shall be placed facing upstream and be fully entered as per Vic Roads Sec701.12(b)
note | INSPECTION / TEST PROC: Visual
note | INSPECTOR / APPROVER: Contractor Authorised Representative, Subcontractor Authorised Representative, Engineer, Foreman
note | HOLD OR WITNESS POINT: Witness
checkpoint | 5.06 Backfill of material
note | STAGE / FREQUENCY: Pit to Pit
note | RECORDS:
note | – Visual & photo evidence
note | – Select backfill to be used
note | SPECIFICATION / STANDARD: Bedding and backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness.
note | ACCEPTANCE CRITERIA:
note | – Acceptance will be via compaction test ITP ref 5.07
note | – Cover 300mm above pipe
note | – Backfill to be in 150mm loose layers.
note | INSPECTION / TEST PROC: Visual
note | INSPECTOR / APPROVER: Contractor Authorised Representative, Subcontractor Authorised Representative, Engineer, Foreman
note | HOLD OR WITNESS POINT: Witness
checkpoint | 5.07 Compaction testing of backfill material
note | STAGE / FREQUENCY: In reference to Vic Roads Acceptance of Field Compaction & Vic Roads 701 we are defining a “lot” at 50 lin mtrs, and 3 test per 50l/mtrs
note | RECORDS: Test report by Geotech advisor
note | SPECIFICATION / STANDARD: Vic Roads Acceptance of Field compaction RC500.05 June 2017 Code of practice 2.2 Selection of lot.
note | ACCEPTANCE CRITERIA:
note | – Terra Firma test pass based on 95% STD
note | INSPECTION / TEST PROC: Terra Firma test results
note | INSPECTOR / APPROVER: Contractor Authorised Representative, Subcontractor Authorised Representative, Engineer, Foreman
note | HOLD OR WITNESS POINT: Witness
checkpoint | 5.08 Pipe bandages around external connection of pit to pit, and internal final patch of pipe to pit
note | STAGE / FREQUENCY: Each pit
note | RECORDS: Photos of external and internal pit walls
note | SPECIFICATION / STANDARD: Relevant authority construction details
note | ACCEPTANCE CRITERIA: Visual Inspection – Photos
note | INSPECTION / TEST PROC: Photos
note | INSPECTOR / APPROVER: Contractor Authorised Representative, Subcontractor Authorised Representative, Engineer, Foreman
note | HOLD OR WITNESS POINT: Witness
checkpoint | 5.09 CCTV
note | STAGE / FREQUENCY: All drainage lines constructed shall be inspected, via CCTV for internal review of pipe
note | RECORDS: CCTV video to be submitted
note | SPECIFICATION / STANDARD: Vic Roads 701.24 Inspection of drainage lines beneath pavements
note | ACCEPTANCE CRITERIA:
note | – Sign off after vision is viewed.
note | INSPECTION / TEST PROC: CCTV vision
note | INSPECTOR / APPROVER: Contractor Authorised Representative, Subcontractor Authorised Representative, Engineer, Foreman
note | HOLD OR WITNESS POINT: Witness
checkpoint | 5.10 Final As-Built
note | STAGE / FREQUENCY: As required to get accurate as built information, typically pit to pit post installation.
note | RECORDS: As Built
note | SPECIFICATION / STANDARD: N/a
note | ACCEPTANCE CRITERIA:
note | – Show line, grade and position of pipework and pits.
note | INSPECTION / TEST PROC:
note | – As Built Provided by GPL
note | INSPECTOR / APPROVER: Contractor Authorised Representative, Subcontractor Authorised Representative, Engineer, Foreman
note | HOLD OR WITNESS POINT: Witness
checklist | CLYDE NORTH PS - ITP - Main Civil Works Poured Pits
checkpoint | 5.01 - Check Set out/Conformity with Drawings
note | Stage/Frequency - Prior to commencement
note | Records - N/a
note | Specification/Standard - Latest drawing available
note | Acceptance Criteria - Datum point is marked in accessible area by Surveyor.
note | - Acceptable tolerances as per 701.05
note | Inspection/Test Procedure - N/a
note | Hold or Witness Point - Witness
checkpoint | 5.02 - Excavation
note | Stage/Frequency - Prior & during construction
note | Records - Visual & photo evidence
note | Specification/Standard - Vic Roads Sec705.05
note | Acceptance Criteria - As per minimum horizontal clearances in table 701.101
note | Inspection/Test Procedure - Visual
note | Hold or Witness Point - Witness
checkpoint | 5.03 - Design
note | Stage/Frequency - Each pit
note | Records - Visual & photo evidence
note | Specification/Standard - The council drawing referenced in the Pit Schedule
note | Acceptance Criteria - Installed as per the referenced detail drawing
note | Inspection/Test Procedure - Visual
note | Hold or Witness Point - Witness
checkpoint | 5.04 - Materials - mesh
note | Stage/Frequency - Each pit
note | Records - Visual & photo evidence
note | Specification/Standard - As per city council drawing
note | Acceptance Criteria - SL82 centrally placed mesh
note | Inspection/Test Procedure - Visual
note | Hold or Witness Point - Witness
checkpoint | 5.05 - Materials - concrete
note | Stage/Frequency - During construction
note | Records - Visual & photo evidence
note | Specification/Standard - Vic Roads table705.041
note | Acceptance Criteria - 32 mPa minimum concrete grade used for drainage pits reinforced with steel reinforcement
note | Inspection/Test Procedure - Visual
note | Hold or Witness Point - Witness
checkpoint | 5.06 - Materials - Prepare base with mesh
note | Stage/Frequency - Each pit
note | Records - Visual & photo evidence
note | Specification/Standard - As per city drawing
note | Acceptance Criteria - Mesh placed on chairs
note | - Installed as per the referenced detail drawing
note | Inspection/Test Procedure - Visual
note | Hold or Witness Point - Witness
checkpoint | 5.07 - Materials - Pour base with concrete
note | Stage/Frequency - Each pit
note | Records - Visual & photo evidence
note | Specification/Standard - As per city drawing
note | Acceptance Criteria - concrete used as specified in point 5.05
note | Inspection/Test Procedure - Photos
note | Hold or Witness Point - Witness
checkpoint | 5.08 - Prepare upstand walls with mesh and box out
note | Stage/Frequency - Each pit
note | Records - Visual & photo evidence
note | Specification/Standard - As per city drawing
note | Acceptance Criteria - SL82 centrally placed mesh
note | Inspection/Test Procedure - Photos
note | Hold or Witness Point - Witness
checkpoint | 5.09 - Pour upstand walls with concrete
note | Stage/Frequency - Each pit
note | Records - Visual & photo evidence
note | Specification/Standard - As per city drawing
note | Acceptance Criteria - concrete used as specified in point 5.05
note | Inspection/Test Procedure - Photos
note | Hold or Witness Point - Witness
checkpoint | 5.10 - Shaping of floor
note | Stage/Frequency - Each pit
note | Records - Visual & photo evidence
note | Specification/Standard - Vic Roads Sec 705.13 shaping of floor
note | Acceptance Criteria - Drainage pit floors shall be smoothly shaped from the inlets to the outlet for a height of one third of the diameter of the outlet pipe.
note | Inspection/Test Procedure - Photos
note | Hold or Witness Point - Witness
checkpoint | 5.11 - Step Irons
note | Stage/Frequency - Each pit greater than 1.0ms deep
note | Records - Visual & photo evidence
note | Specification/Standard - VicRoads Sec 705.12 Step Irons Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with AS 1657
note | Acceptance Criteria - Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with AS 1657
note | Inspection/Test Procedure - Photos
note | Hold or Witness Point - Witness
checkpoint | 5.12 - Fittings Covers
note | Stage/Frequency - Each pit
note | Records - Visual & photo evidence
note | Specification/Standard - Vic Roads Sec 705.17 fitting of covers
note | Acceptance Criteria - Installed as per the referenced detail drawing
note | Inspection/Test Procedure - Photos
note | Hold or Witness Point - Witness
checkpoint | 5.13 - Concrete Test
note | Stage/Frequency - Each pit
note | Records - Visual & photo evidence
note | Specification/Standard - Vic Roads Sec705.041
note | Acceptance Criteria - VR330/32 minimum concrete grade used for drainage pits reinforced with steel reinforcement
note | Inspection/Test Procedure - Test report
checkpoint | 5.14 - Final As-Built
note | Stage/Frequency - As required to get accurate as built information, typically pit to pit post installation.
note | Records - As Built
note | Specification/Standard - N/a
note | Acceptance Criteria - Show line, grade and position of pipework and pits.
note | Inspection/Test Procedure - As Built Provided by Delta
note | Hold or Witness Point - Witness
checklist | CLYDE NORTH PS - ITP - Main Civil Works Precast Pits
checkpoint | 5.01 - Check Set out/Conformity with Drawings
note | Stage/Frequency - Prior to commencement
note | Records - N/a
note | Specification/Standard - Latest drawing available
note | Acceptance Criteria - Datum point is marked in accessible area by Surveyor.
note | - Acceptable tolerances as per 701.05
note | Inspection/Test Procedure - N/a
note | Hold or Witness Point - Witness
signoff | Precast pit pre-approval has been completed
checkpoint | 5.02 - Excavation
note | Stage/Frequency - Prior & during construction
note | Records - Visual & photo evidence
note
note | Acceptance Criteria - As per minimum horizontal clearances in table 701.101
note | Inspection/Test Procedure - Visual
note | Hold or Witness Point - Witness
checkpoint | 5.03 - Design
note | Stage/Frequency - Each pit
note | Records - Visual & photo evidence
note | Specification/Standard - The drawing referenced in the Pit Schedule
note | Acceptance Criteria - Installed as per the referenced detail drawing
note | Inspection/Test Procedure - Visual
note | Hold or Witness Point - Witness
checkpoint | 5.10 - Shaping of floor
note | Stage/Frequency - Each pit
note | Records - Visual & photo evidence
note | Specification/Standard - Vic Roads Sec 705.13 shaping of floor
note | Acceptance Criteria - Drainage pit floors shall be smoothly shaped from the inlets to the outlet for a height of one third of the diameter of the outlet pipe.
note | Inspection/Test Procedure - Photos
note | Hold or Witness Point - Witness
checkpoint | 5.11 - Step Irons
note | Stage/Frequency - Each pit greater than 1.0ms deep
note | Records - Visual & photo evidence
note | Specification/Standard - Step Irons Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with AS 1657
note | Acceptance Criteria - Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with AS 1657
note | Inspection/Test Procedure - Photos
note | Hold or Witness Point - Witness
checkpoint | 5.12 - Fittings Covers
note | Stage/Frequency - Each pit
note | Records - Visual & photo evidence
note | Specification/Standard - Vic Roads Sec 705.17 fitting of covers
note | Acceptance Criteria - Installed as per the referenced detail drawing
note | Inspection/Test Procedure - Photos
note | Hold or Witness Point - Witness
checkpoint | 5.14 - Final As-Built
note | Stage/Frequency - As required to get accurate as built information, typically pit to pit post installation.
note | Records - As Built
note | Specification/Standard - N/a
note | Acceptance Criteria - Show line, grade and position of pipework and pits.
note | Inspection/Test Procedure - As Built Provided by GPL
note | Hold or Witness Point - Witness