## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Stopping |  |  |  |  | Yes | POST - S - Stopping | 0e537060-7aa2-40ab-82df-35af7cc7e140
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Complete fire stopping between layers of lining & apply compound(s) as specified
checkpoint-status |  |  | checkpoint | Openings/penetrations/corners & bulkheads, correctly formed
checkpoint-status |  |  | checkpoint | Square stopping, slimlines, joints checked & acceptable
checkpoint-status |  |  | checkpoint | Correct compound(s) used to align with consented specifications
checkpoint-status |  |  | checkpoint | Adequate drying time between coats, no visible bubbling/deforms & each coat is sanded as applicable
checkpoint-status |  |  | checkpoint | Light check completed to ensure no sheet joins stand out
checkpoint-status |  |  | checkpoint | Stopping work completed - specified level of finish achieved
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | CST - S - Completion Documents |  |  |  |  | Yes | CST - S - Completion Documents | 38da008d-a7d3-4c76-ba5e-9f14085ce8ce
checkpoint-status |  |  | checkpoint | All relevant Compliance Documentation completed and attached above
boolean | 3f5c3442-2d5f-5ec6-a585-8aa264578f5e |  | tickbox | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
label | 131d3366-2a5b-583a-ae90-8d31cd5d5d34 |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint |  |  | signoff | Request Signoff
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned |  |  | checklist | Internal Lining - Ceilings |  |  |  |  | Yes | POST - S - Internal Lining - Ceilings | 4250f1d9-66fd-489e-8261-8ef38913fde9
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | All preline services & passive fire (where required) completed, area accessible and substrate acceptable
checkpoint-status |  |  | checkpoint | Bracing, adhesive/sealant & lining layer(s) requirements achieved
checkpoint-status |  |  | checkpoint | Services/penetrations, correctly formed & located
checkpoint-status |  |  | checkpoint | Correct fixing pattern/sealant/adhesive/layers installed to align with consented design and specifications
checkpoint-status |  |  | checkpoint | Any bracing elements completed to design specification
checkpoint-status |  |  | checkpoint | All lining(s) completed correctly to specification & level of finish acceptable in respective area(s)
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned |  |  | checklist | Internal Lining - Walls |  |  |  |  | Yes | POST - S - Internal Lining - Walls | 6ffd29b1-10e0-429b-884a-c24536d516e2
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | All preline services & passive fire (where required) completed, area accessible and substrate acceptable
checkpoint-status |  |  | checkpoint | Bracing, adhesive/sealant & lining layer(s) requirements achieved
text | b10aa825-319e-585e-85fa-1b607d61e28d |  | textbox | Specific products used (photos Required)
checkpoint-status |  |  | checkpoint | Services/penetrations, correctly formed & located
checkpoint-status |  |  | checkpoint | Correct fixing pattern/sealant/adhesive/layers installed to align with consented design and specifications
checkpoint-status |  |  | checkpoint | Any bracing elements completed to design specification
checkpoint-status |  |  | checkpoint | All lining(s) completed correctly to specification & level of finish acceptable in respective area(s)
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | Painting |  |  |  |  | Yes | POST - S - Painting | 795aff5a-665a-4d08-982c-d347d4bf3d5c
checkpoint-status |  |  | checkpoint | Any prep work & sealer coat completed
checkpoint-status |  |  | checkpoint | Light inspection completed and approved to continue
checkpoint-status |  |  | checkpoint | Any additional prep work completed (stopping, filling, sanding etc)
checkpoint-status |  |  | checkpoint | First top coat completed
checkpoint-status |  |  | checkpoint | Additional top coat applications completed
checkpoint-status |  |  | checkpoint | Final coat completed as per specifications
checkpoint-status |  |  | checkpoint | Painting work completed - specified level of finish achieved
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS