## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Suspended Copper Works Checklist |  |  |  |  | Yes | Suspended Copper Works Checklist | 05ae9972-f4ce-4dea-bdcd-c688a10e23bb
checkpoint-status |  |  | checkpoint | Pipework installed - domestic hot/cold/rain water
checkpoint-status |  |  | checkpoint | Smoke seal penetrations
checkpoint-status |  |  | checkpoint | Tested
checkpoint-status |  |  | checkpoint | Fire rated if necessary
checklist-flat |  |  | checklist | Suspended Sewer Drainage Checklist |  |  |  |  | Yes | Suspended Sewer Drainage Checklist | 10bc58ef-947e-4db3-a15b-2a2928d388a8
checkpoint-status |  |  | checkpoint | Pipework, material and fittings installed as per approved IFC Drawing
checkpoint-status |  |  | checkpoint | Pipework installation
checkpoint-status |  |  | checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
checkpoint-status |  |  | checkpoint | Smoke seal penetrations
checkpoint-status |  |  | checkpoint | Fire collars installed if necessary
checkpoint-status |  |  | checkpoint | Test sewer
checklist-flat |  |  | checklist | In-Ground Pits/Pumps/Tanks Checklist |  |  |  |  | Yes | In-Ground Pits/Pumps/Tanks Checklist | 16b494eb-d7c2-4cd2-a39c-ea11b9f244f2
checkpoint-status |  |  | checkpoint | Sewer pump well
checkpoint-status |  |  | checkpoint | Storwater pump well
checkpoint-status |  |  | checkpoint | Stormwater pits
checkpoint-status |  |  | checkpoint | Grease interceptor trap
checkpoint-status |  |  | checkpoint | Conduits rain to IFC location
checkpoint-status |  |  | checkpoint | Torpedo tanks
checkpoint-status |  |  | checkpoint | Stormwater detention system
checklist-flat |  |  | checklist | Levels Suspended Drainage Checklist |  |  |  |  | Yes | Levels Suspended Drainage Checklist | 1c2da905-63ee-4136-ad14-06f946b31db8
checkpoint-status |  |  | checkpoint | Pipework, material and fittings installed as per approved IFC Drawing. Includes female/male/DDA bathroom, kitchen
checkpoint-status |  |  | checkpoint | Pipework installation
checkpoint-status |  |  | checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
checkpoint-status |  |  | checkpoint | Smoke seal penetrations
checkpoint-status |  |  | checkpoint | Fire collars installed if necessary
checklist-flat |  |  | checklist | Basement Pumps/Tanks/Booster Pump Checklist |  |  |  |  | Yes | Basement Pumps/Tanks/Booster Pump Checklist | 1e491314-6739-4b38-bf4f-eaf522eb4c69
checkpoint-status |  |  | checkpoint | Domestic cold water booster pump
checkpoint-status |  |  | checkpoint | Domestic cold water break tank
checkpoint-status |  |  | checkpoint | Rainwater pump set
checkpoint-status |  |  | checkpoint | Rainwater tanks
checkpoint-status |  |  | checkpoint | Sewer pump board installed
checkpoint-status |  |  | checkpoint | Stormwater pump board installed
checkpoint-status |  |  | checkpoint | Suspended Pollutant trap
checkpoint-status |  |  | checkpoint | Diversion valve
checkpoint-status |  |  | checkpoint | OSD tank (if applicable)
checkpoint-status |  |  | checkpoint | Smoke sealed
checkpoint-status |  |  | checkpoint | Tested
checkpoint-status |  |  | checkpoint | Fire rated if necessary
checkpoint-status |  |  | checkpoint | Water meter assembly
checklist-flat |  |  | checklist | Rough In Checklist |  |  |  |  | Yes | Rough In Checklist | 22a0d6cf-d683-4a7a-a9d1-bf290542f086
checkpoint-status |  |  | checkpoint | For apartments includes bathroom, bathroom ensuite, kitchen, laundry
checkpoint-status |  |  | checkpoint | For other areas includes female/male/DDA bathroom, kitchen
checkpoint-status |  |  | checkpoint | High Level Rough In
checkpoint-status |  |  | checkpoint | Wall Set Out
checkpoint-status |  |  | checkpoint | Wall Rough In
checkpoint-status |  |  | checkpoint | Waste Rollovers
checkpoint-status |  |  | checkpoint | Gas
checkpoint-status |  |  | checkpoint | Test Water
checklist-flat |  |  | checklist | Corridor Checklist |  |  |  |  | Yes | Corridor Checklist | 2ad0e45b-0fbc-4446-8394-1769ac744510
checkpoint-status |  |  | checkpoint | Rainwater
checkpoint-status |  |  | checkpoint | Hot Water
checkpoint-status |  |  | checkpoint | Hot Water Lagged
checkpoint-status |  |  | checkpoint | Cold Water
checkpoint-status |  |  | checkpoint | Test Hot Water
checkpoint-status |  |  | checkpoint | Test Cold Water
checkpoint-status |  |  | checkpoint | Test Rain Water
checkpoint-status |  |  | checkpoint | Fire Caulking (Corridor to Apt)
checkpoint-status |  |  | checkpoint | Cold Water Meter Manifold
checklist-flat |  |  | checklist | In-Ground Stormwater Drainage Checklist |  |  |  |  | Yes | In-Ground Stormwater Drainage Checklist | 40454d91-cbee-4312-ad5b-6fb0adcebe0f
checkpoint-status |  |  | checkpoint | Pipework, material and fittings installed as per approved IFC Drawing
checkpoint-status |  |  | checkpoint | Pipework installation
checkpoint-status |  |  | checkpoint | Pipework checked for correct invert levels & gradients
checkpoint-status |  |  | checkpoint | Pits checked for correct invert levels & finished floor levels
checkpoint-status |  |  | checkpoint | Ensure correct locations of pits.
checkpoint-status |  |  | checkpoint | Ensure all backfill is in accordance to specifications & compaction requirements.
checklist-flat |  |  | checklist | Day Docket |  |  |  |  | Yes | Add Day Docket Checklist | 4725fafb-5f3d-4272-af27-fa28fb48bd9d
checkpoint-status |  |  | checkpoint | Details added below
text | a25b7203-bd63-5649-adea-f94d06f4da33 |  | textbox | Work completed
text | 5a6f1be8-42f4-5815-b37b-bb26c27a99ac |  | textbox | Materials required
text | a8842232-086e-5b1a-aac6-351f715bf1d4 |  | textbox | Staff
select | ff550cec-854e-5e87-81b0-037a1768d062 |  | dropdown | Hours | 1, 2, 3, 4, 5, 6, 7, 8
checkpoint-status |  |  | checkpoint | Signed off by Ryder Plumbing
holdpoint |  |  | signoff | Signed off by Builder
checklist-flat |  |  | checklist | Vents Checklist |  |  |  |  | Yes | Vents Checklist | 5813ca7f-4f70-4c16-b1b4-d04c134629dc
checkpoint-status |  |  | checkpoint | Vents installed
checkpoint-status |  |  | checkpoint | Smoke sealed
checkpoint-status |  |  | checkpoint | Fire rated
checkpoint-status |  |  | checkpoint | Tested
checklist-flat |  |  | checklist | Hot Water Unit Checklist |  |  |  |  | Yes | Hot Water Unit Checklist | 66630b25-5c18-4b35-be33-01ab6f267a42
checkpoint-status |  |  | checkpoint | Hot water unit installation
checkpoint-status |  |  | checkpoint | Copper works installation
checkpoint-status |  |  | checkpoint | Smoke sealed
checkpoint-status |  |  | checkpoint | Fire rated
checkpoint-status |  |  | checkpoint | Tested
checklist-sectioned |  |  | checklist | Apartment Fit Off Checklist |  |  |  |  | Yes | Apartment Fit Off Checklist | 6772ce3b-7105-49c2-9c21-779d5841ee66
checkpoint-group |  |  | section | Laundry Fit Off
checkpoint-status |  |  | checkpoint | Laundry Trough
checkpoint-status |  |  | checkpoint | Laundry Trough Mixer
checkpoint-status |  |  | checkpoint | Laundry Trough Mini Stops
checkpoint-status |  |  | checkpoint | Laundry Trough Waste
checkpoint-group |  |  | section | Kitchen Fit Off
checkpoint-status |  |  | checkpoint | Kitchen Mini Stops
checkpoint-status |  |  | checkpoint | Kitchen Sink Waste
checkpoint-status |  |  | checkpoint | Kitchen Sink Mixer
checkpoint-status |  |  | checkpoint | Kitchen Dishwasher
checkpoint-status |  |  | checkpoint | Kitchen Cooktop
checkpoint-group |  |  | section | Bathroom Fit Off
checkpoint-status |  |  | checkpoint | Bathroom Shower Mixer
checkpoint-status |  |  | checkpoint | Bathroom Shower Rail/Rose
checkpoint-status |  |  | checkpoint | Bathroom Basin
checkpoint-status |  |  | checkpoint | Bathroom Basin Mixer
checkpoint-status |  |  | checkpoint | Bathroom Bottle Trap
checkpoint-status |  |  | checkpoint | Bathroom Toilet
checkpoint-status |  |  | checkpoint | Bathroom Urinal
checklist-sectioned |  |  | checklist | Other Areas Fit Off Checklist |  |  |  |  | Yes | Other Areas Fit Off Checklist | 847601df-ea86-40ab-aee2-73d6afc42ac6
checkpoint-group |  |  | section | Kitchen/Butler's Pantry Fit Off
checkpoint-status |  |  | checkpoint | Kitchen Mini Stops
checkpoint-status |  |  | checkpoint | Kitchen Sink Waste
checkpoint-status |  |  | checkpoint | Kitchen Sink Mixer
checkpoint-status |  |  | checkpoint | Kitchen Dishwasher
checkpoint-status |  |  | checkpoint | Kitchen Cooktop
checkpoint-group |  |  | section | Female Bathroom Fit Off
checkpoint-status |  |  | checkpoint | Bathroom Shower Mixer
checkpoint-status |  |  | checkpoint | Bathroom Shower Rail/Rose
checkpoint-status |  |  | checkpoint | Bathroom Basin
checkpoint-status |  |  | checkpoint | Bathroom Basin Mixer
checkpoint-status |  |  | checkpoint | Bathroom Bottle Trap
checkpoint-status |  |  | checkpoint | Bathroom Toilet
checkpoint-status |  |  | checkpoint | Bathroom Urinal
checkpoint-group |  |  | section | Male Bathroom Fit Off
checkpoint-status |  |  | checkpoint | Bathroom Shower Mixer
checkpoint-status |  |  | checkpoint | Bathroom Shower Rail/Rose
checkpoint-status |  |  | checkpoint | Bathroom Basin
checkpoint-status |  |  | checkpoint | Bathroom Basin Mixer
checkpoint-status |  |  | checkpoint | Bathroom Bottle Trap
checkpoint-status |  |  | checkpoint | Bathroom Toilet
checkpoint-status |  |  | checkpoint | Bathroom Urinal
checkpoint-group |  |  | section | DDA Bathroom Fit Off
checkpoint-status |  |  | checkpoint | Bathroom Shower Mixer
checkpoint-status |  |  | checkpoint | Bathroom Shower Rail/Rose
checkpoint-status |  |  | checkpoint | Bathroom Basin
checkpoint-status |  |  | checkpoint | Bathroom Basin Mixer
checkpoint-status |  |  | checkpoint | Bathroom Bottle Trap
checkpoint-status |  |  | checkpoint | Bathroom Toilet
checkpoint-status |  |  | checkpoint | Bathroom Urinal
checklist-flat |  |  | checklist | In-Ground Sewer Drainage Checklist |  |  |  |  | Yes | In-Ground Sewer Drainage Checklist | 848f7650-a788-4f0f-8ac8-749f87107a8c
checkpoint-status |  |  | checkpoint | Pipework, material and fittings installed as per approved IFC Drawing
checkpoint-status |  |  | checkpoint | Pipework installation
checkpoint-status |  |  | checkpoint | Pipework checked for correct invert levels & gradients
checkpoint-status |  |  | checkpoint | Book inspection with VBA for in-ground drainage.
checkpoint-status |  |  | checkpoint | Ensure all backfill is in accordance to specifications & compaction requirements.
checkpoint-status |  |  | checkpoint | Test sewer
checklist-flat |  |  | checklist | Suspended Stormwater Drainage Checklist |  |  |  |  | Yes | Suspended Stormwater Drainage Checklist | 8f5804fe-57ca-4084-8542-065dbb66f1d5
checkpoint-status |  |  | checkpoint | Pipework, material and fittings installed as per approved IFC Drawing
checkpoint-status |  |  | checkpoint | Pipework installation
checkpoint-status |  |  | checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
checkpoint-status |  |  | checkpoint | Smoke seal penetrations
checkpoint-status |  |  | checkpoint | Fire collars installed if necessary
checklist-flat |  |  | checklist | Penetrations Checklist |  |  |  |  | Yes | Penetrations Checklist | 9d1e8948-66a6-45dc-b348-a1fb358606a6
checkpoint-status |  |  | checkpoint | All works to be set our as per approved IFC drawings.
checkpoint-status |  |  | checkpoint | Fire collar installation
checkpoint-status |  |  | checkpoint | Cast in drains
checkpoint-status |  |  | checkpoint | Photos of collar end labelling referencing fire matrix if required
checklist-flat |  |  | checklist | Other Areas Suspended Drainage Checklist |  |  |  |  | Yes | Other Areas Suspended Drainage Checklist | ae05846c-936b-4e71-9df7-6a7d7cfd41a3
checkpoint-status |  |  | checkpoint | Pipework, material and fittings installed as per approved IFC Drawing.
checkpoint-status |  |  | checkpoint | Pipework installation
checkpoint-status |  |  | checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
checkpoint-status |  |  | checkpoint | Smoke seal penetrations
checkpoint-status |  |  | checkpoint | Fire collars installed if necessary
checklist-flat |  |  | checklist | In-Ground Pits/Pumps/Tanks Checklist |  |  |  |  | Yes | In-Ground Pits/Pumps/Tanks Checklist | c06f5bdc-4f51-414a-a113-1b2f58b3d81e
checkpoint-status |  |  | checkpoint | Sewer pump well
checkpoint-status |  |  | checkpoint | Storwater pump well
checkpoint-status |  |  | checkpoint | Stormwater pits
checkpoint-status |  |  | checkpoint | Grease interceptor trap
checkpoint-status |  |  | checkpoint | Conduits rain to IFC location
checkpoint-status |  |  | checkpoint | Torpedo tanks
checkpoint-status |  |  | checkpoint | Stormwater detention system
checklist-flat |  |  | checklist | Storm Water Grates Checklist |  |  |  |  | Yes | Storm Water Grates Checklist | d7d5efc1-2620-4394-83de-eba01609b1a6
checkpoint-status |  |  | checkpoint | Grates installed
checkpoint-status |  |  | checkpoint | Smoke sealed
checkpoint-status |  |  | checkpoint | Fire rated
checkpoint-status |  |  | checkpoint | Tested
checklist-flat |  |  | checklist | Apartment Suspended Drainage Checklist |  |  |  |  | Yes | Apartment Suspended Drainage Checklist | ebe553c3-7d49-4989-b1fe-297fd94aa4ec
checkpoint-status |  |  | checkpoint | Pipework, material and fittings installed as per approved IFC Drawing. Includes bathroom, bathroom ensuite, kitchen, laundry
checkpoint-status |  |  | checkpoint | Pipework installation
checkpoint-status |  |  | checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
checkpoint-status |  |  | checkpoint | Smoke seal penetrations
checkpoint-status |  |  | checkpoint | Fire collars installed if necessary
checklist-flat |  |  | checklist | Gas Works Checklist |  |  |  |  | Yes | Gas Works Checklist | ec1524a3-de3a-4b73-957d-21bfcf39d445
checkpoint-status |  |  | checkpoint | Gas Meter set up (Ground floor only)
checkpoint-status |  |  | checkpoint | Gas Riser room pipe installation
checkpoint-status |  |  | checkpoint | Pipe anchor/slide guides
checkpoint-status |  |  | checkpoint | Smoke sealed
checkpoint-status |  |  | checkpoint | Gas tested
checkpoint-status |  |  | checkpoint | Fire rated
checklist-flat |  |  | checklist | Big Ticket Items (In Ground) |  |  |  |  | Yes | Big Ticket Items (In Ground) | f0d17c58-45b7-4e91-93d6-13939839f4f7
checkpoint-status |  |  | checkpoint | Sewer pump well
checkpoint-status |  |  | checkpoint | Storwater pump well
checkpoint-status |  |  | checkpoint | Stormwater pits
checkpoint-status |  |  | checkpoint | Grease interceptor trap
checkpoint-status |  |  | checkpoint | Conduits rain to IFC location
checkpoint-status |  |  | checkpoint | Torpedo tanks
checkpoint-status |  |  | checkpoint | Stormwater detention system
checkpoint-status |  |  | checkpoint | LPOD
checkpoint-status |  |  | checkpoint | Water tap in
checklist-flat |  |  | checklist | Commissioning Checklist |  |  |  |  | Yes | Commissioning Checklist | ff1b7cc5-0b54-4945-b10e-99fe1389354e
checkpoint-status |  |  | checkpoint | Includes female/male/DDA bathroom, kitchen
checkpoint-status |  |  | checkpoint | Test Hot Water Temperature
checkpoint-status |  |  | checkpoint | Test Waste for leaks
checkpoint-status |  |  | checkpoint | Run Cycle on Dishwasher