## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Corridor |  |  |  |  | Yes | Corridor Checklist | 02f9dec6-d8d9-46b2-8d3c-80da08085c3d
checkpoint-status |  |  | checkpoint | Rainwater
checkpoint-status |  |  | checkpoint | Hot Water
checkpoint-status |  |  | checkpoint | Hot Water Lagged
checkpoint-status |  |  | checkpoint | Cold Water
checkpoint-status |  |  | checkpoint | Test Hot Water
checkpoint-status |  |  | checkpoint | Test Cold Water
checkpoint-status |  |  | checkpoint | Test Rain Water
checkpoint-status |  |  | checkpoint | Fire Caulking (Corridor to Apt)
checkpoint-status |  |  | checkpoint | Cold Water Meter Manifold
checklist-flat |  |  | checklist | Sewer Drainage |  |  |  |  | Yes | In-Ground Sewer Drainage Checklist | 1b1aabf1-b720-4842-adfe-b7f60d7530f0
checkpoint-status |  |  | checkpoint | Pipework, material and fittings installed as per approved IFC Drawing
checkpoint-status |  |  | checkpoint | Pipework installation
checkpoint-status |  |  | checkpoint | Pipework checked for correct invert levels & gradients
checkpoint-status |  |  | checkpoint | Book inspection with VBA for in-ground drainage.
checkpoint-status |  |  | checkpoint | Ensure all backfill is in accordance to specifications & compaction requirements.
checkpoint-status |  |  | checkpoint | Test sewer
checklist-flat |  |  | checklist | Pumps/Tanks/Booster Pump |  |  |  |  | Yes | Basement Pumps/Tanks/Booster Pump Checklist | 1bc9af14-4e01-4fb6-bb54-1070ceed6777
checkpoint-status |  |  | checkpoint | Domestic cold water booster pump
checkpoint-status |  |  | checkpoint | Domestic cold water break tank
checkpoint-status |  |  | checkpoint | Rainwater pump set
checkpoint-status |  |  | checkpoint | Rainwater tanks
checkpoint-status |  |  | checkpoint | Sewer pump board installed
checkpoint-status |  |  | checkpoint | Stormwater pump board installed
checkpoint-status |  |  | checkpoint | Suspended Pollutant trap
checkpoint-status |  |  | checkpoint | Diversion valve
checkpoint-status |  |  | checkpoint | OSD tank (if applicable)
checkpoint-status |  |  | checkpoint | Smoke sealed
checkpoint-status |  |  | checkpoint | Tested
checkpoint-status |  |  | checkpoint | Fire rated if necessary
checkpoint-status |  |  | checkpoint | Water meter assembly
checklist-sectioned |  |  | checklist | Toolbox Meeting Checklist |  |  |  |  | Yes | Add Toolbox Meeting Checklist | 20c482c9-a1e5-476f-8535-053fc222157e
checkpoint-group |  |  | section | Attendance
checkpoint-status |  |  | checkpoint | Attendance - list of attendees added below
checkpoint-status |  |  | checkpoint | Apologies - list of non-attendees added below
checkpoint-group |  |  | section | Minutes
checkpoint-status |  |  | checkpoint | Actions from last meeting
checkpoint-status |  |  | checkpoint | Administration
checkpoint-status |  |  | checkpoint | HR
label | cf0daa76-a8be-5814-a2cc-53b5ec778228 |  | note | e.g - Site recognition, any HR issues?
checkpoint-status |  |  | checkpoint | Safety: (including hazards / near misses / controls / site specific)
checkpoint-status |  |  | checkpoint | Environment: (including hazards / controls / incidents / impacts)
checkpoint-status |  |  | checkpoint | Training
label | 6bb589c0-7688-5942-b0e7-f1984330e3b0 |  | note | Competency Assessment Guides (Apprentices) if applicable – are they up to date?
checkpoint-status |  |  | checkpoint | Plant & Equipment
checkpoint-status |  |  | checkpoint | Issues & Customer Feedback
checkpoint-status |  |  | checkpoint | Client/Job specific information:
checkpoint-status |  |  | checkpoint | Memo’s and other office correspondence
checkpoint-group |  |  | section | Document Review
checkpoint-status |  |  | checkpoint | Document uploaded below if applicable
checkpoint-group |  |  | section | New Business / Other
checkpoint-status |  |  | checkpoint | Any new business / other comments added below
checkpoint-group |  |  | section | Meeting Closure
checkpoint-status |  |  | checkpoint | Meeting Closed
text | 15dbc8ea-d91e-5ce9-a3b3-42131240438f |  | textbox | Meeting Closed time
text | 8fa0f2c2-6c31-5e80-aed7-76868af99a27 |  | textbox | Date for next meeting
text | f8f2040b-2685-5748-87c3-7b25b6edd291 |  | textbox | Minutes taken by (Name)
checklist-flat |  |  | checklist | Hot Water Unit |  |  |  |  | Yes | Hot Water Unit Checklist | 42f3b545-c856-450f-839f-b7b0f7a7049c
checkpoint-status |  |  | checkpoint | Hot water unit installation
checkpoint-status |  |  | checkpoint | Copper works installation
checkpoint-status |  |  | checkpoint | Smoke sealed
checkpoint-status |  |  | checkpoint | Fire rated
checkpoint-status |  |  | checkpoint | Tested
checklist-sectioned |  |  | checklist | Fit Off |  |  |  |  | Yes | Fit Off Checklist | 4ee04e8b-f778-471e-8b6e-652366db22f5
checkpoint-group |  |  | section | Kitchen Fit Off
checkpoint-status |  |  | checkpoint | Kitchen Mini Stops
checkpoint-status |  |  | checkpoint | Kitchen Sink Waste
checkpoint-status |  |  | checkpoint | Kitchen Sink Mixer
checkpoint-status |  |  | checkpoint | Kitchen Dishwasher
checkpoint-status |  |  | checkpoint | Kitchen Cooktop
checkpoint-group |  |  | section | Female Bathroom Fit Off
checkpoint-status |  |  | checkpoint | Bathroom Shower Mixer
checkpoint-status |  |  | checkpoint | Bathroom Shower Rail/Rose
checkpoint-status |  |  | checkpoint | Bathroom Basin
checkpoint-status |  |  | checkpoint | Bathroom Basin Mixer
checkpoint-status |  |  | checkpoint | Bathroom Bottle Trap
checkpoint-status |  |  | checkpoint | Bathroom Toilet
checkpoint-status |  |  | checkpoint | Bathroom Urinal
checkpoint-group |  |  | section | Male Bathroom Fit Off
checkpoint-status |  |  | checkpoint | Bathroom Shower Mixer
checkpoint-status |  |  | checkpoint | Bathroom Shower Rail/Rose
checkpoint-status |  |  | checkpoint | Bathroom Basin
checkpoint-status |  |  | checkpoint | Bathroom Basin Mixer
checkpoint-status |  |  | checkpoint | Bathroom Bottle Trap
checkpoint-status |  |  | checkpoint | Bathroom Toilet
checkpoint-status |  |  | checkpoint | Bathroom Urinal
checkpoint-group |  |  | section | DDA Bathroom Fit Off
checkpoint-status |  |  | checkpoint | Bathroom Shower Mixer
checkpoint-status |  |  | checkpoint | Bathroom Shower Rail/Rose
checkpoint-status |  |  | checkpoint | Bathroom Basin
checkpoint-status |  |  | checkpoint | Bathroom Basin Mixer
checkpoint-status |  |  | checkpoint | Bathroom Bottle Trap
checkpoint-status |  |  | checkpoint | Bathroom Toilet
checkpoint-status |  |  | checkpoint | Bathroom Urinal
checklist-flat |  |  | checklist | Big Ticket Items (In Ground) |  |  |  |  | Yes | Big Ticket Items (In Ground) | 5a0d3b9b-dc80-400f-bfd7-b18aa0273504
checkpoint-status |  |  | checkpoint | Sewer pump well
checkpoint-status |  |  | checkpoint | Storwater pump well
checkpoint-status |  |  | checkpoint | Stormwater pits
checkpoint-status |  |  | checkpoint | Grease interceptor trap
checkpoint-status |  |  | checkpoint | Conduits rain to IFC location
checkpoint-status |  |  | checkpoint | Torpedo tanks
checkpoint-status |  |  | checkpoint | Stormwater detention system
checkpoint-status |  |  | checkpoint | LPOD
checkpoint-status |  |  | checkpoint | Water tap in
checklist-flat |  |  | checklist | Rough In |  |  |  |  | Yes | Rough In Checklist | 5bd34784-a16b-4a77-8715-d2da79c93c34
checkpoint-status |  |  | checkpoint | Includes female/male/DDA bathroom, kitchen
checkpoint-status |  |  | checkpoint | High Level Rough In
checkpoint-status |  |  | checkpoint | Wall Set Out
checkpoint-status |  |  | checkpoint | Wall Rough In
checkpoint-status |  |  | checkpoint | Waste Rollovers
checkpoint-status |  |  | checkpoint | Gas
checkpoint-status |  |  | checkpoint | Test Water
checklist-flat |  |  | checklist | Commissioning |  |  |  |  | Yes | Commissioning Checklist | a4c5a4e4-43ba-4640-8034-b7f9b6c950b6
checkpoint-status |  |  | checkpoint | Includes female/male/DDA bathroom, kitchen
checkpoint-status |  |  | checkpoint | Test Hot Water Temperature
checkpoint-status |  |  | checkpoint | Test Waste for leaks
checkpoint-status |  |  | checkpoint | Run Cycle on Dishwasher
checklist-flat |  |  | checklist | Suspended Copper Works |  |  |  |  | Yes | Suspended Copper Works Checklist | a7f093ce-bff7-4f17-9903-28412b96b3f7
checkpoint-status |  |  | checkpoint | Pipework installed - domestic hot/cold/rain water
checkpoint-status |  |  | checkpoint | Smoke seal penetrations
checkpoint-status |  |  | checkpoint | Fire rated if necessary
checkpoint-status |  |  | checkpoint | Tested
checklist-flat |  |  | checklist | Vents |  |  |  |  | Yes | Vents Checklist | b67474bb-92a0-422d-a6e6-4b78c1379bb1
checkpoint-status |  |  | checkpoint | Vents installed
checkpoint-status |  |  | checkpoint | Smoke sealed
checkpoint-status |  |  | checkpoint | Fire rated
checkpoint-status |  |  | checkpoint | Tested
checklist-flat |  |  | checklist | Daily Site Diary |  |  |  |  | Yes | Add Daily Site Diary Checklist | bd5abf8c-4ae0-41a8-b629-a6c2a94994b2
checkpoint-status |  |  | checkpoint | Attach relevant photos and documents
text | 00a01268-9f88-535c-b15b-5be03dcb08f8 |  | textbox | Time on Site
text | 0b767554-eb89-51b3-8f7e-acaba4c1f48a |  | textbox | Time off site
text | ac8247a5-e62a-5c9f-ae3c-b1434fb562d2 |  | textbox | Vehicles
text | 66d3ea77-1531-59e5-bd9a-4a58851f9c8b |  | textbox | Plant
text | c4450817-d9f9-59c2-a44a-d8ea36f1a84a |  | textbox | Ryder Plumbing Staff Onsite (list names)
checkpoint-status |  |  | checkpoint | Traffic Control
text | 89998085-26f7-5e1c-92f2-da537f8ad91b |  | textbox | Number of Controllers
text | ff96a31d-9705-51d5-b83e-5e8f90e0f27b |  | textbox | Time on Site
text | ad237b9b-b223-5d8e-b3e1-ff3caed4327f |  | textbox | Time off site
text | 2810b889-9798-5514-89a8-ef3dd35e2df4 |  | textbox | Deliveries / Sub Contractors:
checkpoint-status |  |  | checkpoint | Works Completed
checkpoint-status |  |  | checkpoint | Incomplete Works (add details in comments)
holdpoint |  |  | signoff | Signed off by Ryder Plumbing
checklist-flat |  |  | checklist | Stormwater Drainage |  |  |  |  | Yes | In-Ground Stormwater Drainage Checklist | c229e7d1-04ce-4bb6-b733-7c80aef3e2b8
checkpoint-status |  |  | checkpoint | Pipework, material and fittings installed as per approved IFC Drawing
checkpoint-status |  |  | checkpoint | Pipework installation
checkpoint-status |  |  | checkpoint | Pipework checked for correct invert levels & gradients
checkpoint-status |  |  | checkpoint | Pits checked for correct invert levels & finished floor levels
checkpoint-status |  |  | checkpoint | Ensure correct locations of pits.
checkpoint-status |  |  | checkpoint | Ensure all backfill is in accordance to specifications & compaction requirements.
checklist-flat |  |  | checklist | Penetrations |  |  |  |  | Yes | Penetrations Checklist | c6e4f923-5665-48cc-a066-642a67211634
checkpoint-status |  |  | checkpoint | All works to be set our as per approved IFC drawings.
checkpoint-status |  |  | checkpoint | Fire collar installation
checkpoint-status |  |  | checkpoint | Cast in drains
checkpoint-status |  |  | checkpoint | Photos of collar end labelling referencing fire matrix if required
checklist-flat |  |  | checklist | Above Ground Pits/Pumps/Tanks Checklist |  |  |  |  | Yes | Above Ground Pits/Pumps/Tanks Checklist | c8f000ec-c8e5-4850-88cf-f4de1b7cb420
checkpoint-status |  |  | checkpoint | Diversion valve
checkpoint-status |  |  | checkpoint | Rainwater pump set
checkpoint-status |  |  | checkpoint | Rainwater tanks
checkpoint-status |  |  | checkpoint | Sewer pump installed
checkpoint-status |  |  | checkpoint | Sewer control panel
checkpoint-status |  |  | checkpoint | Stormwater pump installed
checkpoint-status |  |  | checkpoint | Stormwater control panel
checkpoint-status |  |  | checkpoint | Grease interceptor trap
checkpoint-status |  |  | checkpoint | Hot water unit installation
checkpoint-status |  |  | checkpoint | Main Meter assembly
checkpoint-status |  |  | checkpoint | Main Gas Meter cupboard
checklist-flat |  |  | checklist | Pits/Pumps/Tanks |  |  |  |  | Yes | In-Ground Pits/Pumps/Tanks Checklist | f35e87f5-9aed-4021-831f-999681092569
checkpoint-status |  |  | checkpoint | Sewer pump well
checkpoint-status |  |  | checkpoint | Storwater pump well
checkpoint-status |  |  | checkpoint | Stormwater pits
checkpoint-status |  |  | checkpoint | Grease interceptor trap
checkpoint-status |  |  | checkpoint | Conduits rain to IFC location
checkpoint-status |  |  | checkpoint | Torpedo tanks
checkpoint-status |  |  | checkpoint | Stormwater detention system
checklist-flat |  |  | checklist | Storm Water Grates |  |  |  |  | Yes | Storm Water Grates Checklist | f443da95-8cf9-452d-b437-429c689b11bc
checkpoint-status |  |  | checkpoint | Grates installed
checkpoint-status |  |  | checkpoint | Smoke sealed
checkpoint-status |  |  | checkpoint | Fire rated
checkpoint-status |  |  | checkpoint | Tested
checklist-flat |  |  | checklist | Suspended Drainage |  |  |  |  | Yes | Levels Suspended Drainage Checklist | fc1bd261-be5f-40cc-a4a8-5f9406abe9e5
checkpoint-status |  |  | checkpoint | Pipework, material and fittings installed as per approved IFC Drawing. Includes female/male/DDA bathroom, kitchen
checkpoint-status |  |  | checkpoint | Pipework installation
checkpoint-status |  |  | checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
checkpoint-status |  |  | checkpoint | Smoke seal penetrations
checkpoint-status |  |  | checkpoint | Fire collars installed if necessary