## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Underfloor Heating |  |  |  |  | Yes | Underfloor Heating | 2d23f5f7-7744-4c3d-b586-9a91f8fef9e8
checkpoint-group |  |  | section | Subfloor, Heating Elements installed
checkpoint-status |  |  | checkpoint | Area floor level acceptable + Laying of Heating elements (Photos)
checkpoint-status |  |  | checkpoint | Screed coverage completed and acceptable (Photos)
checkpoint-status |  |  | checkpoint | Watchdog installed and tested (Photos )
checklist-sectioned |  |  | checklist | Install QA |  |  |  |  | Yes | Install QA | 5562c94b-9542-45c9-94a6-bee6572f444d
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area tidy and accessible
checkpoint-status |  |  | checkpoint | Height of the flange checked (40mm below subfloor + 10mm underneath flange)
checkpoint-status |  |  | checkpoint | Depth of recess checked (50mm minimum)
holdpoint |  |  | signoff | Raise Remedial/ Request signoff
checkpoint-group |  |  | section | Screeding QA
checkpoint-status |  |  | checkpoint | General observations
checkpoint-status |  |  | checkpoint | Screeding completed and falls as per spec
checkpoint-status |  |  | checkpoint | Concrete sitting flush or lower than lining
checkpoint-group |  |  | section | Underfloor Heating Install
checkpoint-status |  |  | checkpoint | Chisel out channels for cold tail connections
checkpoint-status |  |  | checkpoint | Clean and sweep floor
checkpoint-status |  |  | checkpoint | Correct products used - as per specification
checkpoint-status |  |  | checkpoint | Element marked out in correct location
checkpoint-status |  |  | checkpoint | Apply adhesive to floor where element will be looped
checkpoint-status |  |  | checkpoint | Element is tapped with Warmup fixing tape
checkpoint-status |  |  | checkpoint | Band tape installed to hold at correct centres
checkpoint-status |  |  | checkpoint | Fix floor probe
checkpoint-status |  |  | checkpoint | Ensure element has been tested completed
checkpoint-group |  |  | section | Handover
checkpoint-status |  |  | checkpoint | Works completed 100% as per spec and area left tidy
holdpoint |  |  | signoff | Raise Remedial/ Request signoff
checklist-sectioned |  |  | checklist | Waterproofing |  |  |  |  | Yes | Add Waterproofing Checklist | 5e7e3740-70e0-403e-a789-838512fe6377
checkpoint-group |  |  | section | Preapplication QA
checkpoint-status |  |  | checkpoint | Work area accessible
checkpoint-status |  |  | checkpoint | Substrate as per spec and acceptable
checkpoint-status |  |  | checkpoint | Walls not padded and ok to proceed
checkpoint-status |  |  | checkpoint | Area marked as per spec
checkpoint-group |  |  | section | Application QA
checkpoint-status |  |  | checkpoint | Product used as per spec
checkpoint-status |  |  | checkpoint | Product application as per spec
checkpoint-status |  |  | checkpoint | General photos and site observations
checkpoint-group |  |  | section | Handover
checkpoint-status |  |  | checkpoint | Works completed 100% as per spec and area left tidy
holdpoint |  |  | signoff | Main Contractor sign off
checklist-sectioned |  |  | checklist | Acoustic |  |  |  |  | Yes | Add Acoustic Checklist | 98b7b204-2bc9-4888-848c-c36294874016
checkpoint-group |  |  | section | Preinstall QA
checkpoint-status |  |  | checkpoint | Work area accessible
checkpoint-status |  |  | checkpoint | Substrate as per spec and acceptable
checkpoint-group |  |  | section | Install QA
checkpoint-status |  |  | checkpoint | Installation of acoustic underlay on floor finishing at doorway
checkpoint-status |  |  | checkpoint | Waterproofing applied with PFF rod on all wall bases on flor
checkpoint-status |  |  | checkpoint | Installation of shower base, hob and aluminium channel for glass
checkpoint-status |  |  | checkpoint | Undertile heating and thermal screed applied with alarm fitted and tested
checkpoint-status |  |  | checkpoint | Water Test for shower by Warmup
checkpoint-group |  |  | section | Handover
checkpoint-status |  |  | checkpoint | Works completed 100% as per spec and area left tidy
holdpoint |  |  | signoff | Main Contractor sign off
checklist-sectioned |  |  | checklist | Thermostat |  |  |  |  | Yes | Add Thermostat Checklist | a1a556cb-b985-4981-891b-980506677e38
checkpoint-group |  |  | section | New Thermostat controller installed as per specification
checkpoint-status |  |  | checkpoint | Heating elements megger tested
checkpoint-status |  |  | checkpoint | Connect new thermostat and install into flush box (Photo)
checklist-flat |  |  | checklist | Handover checklist |  |  |  |  | Yes | Handover Checklist | c9a150c4-8ffe-489f-b89f-b7c44f291e4b
checkpoint-status |  |  | checkpoint | PS3s, warranties, user manuals and any other documents attached
checklist-flat |  |  | checklist | Residential Works Checklist |  |  |  |  | Yes | Residential Works Checklist | f55665e4-8ff4-4013-aa74-df72d7f8172f
checkpoint-status |  |  | checkpoint | Please attach photos