## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | 44be1824-dc3a-4074-972f-e67db0709f58 |  | checklist | Underfloor Heating |  |  |  |  | Yes | Underfloor Heating | 11645c4a-e59a-4cf5-b224-1b298ba1f4e7
checkpoint-group | d2c198c3-61c0-4c7b-a6b2-813e8348ffca |  | section | Subfloor, Heating Elements installed
checkpoint-status | 8810a164-d1f1-4d89-b872-fd690915d774 |  | checkpoint | Area floor level acceptable + Laying of Heating elements (Photos)
checkpoint-status | e3e9f3ff-9181-48ba-a76b-fd5d33dbbe1c |  | checkpoint | Screed coverage completed and acceptable (Photos)
checkpoint-status | 44e0517c-7676-4d0e-9b57-2289e0c656b5 |  | checkpoint | Watchdog installed and tested (Photos )
checklist-sectioned | 203b2273-2068-49e1-a41e-f6b34bd1e8ae |  | checklist | Thermostat |  |  |  |  | Yes | Add Thermostat Checklist | 41013566-6d36-4350-9a52-1651ba0f9af8
checkpoint-group | 48c6b2cf-2f9b-4ac9-9056-c5af98a60073 |  | section | New Thermostat controller installed as per specification
checkpoint-status | 33d18a3f-5b15-48e3-91f5-9a61125d088c |  | checkpoint | Heating elements megger tested
checkpoint-status | 3a9a5a01-51f3-4495-920a-49f0ec6edeac |  | checkpoint | Connect new thermostat and install into flush box (Photo)
checklist-flat | 31de3020-eb57-4765-9ec5-771a86e2eb8c |  | checklist | Flooring |  |  |  |  | Yes | Flooring | b18a6656-8f78-47b1-a080-efdde632b406
checkpoint-status | 04ad84d6-d59d-4439-ba11-a8d584392c40 |  | checkpoint | Floor is acceptable for laying Ardex DS70 acoustic mats
checkpoint-status | 3fdf3842-469c-445b-a97f-d5faed25d01d |  | checkpoint | Ardex DS70 Acoustic mats have been laid and glued throughout the Substrate, excluding inside shower floor
checkpoint-status | e7265f01-eb94-4f0f-896b-e4f5cd83ea0a |  | checkpoint | Ardex WPM750 Waterproofing membrane glued throughout bathroom floor
label | ede2b8b5-abce-5378-8835-c1ba4ea30263 |  | note | About 2.1M High in bathroom walls, and upstand throughout all other walls in bathroom
checkpoint-status | db239b19-b813-4cca-b4a5-3f487baf70e6 |  | checkpoint | Underfloor heating elements have been laid, glued and taped to the waterproofing substrate
checkpoint-status | 260a9985-82df-4c3e-bdfc-844041ae7451 |  | checkpoint | Warmup Watchdog alarm connected to the elements as a QA Check to make a noise if system is damaged by third parties
checkpoint-status | b068ae12-fda8-466c-834f-c06b08d92565 |  | checkpoint | Elements encapsulated with Ardex Floor Levelling Compound
checkpoint-status | 2040f97f-1a57-488c-a1cd-3bfd43afaf44 |  | checkpoint | Warmup satisfied with works we have undertaken, and happy to handover for Tiling