## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 78f53b04-1d76-4a7d-a732-bae66a6eff54 |  | checklist | POST - S - Underfloor heating |  |  |  |  | Yes | POST - S - Underfloor heating | 5297e47a-d6de-4f7d-a560-5ab5df89c0cd
checkpoint-status | be793abb-fe71-4027-96fb-dd47abc0bc4c |  | checkpoint | Wiring on the floor completed correctly
checkpoint-status | e62f2f43-07ad-4e1e-8dcf-6dae054068b1 |  | checkpoint | Self levelling coverage completed and acceptable
checkpoint-status | f68e5587-0954-49f4-bf17-a38f5422eb39 |  | checkpoint | Underfloor heating completed - specified level of finish achieved
checkpoint-status | 57061e70-a997-4322-83e7-3791407cd3fe |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | 59e87c0f-137e-4e76-8956-b4e7f7ae1968 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | 868f6755-f1d7-490f-b8f2-aea0b8aa2148 |  | checklist | Pre-commencement Checklist |  |  |  |  | Yes | Pre-commencement Checklist | 9096130b-7cb7-4f1c-8698-1c7644981392
checkpoint-status | 05e8bc87-74fa-4dfc-9b7d-c9df2ee18ff0 |  | checkpoint | Quality Management Plan Completed, Agreed and Attached
checkpoint-status | 63846bd2-69d0-44b2-958d-0fb4f269ef3f |  | checkpoint | Inspection & Test Plan Completed, Agreed & Attached
checkpoint-status | a9d7356a-66ff-4124-9ec1-15908b033a95 |  | checkpoint | Relevant Breakdown & Checklist Setup on Conqa & Reviewed by Main Contractor
checkpoint-status | e9b74007-9810-4850-9176-707ce3919fd5 |  | checkpoint | Conqa Setup & Project Team Trained & Given Access
checkpoint-status | 22e00068-f669-4869-929d-5667472ca392 |  | checkpoint | Review Access Granted to Main Contractor & Relevant Parties
checkpoint-status | ee60efdf-eec7-42cb-bae3-0fb162188e9e |  | checkpoint | Matrix/Insight Setup (if required)
checklist-flat | 1b29da8b-57cd-485b-97b7-eae46452e820 |  | checklist | Underfloor Heating |  |  |  |  | Yes | zSYS - QA - Underfloor Heating (old version, 01-09-23) | aa969a3b-d4a6-4c0e-b1a9-01f9ce90f9aa
checkpoint-status | 3062b4a6-63ee-4e4e-bf6c-3b651fe2de73 |  | checkpoint | Area floor level acceptable
checkpoint-status | e0fb787d-9253-43e7-92a6-d37394f36b75 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | e1548822-9a09-47e1-b0c5-191d4caf0583 |  | checkpoint | Self leveling coverage completed
holdpoint | cf71e51b-b30f-4f74-8028-1e36cf5bc55b |  | signoff | Raise Remedial/ Main Contractor Sign Off
checklist-flat | 05386168-a46c-4dbd-a41b-e81d397ecc7f |  | checklist | Completion Documents |  |  |  |  | Yes | zSYS - Completion Documents (old version) | b83333ce-c23a-433e-b33b-ea551e9a73db
checkpoint-status | 9b111849-ff18-4136-8554-3afe615ad687 |  | checkpoint | All relevant Compliance Documentation completed and attached
button | adebbd29-a24b-4638-9e79-803df4c1bb02 |  | button | PS3 attached | YES, N/A
button | 71fd27aa-c105-4ba3-93ad-6f067bacf381 |  | button | Warranties attached | YES, N/A
checklist-sectioned | abf28ead-69f1-4c3b-af39-b8bc99e7cd3d |  | checklist | Underfloor Heating |  |  |  |  | Yes | Underfloor Heating | d8443945-565e-45aa-b455-777d43f0aeb3
checkpoint-group | 0bc5ee63-0949-44fc-acb7-ab82705c8dea |  | section | Subfloor, Heating Elements installed
checkpoint-status | 671e71f5-47f3-47cd-8381-e5cd0c05c2bc |  | checkpoint | Area floor level acceptable + Laying of Heating elements (Photos)
checkpoint-status | dd9d5987-d58f-4157-b8b1-453574fd4533 |  | checkpoint | Screed coverage completed and acceptable (Photos)
checkpoint-status | 5082a791-8214-4148-8368-9ea120f2b055 |  | checkpoint | Watchdog installed and tested (Photos )
checklist-flat | f906ec33-5238-42c2-8268-840aa0a4ca6b |  | checklist | CST - S - Completion Documents |  |  |  |  | Yes | CST - S - Completion Documents | de611025-9503-4630-9157-0ef9888e7283
checkpoint-status | 422c028c-e42b-4e6f-b0d3-26b6d4c60197 |  | checkpoint | All relevant Compliance Documentation completed and attached above
boolean | dbb41a0a-798a-5e30-bbf5-01a217b108d8 |  | tickbox | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
label | 3c96bee7-0114-540b-b6f7-74fc9c5a313f |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | 2939ed82-4b81-4ee4-a57a-3b8fc1b3abb2 |  | signoff | Request Signoff
checkpoint-status | 0af54629-83c4-4d3e-acf0-288b5bf38a8e |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | eef38e22-9997-42fe-8001-ac30895708ab |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned | 2e855df2-d0d4-40c6-9ece-6909995e0ad2 |  | checklist | Thermostat |  |  |  |  | Yes | Add Thermostat Checklist | eec1dcfb-b2ea-4b38-b98e-e420b3e5920c
checkpoint-group | 6de7ee7e-4009-4e8b-a72f-bf5fac7d423a |  | section | New Thermostat controller installed as per specification
checkpoint-status | 2fad4841-2f01-47b6-8fe5-6b859c11dfd1 |  | checkpoint | Heating elements megger tested
checkpoint-status | e5f692d8-4637-4aa0-97a2-3a8d74773a69 |  | checkpoint | Connect new thermostat and install into flush box (Photo)
checklist-flat | 67e0f664-00fd-4812-9306-21d44d2ca075 |  | checklist | POST - S - Underfloor heating |  |  |  |  | Yes | zSYS - POST - S - Underfloor heating (archived) | ff9baca7-9292-4fc5-a044-7e27d387259b
checkpoint-status | e316155f-2e92-4903-a770-b675ec2f91ac |  | checkpoint | Wiring on the floor completed correctly
checkpoint-status | e77232bf-b546-4d2b-b7c0-a3b10dd4c529 |  | checkpoint | Self leveling coverage completed and acceptable
checkpoint-status | 19ac9e85-d1ad-47b2-b804-6f1a6f294956 |  | checkpoint | Underfloor heating completed - specified level of finish achieved