## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | CLD-208 Stramit Sharpline (Building A) - Panel Site ITP | itp |  |  |  | Yes | CLD-208 Stramit Sharpline (Building A) - Panel Site ITP | 0cf9cd3a-7881-43a9-8c80-e8ccbd8d7f14
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC Shop Drawings Approved
label | 669cc0cf-0950-535d-8987-b2b9f57de268 |  | note | Responsibility: MPX
label | c46d978a-9e96-5f0b-b3f7-2556539cca44 |  | note | – – – – – – – – –
label | a172b68d-7d20-5cc9-a37a-440cf8c737b1 |  | note | Acceptance Criteria: MPX / Architect Sign Off
text | 58578953-dc51-5a72-b13a-77f55791b8db |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | 3881e2be-b0a7-5f3d-a74e-d8adf16c8aac |  | note | Responsibility: MPX
label | 6032cb80-606d-5961-b4cb-85a11714eb09 |  | note | – – – – – – – – –
label | f91c805f-1983-5344-8c84-1d7ea3467ee8 |  | note | Acceptance Criteria: MPX / Architect Sign Off
text | 871bd2a5-718e-5b83-b96c-0eac010d8a1a |  | textbox | Date:
label | 702e5a3a-fb45-5c80-a87e-3e29ed950c3d |  | note | Comments: Check colour is correct as per shop drawings
checkpoint-status |  |  | checkpoint | Materials (Panels/Bolts/Screw/Washers) delivered to site free of damage and deformation
label | a556be69-790c-58c2-aea4-cc56388a970d |  | note | Responsibility: Facadex
label | 7e476614-14dc-527f-b828-07ecb52dffc2 |  | note | – – – – – – – – –
label | 9b0282c5-c91d-50e9-83ba-c38112c8326c |  | note | Acceptance Criteria: Facadex sign off.
text | f059e73c-44bf-5cff-978f-0817b370b706 |  | textbox | Date:
label | cb653139-1b38-58b4-bf96-97b2a1d5814e |  | note | Comments: Check colour is correct as per shop drawings
checkpoint-status |  |  | checkpoint | Grid lines established and site set out complete
label | 72e7402e-853e-5e22-82ae-8fd2b06c87fe |  | note | Responsibility: Facadex
label | 5487bd5c-daf5-5c65-8834-879c0e2f58d2 |  | note | – – – – – – – – –
label | d863bd33-c8bf-5822-87cc-7b38aa23cc77 |  | note | Acceptance Criteria: Facadex sign off.
text | 39a058fe-123e-54b4-b5d3-70532f33160e |  | textbox | Date:
label | 7305595c-686a-5f06-a743-44a0ac986266 |  | note | Comments: If installed off site no gridline available
checkpoint-status |  |  | checkpoint | Stramit Sharpline Cladding Panels installed to IFC specification
label | b6acb7d9-aef5-5c16-8d66-9cffdfd052d6 |  | note | Responsibility: Facadex
label | e4f1a16a-14cd-5f94-906b-23f0acf067d8 |  | note | – – – – – – – – –
label | 350a207a-6899-5fcb-8750-4ce5ef6fdc2d |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 86122cb3-7122-51bc-9994-a7b94f76d523 |  | note | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 7eea2795-b505-5a33-8d61-d3959ba492a2 |  | note | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | d37eb468-8dc2-5c61-a0ff-a03f577c6d83 |  | note | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | f266f6e2-c7c1-570a-b1ad-99d80c084fe2 |  | note | ○ +/- 3mm @ every 1000mm in length & height
text | 7602dc7b-7f4d-5e75-afe2-e5d939ab62e7 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Sharpline Cladding Panels checked for paint scratches and dents post installation
label | 82f64378-adcc-5b3f-bf87-99b48e7dfd15 |  | note | Responsibility: Facadex
label | 932d270e-c671-5b8b-a1b2-1bd9d24c2b0e |  | note | – – – – – – – – –
label | 853fe848-1aab-5ba4-857f-51c6fa2227cc |  | note | Acceptance Criteria: Facadex sign off.
text | f0aa6094-8f20-5e9e-bb27-94d037e42858 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | 0.48BMT colourbond flashing has been installed and sealed the bottom and top.
label | 07092940-e95d-541b-a3ee-397c7f200b93 |  | note | Responsibility: Facadex
label | f39e233b-695f-536f-965e-49a1470b771e |  | note | – – – – – – – – –
label | 2999896e-f7cc-5096-88ec-2552a316b909 |  | note | Acceptance Criteria: Facadex sign off.
text | 0455ba80-15d9-5502-b407-31beccf968ac |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Connections (screws/rivets) checked for damages
label | b21332a2-76e9-59d9-8459-fc83826d6bdc |  | note | Responsibility: Facadex
label | 6cf8cab4-f13a-5219-916a-bf03f49e0997 |  | note | – – – – – – – – –
label | e8a884fb-33ce-5b90-ab22-b610a14c584c |  | note | Acceptance Criteria: Facadex sign off.
text | b226a600-bb9e-58f0-a0ae-bb82fde3ce6b |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | 467f0db9-2ef7-5b6c-a7ce-4fa467169b5a |  | note | Responsibility: Facadex / Builder
label | fec32883-9a57-58ab-9826-e7c54ae5e141 |  | note | – – – – – – – – –
label | 6189fc62-0d89-5705-81ce-47d3f6d2f247 |  | note | Acceptance Criteria: Defect notification via email or chosen correspondence
label | 318104ad-ed5a-562e-94b5-cdfbb258f81d |  | note | ○ Evidence of close out / rectification
label | f9a6d236-a7c7-521d-a82c-35d0082fd95c |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | e69e9683-6907-5609-84bf-d6868ded002d |  | note | ○ Sign of only once agreed that wall is defect free
text | 618287c2-9449-55b5-a165-c533deb58cec |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | fc91223f-63c9-5f4a-8540-ffa885ae613d |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | 9a3d1c0b-aa4b-5ef5-b815-dbda439c16a2 |  | textbox | Foreman – Checklist Completed:
text | 48d4307c-4717-5676-b3ca-e992f716b3d3 |  | textbox | Date / Time:
text | aa399e8f-897d-52be-a5cc-8e38cd8719b8 |  | textbox | Coordinator – Checklist Completed:
text | 6c8bb94a-f6f5-5db2-9e70-b54a3fd8213c |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLD-214 Lysaght Spandek Cladding - Building E Factory ITP | itp |  |  |  | Yes | CLD-214 Lysaght Spandek Cladding - Building E Factory ITP | 1b5afb90-3207-4c2d-8179-68a0fa516b24
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC shop drawings approved for fabrication
label | a3333e7c-b80d-5f09-aebc-521a893bd127 |  | note | Responsibility: MPX
label | 9cccec56-296a-5e78-9ba5-0cc264fb6694 |  | note | – – – – – – – – –
label | 5dc4a8da-d11d-5508-9498-d9d5e468d6d9 |  | note | Acceptance Criteria: MPX / Architect sign off
text | 5a5d86a7-3964-54fa-996f-c670733e3fdb |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | fff85645-c5f2-559f-b6a2-e9ba42930660 |  | note | Responsibility: MPX
label | a202569f-f787-54c2-b70a-9c26b2267344 |  | note | – – – – – – – – –
label | c397efae-12dc-581f-beec-92152ddb8747 |  | note | Acceptance Criteria: MPX / Architect sign off
text | 17648501-f7e4-5db2-b29a-bc677ff6dc4a |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Confirm and check finish as per approved IFC drawings
label | 611204db-bb61-56c0-b50d-e485dbebc33d |  | note | Responsibility: Facadex
label | 87a80509-96bf-5f4b-8138-076e36990bad |  | note | – – – – – – – – –
label | 49849edf-199f-5e7b-ab57-d6728bc37142 |  | note | Acceptance Criteria: Facadex sign off.
text | 2c5ee8ec-3c01-589f-8286-3246f9c1cc21 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check panel size and dimensions against IFC drawings
label | f2fa9c78-e63b-5695-a4c7-c166429eb33c |  | note | Responsibility: Facadex
label | ccfbcd71-8818-55b0-a247-30b413577c90 |  | note | – – – – – – – – –
label | e498f802-39a8-5f92-b206-fe7675e5b547 |  | note | Acceptance Criteria: Facadex sign off.
text | 97250112-c815-557f-8354-e62497c78432 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check diagonal dimension to ensure odd shape panel are done correctly
label | 665b5740-2b63-57dc-97d8-84e4bb8023cf |  | note | Responsibility: Facadex
label | 7bab275f-8a73-5e57-9924-db038c275de5 |  | note | – – – – – – – – –
label | c95f3a1c-8478-545f-9c49-fa3f0bdeb61f |  | note | Acceptance Criteria: Facadex sign off.
text | 8069eb4a-0b8f-54f8-aecb-b4700494500f |  | textbox | Date:
checkpoint-status |  |  | checkpoint | QA has checked delivery docket and receipt from powder coater
label | b598ef93-6038-5369-b16e-a7ae2bb6e2d4 |  | note | Responsibility: Facadex
label | 07fbc8e3-331d-50d7-8b57-8dead350f050 |  | note | – – – – – – – – –
label | 2f5b388d-ace7-5850-a821-f56eb066104f |  | note | Acceptance Criteria: Facadex sign off.
text | 2989dff9-1d2d-5e87-8fd0-335b96ba28f1 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Is fabricated item labelled as per drawing?
label | 5aeea6c3-592c-55e9-a47d-24732fc0987a |  | note | Responsibility: Facadex
label | 71e6d5f7-66e7-524d-a578-695d21fc44a5 |  | note | – – – – – – – – –
label | 25f39fb2-0608-544a-b3c8-3bf27148347f |  | note | Acceptance Criteria: Facadex sign off.
text | c91dcd48-a9fa-52a7-b269-c72444c1314f |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Fabrication complete
label | 4316ec6e-c9e7-5f4c-920e-31ca02a4ac9a |  | note | Responsibility: Facadex
label | 4c878d7e-f817-5d6e-9318-06aef250fdea |  | note | – – – – – – – – –
label | b0de7908-3ff2-5348-8c1d-ddb558af1ffb |  | note | Acceptance Criteria: Facadex sign off.
text | e8c899d2-a1d7-5f36-b0de-e66d84537be7 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Prevent direct contanct between incompatible materials
label | 42cd4751-60c1-544a-8bb4-3116a8bac783 |  | note | Responsibility: Facadex
label | b3dd02bf-7115-5932-b02a-46da32dc5b2a |  | note | – – – – – – – – –
label | 725b39b6-baf2-5d75-a3f5-c79f66bd3bf0 |  | note | Acceptance Criteria: Facadex sign off.
text | cf53e55d-125b-5b15-8294-00b3c931e20d |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Materials ready to deliver on site
label | 4429ca28-14cf-5e69-a9d6-3111ebd2566b |  | note | Responsibility: Facadex
label | 15531a9b-f346-538a-b5ae-6ac45f92c020 |  | note | – – – – – – – – –
label | 780d43b5-7976-5985-b507-fea3a84499f8 |  | note | Acceptance Criteria: Facadex sign off.
text | a606df7e-c20f-53e1-9658-a3a058bb9b3b |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | b5c36d03-a689-51d7-aee1-5d8f5839744f |  | note | Responsibility: Facadex / Builder
label | 681a078d-dca9-5a94-a5e0-ceca7f8bbccd |  | note | – – – – – – – – –
label | 7ae48706-74da-578b-bc6b-3d6ef89389ab |  | note | Acceptance Criteria: Defect notification via email or chosen correspondence
label | 397c1d4b-12e3-5d7a-b123-4c079eeaf8a6 |  | note | ○ Evidence of close out / rectification
label | 0ff9cec7-b7ed-59bc-8a71-fe6c3447446a |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | a3234d26-728f-591d-a705-d6656a851613 |  | note | ○ Sign of only once agreed that wall is defect free
text | b80543f3-203c-5e4c-8561-7da29cfae8f6 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | f5497a0e-4b31-5002-b946-a0afc0b47bf3 |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | c11940eb-274d-5830-bd48-f266e50b499b |  | textbox | Foreman – Checklist Completed:
text | 97c7bb41-22ec-5e44-9f27-74a29e664757 |  | textbox | Date / Time:
text | f6a66abb-431d-5a1c-baa5-e8eb9b8fd616 |  | textbox | Coordinator – Checklist Completed:
text | 2b6bfdfc-496a-5614-a0d6-002b7c11b28b |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLG-514 Site Subframing ITP | itp |  |  |  | Yes | CLG-514 Site Subframing ITP | 1deecc07-31df-4e31-8d77-4b082ee73dd9
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC Shop Drawings Approved
label | ca1cfcea-4710-5f04-bd78-403b7c6f5c3e |  | note | Responsibility: MPX
label | 4281ae9d-6bf0-599a-a102-3ae0f200829b |  | note | – – – – – – – – –
label | 609668aa-6bd5-546f-a956-3a5282c3a54e |  | note | Acceptance Criteria: MPX / Architect Sign Off
label | 170f1025-6dc9-5fe2-9cf6-7d0a09197c43 |  | note | – – – – – – – – –
text | 504b8577-ed4e-5020-bab8-a35c3bf44b2e |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | e5a061bd-8b11-5a6a-bbc5-ba319dc9435b |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | b2448552-d312-5712-8fe9-88571e1a2b71 |  | note | Responsibility: MPX
label | 9706524e-a881-5f43-890c-57b97cf33907 |  | note | – – – – – – – – –
label | c8be18c3-ece9-5114-8200-82433c914211 |  | note | Acceptance Criteria: MPX / Architect Sign Off
label | 7007f896-f6e9-5b57-a285-dc307db8783c |  | note | – – – – – – – – –
text | d90c2536-f6df-5a60-be0c-cbf64f204fdb |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 47e16b24-d3bf-5e3b-904d-3808a18b7235 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Materials (truss frame/Bolts/Washers) delivered to site free of damage and deformation
label | 32366e11-72ac-56e7-a9fd-03057491fc33 |  | note | Responsibility: Facadex
label | 302d4b8e-eaca-5e98-ba79-a8b65028fac6 |  | note | – – – – – – – – –
label | 0315af89-1e08-5188-bb70-10cb1b76e018 |  | note | Acceptance Criteria: Facadex sign off.
label | 5efd7e28-4a30-59ee-a50a-bb50e80ea80a |  | note | – – – – – – – – –
text | 256ac7e7-1af0-5eca-83d8-64ab150d947c |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | fb629c89-f198-5569-838a-30a1ba2b4882 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Grid lines established and site set out complete
label | f875bd85-fe13-56ee-80d8-e26abddec915 |  | note | Responsibility: Facadex
label | 081d1d7c-4ad2-537b-b9f0-42b936204a3d |  | note | – – – – – – – – –
label | 4e9433d4-f75e-5cfe-930a-ec0ce8eaca2d |  | note | Acceptance Criteria: Facadex sign off.
label | 15609083-7c40-5787-a0b0-2221621f2110 |  | note | – – – – – – – – –
text | d8b62baa-fc43-54ab-8c1a-5fcd83628794 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | ed5f3b1b-7b61-5159-bd58-366e8139031d |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Truss Framing underside of the bridge installed as per shop details
label | 2c456287-b374-5d2e-846e-da1e8b927a5f |  | note | Responsibility: Facadex
label | 118b3ef2-c3db-5aca-8fe7-81cf4eec6f72 |  | note | – – – – – – – – –
label | d410e506-d37e-5d70-b9e4-d69f72f4d5b7 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 241a4e09-7be5-5d1f-8f35-9ceccb3c224e |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | d7d2871c-863b-56d3-a40e-9eecb910e0fe |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | f178d5ed-1aaf-59c2-84c8-47843f635639 |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | 05a1800f-375d-5576-9222-84718c3149b2 |  | note | ○ Expansion & Contraction:
label | 49e104c7-99be-57c0-a2a4-9fff033406f6 |  | note | +/- 3mm @ every 1000mm in length & height
label | 17d6ed1c-8ca5-59a1-b444-9d2c424aa0e8 |  | note | – – – – – – – – –
text | f5f7aab2-dcab-591a-954d-0b00af62f61a |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 8de09ba2-5a2b-55b5-8e13-c3b945e6042a |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Truss Framing aligned finished level and plumb
label | 1492d3ad-8f04-5dc8-92a3-da7695ec13b0 |  | note | Responsibility: Facadex
label | 87c22a7a-a1dd-5058-b132-aaac6fff3348 |  | note | – – – – – – – – –
label | 3966b101-b897-52cd-a576-116c436bc736 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | ca505238-29a2-5d8f-9479-1d669191a870 |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 9078c41d-3889-5475-b12d-b5b342d2d0cc |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | e9749fa5-9733-5129-a9ef-ba0a206aca21 |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | 41f6d550-403e-5e89-a45f-20039c62b5f5 |  | note | ○ Expansion & Contraction:
label | aaab6584-ebd4-5729-9742-3e3fbfbdc6ca |  | note | +/- 3mm @ every 1000mm in length & height
label | 96bbbb31-4da7-507e-be71-e3dfc3b9b30c |  | note | – – – – – – – – –
text | 432727b7-24a9-5e86-a9f5-2a553ec8918b |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | e28096f7-c2a3-5ac0-9682-bf237986897d |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Top hat to primiry steel (side) or to truss frame (underside) installed and leveled for panel installation
label | f9c1f15a-80eb-578a-9ce2-59afe415e853 |  | note | Responsibility: Facadex
label | 8a98cf86-cc08-55d7-8468-bcaf9e378074 |  | note | – – – – – – – – –
label | 69bbe9aa-aeb7-51d0-ac87-96e597080fa0 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 7013d01f-ac68-5814-977f-e99933e84175 |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 3bc206df-23aa-5f18-a97f-cc7285e75caf |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 068d404e-eb57-5047-ac62-8c206a4963bc |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | 2f069ec0-b602-52d3-bb84-5d8bddf39009 |  | note | ○ Expansion & Contraction:
label | de3a0032-36a8-5421-bfc5-dafb6b34d250 |  | note | +/- 3mm @ every 1000mm in length & height
label | 87e2703b-84b1-50b6-8a40-a6e24f88bae5 |  | note | – – – – – – – – –
text | 8b13b276-cea1-5d71-9ce8-80b2e3180a96 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 17985dca-f94b-5d25-b726-c1577ccc1ee4 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Connections (bolts/washers/screws) checked for damages
label | 38fb463c-4e57-5c8b-b0e6-2c5266a5a56f |  | note | Responsibility: Facadex
label | 4a9f54df-d1ee-5876-9e23-34e06ac22e80 |  | note | – – – – – – – – –
label | 677e4a83-2cff-5d07-9679-925fae9546e3 |  | note | Acceptance Criteria: Facadex sign off.
label | d0b1d2e6-cfe0-5321-bf0a-8eabce10ad9c |  | note | – – – – – – – – –
text | 33103e92-79e7-53df-86c4-472c6437ce13 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | c5ea2b83-7f9c-5889-b901-d7ed2de7c697 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | f73a52b6-078b-59d5-a715-3f3405f55cd6 |  | note | Responsibility: Facadex / Builder
label | 7d8cdef6-9e57-565e-ba22-1a5e1165a62a |  | note | – – – – – – – – –
label | 0fe48ec3-3ff8-593c-bff6-dc60e142bf71 |  | note | Acceptance Criteria: Defect notification via email or chosen correspondance
label | 3449ce20-2b41-5bf5-a2df-18d66257c561 |  | note | ○ Evidence of close out / rectification
label | 4592b1d0-238d-5472-a852-eee36230c4c9 |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | bf7521b3-14ac-571d-9e69-34c69eabc31b |  | note | ○ Sign off only once agreed that wall is defect free
label | 3a68cd72-1cbc-5da0-8f31-79b01a3fcb73 |  | note | – – – – – – – – –
text | e35239de-e0cd-5464-bd32-237fa0038fc3 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | b706439a-2594-5764-b4f8-36163f0427b2 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | 95917769-7c15-5c08-9d1d-b18a691b72e3 |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | 546d2b4c-9494-500c-a684-70d1dcd8ac87 |  | textbox | Foreman – Checklist Completed:
text | 04873a73-fb3e-5cb7-9c67-d35864ca45cc |  | textbox | Date / Time:
text | 67c2a9d9-0f50-5341-b706-ca5a4e7e9c6c |  | textbox | Coordinator – Checklist Completed:
text | 1e6381cf-b5cc-5c47-9c78-9ef3990c3c36 |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLD-200 3mm Alum Perf (Building D) - Factory ITP | itp |  |  |  | Yes | CLD-200 3mm Alum Perf (Building D) - Factory ITP | 27d92e09-9005-4069-bd6d-7363f33b7faf
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC shop drawings approved for fabrication
label | f8bf50c1-2b15-5fd5-8f2a-3eabc9cf41a7 |  | note | Responsibility: MPX
label | b03c096c-1cb6-5ff5-8859-e7d2b2df1713 |  | note | – – – – – – – – –
label | 151d1a2b-3637-58cd-836d-d7ed26969bc0 |  | note | Acceptance Criteria: MPX / Architect sign off
text | 7f87f976-c9d0-5d37-89a7-4a9856aabbe5 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | 03d79718-9762-58fe-be9c-e34451817fdc |  | note | Responsibility: MPX
label | 6f4c829e-da6b-574c-b7b3-1471219e4e27 |  | note | – – – – – – – – –
label | 903bbff7-2242-5735-abf3-7735a929fe8b |  | note | Acceptance Criteria: MPX / Architect sign off
text | 59a56de6-ec47-5c97-ba42-c9c5961ecd50 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check if the pattern is correct to IFC (5005-H34 alloy 51% open area)
label | 86ebb5d6-15b5-5ce0-9e83-34934c00da44 |  | note | Responsibility: Facadex
label | 56e9e15e-d39b-5f70-8d9f-70b7b72b0628 |  | note | – – – – – – – – –
label | 5608c646-b8fd-5079-9a11-b0f42924250c |  | note | Acceptance Criteria: Facadex sign off.
text | fc404b75-a954-56bc-9189-2c1b89b47681 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check if the stiffeners has been installed @450mm Crs
label | cdbbd51e-5253-5265-91ba-14bafe9dadeb |  | note | Responsibility: Facadex
label | 57e68927-5b73-5ba7-bb30-ed468720e0d0 |  | note | – – – – – – – – –
label | 56eef4a4-0e63-5274-8812-23edf0c73f47 |  | note | Acceptance Criteria: Facadex sign off.
text | 38906382-2c3e-5ded-81b2-c0384528f1bb |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Confirm and check finish as per approved IFC drawings
label | c2a46d80-5e34-542d-a9f9-eebc2cca5ee6 |  | note | Responsibility: Facadex
label | 4a35ea92-21b5-5891-bb53-73a8af7786a2 |  | note | – – – – – – – – –
label | 72c20cb0-8162-5bda-b3a9-ccf58d308bbe |  | note | Acceptance Criteria: Facadex sign off.
text | a73408e6-eee3-5504-bde7-2057594bf9ad |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check panel size and dimensions against IFC drawings
label | 94fe7068-b7ad-5506-a7df-63697b0cd6d0 |  | note | Responsibility: Facadex
label | 7d377b00-3ea6-51c4-a20c-05901f3eb887 |  | note | – – – – – – – – –
label | 5b9f8fe6-2bfd-5427-bfd5-15c1e68e6532 |  | note | Acceptance Criteria: Facadex sign off.
text | c46059eb-2fca-559b-8632-23fdca2e9d0e |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check diagonal dimension to ensure odd shape panel are done correctly
label | 368d83d1-6886-5e9e-9fb7-e15843b5e5a3 |  | note | Responsibility: Facadex
label | b510b8ec-16c1-5f18-9a99-e5ccec917631 |  | note | – – – – – – – – –
label | c31ef67b-1365-54f9-9516-aad369ef4e77 |  | note | Acceptance Criteria: Facadex sign off.
text | a7972fe3-871b-584c-be2d-d1d81ed1c70d |  | textbox | Date:
checkpoint-status |  |  | checkpoint | QA has checked delivery docket and receipt from powder coater
label | 6c3f064d-f5fa-5cfd-9c5e-c89b6272a2c4 |  | note | Responsibility: Facadex
label | c8617a7a-f0fa-51ab-8761-1a7cb5ed771f |  | note | – – – – – – – – –
label | b353d635-7cb9-5c36-aa5d-45521105446d |  | note | Acceptance Criteria: Facadex sign off.
text | 979e20a9-ef45-5331-8d3a-cf12bf18c121 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Is fabricated item labelled as per drawing?
label | 6750b502-a270-5d76-a50d-28de41fefe10 |  | note | Responsibility: Facadex
label | 34537b03-d047-55bb-a79f-b9bf9cf0af99 |  | note | – – – – – – – – –
label | 98391080-3a82-5f8f-b805-7ef396e74918 |  | note | Acceptance Criteria: Facadex sign off.
text | 23ca21ba-3212-52fa-a1c0-96c51a84e5a6 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Fabrication complete
label | 25718e8b-41fa-50d7-9f4c-a28b9c154e30 |  | note | Responsibility: Facadex
label | f3d46996-ea10-5255-b406-6a02c06e699e |  | note | – – – – – – – – –
label | a023b9a6-3ba2-5927-8a49-ba9228ac4f76 |  | note | Acceptance Criteria: Facadex sign off.
text | 9115af82-6c1f-5155-9886-d682eed6f6ac |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Prevent direct contanct between incompatible materials
label | 1d68643b-efa9-50bc-bc4d-a1b0cdf561c7 |  | note | Responsibility: Facadex
label | 040f123d-df86-52ad-887d-de947b957f24 |  | note | – – – – – – – – –
label | 167dfb12-ff1a-5bd6-8528-79219cf0f283 |  | note | Acceptance Criteria: Facadex sign off.
text | 0d0f30ec-8265-56c1-a089-c630edde138f |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Materials ready to deliver on site
label | 995709d0-0640-562c-87b9-805659a1058d |  | note | Responsibility: Facadex
label | ae6a1709-7c3a-540e-8690-f80fa81a3993 |  | note | – – – – – – – – –
label | e8208a89-65f5-54a6-8316-b67787bfe2fb |  | note | Acceptance Criteria: Facadex sign off.
text | 262c7313-281c-5872-b317-ff09586478ee |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | 5e21d3c8-02ab-5404-9450-354b77644691 |  | note | Responsibility: Facadex / Builder
label | 1ee0b60f-f446-563e-b3c7-34ed8507ba99 |  | note | – – – – – – – – –
label | 9c6491fc-903c-5cb8-ae65-9283d0963dca |  | note | Acceptance Criteria: Defect notification via email or chosen correspondence
label | d5ed8184-e420-571d-9aa3-e5d68ce22af9 |  | note | ○ Evidence of close out / rectification
label | 3553b29d-b308-551a-9ab5-6f56437ccfcd |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | 610ca791-0aca-5e6d-9b6a-5c888349b6af |  | note | ○ Sign of only once agreed that wall is defect free
text | 28968b59-2bdc-5ae3-8c11-8cbc226876b8 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | a29beb50-231c-5ab6-aa06-9a982b151b0d |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | 6eb18138-6929-58e3-8dc6-51b97eab0437 |  | textbox | Foreman – Checklist Completed:
text | e8a3822d-7a1a-5282-8efd-83639f848fdd |  | textbox | Date / Time:
text | 1f2a581e-8935-5cae-8a93-a4f33b1d6d39 |  | textbox | Coordinator – Checklist Completed:
text | 07ee9c03-1169-5696-bc42-6a2641204e26 |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLG-513 Steel Bracket Underside Site ITP | itp |  |  |  | Yes | CLG-513 Steel Bracket Underside Site ITP | 30255932-f682-4120-9939-0a0c103e689d
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC Shop Drawings Approved
label | c3240646-0f09-5f85-a0d1-78023cea3934 |  | note | Responsibility: MPX
label | eab55926-d48d-50ba-ad1c-3eaa3464c740 |  | note | – – – – – – – – –
label | 3581e9c3-9d73-5b4e-ade3-418d6c68b3b1 |  | note | Acceptance Criteria: MPX / Architect Sign Off
text | bb893e03-75a4-59d6-8ee9-d303f54377bc |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | 41740643-c5c2-55b0-943f-91e0fd81a5bb |  | note | Responsibility: MPX
label | db793fa8-5c4d-55f7-9882-dff9311e1f94 |  | note | – – – – – – – – –
label | 22b1da42-a669-50e3-9f5a-45332aff949f |  | note | Acceptance Criteria: MPX / Architect Sign Off
text | 8edda140-c7ec-5113-b0e4-d78398c2a106 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Materials (steel bracket/Bolts/Washers) delivered to site free of damage and deformation
label | 6dc7f246-35a8-5f60-b948-516a4f929bf3 |  | note | Responsibility: Facadex
label | 22021336-4ffd-5f7d-bdf2-1ee967186542 |  | note | – – – – – – – – –
label | 0da06665-520d-5798-b665-d10d7026ba74 |  | note | Acceptance Criteria: Facadex sign off.
text | cde514eb-39d7-5b9a-8d75-9581eb02574d |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Grid lines established and site set out complete
label | 3141c451-63b0-5722-b6a0-c06a92787217 |  | note | Responsibility: Facadex
label | 674ccd8b-7e32-54e5-8eef-0508d2007d97 |  | note | – – – – – – – – –
label | a193d8a8-23a2-5cbb-b9ff-5ad925030a1c |  | note | Acceptance Criteria: Facadex sign off.
text | 5ee77c2e-b520-55e7-9ebf-c7ff1b89d45c |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Bracket installed as per shop details and location
label | 008c8c19-3ac1-5156-9904-91e0c3990c78 |  | note | Responsibility: Facadex
label | f59a2c08-f67b-5fb3-be2e-1155669d3f22 |  | note | – – – – – – – – –
label | f7d3f57b-640b-5184-8253-99236fbf6b54 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 3e6a00b8-f03c-5c9a-9ef7-6850178a804d |  | note | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 05da79f5-1265-5c18-a4e1-703eae8b4e6b |  | note | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | ad2cb899-aa04-50c1-b5dc-b757c8c86762 |  | note | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | c4bcee52-942b-5538-9a91-84ddcc4e9e75 |  | note | ○ +/- 3mm @ every 1000mm in length & height
text | c8496123-acf0-54c6-9743-3d54f991e857 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | ensure the correct steel bracket has been installed to the desinated spot along the underside of the pre-camped brdige
label | 57b6b9b7-4639-5590-9654-84f6466e5a97 |  | note | Responsibility: Facadex
text | 4a36b8d5-8d94-5486-8644-85f69c6d9b96 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Ensure the steel bracket installed was not bended or deformed.
label | a7153638-595e-56fb-8ce1-cea794e8f537 |  | note | Responsibility: Facadex
text | c83bdaf8-fbf6-5b93-a347-e21fe6c5a5d7 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Connections (bolts/washers/screws) checked for damages
label | 3831a28d-98bd-56ca-bb33-3053628d3505 |  | note | Responsibility: Facadex
label | efc4b8bc-f46a-5440-a63b-9bc2ccb0bc06 |  | note | – – – – – – – – –
label | 588f4fdb-0aaf-593f-8a37-7dc8988b4fc2 |  | note | Acceptance Criteria: Facadex sign off.
text | 5ff0c521-fd50-59f2-aaaf-7b527903ad30 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | 4d0b34aa-9384-5d0b-8ad1-bc83cb0afeec |  | note | Responsibility: Facadex / Builder
label | bfca21eb-6d1c-5a01-866a-82209d584e13 |  | note | – – – – – – – – –
label | 6ee79ba6-a6ba-5738-b983-cf01b7de8648 |  | note | Acceptance Criteria: Defect notification via email or chosen correspondence
label | 7d59df8b-72a1-510e-be22-d34941753cc9 |  | note | ○ Evidence of close out / rectification
label | 29f6da8f-0841-54e0-88fc-c0a81edab474 |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | f8ed5e2e-48f9-5bfd-a9d4-5544d9f0c509 |  | note | ○ Sign of only once agreed that wall is defect free
text | 7c5441cf-7968-5ca2-8e15-e34fa7fe331b |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | 594507cd-3c62-558a-b1eb-c81b04be43c9 |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | 7a78ff3f-1769-5558-bebc-e2a431d0cc67 |  | textbox | Foreman – Checklist Completed:
text | 9824c467-4482-5cce-b499-98da71baf4d6 |  | textbox | Date / Time:
text | 260fdb6f-62e7-5b1f-b93f-ff12fdcdcef8 |  | textbox | Coordinator – Checklist Completed:
text | f4437b8e-dc5a-5e3a-9bf5-43d1b898ef02 |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLD-200 3mm Alum Perf (Building A) - Panel Site ITP | itp |  |  |  | Yes | CLD-200 3mm Alum Perf (Building A) - Panel Site ITP | 345a4aae-f81f-492d-a27c-657fed9fbd13
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC Shop Drawings Approved
label | f4ab4d75-6394-5326-9c26-1ba5e4ccba27 |  | note | Responsibility: MPX
label | 5d5dfcec-2481-52d5-8569-f4fb3e07eddc |  | note | – – – – – – – – –
label | d6fb6299-b064-5da5-9ead-cd4b51d4b5e2 |  | note | Acceptance Criteria: MPX / Architect Sign Off
text | 9cca61ce-329a-5b8b-9d6d-f9322954cf72 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | da279f25-f984-516c-9d21-80dbd65bd8c4 |  | note | Responsibility: MPX
label | 1841efa9-1d5b-50e7-961b-3fef0cda4731 |  | note | – – – – – – – – –
label | a096e1fe-c797-52ee-9ff5-4e30f7bfc6a6 |  | note | Acceptance Criteria: MPX / Architect Sign Off
text | 72f289c3-97cc-5454-80a3-1628438d588a |  | textbox | Date:
label | 508c0e46-bb4d-552e-bb8a-8e3029f62ca6 |  | note | Comments: Check colour is correct as per shop drawings
checkpoint-status |  |  | checkpoint | Module (Panels/Bolts/Screw/Washers) delivered to site free of damage and deformation
label | 35ce1de9-d772-5bb3-97aa-19f4ee3374d4 |  | note | Responsibility: Facadex
label | ff217c1e-c335-5156-90f1-e662c03d8bff |  | note | – – – – – – – – –
label | 5943410d-dfe8-5e60-8eaf-427c18ef6b93 |  | note | Acceptance Criteria: Facadex sign off.
text | 80998a02-3484-5c4c-8ada-5ecda53622c0 |  | textbox | Date:
label | 89a28454-a3f3-5226-8587-9315757ed1f3 |  | note | Comments: Check colour is correct as per shop drawings
checkpoint-status |  |  | checkpoint | Grid lines established and site set out complete
label | ba6b2fd1-24e6-5989-85e6-cae1aee7fa4b |  | note | Responsibility: Facadex
label | 3a837202-8cd5-5872-9204-10d00ec71493 |  | note | – – – – – – – – –
label | 0a6ac76d-0554-5496-bdb7-c65df60d9ea5 |  | note | Acceptance Criteria: Facadex sign off.
text | 3d36e47b-29a5-5036-88b5-c3c1fff2af7d |  | textbox | Date:
label | ab04cb72-7cc8-54b6-9326-eb753dda4261 |  | note | Comments: If installed off site no gridline available
checkpoint-status |  |  | checkpoint | 250x50x6mm Alum angles spanning at the back of the module has been secured and fastened to the L brackets for haning the module.
label | 1205af6b-8774-579f-a97b-b2d7492e21fb |  | note | Responsibility: Facadex
label | 2e7a89f4-cb1d-5fc0-8918-eb14568ec4ca |  | note | – – – – – – – – –
label | 15272ebd-483e-57cf-8e9f-b14b23403d87 |  | note | Acceptance Criteria: Facadex sign off.
text | 528a5a25-f258-5b7f-912e-2bb4c11de8a8 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | ensure the 40x40x3mm SHS horizontal rail 450crs fixed to the C channels at the back of the module
label | 0737ae92-9996-5dd9-ad8e-2fd3cced0f5a |  | note | Responsibility: Facadex
label | 13c98a9b-d6c3-559d-9bf6-8204d6b58a2b |  | note | – – – – – – – – –
label | a4bbb378-63fc-5789-8d35-f6d1bb327337 |  | note | Acceptance Criteria: Facadex sign off.
text | c067a48a-6889-5794-8643-91ae4ace1c2a |  | textbox | Date:
checkpoint-status |  |  | checkpoint | ensure the Subsill has been installed with the support 250x100x3mm alum angles at the bottom.
label | 860da244-4c08-5980-be30-15dbe640ff45 |  | note | Responsibility: Facadex
label | d1321e42-4173-55ad-afff-5c31b4c17e35 |  | note | – – – – – – – – –
label | ffc817f5-1fce-5c84-8d34-d510563b5417 |  | note | Acceptance Criteria: Facadex sign off.
text | 83873b29-8b99-57c4-aa80-05ffd0b3aa2a |  | textbox | Date:
checkpoint-status |  |  | checkpoint | bottom Shelfangles chemset fix to concrete slab has been installed for the module to be sit on where ther is a louvre behind.
label | 653b566b-c54f-52db-83d3-ccf4db0ce6f6 |  | note | Responsibility: Facadex
label | cc5e5309-33e3-5f3b-b9ed-5851639c344d |  | note | – – – – – – – – –
label | f696a5e3-9920-5d27-bd14-ef48287e3997 |  | note | Acceptance Criteria: Facadex sign off.
text | 0b59d941-bcdb-5f52-8021-ba699a29e518 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | 0.48BMT colourbond flashing has been installed for the weather proof to IFC
label | 34f874ea-51dc-51e5-a815-09249ed265d5 |  | note | Responsibility: Facadex
label | fd680ed0-aeb1-500f-bf77-5e883550e776 |  | note | – – – – – – – – –
label | c9e61c20-f3b2-5005-b557-a4dad8a69c05 |  | note | Acceptance Criteria: Facadex sign off.
text | 9d2ebadb-d85e-5a80-99b2-724e954abea4 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Perf with CW frame Panels checked for paint scratches and dents post installation
label | 93a5985f-ca51-5b97-a5a2-cb934cf33afd |  | note | Responsibility: Facadex
label | 7db5645b-6f6a-54bd-8973-0b05f97f0a73 |  | note | – – – – – – – – –
label | 56568620-acb9-551e-9d33-57bd433d7252 |  | note | Acceptance Criteria: Facadex sign off.
text | d10d724a-6d9d-51f1-b0c5-36a2a198bfc0 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Perf Cladding Panels installed to IFC specification
label | b9d8eb28-db73-50b9-b317-fa6af7bb78bc |  | note | Responsibility: Facadex
label | 15e062f5-21bd-519e-8e8d-1f6c72810b99 |  | note | – – – – – – – – –
label | c5daf57f-c3c0-5187-90c1-dd8903ebe6fa |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 190e1a9a-9e20-5f44-b260-47cf6ccc7db8 |  | note | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | f8878921-fa12-52dd-bd0b-ead563f6342b |  | note | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 1b265d6f-ca5a-52f1-9e19-b59d3871f3bd |  | note | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | cf2e8038-38aa-5aec-bba4-099c63c0ce72 |  | note | ○ +/- 3mm @ every 1000mm in length & height
text | 88d5e56a-bdc7-5a64-b2b2-f4cfedc4f7e0 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Connections (screws/rivets) checked for damages
label | a463d86c-9b96-5f9b-9da0-94cb068f6249 |  | note | Responsibility: Facadex
label | 13de1d3e-9aa3-571a-b35f-ff3e2ffe16bd |  | note | – – – – – – – – –
label | 07311e01-41a7-54ae-9fbc-f28d9fa61b3e |  | note | Acceptance Criteria: Facadex sign off.
text | dac4340c-7fc7-512b-b90a-b932d2286af8 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | e311379a-c65c-5948-877c-4b8413c46358 |  | note | Responsibility: Facadex / Builder
label | 470ef818-555f-5360-bc07-59f54856f4f2 |  | note | – – – – – – – – –
label | 71eb22a8-f9ae-56c7-b66e-6ea3db2fbeff |  | note | Acceptance Criteria: Defect notification via email or chosen correspondence
label | 6f403562-3484-5770-b13c-5ece17ebf7a1 |  | note | ○ Evidence of close out / rectification
label | bdb490e9-6fcc-5bdd-9768-05c96d38fc10 |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | ebaa6e34-961b-5093-b480-e39e7ca2210b |  | note | ○ Sign of only once agreed that wall is defect free
text | f8683e0b-7cbd-5812-b39e-1579c5f9dc9d |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | 7e1dd82c-3253-5a79-89cd-d2f34c5c715d |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | 78c454bb-50a8-5d99-9c44-cf508e17af52 |  | textbox | Foreman – Checklist Completed:
text | 8b38e696-0e6a-5f3e-842f-be5d710947df |  | textbox | Date / Time:
text | 09ea512b-e9f6-5784-aa8a-9f2ea2357973 |  | textbox | Coordinator – Checklist Completed:
text | 5960b02f-a7e9-5b19-911f-a9c006131023 |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLD-200 3mm Alum Perf (Building E) - Subframing Site ITP | itp |  |  |  | Yes | CLD-200 3mm Alum Perf (Building E) - Subframing Site ITP | 3743c2bd-dc1e-48f2-bc0a-90e7189bc914
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC Shop Drawings Approved
label | f7add9f9-759e-5bb9-9b47-7b3cd5f6b1a6 |  | note | Responsibility: MPX
label | c1b90234-b65b-51fd-9842-b6c563c408cb |  | note | – – – – – – – – –
label | abdb5412-497d-5e10-b679-f969a8c79fc0 |  | note | Acceptance Criteria: MPX / Architect Sign Off
text | 0b38231a-c0de-508c-a352-1046e90477b6 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | e2211220-2d93-5b79-8556-c008297655b6 |  | note | Responsibility: MPX
label | 95b970b9-50cc-5b7c-a9e5-4dfb9ea070ae |  | note | – – – – – – – – –
label | 24f0d316-bd8a-5adc-9b93-44fb8bb9d24c |  | note | Acceptance Criteria: MPX / Architect Sign Off
text | 6f68c1a2-fcc6-5235-8ae0-ecd312ad8379 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Materials (top hat/screws) delivered to site free of damage and deformation
label | a8c8a14b-9588-5fae-b662-e654086d4039 |  | note | Responsibility: Facadex
label | 67ec60fc-0653-5f95-a178-445c40f900fb |  | note | – – – – – – – – –
label | d0e4e265-02d5-5e70-ad8e-98df50568a8c |  | note | Acceptance Criteria: Facadex sign off.
text | c47881e2-002d-59dc-bd22-e7cb5d6cfb5d |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Grid lines established and site set out complete
label | 9b8761ec-a8e8-538a-ab7d-9c9e74985ce5 |  | note | Responsibility: Facadex
label | a21f81ee-6883-581e-a680-b2566932a9b9 |  | note | – – – – – – – – –
label | 37033f78-360c-5938-bc69-e70a3ccd6850 |  | note | Acceptance Criteria: Facadex sign off.
text | e510ebdb-4697-5927-9912-549e1cd99394 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | 75x254x75x3mm thk folded Z has been set out and installed to steel purling @1500 crs and fixings @900crs as per IFC
label | 9493d750-316f-54aa-a80e-4f10559832df |  | note | Responsibility: Facadex
label | 47681b08-1530-5179-a7bd-91a6a531cd8c |  | note | – – – – – – – – –
label | 4f130b90-0690-53b9-87c8-873ec525e4a2 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | cedc4d9f-d73a-52ff-9e3d-67f4a1e2c36d |  | note | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 4db2eafa-b6bc-58ee-81a3-50e0ea716ceb |  | note | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 828dd395-19b7-5a7b-98d5-4873af4dc26c |  | note | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | 6326261e-804e-5c73-b7d9-a2a3f8376f46 |  | note | ○ +/- 3mm @ every 1000mm in length & height
text | 5cc267c6-4d3c-54c2-b4ca-a980830444ed |  | textbox | Date:
checkpoint-status |  |  | checkpoint | 50x50x3mm alum SHS/EA horizontal has been set out and installed to vertical folded Z with #12 tek screws@600crs
label | b58248a1-76bc-5f0a-8add-b9af0731e2dc |  | note | Responsibility: Facadex
label | dadf9198-9456-599b-8243-5c05b3738f1c |  | note | – – – – – – – – –
label | 0997ba6d-b2dd-5a86-a23f-49d026514f2c |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | deff8859-28ed-5140-b78b-638773480581 |  | note | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 56f75fa2-2d08-52e0-a54f-aa38d943bcb2 |  | note | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 77ba9ba0-e7dd-5f9f-842a-899be66cfbd3 |  | note | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | 5a4f0bbf-1d9e-5fcf-86c9-e4128b33f26f |  | note | ○ +/- 3mm @ every 1000mm in length & height
text | 15e74009-cf5c-54c0-bff3-78ba815934c3 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Packers has been used to ensure the subframe is plumb for perf panels to be cladded on.
label | 7a21f397-e152-5545-82f2-ea3c910bb735 |  | note | Responsibility: Facadex
label | cfa42279-3579-57f1-a688-5fd47dc34eec |  | note | – – – – – – – – –
label | 43c7e4d0-6b41-5782-84e5-5b8ba6c34bc9 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 2a25d86f-515d-58f6-8a31-2ea1917e8fe0 |  | note | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | f993950e-04b6-5722-b8b1-e72ecd64e61d |  | note | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 6e78ab74-f15d-58bd-9123-6202fed0771b |  | note | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | 96533962-589b-5caf-a396-a843fc1ce25a |  | note | ○ +/- 3mm @ every 1000mm in length & height
text | 031cd790-3cfe-5958-8dcd-9def3924c52b |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Connections (bolts/washers/screws) checked for damages
label | d2afa7fc-46d0-5f37-9bce-a385a438e04e |  | note | Responsibility: Facadex
label | 0a11bc77-4dc4-53fa-8452-c513c59662fa |  | note | – – – – – – – – –
label | e05384f5-6487-5925-ad2c-8eafd357c57f |  | note | Acceptance Criteria: Facadex sign off.
text | dd06f637-2dfa-5f55-8625-03cc339fe070 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | c53acbe4-2e60-5f7a-ac73-766616ed38a8 |  | note | Responsibility: Facadex / Builder
label | bb1b0191-9bdb-5f32-8a16-15f1a215be82 |  | note | – – – – – – – – –
label | 57cccb83-64bc-5369-ac84-59c45bc8b3a2 |  | note | Acceptance Criteria: Defect notification via email or chosen correspondence
label | c127771d-0f70-5908-8ec9-32ac47bbe36e |  | note | ○ Evidence of close out / rectification
label | d4e98443-90d6-5148-a34e-a801cc97eba3 |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | e29ae4f0-bdbd-594f-8c3c-6506cb3052d5 |  | note | ○ Sign of only once agreed that wall is defect free
text | a984cb38-1ad7-55dd-8c33-28d0f8a1af42 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | 73c35db8-4c80-5e2f-ab2f-e33d13f33437 |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | 6c159c1f-d5ca-5f08-870c-8f2e15d1bf07 |  | textbox | Foreman – Checklist Completed:
text | 5fe92dc3-27ba-5c5e-b190-e0c4844761c1 |  | textbox | Date / Time:
text | e7135ae5-4d61-56c1-add2-f718c474c8b3 |  | textbox | Coordinator – Checklist Completed:
text | 6ffff697-cb9e-5360-950f-a9faa97cc72c |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLG-514 Steel Bracket Underside Site ITP | itp |  |  |  | Yes | CLG-514 Steel Bracket Underside Site ITP | 3d078879-0289-4c39-b64c-5e26861ea934
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC Shop Drawings Approved
label | 446929ec-207e-59b9-a75b-4981ade028d5 |  | note | Responsibility: MPX
label | a846ad6f-59b3-585e-b89f-cfd2995ea844 |  | note | – – – – – – – – –
label | 731eb317-4f80-534c-8382-d8a5dd75b1d6 |  | note | Acceptance Criteria: MPX / Architect Sign Off
label | 054d0dd8-dcba-5406-a7b1-1306fdae3f36 |  | note | – – – – – – – – –
text | 2586f405-74e6-599b-8a42-bd7476124dae |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 471f77b0-0fac-5db8-9f8c-4a4a376ca753 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | 4703acc6-391a-58e4-a072-fe11698ac9ec |  | note | Responsibility: MPX
label | 3dfa898f-e30e-59f9-b597-bacea8ed62a4 |  | note | – – – – – – – – –
label | 22108652-d564-50eb-aee8-826406fa1add |  | note | Acceptance Criteria: MPX / Architect Sign Off
label | 0ca97ff6-cfd2-5690-a06c-f944bd6f007e |  | note | – – – – – – – – –
text | e4735e44-f793-5b88-89a9-37056dd63d6f |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | caa3d915-459f-5b96-a97a-87969dac0b5d |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Materials (steel bracket/Bolts/Washers) delivered to site free of damage and deformation
label | c38aab59-a336-56e6-aed7-68903d235a46 |  | note | Responsibility: Facadex
label | 1e269b30-e967-5cd5-bc47-c15cbcfb5831 |  | note | – – – – – – – – –
label | 29b444ba-add5-5f9b-8716-82c5bd20f5f3 |  | note | Acceptance Criteria: Facadex sign off.
label | 0afcb73f-4181-596e-a755-f14eea67e934 |  | note | – – – – – – – – –
text | d5753630-14e7-5c49-8cde-461e6893ac17 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | c2b8e71b-15ef-50b7-80d8-28287fa9f84b |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Grid lines established and site set out complete
label | a060f5e9-c701-5197-bf89-4232bc44d131 |  | note | Responsibility: Facadex
label | d482558e-2b0f-5054-bf02-ac35df439adb |  | note | – – – – – – – – –
label | 1795adbc-d09e-5fce-a25b-bd5f2a377e37 |  | note | Acceptance Criteria: Facadex sign off.
label | 4cda1194-033a-5dcf-ad98-c93ba7a89619 |  | note | – – – – – – – – –
text | 37e160d1-5c93-5fcc-96bd-068f62dc9606 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | ae614639-9df8-589f-ad44-542268f09527 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Bracket installed as per shop details and location
label | 3a7440b3-c235-5e52-b25a-626474e238d9 |  | note | Responsibility: Facadex
label | b946e7f8-1fbd-5758-96b8-cf4cb44482f9 |  | note | – – – – – – – – –
label | 33859a26-e662-518b-9558-022d70447ca9 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 238eae00-416f-58de-9faf-5a84a7d5c09b |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | d08b79cb-721e-562d-ac53-cb45ed682e64 |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | cb0ced9d-baa3-5fba-80f6-5ae1bccc94be |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | fdce1ccb-bf6b-5646-b114-d1acace66ed5 |  | note | ○ Expansion & Contraction:
label | 24d3f3db-3d55-5adf-af70-07bdf0f19d5c |  | note | +/- 3mm @ every 1000mm in length & height
label | afec86cd-3f19-56ac-b505-910e0ed9b3f5 |  | note | – – – – – – – – –
text | 879889fa-00dd-580d-96bb-55ef6f006da2 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 12fb507f-50f7-5cc9-ba37-d598312b8e85 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Ensure the correct steel bracket has been installed to the desinated spot along the underside of the pre-camped bridge
label | f8deef29-e2d7-5c60-b3fd-9300c3dd4d14 |  | note | Responsibility: Facadex
label | e281e2f9-9839-5b91-aadf-ab3e8ae6a813 |  | note | – – – – – – – – –
label | 90a9f066-eed3-5f67-b578-46cbf3b5d5a6 |  | note | Acceptance Criteria:
label | 576124df-4b3a-5953-a5b4-fee89cf1b28f |  | note | – – – – – – – – –
text | f7b05487-16af-50d9-a521-ec5d4ef5d50b |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | c4d748d8-e0a8-5c52-a250-e4ed7c6518a6 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Ensure the steel bracket installed was not bended or deformed.
label | 9da162dd-2ef0-5043-b2af-94b5669f4f8a |  | note | Responsibility: Facadex
label | 51aa664b-b018-538e-a0b2-87c5919ce540 |  | note | – – – – – – – – –
label | 0c9ffbff-e3da-568e-932f-7432fb267829 |  | note | Acceptance Criteria:
label | 70bc710a-e37d-5d4c-9604-4cfc9fc9bb93 |  | note | – – – – – – – – –
text | 41d3859e-71b4-5d37-a049-08f7dbee44aa |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | b4339ebf-8a72-58c3-9914-5d3348439ee0 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Connections (bolts/washers/screws) checked for damages
label | 17fede8f-98b1-577a-9066-81cd12f2596b |  | note | Responsibility: Facadex
label | 25fb70b4-4e49-531c-a0ec-6f729f7342d1 |  | note | – – – – – – – – –
label | 8bba2961-c05e-537c-bbea-a71269e8acda |  | note | Acceptance Criteria: Facadex sign off.
label | 24bd7d45-3714-59d2-a944-d54e0db1c290 |  | note | – – – – – – – – –
text | a152a6de-3626-5131-907c-8a2b5b2dab39 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 89106cfa-cf74-5bf8-bd2e-1e33a8759c50 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | fbf2299e-04e0-5848-a683-66e3e294828c |  | note | Responsibility: Facadex / Builder
label | b4520626-12fd-54d5-b54a-fe3bb2ddca34 |  | note | – – – – – – – – –
label | 609e6090-d775-59ab-9aa0-b49b47fabc01 |  | note | Acceptance Criteria: Defect notification via email or chosen correspondance
label | ace08c4c-14ae-50f8-8958-bf08d9a66fda |  | note | ○ Evidence of close out / rectification
label | e9cb2343-f464-5e9b-a9a0-5b0b117008fe |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | 47c2026e-3650-50e6-9bd9-dd0d37d095bd |  | note | ○ Sign off only once agreed that wall is defect free
label | e34b48b4-8ab0-514e-9156-d948486b4969 |  | note | – – – – – – – – –
text | 216eb731-bab4-5668-bddb-b39f460d0169 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 8f3c632e-3b6f-5aec-85b9-ed0151904ae1 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | 1fc3e133-9d31-57c5-902b-bf91f2353b1b |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | 38d322a9-24f5-55ba-8d7a-d5367fecdc23 |  | textbox | Foreman – Checklist Completed:
text | d512c136-19af-5221-b244-f9234c7d7738 |  | textbox | Date / Time:
text | 11611a57-271c-5bab-a228-77c42ffe2aa3 |  | textbox | Coordinator – Checklist Completed:
text | dec1d809-7db8-5295-91a3-e7aa4b4a9843 |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLD-214 Lysaght Spandek - Cladding Building E Panel Site ITP | itp |  |  |  | Yes | CLD-214 Lysaght Spandek - Cladding Building E Panel Site ITP | 4da68964-d0f6-4a43-8b7c-45538d8e23ea
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC Shop Drawings Approved
label | bcf9600b-e06a-5c8b-9a05-82f80f9604c3 |  | note | Responsibility: MPX
label | 1c7f1a52-ae7c-5980-ba22-df953902c1cd |  | note | – – – – – – – – –
label | dc3dbf33-c3e0-5771-8fff-edbc4a6459aa |  | note | Acceptance Criteria: MPX / Architect Sign Off
text | 6715e569-249e-5bfa-b463-3256656efb05 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | cfbf43ec-8477-5d75-b35f-d16f90f7f9d1 |  | note | Responsibility: MPX
label | cddab6d3-4de3-5512-be0c-6b771ecb62c8 |  | note | – – – – – – – – –
label | 188e4688-40b1-5945-9ac9-a0a72345b9a2 |  | note | Acceptance Criteria: MPX / Architect Sign Off
text | f9783f88-23b6-5c75-bdc8-581356f28f6b |  | textbox | Date:
label | 52a6fd1d-8e57-5da0-871b-9aedeed0f079 |  | note | Comments: Check colour is correct as per shop drawings
checkpoint-status |  |  | checkpoint | Materials (Panels/Bolts/Washers) delivered to site free of damage and deformation
label | 566d6639-2bd4-5a2f-9860-526ae29ed279 |  | note | Responsibility: Facadex
label | 1238b031-09e2-50ca-be25-c483d7a461e5 |  | note | – – – – – – – – –
label | 5c01bee3-4eab-564a-8e61-a03ca4ac48d3 |  | note | Acceptance Criteria: Facadex sign off.
text | d49e66a9-b28d-598b-a09b-4bc1d148c593 |  | textbox | Date:
label | 685db40e-500b-5146-b5db-24ba0726ee3f |  | note | Comments: Check colour is correct as per shop drawings
checkpoint-status |  |  | checkpoint | Grid lines established and site set out complete
label | 367c3985-c769-59f6-bd92-660cbb062a30 |  | note | Responsibility: Facadex
label | 6907025b-82c1-54c1-b036-da6feaebe3aa |  | note | – – – – – – – – –
label | 69d34d03-01f4-5d83-acb8-19ca23d6a15d |  | note | Acceptance Criteria: Facadex sign off.
text | 5ca2b9f1-7d51-5a14-a878-8a2cb0e9baf3 |  | textbox | Date:
label | f276063a-aa18-59d2-a475-1ef5acb72f8a |  | note | Comments: If installed off site no gridline available
checkpoint-status |  |  | checkpoint | Cladding Panels installed to manufacturers specifications
label | 615537d7-6623-5601-b1c2-dfe25a864c21 |  | note | Responsibility: Facadex
label | 39ccbd35-29ac-562d-a477-6f2070916ba6 |  | note | – – – – – – – – –
label | 4e9a1ec3-f6e7-56d7-b5d1-948a634ee02f |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | ddc1d765-2390-5dbf-8161-d617498b0a4c |  | note | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | fe9eaf7b-194e-55d8-b022-7cff536fcb2f |  | note | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 6259e773-5a9d-51f3-98aa-fd7c7e4ac2fc |  | note | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | 6551bd53-f921-5576-bc9a-0aad386fb2b3 |  | note | ○ +/- 3mm @ every 1000mm in length & height
text | 46c8a8d6-c81d-56eb-a392-997ca48dc38f |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Cladding Panels checked for paint scratches post installation
label | e8750be4-e657-5bf4-a89a-aa9813163dfa |  | note | Responsibility: Facadex
label | 4b807a8c-69b6-5cf2-9e56-816b52e1e226 |  | note | – – – – – – – – –
label | 41e0ca57-5acf-5cfc-9eb0-f96447743a2a |  | note | Acceptance Criteria: Facadex sign off.
text | fef52879-26c7-5466-996e-30767044f296 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | 0.55mm colorbond flashing has been installed to the gap to the strcutrue
label | 35b8d9e4-f999-5e34-b34f-7e62abd9138d |  | note | Responsibility: Facadex
label | 359b4b3e-dc7e-5908-abfd-f3064c1c9f43 |  | note | – – – – – – – – –
label | dd51a17f-c580-55b3-bbe6-e0e8564bdd10 |  | note | Acceptance Criteria: Facadex sign off.
text | d2e4648d-d1cb-511a-9240-2eb6fbda46e0 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Connections (bolts/washers/screws) checked for damages
label | 22d3f10f-ab22-58b4-badb-3609064224c8 |  | note | Responsibility: Facadex
label | c0a91032-a42f-5478-8620-024a7da0503d |  | note | – – – – – – – – –
label | e04139cc-81d6-5701-a519-eeff7178b047 |  | note | Acceptance Criteria: Facadex sign off.
text | c75db587-f8ae-588a-b59b-02ef59d50315 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | 53b356fb-3ebc-5fde-a659-c55ccb05b386 |  | note | Responsibility: Facadex / Builder
label | 19da8aec-8754-5816-9809-5450cffb186c |  | note | – – – – – – – – –
label | a61ab95a-dc0d-5dad-beae-c16addfe5108 |  | note | Acceptance Criteria: Defect notification via email or chosen correspondence
label | 817e7288-448d-5234-8909-812ae3788046 |  | note | ○ Evidence of close out / rectification
label | b17cd0c9-e5fc-5c8a-991b-c8fa48897bc5 |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | 2169f057-f8f5-58d8-ba99-0001c0126256 |  | note | ○ Sign of only once agreed that wall is defect free
text | 9b6f19e0-761c-547a-b5a9-ee5d6002e567 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | 82611b21-73ae-5b50-a6d9-a3774b9f6d96 |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | e4bfcbec-6979-5930-8b6a-2e82d9225a2b |  | textbox | Foreman – Checklist Completed:
text | c0539f09-1b02-55e7-a57d-0ca3caae8c7c |  | textbox | Date / Time:
text | e46c2043-c782-5dc1-ba54-0837fcda32c0 |  | textbox | Coordinator – Checklist Completed:
text | 7a11e27c-90cf-5721-b236-6fcc32eae561 |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLD-214 Lysaght Spandek - Cladding Building D Factory ITP | itp |  |  |  | Yes | CLD-214 Lysaght Spandek - Cladding Building D Factory ITP | 4db75297-b146-4025-b6e8-00952c913ad0
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC shop drawings approved for fabrication
label | a9a66e95-c9fa-5908-ab13-7265e213e731 |  | note | Responsibility: MPX
label | 2670cf60-7b2a-5baf-8718-a8ccacd43967 |  | note | – – – – – – – – –
label | 53b49f38-b5c1-5430-b6e8-8c396331e5dc |  | note | Acceptance Criteria: MPX / Architect sign off
label | f6512159-0a54-5b30-bba5-9fff542de793 |  | note | – – – – – – – – –
text | 1f6828db-2b4c-5d2c-8f4e-89d05729a77f |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | c7d5213a-1eb3-5791-b18e-06e74e1c30fe |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | 9632c11b-6979-57aa-bfb3-a0f986af9816 |  | note | Responsibility: MPX
label | bdd74657-de38-5fa1-a41d-68fb98230878 |  | note | – – – – – – – – –
label | d8b20b01-8df3-54ae-8507-cf2b9b8d3fa4 |  | note | Acceptance Criteria: MPX / Architect sign off
label | 8bfb0605-588b-5c4d-9f2d-c98e460e656a |  | note | – – – – – – – – –
text | 7d79ffe9-ddd7-5fc4-99c6-762d37dff13d |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 1a933552-38f6-5ee7-8452-1f21f38d4058 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Confirm and check finish as per approved IFC drawings
label | 0bc3fe8e-1f2a-5d7a-a305-11c48a005d79 |  | note | Responsibility: Facadex
label | 7d8f54c3-f5d6-50de-806b-a36de2013aa0 |  | note | – – – – – – – – –
label | 4914d361-9f83-5c21-94b1-b757a2bbbcc1 |  | note | Acceptance Criteria: Facadex sign off.
label | e83b4e71-ebd9-5428-8168-9c732ab714ba |  | note | – – – – – – – – –
text | 9f565e2d-c408-5aad-8752-db553ef9cc29 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 06b2286d-4028-5462-b5bd-2264e93d5e49 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check panel size and dimensions against IFC drawings
label | 516e4076-a3f5-53e7-b1d6-37bd54d18f20 |  | note | Responsibility: Facadex
label | 3f8f7461-69a6-562b-a3be-d32cf8e1cfef |  | note | – – – – – – – – –
label | 46b3e7ec-52f7-52a9-8bc3-2db45e102c6c |  | note | Acceptance Criteria: Facadex sign off.
label | d449f378-52c9-5325-a9af-df38bf61b2cb |  | note | – – – – – – – – –
text | 791b4ad9-8e88-5bf6-b029-dae931b0c6d5 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 6e7b76b3-04e5-589e-9d14-bb6c642ecf88 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check diagonal dimension to ensure odd shape panel are done correctly
label | 56d6ecb6-1747-5441-8323-88650be6ec30 |  | note | Responsibility: Facadex
label | ac281623-d9bd-5c11-a8d0-e2ced8edfe1e |  | note | – – – – – – – – –
label | 542c1218-3f90-55a2-8a50-e9ac1f283ef9 |  | note | Acceptance Criteria: Facadex sign off.
label | 33b4205e-192f-5ad6-aa4b-d3d71f3dc9ca |  | note | – – – – – – – – –
text | 513605ca-cc0b-5bc7-85f2-16f9be85f84a |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | e6edcfd6-356a-52f0-8cb3-b42f09f61002 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | QA has checked delivery docket and receipt from powder coater
label | 9b739235-ddff-5c00-acd4-3d62cea5814b |  | note | Responsibility: Facadex
label | 688a2c46-b905-59ce-8156-34ba133f174e |  | note | – – – – – – – – –
label | 8743858e-f797-5ca9-9548-b63bdda6e830 |  | note | Acceptance Criteria: Facadex sign off.
label | 1eeeae14-87b4-5278-866c-019de20d68f2 |  | note | – – – – – – – – –
text | 166a798f-b5e8-5cd6-a61a-ab4d06f2013c |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 89815d83-92fe-5f8b-9388-bbe781a2988a |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Is fabricated item labelled as per drawing?
label | 54fba689-f54c-5709-9bed-c430a7688b44 |  | note | Responsibility: Facadex
label | 5b0372b9-f9a6-5a9e-b8e1-f69e04a378ce |  | note | – – – – – – – – –
label | 0b6348a2-88f6-5caf-9fb4-623b594c54a2 |  | note | Acceptance Criteria: Facadex sign off.
label | e8600f6a-0f6f-584a-9fe2-c9a3229f6b4e |  | note | – – – – – – – – –
text | 4348d698-f27e-5a64-8b98-16f12647512d |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 6406c432-1941-5865-8f27-6c1e6c28da7c |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Fabrication complete
label | 82c13036-b0be-5cde-b00e-ad29be664813 |  | note | Responsibility: Facadex
label | 23bd7dd1-227c-5e34-ba58-2e22901bf38f |  | note | – – – – – – – – –
label | a4ac351e-465c-528d-bd19-1be7e3b67156 |  | note | Acceptance Criteria: Facadex sign off.
label | 807317d5-abae-54f5-a3f9-a45a53726ab6 |  | note | – – – – – – – – –
text | 319a0117-5468-591b-bbc0-832549afdb25 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 70209290-f1be-5445-b72d-d158ef34bdc7 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Prevent direct contanct between incompatible materials
label | 27948ffe-0ee3-5ae3-96a2-e4ffc6f8fbff |  | note | Responsibility: Facadex
label | 39b54c95-bdc4-53f7-a8a0-dcbf26e586a8 |  | note | – – – – – – – – –
label | 58564756-ddb8-590f-9624-ae526143c26b |  | note | Acceptance Criteria: Facadex sign off.
label | 14a5ea5b-0f70-5fcf-b0cf-06775818a362 |  | note | – – – – – – – – –
text | 33e6af0a-450e-5392-9273-55a9d1ab51d7 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | e7554545-612f-5b54-b0b0-389a2d19c101 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Materials ready to deliver on site
label | 325c165c-92d9-5095-a728-83d6457d9eab |  | note | Responsibility: Facadex
label | 81161f0f-d162-52b7-8ece-91c952d54089 |  | note | – – – – – – – – –
label | f2c5956e-51c0-5ea1-9494-517eb4757497 |  | note | Acceptance Criteria: Facadex sign off.
label | ce4d00bd-13aa-5fc7-af63-ff177239bd16 |  | note | – – – – – – – – –
text | b470e367-8238-5850-b490-1fe155152554 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 47f19f10-329d-53b6-af1b-25addf7834c4 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | 51fe6c08-1ef6-5154-810f-8fbc09068d48 |  | note | Responsibility: Facadex / Builder
label | d9822551-7753-5385-80ff-de961cad0bcd |  | note | – – – – – – – – –
label | df5259f0-2d3c-5916-9445-2a806effb4b0 |  | note | Acceptance Criteria: Defect notification via email or chosen correspondance
label | ae6f1d72-ba39-5d05-b0bf-6c4f5cbb0fed |  | note | ○ Evidence of close out / rectification
label | ff38436b-99f4-503e-bacc-6e6cfcc7b3d8 |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | d7d8571b-8cf3-5c88-a098-fee8ec3e9fc8 |  | note | ○ Sign off only once agreed that wall is defect free
label | 73cb7ca3-6c35-5f43-a901-9c902a186353 |  | note | – – – – – – – – –
text | 2f416b78-3ca0-5a28-80da-33a131a40e89 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | c13326a2-cef0-56bb-b962-12232c359f67 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | b0588c1b-3861-509d-82d5-0f40fcb2c8f5 |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | 1f1003eb-1a50-5b42-95ad-9529456ac2e9 |  | textbox | Foreman – Checklist Completed:
text | eb69e2d8-aa19-542f-add7-ecda0c7b03c5 |  | textbox | Date / Time:
text | 7e218d16-c695-5357-a8e0-56871ccb4179 |  | textbox | Coordinator – Checklist Completed:
text | 58eb3a46-0002-5ab8-b2ca-cc72a0824835 |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLD-100 Lysaght Interlocking - Cladding Building E Panel Site ITP | itp |  |  |  | Yes | CLD-100 Lysaght Interlocking - Cladding Building E Panel Site ITP | 50fd0b21-230b-47a9-8f1f-b3562fb473ad
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC Shop Drawings Approved
label | 03eab955-8dac-5016-9c37-2e87d0b0abc2 |  | note | Responsibility: MPX
label | 97b8b169-2cf7-5c26-8d3c-df60d8cf841f |  | note | – – – – – – – – –
label | 170ffe55-80bf-5e18-9873-395c0ec86056 |  | note | Acceptance Criteria: MPX / Architect Sign Off
text | f5dd62ec-3801-5a9a-9f63-0146f85184d6 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | 9ec44959-8f09-589c-84ee-d9305f39b8ef |  | note | Responsibility: MPX
label | abe7e25e-95c8-5ad9-ac72-0bc7025bb820 |  | note | – – – – – – – – –
label | 39f6b189-fedf-5548-9a47-6dc183b4597e |  | note | Acceptance Criteria: MPX / Architect Sign Off
text | 38e8af76-ce48-5fd6-b9fa-390d954e6241 |  | textbox | Date:
label | a45be81e-c730-5c8a-880a-4944b598aa7e |  | note | Comments: Check colour is correct as per shop drawings
checkpoint-status |  |  | checkpoint | Materials (Panels/Bolts/Washers) delivered to site free of damage and deformation
label | 0f961f53-7aa6-5cfe-8261-21fdc77c5989 |  | note | Responsibility: Facadex
label | 6d8cfc2d-d92e-5e56-bc02-490a36598148 |  | note | – – – – – – – – –
label | c0f6777d-2d85-5550-859d-5c172c0e35ab |  | note | Acceptance Criteria: Facadex sign off.
text | 190a58a7-1e92-5bfb-95d7-c5aa64c32be9 |  | textbox | Date:
label | 95aba775-6fb2-539d-8724-702bee69868a |  | note | Comments: Check colour is correct as per shop drawings
checkpoint-status |  |  | checkpoint | Grid lines established and site set out complete
label | 46799f0a-8f4b-5056-966e-477b123ee4f3 |  | note | Responsibility: Facadex
label | 05ef780d-b5f4-5882-8a82-ea138be5c78b |  | note | – – – – – – – – –
label | e2d1b171-7107-5833-865c-a1c157dbe5b5 |  | note | Acceptance Criteria: Facadex sign off.
text | e1cf66d0-96d9-5482-a9ad-5bc9a2b4e66a |  | textbox | Date:
label | 29fbcd43-5400-5e5c-a540-359e34005f9b |  | note | Comments: If installed off site no gridline available
checkpoint-status |  |  | checkpoint | Cladding Panels installed to manufacturers specifications
label | e4f6ce58-7adb-553f-82ac-0f009418ef58 |  | note | Responsibility: Facadex
label | 1cda2c3c-a85f-58a0-8014-c8589b6068b5 |  | note | – – – – – – – – –
label | 3b189ade-5495-5434-873b-13e9b41b6301 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 8ead4e33-9a60-510a-b87d-04558d8a60d8 |  | note | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 4172c8ee-192f-5d27-8c4c-333fd773fdc8 |  | note | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 2aba5afe-3d41-536d-97bf-f97753dea4a0 |  | note | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | 276dc635-6fa7-5ea6-be44-0bdf6a592cd7 |  | note | ○ +/- 3mm @ every 1000mm in length & height
text | b856a7d3-3852-59b6-9435-33689942fd53 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Cladding Panels checked for paint scratches post installation
label | 9c79832a-28cc-588a-afd1-4a098f759bca |  | note | Responsibility: Facadex
label | 5973d532-708e-5a06-92d6-0a5f12993b13 |  | note | – – – – – – – – –
label | 8e2b8d09-a0e3-576b-b5bd-305b7d06d8da |  | note | Acceptance Criteria: Facadex sign off.
text | c14afaab-67c0-5675-a759-18468c6bf378 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | 0.8 BMT Raw interlocking sheet has been cut and installed in situ to the size required by site
label | 600164e5-6ad8-54fe-ac5b-e093e256e261 |  | note | Responsibility: Facadex
label | d1395236-d9e9-5e3b-95de-c0017658a67d |  | note | – – – – – – – – –
label | c750d105-3cb2-5cdb-bbef-8f792e4a51e9 |  | note | Acceptance Criteria: Facadex sign off.
text | 2538d4fb-ed96-5cc0-9986-c60b83a71e57 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Connections (bolts/washers/screws) checked for damages
label | 54c0b229-5157-5a43-a7d3-b03c62889816 |  | note | Responsibility: Facadex
label | 6564a1d8-020d-51ed-a3bb-60f7b8bad36c |  | note | – – – – – – – – –
label | 7e1ee640-6109-5c4f-8e38-43c5b72af999 |  | note | Acceptance Criteria: Facadex sign off.
text | e075aa4c-1de3-59d5-9f20-56c8446cc09d |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | 671d7553-f0d3-51fe-a406-6f2d92f3da44 |  | note | Responsibility: Facadex / Builder
label | 1877d29b-932e-5f29-9a90-6b08dda3c85d |  | note | – – – – – – – – –
label | 2a99bc11-5239-567e-afa0-f2cc6614da57 |  | note | Acceptance Criteria: Defect notification via email or chosen correspondence
label | 70e285a0-1b7a-50b9-9108-a91a15c02d7e |  | note | ○ Evidence of close out / rectification
label | 7cf4af0d-5b95-5b01-afc2-265f24ae37fc |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | bfd28a7b-632c-5dc4-8b2e-dde0716ee2d2 |  | note | ○ Sign of only once agreed that wall is defect free
text | bec13e36-5450-5544-bce8-6bc4fd564fe1 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | 399f711f-62b2-5d5e-881a-3c232c50b563 |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | 8066eb34-ef0e-520e-bc13-fc633b8f4652 |  | textbox | Foreman – Checklist Completed:
text | 66a1b592-f574-52f8-91da-40a96bad50b6 |  | textbox | Date / Time:
text | cb32d73a-7503-5760-a0be-219d8596b5d9 |  | textbox | Coordinator – Checklist Completed:
text | 5b0fb65d-b8b9-5af6-8a95-e5bfc31d6725 |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLD-100 Lysaght Interlocking - Cladding Building D Panel Site ITP | itp |  |  |  | Yes | CLD-100 Lysaght Interlocking - Cladding Building D Panel Site ITP | 638bcef9-1ce9-4044-ab7b-c95122057d0b
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC Shop Drawings Approved
label | c71feb76-c16f-56ee-9283-0e0bd46cede0 |  | note | Responsibility: MPX
label | 3df0222b-8352-5f6b-b544-443082f075d4 |  | note | – – – – – – – – –
label | 2f9ef622-6bf0-5ef0-8d8d-b638415c2480 |  | note | Acceptance Criteria: MPX / Architect Sign Off
text | 84ff5302-79ee-5132-9c09-f01ccbfa0c7a |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | 2ed722bb-9b6a-588c-9b93-b7d6fa7717f5 |  | note | Responsibility: MPX
label | 6ff2f511-ea3f-5c75-a9d7-c85e116f9496 |  | note | – – – – – – – – –
label | 604cada8-2e1c-5713-9937-aeddb99888a6 |  | note | Acceptance Criteria: MPX / Architect Sign Off
text | 834c593e-f158-5682-9739-6438796d7e58 |  | textbox | Date:
label | 92feb10b-8dd7-53a1-a9c6-2e1b89e18bf1 |  | note | Comments: Check colour is correct as per shop drawings
checkpoint-status |  |  | checkpoint | Materials (Panels/Bolts/Washers) delivered to site free of damage and deformation
label | 7a52a145-4029-5c2d-9a51-d8f2bf5cb9a3 |  | note | Responsibility: Facadex
label | c98f5028-1820-5131-99eb-55f309c4d2b2 |  | note | – – – – – – – – –
label | 12ae122e-be3c-5a42-ac11-513dfec91dd5 |  | note | Acceptance Criteria: Facadex sign off.
text | e5005d1f-e271-5bce-a601-1d9d88f2aa12 |  | textbox | Date:
label | dc314f03-ca97-599e-abc9-d1c99c22241c |  | note | Comments: Check colour is correct as per shop drawings
checkpoint-status |  |  | checkpoint | Grid lines established and site set out complete
label | 101189e0-8c23-5be9-9c72-54a3e62b3f55 |  | note | Responsibility: Facadex
label | bf732786-9df6-5324-b50e-6683cdfac6e8 |  | note | – – – – – – – – –
label | 59bcd62c-caf7-5496-b951-ad169fbf567e |  | note | Acceptance Criteria: Facadex sign off.
text | ad2522c1-bbf2-5c1b-8a30-b2b71c0f2cbc |  | textbox | Date:
label | eec94c13-b285-514e-8bfe-b3da84f6d998 |  | note | Comments: If installed off site no gridline available
checkpoint-status |  |  | checkpoint | Cladding Panels installed to manufacturers specifications
label | 6165fef2-aac8-5152-9700-99281b61974a |  | note | Responsibility: Facadex
label | d20c6183-6ad1-52db-851e-75f387100b31 |  | note | – – – – – – – – –
label | 6b05d312-eedc-5b20-9d42-e0a89c41bfa1 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 33814e6f-14bc-5472-8075-a4c095443f8c |  | note | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | a7a51ea4-49af-5a29-9c69-40cd059f81e2 |  | note | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 23b26967-b8d3-527b-bc20-c042ce0e3db3 |  | note | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | 66d09e02-0add-5e7b-8357-2e0c57794859 |  | note | ○ +/- 3mm @ every 1000mm in length & height
text | 2d0dbcf6-82b4-59ce-a8aa-72b27d74333d |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Cladding Panels checked for paint scratches post installation
label | e9183f56-2806-506c-8125-f90f777d16a3 |  | note | Responsibility: Facadex
label | d7cf1cbd-e2dc-57f0-b592-a77c798ba4fa |  | note | – – – – – – – – –
label | 61c6e6c1-01b4-5dd2-b8cd-044d07be17e3 |  | note | Acceptance Criteria: Facadex sign off.
text | 1a8c7c87-f951-5479-a1a6-a99905dc6e3d |  | textbox | Date:
checkpoint-status |  |  | checkpoint | 0.8 BMT Raw interlocking sheet has been cut and installed in situ to the size required by site
label | 62a1bf2f-b784-583f-b498-879a54ae5dc9 |  | note | Responsibility: Facadex
label | 78dbef3f-6749-5b45-a3d7-b55cc889fdb1 |  | note | – – – – – – – – –
label | eb429a16-9abc-502d-a5f5-1538396366c9 |  | note | Acceptance Criteria: Facadex sign off.
text | c508bb8d-c5c4-50f4-9d72-e8eded9c5efa |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Connections (bolts/washers/screws) checked for damages
label | e7e55039-c30b-5e48-8ce1-96317248db11 |  | note | Responsibility: Facadex
label | 056635ad-01fc-5bad-92fc-10919fd80e64 |  | note | – – – – – – – – –
label | 890b5d25-98ae-5627-9827-03ff8bd7a193 |  | note | Acceptance Criteria: Facadex sign off.
text | d0365566-30d9-51b7-b2cc-e983a1325fd5 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | cc0433ba-fccd-5f6b-a4a5-8f79bcd97067 |  | note | Responsibility: Facadex / Builder
label | 305f35c6-98f5-5e7a-b4a7-951ecadbf277 |  | note | – – – – – – – – –
label | 87386de5-aa8e-57d2-a43a-30b89872f832 |  | note | Acceptance Criteria: Defect notification via email or chosen correspondence
label | 352bc7d8-3582-5238-ac8a-108839159b7e |  | note | ○ Evidence of close out / rectification
label | a4a6eab5-a51b-5a3d-bf21-c896084dcf6f |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | 8a02981d-136f-58bb-9307-1b023c34fd9d |  | note | ○ Sign of only once agreed that wall is defect free
text | d2547aa9-2ad6-56e4-960f-9168a55ecb4a |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | e9f85cd6-d0b9-5db5-9afa-e73c6bf232bb |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | a4a8da63-9cc2-5a9f-b98c-6b15bff92e2f |  | textbox | Foreman – Checklist Completed:
text | 5f1a6730-c4fb-5da1-8e78-904b0adfd398 |  | textbox | Date / Time:
text | c3a2cf78-d409-531a-a82a-9e6311965fcd |  | textbox | Coordinator – Checklist Completed:
text | 6a55a496-fb58-57e5-b66d-8f70b984256b |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLD-200 3mm Alum Perf (Building E) - Factory ITP | itp |  |  |  | Yes | CLD-200 3mm Alum Perf (Building E) - Factory ITP | 6f8f5924-33c1-429e-9fbc-5c99d72ef988
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC shop drawings approved for fabrication
label | 1ac77557-02ae-5187-a0ce-13767d181075 |  | note | Responsibility: MPX
label | 8ccd7ce1-ea7b-5e3f-8097-eb6956229804 |  | note | – – – – – – – – –
label | 1002a81d-b781-58d7-bb5e-599db8af42a2 |  | note | Acceptance Criteria: MPX / Architect sign off
text | cfd48a2d-8875-500f-8f18-40642d60312b |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | 33b86b61-899f-5c1e-ba65-54b814e6e150 |  | note | Responsibility: MPX
label | 43e6e1d2-0929-566f-b4c2-6ea26948fa19 |  | note | – – – – – – – – –
label | 782de284-e1b2-5c9f-b1ee-778c2ac274e9 |  | note | Acceptance Criteria: MPX / Architect sign off
text | b7b93e66-0743-50e3-82ef-57fab5bc6ab2 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check if the pattern is correct to IFC (5005-H34 alloy 51% open area)
label | e579f44e-4780-584e-9272-be3eecce2e46 |  | note | Responsibility: Facadex
label | f64348d7-0689-57fd-b77c-7ad493f80a17 |  | note | – – – – – – – – –
label | 1628e95e-c021-5df2-9239-de016d52a8dd |  | note | Acceptance Criteria: Facadex sign off.
text | 01ea318c-a532-5ea7-ba64-768815855604 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check if the stiffeners has been installed @450mm Crs
label | d0e4d96b-241f-552b-b8a6-3910e4855ee4 |  | note | Responsibility: Facadex
label | 3bc6543e-07ff-53df-991b-6aeb13998f1c |  | note | – – – – – – – – –
label | 3b320064-a887-5601-956b-6e3fd78523b5 |  | note | Acceptance Criteria: Facadex sign off.
text | 2d9a8e80-78f8-5202-ab41-37fdb11246e0 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Confirm and check finish as per approved IFC drawings
label | 4fbbb734-d0de-5955-a0a7-9bd3038c9858 |  | note | Responsibility: Facadex
label | 3232966c-5f4e-52fd-95e6-a476fb41e6ad |  | note | – – – – – – – – –
label | 2ed9377b-f918-5825-aedf-6c8b5e9bf19a |  | note | Acceptance Criteria: Facadex sign off.
text | 6751207e-615a-56a3-bf69-da227522a027 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check panel size and dimensions against IFC drawings
label | e72f1d1b-7620-5f05-8147-5ab1883f664a |  | note | Responsibility: Facadex
label | 32c7c456-cafd-5f6e-8863-4803c7000dc5 |  | note | – – – – – – – – –
label | 822d1d69-e242-5c45-9ef9-a5521d50435d |  | note | Acceptance Criteria: Facadex sign off.
text | 93c7daed-623d-50fa-9c6c-11ffee736bb1 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check diagonal dimension to ensure odd shape panel are done correctly
label | dfa3417e-af3d-5147-82ca-033c8f36efd9 |  | note | Responsibility: Facadex
label | 3d1f3ddb-851f-5203-8a54-8a78b9877eee |  | note | – – – – – – – – –
label | 21f1d131-9413-5cb9-accc-aabd05d2840a |  | note | Acceptance Criteria: Facadex sign off.
text | 4890427d-63b0-57c2-8b9c-b7cb0993a755 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | QA has checked delivery docket and receipt from powder coater
label | 05ffeea0-4700-557d-960d-34fbd315dae8 |  | note | Responsibility: Facadex
label | 645fa967-f532-5c56-8c06-5dad9e4b1003 |  | note | – – – – – – – – –
label | 801cca78-a008-5e39-94b1-8f1dcddcd2df |  | note | Acceptance Criteria: Facadex sign off.
text | 96b51ec7-7dff-5f6c-b35b-2bd847a5790b |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Is fabricated item labelled as per drawing?
label | 40ddaccf-3d0f-586e-9169-385988762634 |  | note | Responsibility: Facadex
label | 0d5fb38b-20a1-5cec-8b9a-236a43ce4367 |  | note | – – – – – – – – –
label | 2b75fa73-70e0-57c5-983e-376633940438 |  | note | Acceptance Criteria: Facadex sign off.
text | ad35fe4e-6810-5d6d-bff4-3f60d4452cc6 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Fabrication complete
label | a4bcfec2-192b-52d4-a3f3-f92303508c66 |  | note | Responsibility: Facadex
label | dc8dbaf1-3815-5722-b4e6-994eeace6500 |  | note | – – – – – – – – –
label | ce5cdf6e-0eaf-5ff0-bb2b-1ac441d1c34a |  | note | Acceptance Criteria: Facadex sign off.
text | 6a146cde-afbf-5a3c-9989-5e0aab7616d0 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Prevent direct contanct between incompatible materials
label | 78ea685b-796d-5530-a6e7-553ca10b87e4 |  | note | Responsibility: Facadex
label | 56d06d2d-698f-50ba-a286-1e7871d89072 |  | note | – – – – – – – – –
label | 02088e7f-565f-5b5a-b262-27600d7ac6b7 |  | note | Acceptance Criteria: Facadex sign off.
text | f0b2478c-4649-5b6f-8384-7a9d7fae00d8 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Materials ready to deliver on site
label | d89864c2-766c-5284-a57e-aced7fb518b3 |  | note | Responsibility: Facadex
label | f8808548-6eb4-5276-9b96-280849617332 |  | note | – – – – – – – – –
label | 364743e6-65f3-5019-8282-7df46daa21eb |  | note | Acceptance Criteria: Facadex sign off.
text | 1526c638-6674-5f16-99e2-7637c2dc6eee |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | 9f2f6c7e-76fa-5a60-9b16-78b390e2aab7 |  | note | Responsibility: Facadex / Builder
label | 7e52c24c-9a69-50c2-918a-edfbe73f149b |  | note | – – – – – – – – –
label | e2de1892-bbee-54d8-8e2b-83186ecb92fa |  | note | Acceptance Criteria: Defect notification via email or chosen correspondence
label | 1dc0cbc0-ce4b-5dce-8c17-2bad96c4ae6d |  | note | ○ Evidence of close out / rectification
label | c1702f72-074d-5099-9fd6-fedd53b8d3c5 |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | 9c7681fc-5445-5136-8ef5-bf1bb4de02f2 |  | note | ○ Sign of only once agreed that wall is defect free
text | 7005d91d-62a0-50ca-a8d1-b51994aa6f10 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | 17b66c79-bdea-5421-b784-7cde0a0a4594 |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | a7190352-a913-5777-aa49-9981c32e9ba8 |  | textbox | Foreman – Checklist Completed:
text | 94378779-abca-55cf-ab9b-4fdf1daa77c6 |  | textbox | Date / Time:
text | 4af52bd1-3b3c-5cb8-ac4b-e3cd38803a68 |  | textbox | Coordinator – Checklist Completed:
text | 30ff17af-fbef-5ae4-80e1-7687ac44c711 |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLD-200 3mm Alum Perf (Building D) - Subframing Site ITP | itp |  |  |  | Yes | CLD-200 3mm Alum Perf (Building D) - Subframing Site ITP | 74b4eefa-e007-4f58-abe1-27e3275e88f6
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC Shop Drawings Approved
label | f6ec8aa5-ebd4-5e8e-b9ce-b6e55e8580fd |  | note | Responsibility: MPX
label | 91f7e2cd-bfcb-572a-b990-68ce935601ff |  | note | – – – – – – – – –
label | 5d2aedbe-e0cf-547a-aa83-a2e9406ee3da |  | note | Acceptance Criteria: MPX / Architect Sign Off
text | 21b0962d-e5b2-5d58-a44b-dcdde1700369 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | 7da1087f-c4d5-59d8-9c01-401c97785291 |  | note | Responsibility: MPX
label | 9aa3e68e-80e0-5cfb-8ffe-c44a34fc2f82 |  | note | – – – – – – – – –
label | 6a100151-1a22-5d98-8e40-e636b1f36dd3 |  | note | Acceptance Criteria: MPX / Architect Sign Off
text | a8e26b3c-0b91-5925-b482-64d9896b0def |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Materials (top hat/screws) delivered to site free of damage and deformation
label | 80e68760-7d56-598c-a67a-7bad5df20c86 |  | note | Responsibility: Facadex
label | 07fbd133-5db0-5ca5-813e-b3e52788f22d |  | note | – – – – – – – – –
label | a4e6fd64-e9f1-5491-bb37-469d33dc38aa |  | note | Acceptance Criteria: Facadex sign off.
text | 6bd51f3f-8555-5da7-b775-b6ce4aea9e59 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Grid lines established and site set out complete
label | f6ae6c95-fbdd-5e68-8ad4-f749c3c4c652 |  | note | Responsibility: Facadex
label | c884c990-7c75-57f0-88ea-1ee6d8d678f8 |  | note | – – – – – – – – –
label | 93bafda5-e6ff-5015-93df-ee056ac4cc13 |  | note | Acceptance Criteria: Facadex sign off.
text | e1f11060-97be-5b57-9d86-df8745bf63d5 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | 75x254x75x3mm thk folded Z has been set out and installed to steel purling @1500 crs and fixings @900crs as per IFC
label | 6323a4ae-bc71-5b9c-97bf-88ee28c4f6ae |  | note | Responsibility: Facadex
label | d82f08cd-1865-5080-a8ef-5ba5c3e5dd68 |  | note | – – – – – – – – –
label | aa1fee0c-5f7f-5868-b3eb-84e6de292943 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 6bb3b4c5-5641-506b-a4bf-cac0614c3d4c |  | note | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 6e086c8c-cb62-53e6-a388-98b2cc1aea95 |  | note | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 2e8fcd9b-aa81-5fc3-ac8b-d782554ef9ca |  | note | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | 463d90ef-54ef-5eb9-a3b7-0c955cdb97f8 |  | note | ○ +/- 3mm @ every 1000mm in length & height
text | f384f185-a248-58f4-b989-3715937d353a |  | textbox | Date:
checkpoint-status |  |  | checkpoint | 50x50x3mm alum SHS/EA horizontal has been set out and installed to vertical folded Z with #12 tek screws@600crs
label | 9ad96354-3d72-57fe-8a75-f965d0c931e3 |  | note | Responsibility: Facadex
label | b3e519e8-7626-5099-9112-4fee9928e8af |  | note | – – – – – – – – –
label | 30e202ac-cc9a-5833-a93f-40a7b74d6820 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | b6ee9388-7d28-51f3-a865-8795c40e7085 |  | note | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 6055dd58-7c61-5188-90af-3b6f41032954 |  | note | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 6134284c-b6e5-526b-bd98-3016c98725f7 |  | note | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | 09241df1-3652-56c0-a334-107fc2ed56e4 |  | note | ○ +/- 3mm @ every 1000mm in length & height
text | 9a685ba3-5529-5896-b353-167e64aa3e76 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Packers has been used to ensure the subframe is plumb for perf panels to be cladded on.
label | 9ae5cf42-0b3a-5ebd-befd-93a9250cc2b2 |  | note | Responsibility: Facadex
label | 4962d38d-9f0a-536b-8e41-127ee3385929 |  | note | – – – – – – – – –
label | ef39b8a2-548e-50d4-a4f5-da891094301d |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 122c9961-36f7-5aff-bb45-16619942720f |  | note | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | d2f986b4-d7d3-5481-ba92-8592f5e667b5 |  | note | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 7ca3caff-6d0c-5f7f-ac6c-e28e21be57a9 |  | note | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | 8222b430-467b-5e32-9dbe-1b23e36a9dbe |  | note | ○ +/- 3mm @ every 1000mm in length & height
text | 79e3a713-e476-5093-91fa-9c7a50cd8494 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Connections (bolts/washers/screws) checked for damages
label | 3b0930c4-d70b-5595-b4da-e1c8108945c9 |  | note | Responsibility: Facadex
label | 19a152e2-3c72-5f46-b687-b367de4dbeb3 |  | note | – – – – – – – – –
label | f3bad722-9197-532d-9605-8a5c144b60af |  | note | Acceptance Criteria: Facadex sign off.
text | 78f9e6f2-67e4-5915-810f-031772e06f0c |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | 312f6176-4594-5332-ba09-aca7148b9cf7 |  | note | Responsibility: Facadex / Builder
label | 57af072b-6b29-5d60-877e-3dd7e60e9d70 |  | note | – – – – – – – – –
label | 6595be42-eb7d-5e91-88ce-60b9cd63d66d |  | note | Acceptance Criteria: Defect notification via email or chosen correspondence
label | 9cbf9ce0-7bdf-582c-98c7-c738e7b941c0 |  | note | ○ Evidence of close out / rectification
label | debb6375-d88d-5379-be39-cbb407961b49 |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | 968f9588-f7fb-5234-b0d2-8f1a0cfb712c |  | note | ○ Sign of only once agreed that wall is defect free
text | 19d9097e-934a-51a9-9e02-0648148f0523 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | c55f3c8b-3df3-5c1a-82f9-4471ed98696c |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | 660e2475-7774-5676-9b4f-855dcc34ca12 |  | textbox | Foreman – Checklist Completed:
text | 4da974ae-dad1-5ea4-9da7-7f30659ca46b |  | textbox | Date / Time:
text | 3a5b453d-41d7-5049-9864-6a2185a81266 |  | textbox | Coordinator – Checklist Completed:
text | c5f92425-cd9b-5ed0-aa3b-97672143cd1b |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLD-208 Stramit Sharpline (Building A) - Factory ITP | itp |  |  |  | Yes | CLD-208 Stramit Sharpline (Building A) - Factory ITP | 77ac262a-28e8-4274-8b0f-7b1f4c174e20
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC shop drawings approved for fabrication
label | 4381d922-4c27-5278-8134-4fbce02c8e12 |  | note | Responsibility: MPX
label | fe59fa26-4f72-5109-b088-e5d72e1fed97 |  | note | – – – – – – – – –
label | 99d8a113-f4ca-5c38-8efd-ed92f8731af5 |  | note | Acceptance Criteria: MPX / Architect sign off
text | 61a3875b-d5ed-54d7-8795-4721bd2f43bd |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | a80e54ae-5dd7-57bf-8a48-c6bfc3c8d453 |  | note | Responsibility: MPX
label | ff2c2459-f066-5a78-aaba-00818ad21105 |  | note | – – – – – – – – –
label | 86b478a5-5a58-51fa-b8a5-2f7e487d8638 |  | note | Acceptance Criteria: MPX / Architect sign off
text | bb728d45-d63a-5b13-97a1-56e405a2678d |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Confirm and check finish as per approved IFC drawings
label | 9db0196e-a46f-50ea-ade2-410d7b7ee156 |  | note | Responsibility: Facadex
label | 7e53547d-1062-55e2-953b-b671b73233df |  | note | – – – – – – – – –
label | 9f185d16-ba4d-5e66-bbc9-1dd87ee565c0 |  | note | Acceptance Criteria: Facadex sign off.
text | bf441022-9413-5b44-86d8-67df151fd4ae |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check panel size and dimensions against IFC drawings
label | 4820c2d9-5821-5dbb-a4cd-a26002f63ac3 |  | note | Responsibility: Facadex
label | 25bae4ab-2dab-55c1-a8bb-eeac3b4ce4ff |  | note | – – – – – – – – –
label | f84897d2-7dd9-50c2-98c3-7a4f70c1a6da |  | note | Acceptance Criteria: Facadex sign off.
text | 1e373ff3-a970-5240-a865-ab6242d3a306 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check diagonal dimension to ensure odd shape panel are done correctly
label | 828da9e7-77cd-5607-b228-6f69adb97f57 |  | note | Responsibility: Facadex
label | fa1bbf34-d395-527a-ad6c-cf670fbc304b |  | note | – – – – – – – – –
label | 2261cf7a-310d-5ebe-b8b1-c84251bcccec |  | note | Acceptance Criteria: Facadex sign off.
text | bcdd71b2-9ddd-5ccb-b3d1-b6ae60e5596e |  | textbox | Date:
checkpoint-status |  |  | checkpoint | QA has checked delivery docket and receipt from powder coater
label | db10f22b-b5a7-5194-a0ff-5faa4f2873e9 |  | note | Responsibility: Facadex
label | a01467d1-3cdd-55b6-b179-f6011976dc2b |  | note | – – – – – – – – –
label | fe9a3635-4c99-5a06-9dd6-03555002bfbc |  | note | Acceptance Criteria: Facadex sign off.
text | bcf0b376-ff32-51bb-8790-3c553ef18965 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Is fabricated item labelled as per drawing?
label | aaf69d24-7bda-51e5-818a-f4a62f721a8a |  | note | Responsibility: Facadex
label | 320b1fc0-eec6-5548-8cd3-057336b00fcd |  | note | – – – – – – – – –
label | 15e5d2e2-a4b4-52a2-a592-754da5f3aa58 |  | note | Acceptance Criteria: Facadex sign off.
text | d93b39ba-fae5-505d-87e4-e143d1be2810 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Fabrication complete
label | fcc3a4db-0f7c-55d7-8d35-0b4fba3585f6 |  | note | Responsibility: Facadex
label | 7c8b802d-c823-5131-9240-545554d8d055 |  | note | – – – – – – – – –
label | 3d1c6d94-2900-5af7-8477-136f803036a1 |  | note | Acceptance Criteria: Facadex sign off.
text | ab257e42-3b86-52a2-8544-0035d0b7ce79 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Prevent direct contanct between incompatible materials
label | a32fa746-f1cb-5696-92d5-78c5389a5a1a |  | note | Responsibility: Facadex
label | f9c44627-0014-56be-9057-d4bb35471edf |  | note | – – – – – – – – –
label | 1cc3380f-bf01-56c8-93ff-3821769c6735 |  | note | Acceptance Criteria: Facadex sign off.
text | b82edbaa-7b6c-5d99-ba51-92392488256b |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Materials ready to deliver on site
label | 5331e1bf-9075-5010-aab7-29e439a564f2 |  | note | Responsibility: Facadex
label | 306b32ad-f3e9-5d1d-aeca-901ff81c9849 |  | note | – – – – – – – – –
label | 530a1f73-a331-5ac9-afd8-1c4766fe1682 |  | note | Acceptance Criteria: Facadex sign off.
text | 09345664-44de-5e6c-a2be-aa74592fc943 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | 2b2b461f-e447-58f9-8ca8-f278b0fd859c |  | note | Responsibility: Facadex / Builder
label | a7f48455-f056-5fa7-9e82-d372a687e351 |  | note | – – – – – – – – –
label | c378a37f-53b1-5cf7-b52d-9aa77afb096a |  | note | Acceptance Criteria: Defect notification via email or chosen correspondence
label | 9acc5829-e108-5172-8c56-87297ba2b4c5 |  | note | ○ Evidence of close out / rectification
label | 114f4dab-4136-5eef-b938-2f9f7144a734 |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | 293ec809-cbbe-5ffe-8d2c-7873ab72c230 |  | note | ○ Sign of only once agreed that wall is defect free
text | f58b9158-0f27-5289-ad97-0cbc90559f4f |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | dda16a20-5b0d-5b91-9b06-442a2d24736d |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | 6f3c684b-6de9-541d-9a6d-ef676e7b44aa |  | textbox | Foreman – Checklist Completed:
text | 55c250eb-f3a6-563a-b960-a521ac3b6add |  | textbox | Date / Time:
text | e8a7e46e-91ea-5a38-9cba-a5b706bfdcf7 |  | textbox | Coordinator – Checklist Completed:
text | 3a3650f0-4a73-55c3-ac3d-3e5d1757a79f |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLG-506 Z450 Steel Frame ITP | itp |  |  |  | Yes | CLG-506 Z450 Steel Frame ITP | 81f12331-8e8b-46e9-a859-3d15f036f6dc
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC Shop Drawings Approved
label | 1bcd1a4a-444f-5827-a08b-3226caee2d32 |  | note | Responsibility: MPX
label | 4aa2f3da-ac73-5f26-88de-fcf02317418d |  | note | – – – – – – – – –
label | 4f588a14-b814-59c3-9763-b1d683cf4cfc |  | note | Acceptance Criteria: MPX / Architect Sign Off
label | 2ca513aa-2ed0-598d-a4c9-b8718a41cb2c |  | note | – – – – – – – – –
text | df8bf5cd-afeb-54bc-8081-330232dc065d |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 7a066aee-8050-5e21-ab75-56e18a23d9a4 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | e847074d-6595-507e-8c4b-4429d1bccad5 |  | note | Responsibility: MPX
label | 036ecfca-1a6d-5b6a-a5f7-5462bde9f25c |  | note | – – – – – – – – –
label | 0c5b176d-df3e-5ae6-b099-10bab0bcfb64 |  | note | Acceptance Criteria: MPX / Architect Sign Off
label | b5d9ba7d-1c51-575b-bd6b-32017f82acc0 |  | note | – – – – – – – – –
text | 5dd0f348-0b37-54d0-9793-4c25b52956e8 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | b008e9d6-a432-5f4a-9d13-7f69981cd1ae |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Materials (truss frame/Bolts/Washers) delivered to site free of damage and deformation
label | 835aa689-24d9-5373-ac41-3dc41cc23ac3 |  | note | Responsibility: Facadex
label | 53acc76a-9fb1-57c1-a326-3e5730bb89da |  | note | – – – – – – – – –
label | 7440e552-c894-5684-8842-384c074ded74 |  | note | Acceptance Criteria: Facadex sign off.
label | f91ca74c-1a1f-540c-b45b-e90fb42235b7 |  | note | – – – – – – – – –
text | 7ccfafb4-fbc5-5b8c-aeb3-99159cd834fa |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | b038c996-cd8d-5a74-aeda-6965954b6078 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Grid lines established and site set out complete
label | 4b9960c5-6289-5a38-bf6b-c0d6620cd943 |  | note | Responsibility: Facadex
label | 338e2a6e-e91f-55c1-9839-5d0abca62256 |  | note | – – – – – – – – –
label | 3849c1d0-00ff-5ec8-a4c1-4c357885fa22 |  | note | Acceptance Criteria: Facadex sign off.
label | f08d7ece-f180-5c95-a1e2-58dfd89208a4 |  | note | – – – – – – – – –
text | 04be87f9-4513-5230-85a5-296db8913398 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 6409af52-542a-553f-b19c-55cefb9fdb65 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Truss Framing installed as per shop details
label | fb26027a-4667-5c41-8a29-84bd8e54d335 |  | note | Responsibility: Facadex
label | ef186338-6715-52e4-9e42-e760d095c5f2 |  | note | – – – – – – – – –
label | d904b0e8-6a07-5d81-906f-42e85acec713 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | e013b175-90f5-52ea-b264-1541e7a7bd8e |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 69e8ab62-85aa-5169-82bc-ea397b344186 |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 314cf91c-9e8c-5d07-ae97-26adb4ea9325 |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | 36bb6bf9-2f32-5f0e-a0ae-67e8dde58be8 |  | note | ○ Expansion & Contraction:
label | 50e0159e-cccd-5022-9b44-e2b347737491 |  | note | +/- 3mm @ every 1000mm in length & height
label | 6dd14948-4cc1-5bad-9d69-d40646fd9692 |  | note | – – – – – – – – –
text | b4c38b14-42da-5cd2-8d50-769242f165a4 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | c31c14c4-efc8-5938-8485-320a15d8c2ac |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Truss Framing aligned finished level and plumb (height adjusted with deflaction head)
label | 2818d4b6-6170-580b-8bd8-e0a2628b4176 |  | note | Responsibility: Facadex
label | 22348349-ba73-5ca6-85af-ccfa6238bf73 |  | note | – – – – – – – – –
label | bd731a26-32e2-5106-8172-6543f1b6d963 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 66290e86-f56b-5b17-a9e5-fb39566f6573 |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 23b5b966-16d3-52cb-8dc5-5252497e87eb |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 87917292-d439-59d0-bf72-1d37b4368eb0 |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | 667f6e44-e78e-5190-9466-42ab723066de |  | note | ○ Expansion & Contraction:
label | e744c638-3bc0-5715-8997-2ded23f33446 |  | note | +/- 3mm @ every 1000mm in length & height
label | 82f3c13d-9513-547b-ae39-c98154866755 |  | note | – – – – – – – – –
text | 5382816d-ff06-59ea-84a1-65d8c8f01ba1 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 20ebcd94-7cd0-52f7-9657-b74cfb3c9ae7 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Top hat to the truss frame installed and leveled for panel installation
label | 199757ef-2d0e-5208-a723-c3627b691f49 |  | note | Responsibility: Facadex
label | cfcc19ea-f9e7-5b45-9972-c8c99595a6c5 |  | note | – – – – – – – – –
label | e4247cd1-ccd7-5e94-8dce-8831aef6c4fb |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 25564ade-69a5-5d58-9ac7-14232e326160 |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | ba580eb7-0d27-565a-b58f-4131956d2497 |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 764ba6f9-c3b5-576f-b672-7c67823d9eef |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | 369ce94a-0332-55e1-86ab-f30b0e33eaf8 |  | note | ○ Expansion & Contraction:
label | 76299057-90f4-52b0-a425-7015ae4fa66d |  | note | +/- 3mm @ every 1000mm in length & height
label | 90c9f2ca-325f-5dac-83f6-f7a64e882721 |  | note | – – – – – – – – –
text | 85079f4a-ab95-5302-a215-e9ddb7a9bcb1 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 6d8592c7-1fb0-5e55-93e2-cc72720676e3 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Connections (bolts/washers/screws) checked for damages
label | f219268c-f22f-5e57-94f7-a88027297a37 |  | note | Responsibility: Facadex
label | dbddcc68-d522-559e-aea9-97671ce77760 |  | note | – – – – – – – – –
label | a9157604-65e7-50d5-89c2-be31a95416f2 |  | note | Acceptance Criteria: Facadex sign off.
label | 29805734-bbe8-546f-ae67-103b23d11c88 |  | note | – – – – – – – – –
text | 6500bd74-ab9e-54f3-8cdf-26e3d0c607f4 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | eeefe520-de31-5876-a62b-da6f6910c5e8 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | 28cbdfff-d845-5548-94df-f00f0e6b58bf |  | note | Responsibility: Facadex / Builder
label | 3af68ef5-09a4-570a-8118-3a24cb4d9d9c |  | note | – – – – – – – – –
label | c26fafb2-d514-5268-b6eb-74ed55c84027 |  | note | Acceptance Criteria: Defect notification via email or chosen correspondance
label | 1fa4c526-7ede-5664-af28-4105a5624d42 |  | note | ○ Evidence of close out / rectification
label | 1eb0d537-893b-5b84-85fb-298db8130dc7 |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | 2ec51d52-0294-5de7-8b66-902fe5770d13 |  | note | ○ Sign off only once agreed that wall is defect free
label | 788506ca-3393-5479-97c8-7a517638a3ab |  | note | – – – – – – – – –
text | c8b9e486-9896-5ac7-8e2b-9ac5de71035c |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 4d5654f8-91cf-5311-925b-0332cd0d2aec |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | c9a5e451-e49a-5cee-a41b-2eed3f489a80 |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | 4b8f878d-2678-5944-bf88-4db598b1257f |  | textbox | Foreman – Checklist Completed:
text | 41dc2d5f-b835-552e-9b67-8bb9aa3ed3bd |  | textbox | Date / Time:
text | 1956e1d4-89e2-5c8e-8aab-91621659840f |  | textbox | Coordinator – Checklist Completed:
text | d6cff3be-93da-54e2-b67e-ecd36d503b49 |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLD-208 Stramit Sharpline Sub-Frame (Building A) - ITP | itp |  |  |  | Yes | CLD-208 Stramit Sharpline Sub-Frame (Building A) - ITP | 8401f1c2-153c-476e-954f-b4079cc6752b
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC Shop Drawings Approved
label | cef753dd-4af5-5939-b509-a4259868b2ed |  | note | Responsibility: MPX
label | 3b6d687a-a0da-5918-9011-a688eec348b1 |  | note | – – – – – – – – –
label | 10ff67a6-658e-55cd-b0e4-1fcb7e5162f4 |  | note | Acceptance Criteria: MPX / Architect Sign Off
text | 8c52f311-0b60-5e33-b3a8-138b226f9472 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | 3b7b84a0-fd1d-5e38-8631-59385cd34e45 |  | note | Responsibility: MPX
label | 5d36927a-0253-5333-9fc7-5d76273b9d92 |  | note | – – – – – – – – –
label | 3eb73292-4b47-5b6a-9387-0801fd650b07 |  | note | Acceptance Criteria: MPX / Architect Sign Off
text | 512d9642-0d69-5478-8d21-d4f20781df47 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Materials (top hat/screws) delivered to site free of damage and deformation
label | 63a336fd-c348-5c37-a7f8-023673f4e7bd |  | note | Responsibility: Facadex
label | 3b69af1a-6dca-5e57-a74d-dfe15f9b51d9 |  | note | – – – – – – – – –
label | c6fd2dea-387c-5f9e-9315-633da7b6872c |  | note | Acceptance Criteria: Facadex sign off.
text | 3fb7e675-4cd4-505e-a87b-b39cf936b05d |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Grid lines established and site set out complete
label | aca426de-7782-5d36-91e2-213e3df83e6e |  | note | Responsibility: Facadex
label | 3c5c8f52-a6eb-5e11-8809-66505e297d28 |  | note | – – – – – – – – –
label | fadd5038-96a6-5972-ad52-56c8d6d6be7c |  | note | Acceptance Criteria: Facadex sign off.
text | 1d17c827-c015-5978-b1dd-4a435575abf0 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | 50mm vertical top hat has been set out max 900 crs and installed to Structural Girts with #12 tek screws@600 crs
label | ef29b029-e9d9-5d8b-bc13-0fa4372d76c1 |  | note | Responsibility: Facadex
label | 05504b9a-3054-532c-8cea-5a0a405fb70e |  | note | – – – – – – – – –
label | a350238d-873c-5014-9ae0-3d1093603af5 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | dbd427ba-be8b-5f01-885c-be16004eed88 |  | note | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 7c7622b0-aa6e-58c1-9225-1553230ce7c2 |  | note | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 9247b922-d270-5015-9ab3-ac57d7dee753 |  | note | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | 361dde8f-510f-5bb2-b2b3-7c4f6f702aad |  | note | ○ +/- 3mm @ every 1000mm in length & height
text | 6a118453-1351-5435-9d24-3aaf7757f043 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | 50mm horizontal top hat has been set out and installed to vertical top hat with #12 tek screws@600crs
label | 7d75b1be-e110-5159-bc3d-e151ee2f06a7 |  | note | Responsibility: Facadex
label | 681ea0d7-709e-55f6-8d39-8eac5dc58daf |  | note | – – – – – – – – –
label | e7c1a36f-a536-5e93-aa07-4bb4a674f633 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 4f56679e-1334-5a7e-856e-a0fd4e0827ae |  | note | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | ce6efd7b-d53c-516a-a9bc-03bb3a65f70d |  | note | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 7667eb34-7537-54bb-959b-f9941d9bcde3 |  | note | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | 0d41a090-1bf5-5aea-aca0-c36451bc73df |  | note | ○ +/- 3mm @ every 1000mm in length & height
text | e12fcd4e-7960-5089-934a-13def885c469 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Packers has been used to ensure the top hat frame is plumb for 0.55 BMT stramit sharpline panels to be cladded on.
label | 5ae09d26-cc93-5fb1-93d5-f30c56b1682d |  | note | Responsibility: Facadex
label | c52a38c7-305e-5afe-9ae0-920d50d82fa5 |  | note | – – – – – – – – –
label | fa6eb4d5-7efd-5cdc-a39a-ed8a6e9aa881 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 945936e9-5cb7-55aa-9cd6-10d702d92f63 |  | note | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 7496f83a-579b-57cd-86ee-0817ae1243e8 |  | note | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 531cf3e2-ad3b-52b9-a337-f01e5d2d2d68 |  | note | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | 643f0f23-7465-5053-9493-d2c433d92cc3 |  | note | ○ +/- 3mm @ every 1000mm in length & height
text | 9f53fdd5-81d4-58d7-8474-e445c5deb9cd |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Connections (bolts/washers/screws) checked for damages
label | b170b7ab-9756-55db-ad5c-18c73527334e |  | note | Responsibility: Facadex
label | 3cddb566-4b88-5c55-a96d-b8e844c0f8cd |  | note | – – – – – – – – –
label | 06b07bb5-3c56-5359-ab8a-88b4abfd6b07 |  | note | Acceptance Criteria: Facadex sign off.
text | 8cd633cd-9979-5b60-a1be-6b56aaa306fd |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | 3550258d-5147-5b60-bd13-8b36e3f1ed52 |  | note | Responsibility: Facadex / Builder
label | c640b87e-577c-5ad7-bd7a-b8fa8ec3a8c4 |  | note | – – – – – – – – –
label | a4e8b783-fcae-5f29-b44f-87a42c31f022 |  | note | Acceptance Criteria: Defect notification via email or chosen correspondence
label | 38a1e227-d21d-513a-87a5-8145a62eb22c |  | note | ○ Evidence of close out / rectification
label | 13a96de5-e89c-5ef5-9db6-ae7e61450c5d |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | e495ee69-b3d1-5f91-a6a6-c61b88e04c56 |  | note | ○ Sign of only once agreed that wall is defect free
text | a67d697b-5788-512e-84cb-02ae6c0bc5d9 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | 62f13360-9263-5628-b87a-e615bde484d3 |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | 1f598d3a-9f43-5ecd-8b9e-c1c73991a6a0 |  | textbox | Foreman – Checklist Completed:
text | 60da5f59-f01d-5c0d-b2ca-3dacf54bf835 |  | textbox | Date / Time:
text | 879db942-53cd-5e3a-9108-6cf00bdf9210 |  | textbox | Coordinator – Checklist Completed:
text | 62eb6db6-973a-58b8-85ba-6c2fdff72aec |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLG-506 Deflection Head Site ITP | itp |  |  |  | Yes | CLG-506 Deflection Head Site ITP | 9e5d96e4-0d48-4fc2-be00-3b1bdbd6926d
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC Shop Drawings Approved
label | ec42feba-a65a-5f59-b67d-35c151ef6a32 |  | note | Responsibility: MPX
label | 8f20785d-738b-5ba3-a92f-d31ff84b95e8 |  | note | – – – – – – – – –
label | 922942a5-0f7c-5cbb-9023-0e6b51497081 |  | note | Acceptance Criteria: MPX / Architect Sign Off
label | be78a95d-27d4-50f7-856b-453fc4f6463f |  | note | – – – – – – – – –
text | acad476a-b342-58b2-a86b-25469884561f |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | d64120be-932b-5c82-9b7f-94500bd51c19 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | 95c319e2-fb97-55d3-9753-28b38f78a9bf |  | note | Responsibility: MPX
label | df61d169-0860-5dd3-be67-130de4223cef |  | note | – – – – – – – – –
label | 0a3a00aa-3979-533d-8681-f140fcb2ccc8 |  | note | Acceptance Criteria: MPX / Architect Sign Off
label | ffae6a1f-37f5-52f8-ae05-b323bf97405c |  | note | – – – – – – – – –
text | 36810114-db3a-5ff4-b535-5d71018a084b |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | fd45bc23-a822-5b4f-ab83-6bdeaea2216f |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Materials (Deflection head/Bolts/Washers) delivered to site free of damage and deformation
label | 94a35d7c-1339-537f-aa5a-63a374997d9e |  | note | Responsibility: Facadex
label | 3dbd6bfd-96f7-584b-9188-26f1ab6b61fd |  | note | – – – – – – – – –
label | 211c170f-2148-51db-a0eb-d9c3cce53d86 |  | note | Acceptance Criteria: Facadex sign off.
label | dd3892de-5c93-536f-a215-585ccf71ad0d |  | note | – – – – – – – – –
text | 4fbf78d3-9b5a-5b9a-86ae-6e211ce5be92 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 6d5a7d22-0e11-50f2-bb10-192e6b8032e0 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Grid lines established and site set out complete
label | 78faedd6-a43b-51cd-af0f-051943d30b78 |  | note | Responsibility: Facadex
label | abaf31bb-0514-54fb-b845-4967acdb630d |  | note | – – – – – – – – –
label | ff9f5e9d-51c3-5e9b-a2f5-b74d43aec660 |  | note | Acceptance Criteria: Facadex sign off.
label | 64d8b4ed-21b2-5a9a-9e6b-7a41c903c983 |  | note | – – – – – – – – –
text | d355f971-3bd3-507e-a3b2-2f3a9551137c |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 3acb3171-44f5-590b-b881-071cfb1b06c3 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Deflection head installed as per shop details and location
label | 3f834c06-4882-5635-b9f8-c4c2d697a15d |  | note | Responsibility: Facadex
label | 169809e1-b0c3-538e-8d23-311d66566404 |  | note | – – – – – – – – –
label | f171cb1e-6de3-5313-8fe9-2035cad994dd |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | e8549b72-6dd0-5936-9189-d01e91754c15 |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 066f0883-ee82-5c89-aeca-46511d4087c1 |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | a4cdc3a1-5fea-5a25-8a08-3f7ccf0e22f8 |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | 177cd557-d590-5a21-a4f7-d85b78982055 |  | note | ○ Expansion & Contraction:
label | f6aab044-6dfb-5854-937b-50e3c6a0fbdf |  | note | +/- 3mm @ every 1000mm in length & height
label | 05497910-0055-5323-9fa2-76f00d9762cc |  | note | – – – – – – – – –
text | ec61ee0d-3ad8-5a3e-9728-11f27f09aefa |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 9c2cbe5e-4fce-564f-8a29-591d9ea9559a |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Correct size of deflection head has been installed to allow enough depth to outcome the tolerance of the slab.
label | c6a7a73e-9ae8-56dc-b7a2-3f62d2adab1d |  | note | Responsibility: Facadex
label | 303a7430-204d-5f3f-b068-2e9d147ed6ea |  | note | – – – – – – – – –
text | 48a3813d-0cab-5a3d-a6eb-1a4715f00c06 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | e3823289-0534-5d7d-b539-ca5846d7a845 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Ensure the deflection head installed was not bended or deformed.
label | 131662df-1f1d-5439-aeb5-f65a51e971de |  | note | Responsibility: Facadex
label | be4668bf-b20f-51d5-a87d-f6cb088fe98a |  | note | – – – – – – – – –
text | 1a3c18e2-aacb-5a73-b7e8-81b79f25ff12 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | d7dfb097-d8d1-54da-9736-ef02d9316005 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Connections (bolts/washers/screws) checked for damages
label | f9468045-b91b-5250-bc1e-7f454a44c192 |  | note | Responsibility: Facadex
label | 9ca5e50a-0cac-571d-8e80-e85aacded059 |  | note | – – – – – – – – –
label | 8dcce01d-b651-5f20-aa64-0e065ca2d3aa |  | note | Acceptance Criteria: Facadex sign off.
label | 29ae2819-6c74-5b75-b014-94e65782ac66 |  | note | – – – – – – – – –
text | d17441e7-67e8-5cf8-8c03-3b86a350df67 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | a3d49ec8-1bf1-5fab-a774-51083150b842 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | 23d8f660-8de5-5660-ad9c-8ec99cafcc9a |  | note | Responsibility: Facadex / Builder
label | 5c0df33a-e27d-5fa3-9226-2228cf4f5e5d |  | note | – – – – – – – – –
label | 87ab0518-d3d7-550c-91ea-b2ee624fc2fc |  | note | Acceptance Criteria: Defect notification via email or chosen correspondance
label | 2e84a30d-0720-5cec-96d6-d8111f338892 |  | note | ○ Evidence of close out / rectification
label | a38d3b23-057c-5157-ae4f-c717716c7158 |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | a2aaeeeb-2e7e-51ad-953d-20fcaf0fb2e0 |  | note | ○ Sign off only once agreed that wall is defect free
label | 6cb5e4da-6ab5-5a15-bd67-a27cb3e907a7 |  | note | – – – – – – – – –
text | 2c5fcd4e-5fc8-5bf4-a72c-bd3d9d80d9a7 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 630b2b71-a7ee-5afd-9d2e-de8067c7367c |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | 2ab3abc8-c304-59b2-b339-9a743dfc3782 |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | 07522270-9d02-5537-9151-0c0dfe128e17 |  | textbox | Foreman – Checklist Completed:
text | 219f08ee-29dc-53a5-a085-e5fc76475309 |  | textbox | Date / Time:
text | 2f48276e-c352-5978-9787-94dadb9e7a30 |  | textbox | Coordinator – Checklist Completed:
text | 1418abac-12c8-5a7d-9e8b-fde49106f9e6 |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLD-200 3mm Alum Perf CW Module Subframe (Building A) - ITP | itp |  |  |  | Yes | CLD-200 3mm Alum Perf CW Module Subframe (Building A) - ITP | a5ca9b32-00fd-44fb-88df-566baf0d3461
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC Shop Drawings Approved
label | 212e0306-739a-52d9-b53c-c7dd232e34b9 |  | note | Responsibility: MPX
label | 2c4df560-859d-5402-a50f-79b1c5791bf4 |  | note | – – – – – – – – –
label | a724d97d-8eab-5ae1-ae14-25d42a72f445 |  | note | Acceptance Criteria: MPX / Architect Sign Off
text | 260dbe3f-33e9-5008-8139-f5e107415e2e |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | 0cd39c71-6446-54f6-9df1-2d9b9857a0e4 |  | note | Responsibility: MPX
label | 6d980cb6-c167-57a8-9ca7-e159fa6bdb50 |  | note | – – – – – – – – –
label | 48babea5-2403-52e2-b77c-91bdf8b84cf3 |  | note | Acceptance Criteria: MPX / Architect Sign Off
text | a98decfb-ce1d-5518-bcbf-26f0247f2df9 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Materials (top hat/screws) delivered to site free of damage and deformation
label | 76251740-d912-5a95-87ec-e6053b214a51 |  | note | Responsibility: Facadex
label | 3a919c03-fcec-58d7-a399-37d49f8af8ca |  | note | – – – – – – – – –
label | f057f7a9-3e00-5257-b717-da64ba77e434 |  | note | Acceptance Criteria: Facadex sign off.
text | 9951d255-a1f3-5bd2-9703-6964d46ca914 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Grid lines established and site set out complete
label | bb3ed342-0e97-534d-a158-c48353027b6a |  | note | Responsibility: Facadex
label | 45c250aa-f764-5dd5-82a2-989aa3f529bf |  | note | – – – – – – – – –
label | 0221b609-a27e-5ac6-8833-347595ab26c4 |  | note | Acceptance Criteria: Facadex sign off.
text | 9add7763-b1cb-532d-b4b9-8f25377b8522 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | 50mm vertical top hat has been set out and installed to the primary purlin strcuture where needed.
label | 22c00d2d-6f53-51fa-aa87-8c77247494e6 |  | note | Responsibility: Facadex
text | 87b7e784-9378-5de2-b295-182ea0ce11a4 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | L-hook on bracket has been set out and installed to location on top of the UB with M12 bolts and carpal bracket washer
label | 64a5f5c8-6309-5e96-b48d-a79393449ad4 |  | note | Responsibility: Facadex
label | a40356ad-709e-5850-802e-d5b1f3361366 |  | note | – – – – – – – – –
label | b1f76eeb-3e21-56bd-b494-f59db08999fb |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | ca22f8e4-38f5-5e25-b7cd-ce1025edfa32 |  | note | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 25b7556f-2174-54d0-aa7c-e4f0033a2499 |  | note | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 2bd89fc5-a789-506b-bdee-703dd8f99ac1 |  | note | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | 6eb9b060-4ee3-5747-aca7-2c0afc70876f |  | note | ○ +/- 3mm @ every 1000mm in length & height
text | e089c87d-2621-56c1-af03-174f89afa983 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Packers has been used to ensure the top hat sub-frame is plumb and bracket has been leveled for module to land and installed.
label | 66bd4d24-65b7-5c78-9e27-062c77095b37 |  | note | Responsibility: Facadex
label | c75fa349-1f04-5725-b1d7-883fd81f12ed |  | note | – – – – – – – – –
label | 3746c11f-71d7-5461-a314-66ae3f18105c |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | fc0f252a-fd4a-5d40-824f-ae4e8b5b640e |  | note | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 187e4211-22cc-51de-861f-4f93fac1b88e |  | note | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | d7b3f7bf-1fe7-5267-9614-06f53f613cf9 |  | note | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | 54fb8e4f-335a-5e0c-a426-dd50836cd483 |  | note | ○ +/- 3mm @ every 1000mm in length & height
text | d0a8d73a-2bc3-5302-a4f3-2f55e55d028d |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Connections (bolts/washers/screws) checked for damages
label | 9bc08ddd-5017-5e92-945c-4423636a42a2 |  | note | Responsibility: Facadex
label | f4ec450d-7271-51e6-adc9-c6b27c98a46b |  | note | – – – – – – – – –
label | 159cfa32-55c0-5f94-8edf-ba02f39d4faf |  | note | Acceptance Criteria: Facadex sign off.
text | 6b0c9cb7-9b7d-558d-922a-6c5df07a22d3 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | 255cd87c-4217-5977-b52f-8ccbd1452d74 |  | note | Responsibility: Facadex / Builder
label | bf9bdc5a-b0bd-532a-9a7a-37ced92b68a9 |  | note | – – – – – – – – –
label | 2e6c2051-3477-5585-be17-75331e24fbd2 |  | note | Acceptance Criteria: Defect notification via email or chosen correspondence
label | d6723b2c-298a-5b0c-873c-e99f1d0b14b4 |  | note | ○ Evidence of close out / rectification
label | efed359b-e4dc-5aab-9b41-643310faef42 |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | 65346375-d8cb-5da4-a35b-2e295d5fd716 |  | note | ○ Sign of only once agreed that wall is defect free
text | 36033086-5cc4-58ab-a024-137b509f1c14 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | 4f004623-a04f-579d-a005-27f26b85a267 |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | 16f8c5ba-23f1-5ad1-8df3-81de37bf539d |  | textbox | Foreman – Checklist Completed:
text | 9fe283b1-c87f-5e31-a21e-41f55a9f01d9 |  | textbox | Date / Time:
text | 259e8aa9-77c1-5538-8497-b02d888bfc0f |  | textbox | Coordinator – Checklist Completed:
text | 57088a19-351e-51ac-91e9-ad0050fb8043 |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-flat |  |  | checklist | FADX-ITP-009 (FTC-05) FACTORY FABRICATION | itp |  |  |  | Yes | Factory ITP | a6095cd7-b3eb-40f2-9e85-f02de0de3b78
checkpoint-status |  |  | checkpoint | Check the delivery docket and compliance certificate is available upon receiving raw material
label | 625a6472-170b-5b8a-b1d8-bd1b14a74db4 |  | note | Responsibility: FACADEX
label | e12f7655-b4b4-5b16-8a90-f92f1308b256 |  | note | – – – – – – – – –
label | e693ceb0-08e7-5e0a-8c24-5386ecc817fd |  | note | Acceptance Criteria: Production manager to sign off
label | 148dd441-5bbb-58e1-9ef0-33ae5fa7e88a |  | note | – – – – – – – – –
text | 9e6a368e-157b-594a-b5b9-7de7cb2ab33e |  | textbox | Shop Drawing number:
text | d03267a3-eca2-55a5-b14f-25a89466a084 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Shop Drawings/Engineering and Samples approved for fabrication
label | c095b0a7-1ea3-5f3a-b0d2-dd0adadb5333 |  | note | Responsibility: FACADEX
label | f2bc06a8-7a19-5410-975b-4da196add95c |  | note | – – – – – – – – –
label | e1fc7442-3a21-5b66-b181-76d459ec5517 |  | note | Acceptance Criteria: Production manager to sign off
label | c6a00730-1d67-5e6f-a7b3-e278aef71ac2 |  | note | – – – – – – – – –
text | 82fbf331-9419-5a72-bc22-99a12bbc9f4d |  | textbox | Shop Drawing number:
text | bcb1fab9-06dc-5f78-97cf-824fa170af2d |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Connections as per approved shop drawings
boolean | df63a612-63eb-537b-95ad-7982b2e4fe7e |  | tickbox | (1) Welded (need to provide welding documents
boolean | 146eb661-9a86-5f78-bfd0-08a3224cb073 |  | tickbox | (2) Bolted, classify the bolt type (nug, TF or TB)
boolean | 012f7906-72c6-593e-ac23-ce283c4f7a34 |  | tickbox | (3) Other
text | 03bb9270-8b12-5082-b43e-5d40bf4b40d1 |  | textbox | Other - Please specify:
label | 5448e12d-6ae1-5582-b516-e9a0293fcbbd |  | note | – – – – – – – – –
label | c71b2087-fc4b-5279-80c6-09cdf4870df7 |  | note | Responsibility: FACADEX
label | 12a8cd21-d0ac-539b-bc84-68b6ca68a221 |  | note | – – – – – – – – –
label | 87653685-391f-5b7d-9ad1-407b00f71bbf |  | note | Acceptance Criteria: Production manager to sign off
label | f06ff1ae-cdb4-5678-b844-519bd9e1376f |  | note | – – – – – – – – –
text | a6aedff2-80d2-52f8-9abf-0336a22ec233 |  | textbox | Shop Drawing number:
text | f2880cc8-fcf3-5426-99c5-9c32bbb67596 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Confirm & check finish as per approved Shop Drawings
boolean | 2e11a29b-de07-58c3-ab4c-bea6470cf6d7 |  | tickbox | (1) Paint (check TDS)
boolean | f00db8d0-c784-5027-8dd3-9d70aafc33c3 |  | tickbox | (2) Powder coat (check warranty certificate)
boolean | 31d709c0-9080-50a2-bd2b-f0fc64be6e7b |  | tickbox | (3) Other
text | f50cfc1f-45cb-56c8-bfb0-1a143258277d |  | textbox | Other - Please specify:
label | 84197aa8-0b8e-5173-9082-d7788330ff73 |  | note | – – – – – – – – –
label | 5acde4d6-e455-5089-adb9-018f9d579791 |  | note | Responsibility: FACADEX
label | 9a7c2926-1949-5b80-87f7-33b87c53ba83 |  | note | – – – – – – – – –
label | 01d7b329-6531-5ba2-bb0f-3bde7478939c |  | note | Acceptance Criteria: Production manager to sign off
label | 0d949a47-3f81-5cd3-8ca9-6339638f3db7 |  | note | – – – – – – – – –
text | a77c9985-e79a-5321-a9e8-10b4a55020fd |  | textbox | Shop Drawing number:
text | 5f4b51c9-82a6-59a9-98c5-1572b5b6c05e |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Check Panel size and dimensions against drawing
label | 089915be-6a44-5ea8-a3b5-78598a0bcabc |  | note | Responsibility: FACADEX
label | c9c3c6da-bb8d-5be8-b8bf-866bf66376f1 |  | note | – – – – – – – – –
label | 844a8e96-a882-5230-8989-840db35a7b46 |  | note | Acceptance Criteria: Factory QA to sign off
label | 46e8cb6d-c406-59a6-affe-21786eb9b0d4 |  | note | – – – – – – – – –
text | 64f99acc-9937-5d51-a8c0-72901eaf8500 |  | textbox | Shop Drawing number:
text | 02456bf1-2136-5b3f-aa60-6029454b810a |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check Diagonal dimension to ensure odd shape panel are done correctly
label | 2b5026e7-58c1-5ec8-98c0-b77138403305 |  | note | Responsibility: FACADEX
label | 9bc09515-0f24-5576-8e6e-4671498ba077 |  | note | – – – – – – – – –
label | 632381a2-e2dd-53d2-8a71-6dd0636185ba |  | note | Acceptance Criteria: Factory QA to sign off
label | e585d8ef-2ef4-507a-8abd-9fc43fd3cff6 |  | note | – – – – – – – – –
text | 6bc488d3-bed5-52f1-9dbe-9cab7a5d6786 |  | textbox | Shop Drawing number:
text | ce95dc34-0e5f-54b5-be2c-6fa349d5a6d1 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | QA check delivery docket and receipt from the painter
label | 3c6b7ea5-d9d3-5e7d-a361-c3ed557707e3 |  | note | Responsibility: FACADEX
label | caa27e4a-b513-5943-b441-20a7058e182a |  | note | – – – – – – – – –
label | 94c2b28f-cb9e-5813-8a98-d9b809877e7d |  | note | Acceptance Criteria: Factory QA to sign off
label | c404aae8-ad8a-548c-b5ac-f933f97bf1ef |  | note | – – – – – – – – –
text | 325ee6ad-59b8-5de7-a5dd-364581f24100 |  | textbox | Shop Drawing number:
text | fbf0cff9-9fee-5730-aca7-9bde59f3027d |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Check Frame dimension against Shop Drawings check Factory QA to sign off
label | 1fca1036-de02-5c97-af8b-4652d3b5ce1d |  | note | Responsibility: FACADEX
label | 95b618f2-cf1a-5742-9094-73ce83d5a560 |  | note | – – – – – – – – –
label | 78dfa871-7fad-5fb5-948b-5be63042328a |  | note | Acceptance Criteria: Factory QA to sign off
label | a76a9cdd-54b2-5011-94d0-54ce84296956 |  | note | – – – – – – – – –
text | d046c2c9-fc9b-5ef2-a111-cfb615af71b3 |  | textbox | Shop Drawing number:
text | 26da131b-33e0-5136-81a6-850897c34f09 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check the finished frame is Square and plumb with bracket attached (if applicable)
label | cf0ffb69-97e4-5225-a3bb-a93f6be914ed |  | note | Responsibility: FACADEX
label | c62e1012-c334-5cdd-ae06-337e60e7c830 |  | note | – – – – – – – – –
label | d13cb2ba-1efb-58a6-81e4-65f304ff62a7 |  | note | Acceptance Criteria: Factory QA to sign off
label | a5ed0f30-c5d0-5106-9a85-cae2f9114042 |  | note | – – – – – – – – –
text | 108a7134-20e9-545c-98aa-07f98dad7819 |  | textbox | Shop Drawing number:
text | a082d7a3-da1b-528b-a7a5-d81a6c2fe852 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check if the Crash rail has been fabricated to drawing and attached to the frame of the module
label | b626b1d5-263e-5d73-a155-1e0221dba21c |  | note | Responsibility: FACADEX
label | ed39c058-b5ad-5a73-93a0-60a6e386d25c |  | note | – – – – – – – – –
label | 4257a763-d50c-5a4a-9ddd-36dbf4215ec9 |  | note | Acceptance Criteria: Factory QA to sign off
label | 36ff2fb9-7c03-571f-97b6-817b856c23d5 |  | note | – – – – – – – – –
text | 36fdb0e0-4547-559c-ab46-80a25463113b |  | textbox | Shop Drawing number:
text | af0abd3f-00a8-5054-93c5-13efeebc75b7 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check if external grow cable has been installed into the correct location (if applicable)
label | aa8e7e88-695f-5929-ab6a-fa0349d62f4e |  | note | Responsibility: FACADEX
label | f1aa88ed-3fb4-5a1a-90c6-5f40e9fa8487 |  | note | – – – – – – – – –
label | 451dd017-d135-57c2-8ef7-bc428f692c8a |  | note | Acceptance Criteria: Factory QA to sign off
label | fa0e2c84-533d-52d2-af03-2b8d59a86b87 |  | note | – – – – – – – – –
text | d85d2319-2534-52d4-95c6-0b177c231847 |  | textbox | Shop Drawing number:
text | fbfc3207-36bc-58ea-9672-bd84517ec7b1 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Installed finished panels to the frame, and spilt batten been locked with silicone
label | 32ddbfb1-9744-5283-bfb1-c205323f3bba |  | note | Responsibility: FACADEX
label | 7272fdf1-bb74-504b-ac35-06a153da4d43 |  | note | – – – – – – – – –
label | 476b4383-cadb-5d4d-b1f3-834388fa22cb |  | note | Acceptance Criteria: Factory QA to sign off
label | d4c32353-24af-596d-8e8c-3d8b5d06bc56 |  | note | – – – – – – – – –
text | 9a69d348-7c57-5136-87b4-bcdb3c541a53 |  | textbox | Shop Drawing number:
text | 97b91c12-e470-5e46-a683-12099655090b |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Horizontal cladding shall have a minimum slope of 1:15 and shall be sloped away from visible vertical façade areas to prevent staining
label | 5d5c9719-5188-5782-9c36-9ee7a673505d |  | note | Responsibility: FACADEX
label | 024029c0-dbb7-5e3d-afd7-ac021e849a08 |  | note | – – – – – – – – –
label | 52a96a66-2b6e-5440-9d9b-f6faf4eb3d90 |  | note | Acceptance Criteria: Factory QA to sign off
label | 6f6ebbcd-275f-5266-993a-81cd07b82652 |  | note | – – – – – – – – –
text | 8458c018-434a-5534-a1e6-a61b51043315 |  | textbox | Shop Drawing number:
text | de605846-770f-5e4e-a4fa-9416064223f8 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | No defects/scratch/dents/distortion/crack (visual) on the finish
label | ce1d0570-8d41-546c-b52d-81a071196868 |  | note | Responsibility: FACADEX
label | 7fe1ddbc-dee5-5131-967b-716a359439c5 |  | note | – – – – – – – – –
label | 6f4522e7-6909-5cf6-a386-118f73f0eead |  | note | Acceptance Criteria: Factory QA to sign off
label | c948b176-d30d-56cb-bf80-b613ff574d73 |  | note | – – – – – – – – –
text | 2fb185a6-b2f7-5735-8fb7-2025d2491f9f |  | textbox | Shop Drawing number:
text | d8de6fb4-0dc7-5c14-a771-71e9a94e0b36 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Is Fabricated item labelled as per drawing
select | 20fb3171-6c7f-59e0-94d7-cb88ce7ba0c6 |  | dropdown |  | YES - Label ID, NO
label | b043ddd2-3573-5dde-b93e-a2deeb10acd8 |  | note | – – – – – – – – –
label | 7ce2282e-a2f2-5c7e-a878-3d759cba29cd |  | note | Responsibility: FACADEX
label | d7828805-0d4b-5859-a906-6198046fa530 |  | note | – – – – – – – – –
label | 1b2f77cc-77c5-5e32-9e70-f3fcd9c04e4b |  | note | Acceptance Criteria: Factory QA to sign off
label | d4602960-64ae-5d8c-bb23-f37771debccb |  | note | – – – – – – – – –
label | 7b4af7a0-7de9-55e5-b052-b663a9b59d96 |  | note | Shop Drawing number: N/A
text | ec97bdeb-3b0f-5aac-85c1-5e9dfd0c617e |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Fabrication complete
select | c1860120-9306-58d3-afbb-2a2ff7a1b148 |  | dropdown |  | Yes,No
label | 58ac6d08-91c8-57cd-936f-5a212c386a77 |  | note | – – – – – – – – –
label | a276da2a-0639-5dc7-b5be-5009a98412cf |  | note | Responsibility: FACADEX
label | fb6ec0bd-7a2e-5830-af06-424f60d1b536 |  | note | – – – – – – – – –
label | 329d8472-32c6-5b4d-97e2-6fec6c509d6b |  | note | Acceptance Criteria: Factory QA to sign off
label | d6bf0815-a081-5261-8ba5-c74060a73751 |  | note | – – – – – – – – –
text | 461f8763-466d-5661-9a5c-0d07fa6e0a32 |  | textbox | Shop Drawing number:
text | 11c3db2d-bde7-59dc-85e6-4f650bed8ad2 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Lifting Lugs holes has been drilled on the frames
label | f86ee5e6-322c-580e-8aac-806d0c70ff65 |  | note | Responsibility: FACADEX
label | 215a0cbf-6b97-550c-8213-378e2146daa9 |  | note | – – – – – – – – –
label | 6b57f1ad-da9c-52d7-bfc4-a1afe1a0dbd9 |  | note | Acceptance Criteria: Factory QA to sign off
label | f1a5213d-ade9-5e05-9200-522300c16399 |  | note | – – – – – – – – –
text | 36c42502-437b-5fe1-8db8-105aa10d658d |  | textbox | Shop Drawing number:
text | c53dbe18-d384-523a-b512-258efdfe101c |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Prevent direct contact between incompatible metals, and between green hardwood or chemically treated timber and aluminium or coated steel
label | cc6414b1-ef97-5183-b60c-f569709e4505 |  | note | Responsibility: FACADEX
label | 178967f4-8405-5156-821a-f1b4b1e081fa |  | note | – – – – – – – – –
label | 7d6df5ea-4aaa-5fe8-a078-79681f7b4394 |  | note | Acceptance Criteria: Factory QA to sign off
label | bab38f7d-a826-5282-abb9-077e36e9250b |  | note | – – – – – – – – –
text | d673a6e3-fd6b-576f-9363-dfb99f6febff |  | textbox | Shop Drawing number:
text | 48b973ef-3200-5236-95c6-b51f159b01b4 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Pack onto the stillage for delivery after completion of all above
label | e8dbe55d-be3d-5b32-906b-b1e269c63e8e |  | note | Responsibility: FACADEX
label | 51e0af72-5d6a-515f-8bf2-5a206c9ba063 |  | note | – – – – – – – – –
label | 9d3ebd54-b35f-5c69-8678-30e54fb5b6b4 |  | note | Acceptance Criteria: Factory QA to sign off
label | 187c4d8e-f37a-5f98-b6c5-b902a335751b |  | note | – – – – – – – – –
text | fdc320c1-52b6-5b0e-9937-4c4e57a70fd4 |  | textbox | Shop Drawing number:
text | d7bbeb39-b321-56e7-af21-d1a70f4ce70d |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | 6e59265d-a5ff-5a6d-a194-30dc5b3231e2 |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
label | 27b00249-4140-5af4-8451-a0333b378eab |  | note | Ensure the product was done base on the design complying AS standards including the following where applicable
label | 0f4db547-3000-5a9d-9a8e-f12f988c4276 |  | note | • AS1562.1 Clause 5.5 (Resistance to wind pressures)
label | 09d3fd3c-903b-5ecc-8a36-3d824afdd48c |  | note | • AS1530.1 (Combus􀆟bility)
label | 446bd1f4-0dce-54db-ad0d-83488b2b9ed4 |  | note | • AS5637.1 (Fire Hazard Proper􀆟es)
label | 30b50adb-99aa-51ae-8a94-d9ea489c3e78 |  | note | • A S1530.4 (Fire resistance level)
label | ef5424ba-fbe8-571d-9949-751778ee698a |  | note | • A S2904 (Flashings)
text | f9a7d293-3a48-530f-b1f0-0f7749099f2c |  | textbox | Lead Fabricator – Checklist Completed:
text | 6c95c88e-4636-5f50-a655-2d40bdb28650 |  | textbox | Date / Time:
text | e302f4b5-7212-5a71-b527-a59f6ea25cda |  | textbox | Factory Manager – Checklist Completed:
text | 0d48b999-7129-5b8a-8231-1fe84ea1838b |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLG-506 Factory ITP | itp |  |  |  | Yes | CLG-506 Factory ITP | a8d8a701-b9f9-4e55-ab7c-75f5479594ea
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC shop drawings approved for fabrication
label | 70d823a2-bf8e-5990-b9c0-b1204af298b8 |  | note | Responsibility: MPX
label | c7249360-6dfb-5d42-86e0-86361e912a11 |  | note | – – – – – – – – –
label | 5412c742-5de5-56c5-bf50-87c0159147b1 |  | note | Acceptance Criteria: MPX / Architect sign off
label | 99a80e88-7f5a-5d30-9eff-25803eb81248 |  | note | – – – – – – – – –
text | e35c7fa5-0716-560e-9af8-0a39d16c8c57 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 0f0c66a2-c12b-5d90-a888-6413f0161391 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | 40ae0912-3a96-5059-abb0-cc0066a6ab97 |  | note | Responsibility: MPX
label | 57bc53bf-fd9a-55ca-9f5b-e3efaf67f3f8 |  | note | – – – – – – – – –
label | f6b46f22-9c74-50a9-a29f-206a3a8b293d |  | note | Acceptance Criteria: MPX / Architect sign off
label | 99e86514-6695-5392-9e8d-73c71987f1c0 |  | note | – – – – – – – – –
text | 5c34e264-f1c9-5187-b019-b7154da5f892 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 563fa043-8857-542d-b7e4-bc6510729f71 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Confirm and check finish as per approved IFC drawings
label | 346d58ab-c4f9-58ad-880b-e50dbde2e4e2 |  | note | Responsibility: Facadex
label | 0a5ddfa6-6e70-5e3a-8aaf-388f30121df0 |  | note | – – – – – – – – –
label | 0f409032-86b1-5187-9e59-5457bfbd4aba |  | note | Acceptance Criteria: Facadex sign off.
label | 849126ad-a1de-5363-a727-259f032caa4a |  | note | – – – – – – – – –
text | 7a17b7b6-e320-5549-812d-cbf09cf11ea2 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 0e3e8104-6d74-564a-8058-c849520589ce |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check panel size and dimensions against IFC drawings
label | 8f19cf8d-7a2b-515c-9919-195a505d99f6 |  | note | Responsibility: Facadex
label | 52ca2005-a6de-53a8-a9d1-73be3873cf6c |  | note | – – – – – – – – –
label | c9d1f4ae-d4ab-5ab7-bf45-1dabdf832062 |  | note | Acceptance Criteria: Facadex sign off.
label | 70ad9ff0-0fcd-59c6-acc6-13b98df358f5 |  | note | – – – – – – – – –
text | ba8384a4-410a-5fb9-b714-9ba5157c7541 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 62956516-fd29-55ed-8fbd-118d9707a640 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check diagonal dimension to ensure odd shape panel are done correctly
label | 082e9df3-6659-5fa4-b334-94d1c279401c |  | note | Responsibility: Facadex
label | 9ca1d378-0d2f-55c9-bf16-648e604c3bf5 |  | note | – – – – – – – – –
label | a55d51c4-4651-5f04-a071-368c1155668c |  | note | Acceptance Criteria: Facadex sign off.
label | a8b5e172-77a0-5aa2-b630-6ae79ce51059 |  | note | – – – – – – – – –
text | 9a89897a-7f53-5cd0-a9ae-9f59bea95de4 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 5cc2bbc8-9adc-54b7-a6cd-ef8f1438c026 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | QA has checked delivery docket and receipt from powder coater
label | 2c0769c4-2576-58f8-8a36-6921c041ecbc |  | note | Responsibility: Facadex
label | f62cf42d-8dde-591b-a6ac-2ff20a6cb337 |  | note | – – – – – – – – –
label | 2333e8fa-679e-512c-a06d-9638a26af206 |  | note | Acceptance Criteria: Facadex sign off.
label | 10bebae7-42d7-5efa-9e5d-7eed6da0018a |  | note | – – – – – – – – –
text | fc1c2daa-14ad-58f7-b48f-35ca568e61ad |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 0ea041ac-61e9-5686-bce4-f7114926d2b2 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Is fabricated item labelled as per drawing?
label | 1cff9b89-a192-55ef-93b0-d92fb47d57d9 |  | note | Responsibility: Facadex
label | fd05bf36-81de-5664-8f4b-23e1b139deeb |  | note | – – – – – – – – –
label | c1f857c1-b2da-5430-a195-27b1520f9055 |  | note | Acceptance Criteria: Facadex sign off.
label | b1e2f302-f212-5d83-985e-58ff357383c7 |  | note | – – – – – – – – –
text | 6e016355-55e2-551b-87e8-a6b0637877f2 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 2d19e15e-e745-5f4a-8f5b-09f511d51a23 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Fabrication complete
label | 0e35ebe2-b56b-551b-9cb4-1bba5503182e |  | note | Responsibility: Facadex
label | 6921f94f-a584-5e80-9c66-58bda8a11e51 |  | note | – – – – – – – – –
label | bb7805b9-959e-5661-99e6-12e903cdbaeb |  | note | Acceptance Criteria: Facadex sign off.
label | 71f27e52-65ba-53d9-bd20-394bdb4ae353 |  | note | – – – – – – – – –
text | d810d8e2-0cd8-5782-a647-a65c99bd6417 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | de409ba8-d030-5967-ad8f-b620194b757d |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Prevent direct contanct between incompatible materials
label | e45d48a8-d3f4-5ca1-b45d-6835414a0de9 |  | note | Responsibility: Facadex
label | d3e07e01-e355-5f79-bb03-9ef7d6513162 |  | note | – – – – – – – – –
label | ce198fa2-ca97-5401-8e31-50081deba2e0 |  | note | Acceptance Criteria: Facadex sign off.
label | 46fb2aa4-dc2f-5031-9f95-511a60d9194b |  | note | – – – – – – – – –
text | 5ff982e3-22dd-50fa-b233-34c8b5a5b9b5 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 1b9e6ba0-f21b-5c5b-9fe4-39d93dd40fcd |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Materials ready to deliver on site
label | cf01892c-7b94-5646-9484-31e8f22af958 |  | note | Responsibility: Facadex
label | 212910b4-aa7b-5140-b234-277bf7850697 |  | note | – – – – – – – – –
label | dd90abdd-3574-54e6-8d5e-63939561e8fe |  | note | Acceptance Criteria: Facadex sign off.
label | ca79efe9-0837-565e-8bfc-dc851f156c27 |  | note | – – – – – – – – –
text | 7665a709-76f3-5599-9213-a7db575df216 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | df8c175e-3d98-5e4f-8158-fc7f2d036506 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | 76f90667-7f46-54e8-97cb-e2809ceb2458 |  | note | Responsibility: Facadex / Builder
label | b8124c35-7677-5ddb-abae-ded8afd0a971 |  | note | – – – – – – – – –
label | d7bca593-d191-5149-a727-85ff3572a0e5 |  | note | Acceptance Criteria: Defect notification via email or chosen correspondance
label | 81473786-2d9b-5385-b6b3-f58edcaee6a8 |  | note | ○ Evidence of close out / rectification
label | 920f2859-b3cb-53e6-affd-17bf1f55db2a |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | 1081add7-1428-5e22-9e65-50b4f7facca6 |  | note | ○ Sign off only once agreed that wall is defect free
label | 397e1602-5882-57dd-b4bb-c1d1d874c6c5 |  | note | – – – – – – – – –
text | fa79b4b8-9a32-521f-ae24-32b7c5078619 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 38705878-1805-556c-853a-16168b7affb7 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | 37bcad73-cbe2-52be-be33-498c2ba42c05 |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | 9adc8865-56d9-5d00-afe6-30bf76b4938f |  | textbox | Foreman – Checklist Completed:
text | d1fdeca0-eaa1-5a8d-b09a-d3b371b223bf |  | textbox | Date / Time:
text | d2009e41-99b1-53ee-a2b3-2f98eab2e744 |  | textbox | Coordinator – Checklist Completed:
text | c4e64cd1-2580-55dc-8057-6ca78fafbadc |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLG-513 and SCN-125 Cladding Panel ITP | itp |  |  |  | Yes | CLG-513 and SCN-125 Cladding Panel ITP | aa6f6210-8dfe-455a-bf2d-94f3a0421ca7
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC Shop Drawings Approved
label | b2a04f43-b11c-5bcf-8168-a7b4daa27bb6 |  | note | Responsibility: MPX
label | 7d251a76-66c4-5e40-afce-ee1283b48cc6 |  | note | – – – – – – – – –
label | af518b03-3114-559d-b5d4-3958b573474a |  | note | Acceptance Criteria: MPX / Architect Sign Off
text | 283da348-e673-512c-84fd-28acdf636abd |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | d9768b8e-613e-5c58-86c1-da4a1d24843b |  | note | Responsibility: MPX
label | 7f535113-b73b-5eae-88c5-73d9827b7f1b |  | note | – – – – – – – – –
label | a858d086-b888-5039-9cd5-6a8ef855bf2a |  | note | Acceptance Criteria: MPX / Architect Sign Off
text | 3a1e6f36-c4d3-5227-8635-16b919c4f7f0 |  | textbox | Date:
label | 03066ee1-aa0a-5a09-be9c-b4a3f8f261e9 |  | note | Comments: Check colour is correct as per shop drawings
checkpoint-status |  |  | checkpoint | Materials (Panels/Bolts/Washers) delivered to site free of damage and deformation
label | ec5c908f-cedf-57cb-a590-2bc8335166d3 |  | note | Responsibility: Facadex
label | f46f80c0-bf15-5c7b-84e9-ea4af98dd2fb |  | note | – – – – – – – – –
label | 9079e608-4ea5-5e76-953a-cdf1f51292f6 |  | note | Acceptance Criteria: Facadex sign off.
text | e4946dec-4934-5409-8289-442060359925 |  | textbox | Date:
label | 2e7f0ad1-2592-52b3-aa5c-bcd1e478cfc9 |  | note | Comments: Check colour is correct as per shop drawings
checkpoint-status |  |  | checkpoint | Grid lines established and site set out complete
label | bb3d9c20-d1e0-5107-851a-0817ff7fd8bc |  | note | Responsibility: Facadex
label | b5c5feba-4e75-5618-96ef-2053d550c568 |  | note | – – – – – – – – –
label | a3ee8752-ba91-57ea-ac99-a671a263c632 |  | note | Acceptance Criteria: Facadex sign off.
text | 8509597d-0505-542d-9fb3-b5c91893c8d6 |  | textbox | Date:
label | 4f49ec78-5b6f-51bf-9f00-2bddf0ab979a |  | note | Comments: If installed off site no gridline available
checkpoint-status |  |  | checkpoint | Cladding Panels installed to manufacturers specifications
label | 273291c5-6b02-5721-ac89-3d5c954cce00 |  | note | Responsibility: Facadex
label | 61c7653d-d9db-5f93-97ec-84b5219d2a6b |  | note | – – – – – – – – –
label | 38ac5727-a22f-5010-bd22-f408961e74b1 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | e183caf8-9e17-556c-aca7-6473356a9712 |  | note | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | c002de37-e8a1-5205-bb33-3305da2fc767 |  | note | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 01fe8b3a-1f36-5bf9-9a3b-a33edbbd480c |  | note | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | 28f4cdd8-7377-5448-960a-e76e1d8c06a4 |  | note | ○ +/- 3mm @ every 1000mm in length & height
text | f83bfc8e-4b4e-5e40-8da0-76eb073645c5 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Cladding Panels checked for paint scratches post installation
label | e91658bc-6565-5aa9-95ca-4f40a4dfa96a |  | note | Responsibility: Facadex
label | 4d6e39b9-3ac1-57db-9347-4c71798e7751 |  | note | – – – – – – – – –
label | cf37fbdc-f836-5963-aabc-486060f95b66 |  | note | Acceptance Criteria: Facadex sign off.
text | 038a2d65-f2e6-52b5-aca0-9b8ef80cfae1 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Connections (bolts/washers/screws) checked for damages
label | 92ca7ab0-f14c-54a1-bfc0-dceca31f6f61 |  | note | Responsibility: Facadex
label | 1fbf6278-f6fe-5baa-bc63-c7b1a040e58a |  | note | – – – – – – – – –
label | 036e0b4c-ced2-5342-886d-b179b4ac6b99 |  | note | Acceptance Criteria: Facadex sign off.
text | cc73e77d-661f-52e6-8c41-487cb36a36f7 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | bd9eb073-e441-5f46-9513-2e775a9dab12 |  | note | Responsibility: Facadex / Builder
label | d672fcea-5b08-5f50-b90e-77e38af20a6d |  | note | – – – – – – – – –
label | 83cb090f-0dc5-5727-b20a-08d3e1fb38d5 |  | note | Acceptance Criteria: Defect notification via email or chosen correspondence
label | 1d4eb186-e619-5f33-a1b5-22148f7d1ed5 |  | note | ○ Evidence of close out / rectification
label | a1a12eba-4bff-51c0-9ff7-762b3709d480 |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | acacdb16-cde8-544b-a392-b130d8b765dd |  | note | ○ Sign of only once agreed that wall is defect free
text | 2e7d3485-5bcd-5f6d-8c3f-638c5e3b7368 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | a47e2b10-518e-5d28-8a72-ec1a7af38192 |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | b1d78779-f9bb-5b2a-88b2-2be8a77cb9b7 |  | textbox | Foreman – Checklist Completed:
text | ee70ef67-569a-505e-8b64-7fc9e25c29b6 |  | textbox | Date / Time:
text | 4dce8f07-a328-5ba3-8566-eb4a08dcfaa7 |  | textbox | Coordinator – Checklist Completed:
text | 27f41197-9aac-5964-ba5e-fd28f0ec5330 |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-flat |  |  | checklist | FADX-ITP-008-2 (FTC-05) SITE INSTALLTION - CLADDING | itp |  |  |  | Yes | Site ITP | b397a6d7-cca5-48f1-8861-bed4b54052ac
checkpoint-status |  |  | checkpoint | Multiplex - IFC Drawings Shop Drawings Approval
label | 375dc2e4-6c4c-5cb2-bc5d-8534b49a3c3f |  | note | Responsibility: Multiplex
label | 42a48771-55c5-598d-91b6-863e2cbfd6c6 |  | note | – – – – – – – – –
label | 9b1ac2f3-630a-591b-b466-d18bf4ecd894 |  | note | Acceptance Criteria: Multiplex Sign Off
label | 82d0d0d1-5db8-5fc9-9184-0e7540cb4f53 |  | note | – – – – – – – – –
text | 7db3fb7a-af22-5372-bd7a-e96d2a57a759 |  | textbox | Reference Document AS1562.1-1992
text | 1b9f4d29-1c4e-555a-82cf-7183d1831882 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Multiplex - Material Approval
label | a3ca32ff-d6ad-5c41-9098-cfbc48d55b0f |  | note | Responsibility: Multiplex
label | 2ad41f74-9e3d-5ac4-8cdc-d86ec848ba74 |  | note | – – – – – – – – –
label | b0d84d74-d2f5-5e71-b91f-ea86c01fcb3b |  | note | Acceptance Criteria: Multiplex Sign Off
label | 5ffcd931-5cf4-5f1f-b19e-f82fd74792d6 |  | note | – – – – – – – – –
text | 3b9a6dc3-ee0d-53ce-9dbd-a05be19b048b |  | textbox | Reference Document AS1562.1-1992
text | e41fa686-4e5c-5469-82ac-17f62c0e5fdd |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Materials - check materials meet Aust Stand AS1562.1-1992 and are supplied as ordered and specified for the project
label | 2262002c-4168-5315-aafc-d96c04ab95ee |  | note | Responsibility: Facadex
label | 0246b43e-2645-572e-8fb7-d153169ab1ea |  | note | – – – – – – – – –
label | 77aaccf4-d297-58aa-9003-644689b85104 |  | note | Acceptance Criteria: Facadex sign off - Site Supervisior
label | a177932d-c09e-5da4-8839-c6952480f31a |  | note | – – – – – – – – –
text | 4a75fa36-531d-5ffb-8c2c-96c8b9622192 |  | textbox | Reference Document AS1562.1-1992
text | c96f8371-4a3b-59a0-8aa4-d33f19088f91 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Multiplex - Materials inspection upon delivery and prior to installation
label | 75d6e21b-8588-542f-b3d2-a64dc2634d08 |  | note | Responsibility: Multiplex
label | 7b596a9a-24a6-5e22-9966-d352fa30a225 |  | note | – – – – – – – – –
label | 8b2747ab-71fd-5502-8a22-d0ef77f635fe |  | note | Acceptance Criteria: Multiplex Sign off AS1562.1-1992
label | 79bf3255-45d5-573a-9031-70d59fca297d |  | note | – – – – – – – – –
text | f246091e-d37d-5552-9c12-0252deebe8df |  | textbox | Reference Document AS1562.1-1992
text | 60735879-4169-58e1-88e8-f40dde0616af |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check Structure is level and plumb prior to commencing subframing for wall cladding
label | 9524b9c7-63bc-5c7b-818f-c32a0dc32f2f |  | note | Responsibility: Facadex/MPX
label | 74e66e39-2c89-5f87-9b82-5fc62dd3ce87 |  | note | – – – – – – – – –
label | f1a13bb0-f134-5c80-beac-9fc83f6e1228 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | a89e956f-5906-5a75-a9ab-495a5a3c2489 |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 434e3cd0-53f3-52e5-abf5-984563f51355 |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 871f8509-3732-5463-9bd6-0cba8fbe1cb3 |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | b0ca7f48-f976-52fd-a4fb-0bd7836c1976 |  | note | Expansion & Contraction:
label | a54c81c2-8e5b-5d19-8bd8-582956a98abc |  | note | +/- 3mm @ every 1000mm in length & height
label | 9977885a-32d2-5d09-82c7-4cc130a1470d |  | note | – – – – – – – – –
text | 12d2166e-c7a8-5128-9fa2-2700f3668593 |  | textbox | Reference Document AS1562.1-1992
text | d9a13fbf-14b6-53c7-ba26-f01c8a126c4a |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Site Installation – Grid lines established and RL by MPX
label | 10de62b0-d21a-5b66-b826-4f9de2a8880f |  | note | Responsibility: Facadex
label | 8e748471-2120-5f17-a2ed-98aa7c94a094 |  | note | – – – – – – – – –
label | c1030b1c-1ef5-5c7c-a5b2-db4a71e3524f |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 0f123567-9b21-5878-955f-884a2e069b84 |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | ef6ee5d4-83da-5b6e-b165-2751a3d79cf2 |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | f540c3f1-39b0-5001-a9c7-dd1786455fb2 |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | 5e6634a7-c085-5f37-9e0d-94ad957b4bbd |  | note | Expansion & Contraction:
label | 91654a4f-f42f-5dc3-b6ef-db9c1506acc0 |  | note | +/- 3mm @ every 1000mm in length & height
label | fde3cd3d-7199-5ca4-8cd6-c7b71b6a0d10 |  | note | – – – – – – – – –
text | a5232d9b-6440-549c-8cef-c1fff5d0a899 |  | textbox | Reference Document AS1562.1-1992
text | 26129f59-0496-5e3f-b967-88cb6f00ecb2 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Site Installation – Installation: SHS framing and Cladding including all capping and flashings Sealing and Cauking
label | 2027faa3-75b2-50e2-aafc-ab30106d4128 |  | note | Responsibility: Facadex/MPX
label | aeeaf1e1-bb26-5445-b45c-3c02a173c7cb |  | note | – – – – – – – – –
label | 9e2e4995-f43f-596d-a712-f11b61b2cb0f |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | b8609cdc-42af-5c25-912a-b5ef31aeb78b |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 2a3ad29b-8465-5c5d-a49d-baec46460396 |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 3238d4ba-b63a-55b7-9ef7-f8d3b4e1a351 |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | 4b0b18fd-d4dd-572b-b41d-68a29845a115 |  | note | Expansion & Contraction:
label | 47377dd8-c21c-51d2-bf28-797274ccddb6 |  | note | +/- 3mm @ every 1000mm in length & height
label | 2001a949-448b-5498-991e-18679c6789fb |  | note | – – – – – – – – –
text | 8e7bf28a-b761-5401-ac45-883b0b3e2531 |  | textbox | Reference Document AS1562.1-1992
text | f7bed550-c060-5c8d-82e7-4656733ee043 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Site Installation – Ensure the internal crash rail and external Grow cable are installed correctly
label | 134c248f-2736-5444-a497-bc4641c18556 |  | note | Responsibility: Facadex/MPX
label | 709803c3-6dc8-5aa0-baf2-2426e13ebabf |  | note | – – – – – – – – –
label | 1015d656-9055-5ade-8df0-3bb0f9be9bc2 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 788c1ff0-057a-57cc-8604-d1ede3a3f3a7 |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 01f6c101-fa8c-51d4-8812-896233ea2a24 |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | e718c60e-6e6b-5edb-bb5f-c17fcf1ca434 |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | 5d797ec5-f75a-5672-b6e0-fc4c1e9ea78c |  | note | Expansion & Contraction:
label | feaee893-ab8e-5e2a-8662-7cca3ee5b017 |  | note | +/- 3mm @ every 1000mm in length & height
label | a3f528e7-8f80-5efd-9b7a-643152d5df96 |  | note | – – – – – – – – –
text | 684c500e-4435-5381-af49-636b08eb7934 |  | textbox | Reference Document AS1562.1-1992
text | 9012a517-235f-5637-acfb-4ecca4dfd618 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed wall with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | 6f834f74-6fa6-5a9e-8995-5b9f698b95a6 |  | note | Responsibility: Facadex /MPX
label | 114e2e95-8358-5f71-8ab5-f8912cdbe934 |  | note | – – – – – – – – –
label | 556c8d59-28c7-51f1-a3e4-e42f5fd1b22a |  | note | Acceptance Criteria: Defect notification via Teambnder or Builder email
label | eb2c966a-429e-5d1a-ac6f-1952c0eb8a4c |  | note | Evidence of close out / rectification.
label | 2b806cf2-9380-52aa-ae43-d239d9021d89 |  | note | (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type).
label | 6b9f4dff-268f-52cd-8adc-55a0451e224c |  | note | – – – – – – – – –
text | 9928bf78-7a90-5c53-bcc3-06b651c83fcf |  | textbox | Reference Document AS1562.1-1992
text | ec61ee3d-70f5-5daa-8085-b0bb913c9e79 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | d89b27f3-504f-5ba3-bdb9-656dcb803596 |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | 24abdced-38bb-585e-9c5c-536d049a75d1 |  | textbox | Foreman – Checklist Completed:
text | 96623418-9a82-5076-8999-415ce8fe869d |  | textbox | Date / Time:
text | 8abc786a-1847-505a-ad0e-f29b38a5f540 |  | textbox | Coordinator – Checklist Completed:
text | 76a9a240-b5c4-59dc-ace1-25efc7d609c3 |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLD-200 3mm Alum Perf (Building D) - Panel Site ITP | itp |  |  |  | Yes | CLD-200 3mm Alum Perf (Building D) - Panel Site ITP | be13df6c-c675-44ed-937d-76f84dc1c704
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC Shop Drawings Approved
label | 1f1a2008-9b5f-5ee5-81bd-631b61cefdc2 |  | note | Responsibility: MPX
label | 55fa2254-3ef6-5d70-89dd-1a64e2721eb9 |  | note | – – – – – – – – –
label | ba231f65-eaff-5d85-aeef-980dc8d2d02a |  | note | Acceptance Criteria: MPX / Architect Sign Off
text | cfe3f3a1-20ed-5770-bc6a-ea05f24ccc60 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | 4c241d82-e23f-5a32-81fd-a37dfcd64a4d |  | note | Responsibility: MPX
label | 8d748ae3-6ea3-53b6-aba7-d31fae6ccf46 |  | note | – – – – – – – – –
label | b282e26e-fa16-593e-9193-f95c0508bcd3 |  | note | Acceptance Criteria: MPX / Architect Sign Off
text | ea1b3133-554f-5b60-8e94-df569fa60ec4 |  | textbox | Date:
label | 80bf245c-2b39-5c59-8844-0d0f166659f5 |  | note | Comments: Check colour is correct as per shop drawings
checkpoint-status |  |  | checkpoint | Materials (Panels/Bolts/Screw/Washers) delivered to site free of damage and deformation
label | 7c60cf99-70cf-56d0-9185-6b550eb9a706 |  | note | Responsibility: Facadex
label | 422a5442-c9e8-5554-9876-d6c338c3cc60 |  | note | – – – – – – – – –
label | fdb76bdd-61ab-50f2-9df6-fa3a9974b62d |  | note | Acceptance Criteria: Facadex sign off.
text | b7b9f71b-e052-523c-9c4a-9588b3536e6a |  | textbox | Date:
label | 7d378583-f76d-5c83-8300-1aa780fdb74d |  | note | Comments: Check colour is correct as per shop drawings
checkpoint-status |  |  | checkpoint | Grid lines established and site set out complete
label | 2e3c5609-9315-5dd1-a07a-745130f8bf78 |  | note | Responsibility: Facadex
label | ef2b5d46-76d5-590e-bbe1-32c8f4408d1b |  | note | – – – – – – – – –
label | b76e7a80-62c4-5ada-8c0f-bca5a531c615 |  | note | Acceptance Criteria: Facadex sign off.
text | 78d02d36-d8cc-5a1d-91ee-253f697ee5e3 |  | textbox | Date:
label | 856abb3f-57bc-541a-afe2-24ae07d2b79f |  | note | Comments: If installed off site no gridline available
checkpoint-status |  |  | checkpoint | Perf Cladding Panels installed to IFC specification
label | f35279bf-c28a-5d9e-b331-b48e05edafc0 |  | note | Responsibility: Facadex
label | 3b39f105-daf2-5829-a62a-aea9cc41fb85 |  | note | – – – – – – – – –
label | f51e31dc-cc05-5499-8891-3dfad5f2e1b2 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 5ec5fe13-1ba0-5042-b1db-7b1e5477f7b7 |  | note | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 3df1e95a-2f9d-5618-9316-437ff2f72101 |  | note | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | bbcac7a5-557a-5b4b-ab2f-0046e9468d8a |  | note | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | a125428f-e837-5a2a-9f25-1faf68cc02de |  | note | ○ +/- 3mm @ every 1000mm in length & height
text | 71b8fde7-1a4c-5572-8c48-72461f5bb2f1 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Perf Cladding Panels checked for paint scratches and dents post installation
label | 0dd3f0c9-0870-5d6e-80e3-e36311e6fb63 |  | note | Responsibility: Facadex
label | da0ed67a-7d45-5e34-b00d-98b43c9226cd |  | note | – – – – – – – – –
label | 7e6a0c6d-c3bc-536c-9bf5-228104e50f48 |  | note | Acceptance Criteria: Facadex sign off.
text | fbbb1090-f423-5740-b59f-04914d4fde18 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Perf panel fixed with 4.8mm diameter x 11.4mm Rivets @300crs
label | 4f525839-bb53-57d6-987b-6080f853d17c |  | note | Responsibility: Facadex
label | 72053257-f62a-55e4-b46e-1f54ae3a2f0b |  | note | – – – – – – – – –
label | 5472fbf1-1212-5b20-8c48-2452291db2ea |  | note | Acceptance Criteria: Facadex sign off.
text | ae1d386e-73d6-59bb-aefb-1a526f13d245 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Connections (screws/rivets) checked for damages
label | c4406e99-eb43-54d4-8c68-695ee28dc6fa |  | note | Responsibility: Facadex
label | 6f360488-5c52-53a0-b539-1b0aee3e53b5 |  | note | – – – – – – – – –
label | cd1c8970-2fcc-5b00-840d-df60f00c4e6a |  | note | Acceptance Criteria: Facadex sign off.
text | 321a875f-79e0-50e1-b5e4-37a24f7ee91d |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | a50114f4-7a87-5a41-8e80-9437a89d4689 |  | note | Responsibility: Facadex / Builder
label | 654678f3-9d3a-56e8-93c4-86075203c4d2 |  | note | – – – – – – – – –
label | 240e73a1-6dfb-5a7c-8e59-b842588d1bdc |  | note | Acceptance Criteria: Defect notification via email or chosen correspondence
label | aa85eb3f-8dd8-5be3-8ce7-598ce7581d37 |  | note | ○ Evidence of close out / rectification
label | 361ea8fd-1714-53c8-b130-93372c2f444d |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | df09526e-dd0a-5130-a2aa-c154b22694f1 |  | note | ○ Sign of only once agreed that wall is defect free
text | fcac8eff-f735-5cf0-b4a0-f7186a36b3d2 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | 6327a3a9-b310-5442-ac48-b1dd7553005e |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | 6547d558-e71c-5a8d-a04a-d4dfa03e3d55 |  | textbox | Foreman – Checklist Completed:
text | 13968888-0fcf-5c3d-92a4-113f6805d07e |  | textbox | Date / Time:
text | f824f3a9-dc46-5643-895e-b2384bc34498 |  | textbox | Coordinator – Checklist Completed:
text | aec649e3-e5ed-5f62-833b-d80dcc25fb08 |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLD-200 3mm Alum Perf CW Frame Panel (Building A) - Factory ITP | itp |  |  |  | Yes | CLD-200 3mm Alum Perf CW Frame Panel (Building A) - Factory ITP | be222f7f-6b2f-4fa7-b6e6-050894bf0ab6
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC shop drawings approved for fabrication
label | df2e18f6-25f9-5a59-af5f-7408ade47f6e |  | note | Responsibility: MPX
label | 34af334f-66ea-5d3c-9b97-ae1b985d70ee |  | note | – – – – – – – – –
label | e2933daf-6fec-54ef-9aff-819034ca1882 |  | note | Acceptance Criteria: MPX / Architect sign off
text | 67c38d2f-160f-562c-97a4-2638a1e1751e |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | 15feb8b3-742e-5785-a209-ebfce0f2494c |  | note | Responsibility: MPX
label | 82de8254-9c85-5175-b421-8d6ad30be006 |  | note | – – – – – – – – –
label | e1f7e278-0fa5-50ed-88ed-f761eed666b6 |  | note | Acceptance Criteria: MPX / Architect sign off
text | bccd72ab-233a-539d-a153-bce1f297a735 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check if the pattern is correct to IFC (5005-H34 alloy 51% open area)
label | de2dc5ac-881d-52b2-b4c4-d158bd14b1c0 |  | note | Responsibility: Facadex
label | 3c9a5546-84c2-537a-ada0-275f5cb4b69f |  | note | – – – – – – – – –
label | b9fcd84f-182c-5019-9ebf-8a7b811a98a6 |  | note | Acceptance Criteria: Facadex sign off.
text | 422780ca-587a-5f04-b005-1791194f2fad |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check carpral extruded profile are jointed with mullion to manufacture's spec (carpral)
label | 21deef9d-fb9c-5154-ad5a-6fc08a5dd0ea |  | note | Responsibility: Facadex
label | fc85f315-0f58-5d09-a6f8-ea5c75a94648 |  | note | – – – – – – – – –
label | 53704793-9593-54ab-b5af-069e8de694ba |  | note | Acceptance Criteria: Facadex sign off.
text | 066301de-a8cf-57b1-82fc-7f8c808e45c0 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check 2mm alum is installed to the carpal panel (back of the perf stiffeners), and 2mm alum installed to be back of the carpal utilized panel and insulation to IFC has been installed inside the cavity of the panel
label | a7329352-cd0c-5fbf-9b0f-6a2e6f465917 |  | note | Responsibility: Facadex
label | 827b7e8b-8457-548b-9c10-b19de868f9af |  | note | – – – – – – – – –
label | d1d4eca1-7581-59a1-bfd3-2725b2001ba9 |  | note | Acceptance Criteria: Facadex sign off.
text | 89b6dd44-bdfc-5405-8323-3533f2dd5b78 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Confirm and check finish as per approved IFC drawings
label | 18451f63-21cb-5e1b-8e60-341dfe82ccde |  | note | Responsibility: Facadex
label | a7def3a3-6d54-536d-a278-41fe116d9201 |  | note | – – – – – – – – –
label | b4f88465-80ac-5d7a-b84a-10e9ddf68913 |  | note | Acceptance Criteria: Facadex sign off.
text | a235b576-b8f2-5761-89fb-428e50678ea2 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check panel size and dimensions against IFC drawings
label | 552a70c0-f3e9-5644-931d-fd08f81f7ace |  | note | Responsibility: Facadex
label | d93ad943-b32c-5853-b544-9f2301c52e40 |  | note | – – – – – – – – –
label | e5f652f7-497f-5d25-a68b-f526dddba75c |  | note | Acceptance Criteria: Facadex sign off.
text | 4ccbdca5-5267-5259-a63f-f01a2edddb80 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check diagonal dimension to ensure odd shape panel are done correctly
label | 61f5ef85-75d5-58c5-b981-3c4ce65a037d |  | note | Responsibility: Facadex
label | 9b87d4bc-6d74-58be-a455-a7b7a23a52c9 |  | note | – – – – – – – – –
label | 8b085750-9751-528f-a4b2-8d99e3767b9a |  | note | Acceptance Criteria: Facadex sign off.
text | c9330de2-9d16-55fb-8ca0-2a73433cdd2b |  | textbox | Date:
checkpoint-status |  |  | checkpoint | QA has checked delivery docket and receipt from powder coater
label | 534334e3-febc-5d4f-97a4-5fe21e821006 |  | note | Responsibility: Facadex
label | b0579888-27a3-5f27-8196-b91600de071e |  | note | – – – – – – – – –
label | da1f4620-e77c-5016-9856-5a06b9c54443 |  | note | Acceptance Criteria: Facadex sign off.
text | 2a573f71-ec43-5b87-94e2-e7b6e218f6ad |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Is fabricated item labelled as per drawing?
label | 3e899fea-5822-5503-862a-7efa0b178dd9 |  | note | Responsibility: Facadex
label | 2b07119a-6f0b-5f0d-95c1-34dfdb4739e5 |  | note | – – – – – – – – –
label | 4cfd13a7-46d5-53d4-a62f-70463b120269 |  | note | Acceptance Criteria: Facadex sign off.
text | a683927c-1b63-548a-9e48-272b8bcd2722 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Fabrication complete
label | 293144b3-03d5-5a38-90db-627de99dcf78 |  | note | Responsibility: Facadex
label | 9629ff40-99d0-5b5f-ab91-20f31f9e1871 |  | note | – – – – – – – – –
label | 8b50bc3b-a631-5f1e-ac7c-76eb622eec58 |  | note | Acceptance Criteria: Facadex sign off.
text | 19291acd-ff00-5fe1-8590-c5b1e02863d3 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Prevent direct contanct between incompatible materials
label | 927c3bc3-4d16-5089-b8cb-d84328658408 |  | note | Responsibility: Facadex
label | ecf43b16-59f0-5368-a843-cb1f3c32edeb |  | note | – – – – – – – – –
label | ef7d3423-9e67-5213-8582-16ea4ea252af |  | note | Acceptance Criteria: Facadex sign off.
text | ad795fb3-4fe1-5b4e-b43d-9e306f08b966 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Materials ready to deliver on site
label | f5a52a05-7819-5f99-a2e7-5e2048550eb5 |  | note | Responsibility: Facadex
label | 2fbba4dc-9b87-5efe-8516-2f0fed5d8ff2 |  | note | – – – – – – – – –
label | 783e70ab-a287-5fbe-b1a9-5aebcce92545 |  | note | Acceptance Criteria: Facadex sign off.
text | 17089a07-ba62-5430-b5a6-a94689faba1a |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | a3202fc2-3a0e-5845-8a71-26679ffdfcc5 |  | note | Responsibility: Facadex / Builder
label | 70306c70-6219-5816-82f1-1544cee7e822 |  | note | – – – – – – – – –
label | 16014168-3021-5658-8844-94b16b2f58aa |  | note | Acceptance Criteria: Defect notification via email or chosen correspondence
label | 26c17f93-52a6-571d-93b0-30872a58c77f |  | note | ○ Evidence of close out / rectification
label | fc9ef119-7914-5ca6-82d6-84300c48df3d |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | 0ed43901-989a-5f89-a81b-70826502a9a7 |  | note | ○ Sign of only once agreed that wall is defect free
text | 4cbf6239-751a-50bd-811b-87c86e4a874e |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | 11c159ae-7949-5b59-94b2-2a80af240f14 |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | eedc9c0b-5f51-5f54-ad38-d966aaef5058 |  | textbox | Foreman – Checklist Completed:
text | 0bd8475b-5c24-58b9-a098-5a6cc315c3f3 |  | textbox | Date / Time:
text | 50ae88b6-3839-57d2-b4c6-e97d9bc916b1 |  | textbox | Coordinator – Checklist Completed:
text | 02f1bca4-12d0-5326-8b12-5e11d1944388 |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | Site Subframing for CLG-513 ITP | itp |  |  |  | Yes | Site Subframing for CLG-513 ITP | d247d024-8469-4c36-a009-f7dcd8480715
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC Shop Drawings Approved
label | 872bb06e-7986-5132-9eb2-5c3d18dbc7de |  | note | Responsibility: MPX
label | 6e654132-9e8f-517a-9eaa-502e1d582d60 |  | note | – – – – – – – – –
label | a379b9ea-bd6a-5c8b-8201-331ef7ae9a35 |  | note | Acceptance Criteria: MPX / Architect Sign Off
text | f5a1da4c-bbfd-5ba8-a339-29e400cd85da |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | e2680847-427b-51c4-9670-9fcc7c3f97eb |  | note | Responsibility: MPX
label | f05b7c42-ec61-5753-adf2-6200cc81ed7d |  | note | – – – – – – – – –
label | 5af134e9-e8f0-58a5-b916-705858a93c50 |  | note | Acceptance Criteria: MPX / Architect Sign Off
text | 3850e4ab-ccba-5484-80dc-9d9ab010a564 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Materials (truss frame/Bolts/Washers) delivered to site free of damage and deformation
label | 1b25ad87-9a9b-5e8d-9a91-6c4d5a2401b7 |  | note | Responsibility: Facadex
label | 3cc4479b-3920-50e4-95b3-8974a53bed15 |  | note | – – – – – – – – –
label | b3e9e0bc-bc81-52c7-8a47-b61274b57a7e |  | note | Acceptance Criteria: Facadex sign off.
text | 1f9e0e35-79b1-5fea-b5b3-016c56848283 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Grid lines established and site set out complete
label | 308d2fbb-180e-50b9-a99f-d167496c8418 |  | note | Responsibility: Facadex
label | cef1ef75-415f-544e-85ab-c26162fff9ea |  | note | – – – – – – – – –
label | f72660f4-7b4b-5bee-9601-af66a9891ddd |  | note | Acceptance Criteria: Facadex sign off.
text | ae3d7143-2f02-56ad-ab14-23e263a3f57a |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Truss Framing underside of the bridge installed as per shop details
label | aedd70b3-ea2d-5dba-9d5d-01ae27c4559f |  | note | Responsibility: Facadex
label | 22ba484c-2791-5d7b-9864-f9c936235284 |  | note | – – – – – – – – –
label | bd447e5b-5d46-5c6f-a7f8-1d645134e007 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 9781b086-baa2-537b-8591-5b8268aed542 |  | note | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | cff6699c-b3de-5f3b-aa12-9116369a579e |  | note | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 423351b8-bdd6-5655-a4d2-aaeec887db7b |  | note | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | ce0ae32d-1464-5172-871d-729889a92f3f |  | note | ○ +/- 3mm @ every 1000mm in length & height
text | 8537980a-7021-5d0b-b065-53af21e2347f |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Truss Framing aligned finished level and plumb
label | b89b1b33-ca2a-5ddc-8442-3045c1863ca5 |  | note | Responsibility: Facadex
label | 211a3e21-75f9-51a9-b968-10c95b0d011d |  | note | – – – – – – – – –
label | 8a04eda6-e681-55fb-854d-55ecb71b3daf |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 6c146e49-b0e9-59bf-813d-6251fbd513bc |  | note | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | c6e998b8-d865-563a-9549-cd45b4e4602f |  | note | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | fdfa3211-3ff4-577c-a6aa-c250f7fd48ea |  | note | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | 11f7ff4c-ae3a-5d75-b457-ce54771663da |  | note | ○ +/- 3mm @ every 1000mm in length & height
text | d2812a70-9640-53d8-9012-c4b883166b49 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Top hat to primiry steel (side) or to truss frame (underside) installed and leveled for panel installation
label | 5729cebe-741d-54ff-ab4c-82028253caba |  | note | Responsibility: Facadex
label | 5b1e2f73-0240-55c2-8349-3e4de72c678d |  | note | – – – – – – – – –
label | fcde77e6-81eb-5959-8831-b8ac672c13fa |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 829158b5-7405-5509-a8c2-6297c8e4071c |  | note | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 24d9b503-bbbd-5778-b036-001b77e96dad |  | note | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | edec0f55-8983-5e62-bcb1-c5d9ca5ba730 |  | note | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | 98157bfa-21ac-5407-a96c-98a17efe54b2 |  | note | ○ +/- 3mm @ every 1000mm in length & height
text | adf5a8e3-27a8-5058-82c6-da9225e60461 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Connections (bolts/washers/screws) checked for damages
label | 5b24081a-fb27-59a1-92d1-a8053b22c0e4 |  | note | Responsibility: Facadex
label | 107ea124-62ff-5a0b-abdb-c0a8ed09515d |  | note | – – – – – – – – –
label | 5959cbe0-a947-5014-9d2a-d930f322d26e |  | note | Acceptance Criteria: Facadex sign off.
text | 3ee6e076-93cc-551d-a2fd-726c27556176 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | 53085c23-f0f1-501e-b2ae-9585d83e8c9d |  | note | Responsibility: Facadex / Builder
label | 7ea6fcc3-fbcf-5865-bc55-92e0ce73fc43 |  | note | – – – – – – – – –
label | dd1031db-9000-59e2-a63b-29ffe33c2a91 |  | note | Acceptance Criteria: Defect notification via email or chosen correspondence
label | 69fee68c-f3ff-56c2-8270-d9111423d505 |  | note | ○ Evidence of close out / rectification
label | 53074b67-cd90-538a-adf5-d3e138592aa0 |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | 365c00e4-81b4-508b-adc9-31e63492145b |  | note | ○ Sign of only once agreed that wall is defect free
text | 41b85b9b-1f21-5440-9e5c-dea28ec99537 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | 6b490bdb-1f2a-5d88-a2e6-44fb9c30833e |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | a5033108-951d-5f6f-a842-2e53985bc161 |  | textbox | Foreman – Checklist Completed:
text | 7b79bcbc-5ab4-5ddb-94db-b5818bfc38af |  | textbox | Date / Time:
text | 20400ee7-aebc-53be-8dd9-3d5b29d777e6 |  | textbox | Coordinator – Checklist Completed:
text | 72dba35e-e2b2-5b2b-8cbb-7ff5a6ad6aca |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLG-506 Cladding ITP | itp |  |  |  | Yes | CLG-506 Cladding ITP | de399ecb-aee7-452f-8bfe-df88497160f6
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC Shop Drawings Approved
label | 5f6f4285-f19c-5011-865e-dd9e044d5f6a |  | note | Responsibility: MPX
label | 98375baf-1005-5401-9a1e-a3e7eb8bc2e7 |  | note | – – – – – – – – –
label | e7c86bea-4afc-530b-a37a-93f276d7dd2f |  | note | Acceptance Criteria: MPX / Architect Sign Off
label | f70b0eef-4b8f-5c85-b5db-e6c247e9b0da |  | note | – – – – – – – – –
text | b5250417-424e-5a7c-9447-520d883cb7df |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | ccae36cc-4050-5c30-896f-01c0f9c1af38 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | 2cc762cc-dc69-5dd5-9895-ba07b5e1d63c |  | note | Responsibility: MPX
label | 94c93a6a-af68-5e0f-b4a5-3e7a7ea62cba |  | note | – – – – – – – – –
label | 3739a6d1-e6e3-5449-87cb-1f74adcdce96 |  | note | Acceptance Criteria: MPX / Architect Sign Off
label | 1d887525-1261-5882-93d4-b45c2464b4d3 |  | note | – – – – – – – – –
text | 23a69d7d-a03a-5251-bb52-e3d7084ddd51 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | fcda84b1-fad0-5835-b5e1-20e96b73fc06 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Materials (Panels/Bolts/Washers) delivered to site free of damage and deformation
label | cb9d9f9d-9f64-5905-943d-95635b276926 |  | note | Responsibility: Facadex
label | 267ba891-555c-5e12-a8c9-0c2a10471ad2 |  | note | – – – – – – – – –
label | 30b6eaa1-d18a-59a5-b853-aac63d6e9ca1 |  | note | Acceptance Criteria: Facadex sign off.
label | 5d144fe3-619f-5ede-ab4a-f4c0512a444c |  | note | – – – – – – – – –
text | e913cd93-4d78-5f7d-a168-156b7ffb7fd9 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 3c4602c1-cfed-55e9-af73-b5d4df443498 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Grid lines established and site set out complete
label | d248b3ba-4fd1-5ec2-89a1-2e32a006e6cc |  | note | Responsibility: Facadex
label | a15aa5bb-c99b-5076-b8d9-c2cf8ffdb2de |  | note | – – – – – – – – –
label | 5ca814a9-292f-5bb1-8d6a-d62bd09db0ae |  | note | Acceptance Criteria: Facadex sign off.
label | 5a645ef8-65b7-53c6-86ef-f130c2d3ad58 |  | note | – – – – – – – – –
text | 1ea372fe-6e60-53c6-b912-97fb304b425f |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | c5f3a40f-4c66-5db2-8bc3-57d019c68635 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Cladding Panels installed to manufacturers specifications
label | 5940f548-fb36-56fe-9512-a36d77390075 |  | note | Responsibility: Facadex
label | efddc738-0853-51e8-a4e7-20c2db8a7eb9 |  | note | – – – – – – – – –
label | 75f7d676-3bfa-5f1c-aaa9-aeb0f4a4ae67 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | e85d038e-8bae-5476-832c-6a162e9b98c6 |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 2aa745a3-5b5a-5871-9df0-775c1afbf92c |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 04a1623c-bfae-5956-8094-be39716eb220 |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | 279aac89-6815-5ae6-be87-3ebe33b15bfd |  | note | ○ Expansion & Contraction:
label | 6fb721ee-423d-5b8e-9370-25f85512c815 |  | note | +/- 3mm @ every 1000mm in length & height
label | 1e1a6156-1e2b-527e-8044-ed680e8fc21b |  | note | – – – – – – – – –
text | 121afddb-5b20-5b02-a6a4-5b9e26edde44 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | dfc4c476-06e1-52c1-ae37-51cc86d209d2 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Cladding Panels checked for paint scratches post installation
label | a781b6b6-5ac9-5463-94ad-6d740e34c850 |  | note | Responsibility: Facadex
label | 5e6d4e24-fc43-549f-88be-bc7eeb7eaafc |  | note | – – – – – – – – –
label | 842b0910-b149-5518-8100-e0859cf6dcf9 |  | note | Acceptance Criteria: Facadex sign off.
label | a6c855dc-9354-5906-a8d7-fa568c71cad3 |  | note | – – – – – – – – –
text | 273677db-9ca9-5e09-b960-ab2eabd44ccc |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 99eae1c0-4bb9-516b-a0b8-6dc89073788e |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Connections (bolts/washers/screws) checked for damages
label | 61f16030-ea70-5484-982f-d83f9338e487 |  | note | Responsibility: Facadex
label | 3a0c0a63-a4ca-597c-866f-e329997ec265 |  | note | – – – – – – – – –
label | 75fbf5d8-f8a8-5bfa-8b8d-04d28e7798bc |  | note | Acceptance Criteria: Facadex sign off.
label | cc47b8a9-093c-5813-84c8-10e27284a3d5 |  | note | – – – – – – – – –
text | b0dfe4a6-83af-5d82-a71b-961009526c78 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 0116b09c-b15e-5677-8a08-4cb1a803b0ed |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | c29c0bef-7c21-546a-bfb1-8b3e0efff759 |  | note | Responsibility: Facadex / Builder
label | 1733e048-404c-5578-b489-f4705e1bd06b |  | note | – – – – – – – – –
label | faf83cda-6852-5b98-8842-baf4553b4e05 |  | note | Acceptance Criteria: Defect notification via email or chosen correspondance
label | 06211ab2-08a1-5277-88f2-fd61bdf2c30b |  | note | ○ Evidence of close out / rectification
label | f53411b8-3cd4-5bdb-95cb-e5e09b753a4a |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | 9f5ad69e-4544-5408-b9c9-510a36fb89ca |  | note | ○ Sign off only once agreed that wall is defect free
label | 1b8ab8b7-5bd4-58bf-8b07-0000795bc201 |  | note | – – – – – – – – –
text | 130f0521-930d-5dfc-b7dd-771fd6e23e76 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 07f556d5-762e-5f08-8ad4-c605dbcc9cb3 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | 9dcfeaa4-90f6-59b2-8e5c-e26def4dce4e |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | de0a336c-d0cd-52e5-8b80-5bb75845aebd |  | textbox | Foreman – Checklist Completed:
text | 97fa2ca8-7f28-5e47-9285-8c129fdc38b2 |  | textbox | Date / Time:
text | be0ab724-3589-5fad-97a0-7425526bd1a4 |  | textbox | Coordinator – Checklist Completed:
text | 5922c136-2de2-57bc-a1b2-9e99e51eb966 |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLD-214 Lysaght Spandek - Cladding Building D Panel Site ITP | itp |  |  |  | Yes | CLD-214 Lysaght Spandek - Cladding Building D Panel Site ITP | e16e4de4-78d5-44c8-84c1-c9fbaf306d36
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC Shop Drawings Approved
label | b4150456-3ed5-5a63-9302-093e557fb2c6 |  | note | Responsibility: MPX
label | fc7cc962-8490-579a-b824-a932693c5176 |  | note | – – – – – – – – –
label | 0f8d0e20-a622-52cf-a570-c49bf4541794 |  | note | Acceptance Criteria: MPX / Architect Sign Off
label | f2137cfb-2740-5bd0-ad7f-1388a7cd7072 |  | note | – – – – – – – – –
text | 908ac15b-171b-5090-bc20-c3765925d1ab |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 93103c55-93fe-57b7-acd5-893e38265eb2 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | 1d13cd05-8366-57e1-85ac-f6e3faf8f3de |  | note | Responsibility: MPX
label | 05c641fd-9bfa-53b8-a12d-88af255132cd |  | note | – – – – – – – – –
label | e96917ec-885d-5531-b44f-e576591fa3e4 |  | note | Acceptance Criteria: MPX / Architect Sign Off
label | 064cffd5-763c-5b0f-874e-6530be9535be |  | note | – – – – – – – – –
text | f8cb318a-f91a-52de-9c92-cce7bc6c5a4b |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | dc980dd7-28b3-5997-a68c-84064a35f252 |  | textbox | Date:
label | 0c708364-5e77-5654-b016-ec14f3bc9143 |  | note | Comments: Check colour is correct as per shop drawings
checkpoint-status |  |  | checkpoint | Materials (Panels/Bolts/Washers) delivered to site free of damage and deformation
label | 9a4559fe-c27d-5e6c-b529-2ad8b0b1284f |  | note | Responsibility: Facadex
label | 30b73aac-441a-5f17-91bf-190ba73b05fc |  | note | – – – – – – – – –
label | 79d7692e-d52b-5586-970c-829465f44c22 |  | note | Acceptance Criteria: Facadex sign off.
label | 5badd85b-66be-572f-8b64-fab771380241 |  | note | – – – – – – – – –
text | 379b68df-ce6c-59f7-aaab-73ff680968c8 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | ea08a7e0-aca9-53b6-bb5e-f655328039e5 |  | textbox | Date:
label | d4642ac5-7989-5407-8221-62947d5fa91b |  | note | Comments: Check colour is correct as per shop drawings
checkpoint-status |  |  | checkpoint | Grid lines established and site set out complete
label | af4d51de-b144-567c-b02d-4465158ba38c |  | note | Responsibility: Facadex
label | cbced650-d5fe-5b82-8245-999bb4620fa6 |  | note | – – – – – – – – –
label | ec14dd7d-d5cb-567d-9175-0a59aeb65d3f |  | note | Acceptance Criteria: Facadex sign off.
label | 77fab674-ae76-54d8-96be-bb14db4c28b9 |  | note | – – – – – – – – –
text | c14d3fdd-b671-59a1-9585-9b6696b4e160 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | fead856f-2531-5021-b3a8-730c881e8d45 |  | textbox | Date:
label | 05487ae0-1ee8-57cf-baff-b256a89b95d5 |  | note | Comments: If installed off site no gridline available
checkpoint-status |  |  | checkpoint | Cladding Panels installed to manufacturers specifications
label | 13b52dd0-3403-5fdc-abf2-a86f3b2f5981 |  | note | Responsibility: Facadex
label | 185a39fa-afdf-5bd0-8d8f-8096e339fc37 |  | note | – – – – – – – – –
label | fb36864a-0181-58f8-b5bd-e418bad7a426 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 2c0f6635-000f-5918-aa60-cc75599aac27 |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 60a95d28-2d3b-51dd-b3f8-be6bc6adcf8b |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | a6637f52-3e27-59ac-8960-84cf1cb3ad7d |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | 48b2f667-8bfe-54c0-9513-a64ac3debef3 |  | note | ○ Expansion & Contraction:
label | 4ba2c230-7f64-5990-9f3d-6b2b900842e8 |  | note | +/- 3mm @ every 1000mm in length & height
label | 857e50c8-becf-54e6-a73b-5483859da822 |  | note | – – – – – – – – –
text | 2da06415-a650-545e-9925-d5c54c354d62 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | f5e3113d-3524-5616-b969-2e3d8b5aa429 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Cladding Panels checked for paint scratches post installation
label | 877ce7c9-9b85-54f3-bd2f-b5045cfddbe3 |  | note | Responsibility: Facadex
label | 4c39de45-6cac-5aac-b906-790f8a849a27 |  | note | – – – – – – – – –
label | 46f28669-8595-5b0d-b092-eff38025e617 |  | note | Acceptance Criteria: Facadex sign off.
label | dec237a6-b184-54a4-9114-7e21e716786b |  | note | – – – – – – – – –
text | 67411235-ec7a-50fa-a8f0-d3b0ee0fe256 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | e975ebbe-3397-5075-b6b4-531e3c92950e |  | textbox | Date:
checkpoint-status |  |  | checkpoint | 0.55mm colorbond flashing has been installed to the gap to the strcutrue
label | 1c739fd9-0a7f-5774-b819-67847da6b8d2 |  | note | Responsibility: Facadex
label | 07a55766-475f-5716-a8d7-10c7a475fb92 |  | note | – – – – – – – – –
label | 8d638472-63c1-5188-9e32-e0f05d6ba2de |  | note | Acceptance Criteria: Facadex sign off.
label | 0bd30aac-06ee-5c50-9da7-d24f89e27cc7 |  | note | – – – – – – – – –
text | 1c8acdf0-6f6f-5507-a402-ac8dfd5b6ce5 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 37f7b321-7251-564f-8184-4500919a3752 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Connections (bolts/washers/screws) checked for damages
label | aeec4294-e64e-5573-be90-146a3bf2bdb6 |  | note | Responsibility: Facadex
label | 6f231f8a-c613-5ffa-8e42-4690d548b86d |  | note | – – – – – – – – –
label | d5c60fd6-e8fd-52dd-b60a-29dfefcabf40 |  | note | Acceptance Criteria: Facadex sign off.
label | 26591fca-4c8e-5dfb-9d8d-755153d07bd9 |  | note | – – – – – – – – –
text | 5224dda1-eb01-56c8-bd29-4fe26406463c |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 2483ed47-8b24-54b7-803a-d5387c54127b |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | 556e6aa5-2927-54e5-b2ad-1f2971cbac14 |  | note | Responsibility: Facadex / Builder
label | 0b00aa0b-f33f-5ee4-86cd-71986fa89ac9 |  | note | – – – – – – – – –
label | fbb1cc6a-f5af-5a7b-8854-eae02c9a887d |  | note | Acceptance Criteria: Defect notification via email or chosen correspondance
label | c7319a63-1a51-5ae8-aaf4-b7dc07cc0636 |  | note | ○ Evidence of close out / rectification
label | 9f721e35-db67-5f46-bd4b-cf062c7654d1 |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | 0d09b1db-102e-511a-8a23-f50147aef28b |  | note | ○ Sign off only once agreed that wall is defect free
label | 94df5da6-c327-53e0-a5ec-67831a741395 |  | note | – – – – – – – – –
text | 49cc48d6-7656-534c-be3d-a938ce217e0c |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 41e84972-a26e-5b09-b093-ffa372592ff2 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | 461f9585-463d-5154-a2b4-7a7e7b799844 |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | a17649d0-1d94-5f4c-bc0b-47052ad71f42 |  | textbox | Foreman – Checklist Completed:
text | 058bae9f-fe88-5ee7-b3e5-8154390916d7 |  | textbox | Date / Time:
text | 242cc59b-af70-5daa-a3db-bbb02fd52363 |  | textbox | Coordinator – Checklist Completed:
text | 60df72ae-1d78-53d1-815d-ef52df4ebf78 |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLD-214 Lysaght Spandek - Cladding Building D (North Wall Double 50 Top Hat) ITP | itp |  |  |  | Yes | CLD-214 Lysaght Spandek - Cladding Building D (North Wall Double 50 Top Hat) ITP | e8f11401-8638-4bf2-8848-a391884ddbb4
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC Shop Drawings Approved
label | 5837d270-3395-50e6-8eae-3e716d83e28b |  | note | Responsibility: MPX
label | a6200d96-52d9-56f3-8db7-6c735318aa8f |  | note | – – – – – – – – –
label | 2bcaea4b-8735-558d-8577-633930f11f5e |  | note | Acceptance Criteria: MPX / Architect Sign Off
label | c1eda768-a23f-5f6b-8c71-6ad56a2f1c2a |  | note | – – – – – – – – –
text | 523c5b71-39c0-501e-a6e5-e4b978458e9c |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 8f2ce768-f128-5759-b170-7ba78d443d1f |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | 60eea480-c8e6-59e8-8cc6-e786070bdf93 |  | note | Responsibility: MPX
label | 61c99aac-8848-53af-9678-133da49858db |  | note | – – – – – – – – –
label | 17ca968e-c506-5cac-9c3e-fa41f7a5c07c |  | note | Acceptance Criteria: MPX / Architect Sign Off
label | c2178b19-1790-5077-a10e-77a0b49bf1c2 |  | note | – – – – – – – – –
text | adffc657-d3e3-5d34-9300-afbb39448de9 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | a706c50d-5ff9-5f71-8258-cb8c4e212f2f |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Materials (top hat/screws) delivered to site free of damage and deformation
label | 220fbf5d-db26-57d5-85f2-065cef0770d9 |  | note | Responsibility: Facadex
label | 34c78161-b60e-5232-881e-eab917571a88 |  | note | – – – – – – – – –
label | d95f2e25-f245-54d1-8ac1-fca49f147d96 |  | note | Acceptance Criteria: Facadex sign off.
label | e4c55a17-270d-5128-8700-bf0c12fb6a07 |  | note | – – – – – – – – –
text | 09a20709-54e0-51c6-a357-9f57b7a357af |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | b192a2f0-6109-5845-83f6-b0784073e60b |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Grid lines established and site set out complete
label | 0a0b7dee-4b9b-5eca-89f9-39d55ef31385 |  | note | Responsibility: Facadex
label | 88127bfd-4d5c-5f46-a128-c19e468c1aed |  | note | – – – – – – – – –
label | 5670b3d7-e1b4-513f-994b-af872576b1f4 |  | note | Acceptance Criteria: Facadex sign off.
label | ef3ad88d-204b-5f07-9d37-b60a2c6b285f |  | note | – – – – – – – – –
text | 4c9b9369-f0ef-570a-9a34-63c5b9d7bdfb |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 08b09617-9055-5028-98ef-266b4c6406d4 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | 50mm vertical top hat has been set out and installed to steel frames with #12 tek screws@500 crs
label | 39eaf64b-247e-5a65-bd7e-c5679eeaf8a4 |  | note | Responsibility: Facadex
label | 455d9b88-b7b9-546d-907c-3df986a82500 |  | note | – – – – – – – – –
label | 1b4f5cbf-9a83-5322-b2ad-3ba120318af1 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 8ad9164c-d115-5601-9fa3-02480ebff8c9 |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | e433c447-9d6d-5463-a897-c33a5408f388 |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 4a74ea4f-1aee-57d9-b06f-d4f5f2d32543 |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | 6a8c5213-68ce-5443-bd8d-e6a819bd80f4 |  | note | ○ Expansion & Contraction:
label | bcb9f650-bfec-5b2d-afbe-b9a5fb710969 |  | note | +/- 3mm @ every 1000mm in length & height
label | 616843eb-c541-54ef-8cfb-bdcb596b92c8 |  | note | – – – – – – – – –
text | 027e10cb-3d48-509c-9435-e68952d1f666 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 667d9249-d77e-5b1a-aac6-f881c487e038 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | 50mm horizontal top hat has been set out and installed to vertical top hat with #12 tek screws@500crs
label | afa1f4ed-b7e9-5c27-a067-ce1ed2c4edc1 |  | note | Responsibility: Facadex
label | ba7be4fe-48ef-5a2e-bd96-c50780d9970a |  | note | – – – – – – – – –
label | e02af6ab-8370-5da2-9c6e-c3a39dbdd6ef |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 3cd857c3-5d5e-5b34-b25f-43fc20a2b14f |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | b37b7ad5-c894-5505-865c-3a3aef6c5ac4 |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 6764c146-1241-578d-84c0-2eb8501ef4af |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | 7b506317-f4ca-5b4e-987f-67e05717245c |  | note | ○ Expansion & Contraction:
label | 181541a4-db6d-5e5c-9b59-adf2f1708a4f |  | note | +/- 3mm @ every 1000mm in length & height
label | 5621de11-66ec-5654-a8e3-fe5383c50605 |  | note | – – – – – – – – –
text | 01725c67-c7f5-55d5-b450-37273cf9622a |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 6ad38011-eec9-5066-a16c-820b9dd15867 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Packers has been used to ensure the top hat frame is plumb for lysaght spandek panels to be cladded on.
label | 8a59bb72-ed65-5761-b30d-4f28f0e93a29 |  | note | Responsibility: Facadex
label | 38e3b736-b8ef-5b16-9781-d686cda881cd |  | note | – – – – – – – – –
label | e74f6555-3f16-589c-8a92-17a9d238f340 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | d7d6b560-4c2e-50a1-aadc-d040e6e35688 |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | e5c42b63-0582-5c4f-9255-459115e97d7f |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | bdd76b05-91ac-5daa-93b4-0fa37b0f0a66 |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | fb59c45f-227a-5ede-9830-c5abf08292f3 |  | note | ○ Expansion & Contraction:
label | 870f65eb-2d84-53e3-84b8-488ef6fe419c |  | note | +/- 3mm @ every 1000mm in length & height
label | aa0ef785-69fc-5668-9039-045e9a366654 |  | note | – – – – – – – – –
text | ff822f31-af11-5ecb-b85a-bc0e289be9bb |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | cd9a947d-3984-59b8-b297-5d6b27c51300 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Connections (bolts/washers/screws) checked for damages
label | 5f3c1911-f6f5-5fae-9130-b673db78debd |  | note | Responsibility: Facadex
label | ce6c873e-d0e2-5207-b5e9-277f2f5daddf |  | note | – – – – – – – – –
label | 3d1e071a-d39c-5279-a44d-f6b5d45ee2a4 |  | note | Acceptance Criteria: Facadex sign off.
label | 3d8710b9-ebb8-5195-8ee4-cbc27e3ca433 |  | note | – – – – – – – – –
text | 9e58e814-4fb2-5847-836e-2f5ab0446b57 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | c32609bc-3bbd-5ca7-bc8c-905e6edb4af4 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | 39d0b46a-bc8a-54fe-8f67-81ff538b69eb |  | note | Responsibility: Facadex / Builder
label | f1bec923-7f70-5c93-8f00-d571f5c23e57 |  | note | – – – – – – – – –
label | b523639e-c932-5d49-9ed5-5d81810a9b8c |  | note | Acceptance Criteria: Defect notification via email or chosen correspondance
label | eecd0be0-6299-570a-bb6e-4c5d5526c1d9 |  | note | ○ Evidence of close out / rectification
label | 3d614c97-47ff-56a8-9b42-351ce1a16431 |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | e4e9d3b1-993f-5bc7-a308-f4943f977794 |  | note | ○ Sign off only once agreed that wall is defect free
label | 7f2ec965-2f75-5c7d-8a0a-dca33758e632 |  | note | – – – – – – – – –
text | 847d4fe4-62b6-514d-849f-28c5a1319fae |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 1b18296f-3c51-5bd6-a41f-abe6b1fd15cd |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | c25bddeb-8e48-594a-9f33-0c25f2686120 |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | d2566bf7-8700-53b6-a987-255a57536e63 |  | textbox | Foreman – Checklist Completed:
text | bf69485e-df8f-5773-9423-5cb861bef633 |  | textbox | Date / Time:
text | e328b04f-0668-5a6b-8df3-979622f23a79 |  | textbox | Coordinator – Checklist Completed:
text | 01393da7-b237-51e6-9600-49bf29120849 |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLG-514 Cladding Panel ITP | itp |  |  |  | Yes | CLG-514 Cladding Panel ITP | f1d10fed-f60d-466e-af9a-736da54a6f20
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC Shop Drawings Approved
label | fbe4df89-8d53-5c29-93a6-7467672400f9 |  | note | Responsibility: MPX
label | 01a05e89-803d-5848-a6bc-6cb08a941684 |  | note | – – – – – – – – –
label | 887dd132-f8ba-525c-894f-fbfd516ae3c8 |  | note | Acceptance Criteria: MPX / Architect Sign Off
label | b7464148-1c64-513a-8e63-92d0fe26e1ef |  | note | – – – – – – – – –
text | 118ba8fc-d8af-5043-b5ea-50978f405789 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 685fec29-64c1-5ee7-80c2-6c5922ccfbcd |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | dc123a4a-bac7-5f15-9172-825406bc6eee |  | note | Responsibility: MPX
label | 5b46eac3-e6bc-5ad5-bdaf-28eac94458be |  | note | – – – – – – – – –
label | cc3cfce8-3853-5a75-9992-53f386004f84 |  | note | Acceptance Criteria: MPX / Architect Sign Off
label | 7d7a8b0f-25f0-5fcc-8c87-2f6cefd1d436 |  | note | – – – – – – – – –
text | ac14f261-53a1-5546-992e-3eb6e50133ba |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | bf35d39d-310c-5300-a043-bec61a21c020 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Materials (Panels/Bolts/Washers) delivered to site free of damage and deformation
label | 3bc2fcba-df67-5b91-b87c-7a21afa1362b |  | note | Responsibility: Facadex
label | d0f70131-e2cc-53b3-80d9-b516d47f1fd7 |  | note | – – – – – – – – –
label | f6c4c312-d3dc-5b7a-84df-1da894b7e261 |  | note | Acceptance Criteria: Facadex sign off.
label | 4a90a6b8-906f-5e0e-84ab-401558bae593 |  | note | – – – – – – – – –
text | 7d08682b-f0d7-5861-b290-aec15c3e7703 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | f4e0a783-9516-5762-b2b2-189f27c6ec54 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Grid lines established and site set out complete
label | c91aedcb-0e85-5a66-a1ef-0e1f4243e9ec |  | note | Responsibility: Facadex
label | 007b77a6-3d07-5d61-9fb4-e00f7750fc5a |  | note | – – – – – – – – –
label | 7d54c103-2550-54b1-8e24-5bf6f5c9386b |  | note | Acceptance Criteria: Facadex sign off.
label | 7e885d1b-4928-50dc-91b5-7bc13314b54b |  | note | – – – – – – – – –
text | b98c93cd-aa0e-52dc-8927-a2242335d6c3 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 7d7cf7b9-ec14-59bd-9562-2b4be7021a65 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Cladding Panels installed to manufacturers specifications
label | de87f544-baa2-56aa-ab4a-7caedf924e35 |  | note | Responsibility: Facadex
label | 2d17f104-bd65-5151-a540-59c61f128d90 |  | note | – – – – – – – – –
label | 91b0771f-7f8f-529b-a1de-ea42be823621 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 4edc45f5-6df7-5fd6-afbf-66d26781bba4 |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | fe2079ef-4225-5a42-922c-5edb78d615b2 |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 76424888-1788-5b9f-a2ae-b0781db1ab8b |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | b5d69799-2ad4-5394-b982-6f1ed9230f63 |  | note | ○ Expansion & Contraction:
label | 9f32c86e-b40e-535c-b44a-890cc100e049 |  | note | +/- 3mm @ every 1000mm in length & height
label | c525990a-e8a0-556f-a620-0f59551351e9 |  | note | – – – – – – – – –
text | c6d7801e-d61f-5e70-9689-761e4d8afd95 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 9d25b892-1f09-5a2b-96ec-081e93b947b2 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Cladding Panels checked for paint scratches post installation
label | 64d89e3b-2dbe-557a-88e5-f8546ab6d5a3 |  | note | Responsibility: Facadex
label | e1b242c2-cf49-5c03-a005-21945ff03463 |  | note | – – – – – – – – –
label | 854f67d5-b288-5cf9-8344-06e0be039132 |  | note | Acceptance Criteria: Facadex sign off.
label | 516ed053-a3f7-5d24-91df-7297f6b83ad2 |  | note | – – – – – – – – –
text | 06bba872-8594-5670-a12a-1b624936f856 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | d1ffa5f8-8d18-5c06-b0dc-59df751fb432 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Connections (bolts/washers/screws) checked for damages
label | 4fce2f7b-3bbf-55fc-ad84-3d539e4ab26b |  | note | Responsibility: Facadex
label | 43cc3701-c383-556f-bc3f-ac1757ab0c00 |  | note | – – – – – – – – –
label | 42f94883-77ac-5b5a-9ac3-6e9a6b62dc41 |  | note | Acceptance Criteria: Facadex sign off.
label | ce1f1d29-eab8-5ec2-a773-d20d483a0f96 |  | note | – – – – – – – – –
text | ff712268-6f13-5581-9c0f-11010538ee7a |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 47ac07d5-fbb9-5722-8d4a-7bedabe85497 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | c2d8a077-8733-5ed9-b096-327d1d360087 |  | note | Responsibility: Facadex / Builder
label | 0943f684-7fe3-5d23-bade-0b913ab2b922 |  | note | – – – – – – – – –
label | ac17b521-cf41-5b41-b796-a1174befa54e |  | note | Acceptance Criteria: Defect notification via email or chosen correspondance
label | 1ee5967b-edd5-5803-a9f4-ea3f95eb8e11 |  | note | ○ Evidence of close out / rectification
label | b8d8562b-aaed-531b-b759-332cf5e013ad |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | fb988245-3462-5219-85f5-901f17800ec8 |  | note | ○ Sign off only once agreed that wall is defect free
label | 26e4c2f7-34fd-5573-8936-cc99b7bb0ab7 |  | note | – – – – – – – – –
text | 0e517345-2091-5893-8a73-4780ea54254e |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 5dfebb07-b2d8-5d2e-a624-d986d5e1000d |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | 84473391-6ff2-5a23-ba6d-2aaad0f15c9f |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | 4efcc13d-b4ae-5061-8514-4a3ba188b14d |  | textbox | Foreman – Checklist Completed:
text | 38b1ed22-b454-56a6-bfd0-c178b1455377 |  | textbox | Date / Time:
text | 39b55d60-d11b-5db0-9b45-a89aa05e4114 |  | textbox | Coordinator – Checklist Completed:
text | 26f4bfd8-d07b-55d9-80e0-d214e659fd9b |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLD-200 3mm Alum Perf (Building E) - Panel Site ITP | itp |  |  |  | Yes | CLD-200 3mm Alum Perf (Building E) - Panel Site ITP | f88b5425-e593-49cc-b7ce-d89f94b370eb
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC Shop Drawings Approved
label | 6a4a5a61-4d16-5f69-92a7-aed50ff0cd42 |  | note | Responsibility: MPX
label | a37645f1-f1aa-5aac-bca1-236a69df2c83 |  | note | – – – – – – – – –
label | f4e1970e-b150-5a3d-8757-975593423227 |  | note | Acceptance Criteria: MPX / Architect Sign Off
text | 3e2434a8-37b3-5d09-bba6-2fdeef428b5e |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | 51ebdef0-312a-5bec-9c01-f5082b0e35dd |  | note | Responsibility: MPX
label | 7197349a-d4e8-5361-b3a5-56eaaf2f4c50 |  | note | – – – – – – – – –
label | 6aaf4df3-9440-52ab-b85d-52c21c7cbfa2 |  | note | Acceptance Criteria: MPX / Architect Sign Off
text | 41052aea-a0fd-558b-9dcc-4e54d9e944e3 |  | textbox | Date:
label | dab9ac0b-9e0c-5403-83cc-06a600fb275b |  | note | Comments: Check colour is correct as per shop drawings
checkpoint-status |  |  | checkpoint | Materials (Panels/Bolts/Screw/Washers) delivered to site free of damage and deformation
label | add80639-4b9c-5cfa-9733-a3fe2fb81e71 |  | note | Responsibility: Facadex
label | 29241c56-cdd6-5116-b288-72db62a3b85b |  | note | – – – – – – – – –
label | 9093a6e1-504a-5902-8455-4de3038c3f90 |  | note | Acceptance Criteria: Facadex sign off.
text | c5d88798-a09e-5192-b730-2b849a64f30d |  | textbox | Date:
label | a554ef13-79e0-52cb-8cf9-b3dd0d9e5863 |  | note | Comments: Check colour is correct as per shop drawings
checkpoint-status |  |  | checkpoint | Grid lines established and site set out complete
label | e3c76241-bc3e-5927-a8e4-9a2bff9176ef |  | note | Responsibility: Facadex
label | 447d8a47-35e7-5331-9e22-a9990a018c2e |  | note | – – – – – – – – –
label | b5b0695d-bb14-5f85-b7f1-7d004453b5b3 |  | note | Acceptance Criteria: Facadex sign off.
text | 0a3a0eb9-5001-57e2-8448-299c70c97890 |  | textbox | Date:
label | 4031901c-9b49-5970-b723-6537823c3313 |  | note | Comments: If installed off site no gridline available
checkpoint-status |  |  | checkpoint | Perf Cladding Panels installed to IFC specification
label | deb2cfc4-f567-518c-8e55-6c8266b69454 |  | note | Responsibility: Facadex
label | 48e0c6b0-14ac-5aae-83ec-bf99a518e463 |  | note | – – – – – – – – –
label | ea293bdb-4eb4-5df5-93b3-a819304a7ad0 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 5ca4b7af-22d6-560a-84eb-d1e6b8643821 |  | note | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 4fbc070f-df32-52fe-b82f-187d76d337fa |  | note | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 39a93cef-6d86-5223-a5b9-8bb240fc5878 |  | note | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | 735e1995-cbbf-5a68-80f2-e7194c575cee |  | note | ○ +/- 3mm @ every 1000mm in length & height
text | b9e20dee-a066-5b3b-a036-f4398ce4a195 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Perf Cladding Panels checked for paint scratches and dents post installation
label | b4442540-8d58-5e8f-aef1-63caaf0b6dac |  | note | Responsibility: Facadex
label | bdb41057-29b1-522d-aaad-fde86f9264bf |  | note | – – – – – – – – –
label | 553f162c-2c72-54a8-a5d6-ae0b6d9285d4 |  | note | Acceptance Criteria: Facadex sign off.
text | 26d387a6-bf41-5b87-9ca3-e6bbe0a913a9 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Perf panel fixed with 4.8mm diameter x 11.4mm Rivets @300crs
label | 99c90ae6-cfd9-514f-be4c-c8d45bc8f4cd |  | note | Responsibility: Facadex
label | 5c88f947-6e60-5668-9383-e46f78031ace |  | note | – – – – – – – – –
label | 72ee4e1e-8de6-5014-8868-30b859682845 |  | note | Acceptance Criteria: Facadex sign off.
text | 5d2f96b9-bacd-5593-9eaf-5f5635217e5e |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Connections (screws/rivets) checked for damages
label | fe22e45c-b159-5d3a-8e41-5d3b931b107e |  | note | Responsibility: Facadex
label | 56068d06-e763-529f-95b2-96ebdee06745 |  | note | – – – – – – – – –
label | f6d9529b-c345-5073-988d-d614b4088533 |  | note | Acceptance Criteria: Facadex sign off.
text | c4224923-dfab-507f-b50d-1cf843a79fe7 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | f3ed1ebd-5b74-570b-a82b-32e9ea955a03 |  | note | Responsibility: Facadex / Builder
label | 38551f43-0249-5e67-b955-800c86e05dcb |  | note | – – – – – – – – –
label | 821cc3d1-9cc6-5b17-bc22-c7f38d44d3f3 |  | note | Acceptance Criteria: Defect notification via email or chosen correspondence
label | 0b70b968-0fd4-5a27-a44d-c4d385a2b273 |  | note | ○ Evidence of close out / rectification
label | 16f80a63-b942-5389-80eb-969b8d7cdba6 |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | 84ff4c9d-4792-5b1e-be96-0dc0edf6b797 |  | note | ○ Sign of only once agreed that wall is defect free
text | c418bbd5-4510-5647-b99d-0ebfd772c146 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | 89b1d226-f75e-52eb-9405-0fde728d42b0 |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | cd76b6c8-bb46-5608-9bc8-59cf4fc79154 |  | textbox | Foreman – Checklist Completed:
text | 1077200c-1cf3-5eb7-b969-75e687377e2e |  | textbox | Date / Time:
text | 225be763-29fd-5a89-af87-f856b612b3d0 |  | textbox | Coordinator – Checklist Completed:
text | 08a9fd03-ab99-5530-96cc-8bb88369f993 |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLG-513 Bridge Factory ITP | itp |  |  |  | Yes | CLG-513 Bridge Factory ITP | fc2f67f9-8a7a-4e23-9c4f-ccf5ee8b570c
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC shop drawings approved for fabrication
label | 9b06c25b-a042-589e-aafc-db12f5e58db0 |  | note | Responsibility: MPX
label | 89b904a6-6c94-5785-84bf-841fad0db8a9 |  | note | – – – – – – – – –
label | b2766bd4-ecc2-5fc6-8c3a-9877862e0a67 |  | note | Acceptance Criteria: MPX / Architect sign off
text | 26ad18ae-a9c4-58dd-8c8f-82279ecfb9f2 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | 1a5d5167-20a4-5c35-a3e3-f9de8a231d8c |  | note | Responsibility: MPX
label | c8360a8d-92fb-52e1-ba02-855db93724eb |  | note | – – – – – – – – –
label | 8537cc35-2ea8-5e52-a346-a3cca826332f |  | note | Acceptance Criteria: MPX / Architect sign off
text | 0e3def0a-3890-57f1-9e01-b72f9c546216 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Confirm and check finish as per approved IFC drawings
label | 014a7b44-7849-591e-a1d1-be24c67493ab |  | note | Responsibility: Facadex
label | c4b4a80b-21cf-5ba2-a2bc-5ba3c2d05ed8 |  | note | – – – – – – – – –
label | 4a15fe97-24c5-5ffc-853a-80d0afb957a7 |  | note | Acceptance Criteria: Facadex sign off.
text | ae581f25-9c34-5b65-9c61-752b878d5163 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check panel size and dimensions against IFC drawings
label | 1e92e5b4-762c-583a-a4f9-deb84885fd78 |  | note | Responsibility: Facadex
label | b33fdcfc-5970-51e3-9f57-3d70d5db117e |  | note | – – – – – – – – –
label | 7ace4917-ef00-513e-99a1-10a0aed9301f |  | note | Acceptance Criteria: Facadex sign off.
text | 6ec4f1b5-c8b4-5276-bab9-072a15b0fd2e |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check diagonal dimension to ensure odd shape panel are done correctly
label | 4ca0f0d7-4a02-5b8b-980b-7b5edf10479b |  | note | Responsibility: Facadex
label | b4b3f9f9-b7a8-5893-a903-6882b5870b14 |  | note | – – – – – – – – –
label | e5ccea6e-efd7-5093-8820-f7c1f042edc8 |  | note | Acceptance Criteria: Facadex sign off.
text | 0d9569d8-3220-5594-b56e-59d12335beb5 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | QA has checked delivery docket and receipt from powder coater
label | 3fbfee6a-4aa4-5d81-ac45-62b456a5f92e |  | note | Responsibility: Facadex
label | 6b5d5f7a-dfd2-57f0-a53e-0edc1a912420 |  | note | – – – – – – – – –
label | 605a4888-9cb6-5f91-bde4-3f93b8b6d067 |  | note | Acceptance Criteria: Facadex sign off.
text | 045ce305-f9be-5811-becc-83b6f33dfae9 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Is fabricated item labelled as per drawing?
label | ad2a23c4-1b7d-5d43-8790-68c8af9659f1 |  | note | Responsibility: Facadex
label | 570a91af-32f0-57ae-917f-13619f3623f7 |  | note | – – – – – – – – –
label | 14dfcfbf-aad2-569e-b8bc-4fcbb464760d |  | note | Acceptance Criteria: Facadex sign off.
text | cc48bc1b-1504-57ba-866b-a077a4b0328e |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Fabrication complete
label | 4e3a1ef2-aba7-57f3-87e5-a55375c309cb |  | note | Responsibility: Facadex
label | d31e409c-a575-5da0-a60b-ce46e9ead3cd |  | note | – – – – – – – – –
label | 18c7dab1-24a9-584f-ad25-b6211a389686 |  | note | Acceptance Criteria: Facadex sign off.
text | d3bcf741-d83f-5e96-ab6e-f74a94150e99 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Prevent direct contanct between incompatible materials
label | 6389ab0a-b923-5062-9df5-67b05a2bf405 |  | note | Responsibility: Facadex
label | 96634b8a-586d-5cfe-bbcb-6b13472972a3 |  | note | – – – – – – – – –
label | 38468df4-e9e6-5cdc-a1a6-9bb9b8a08ea7 |  | note | Acceptance Criteria: Facadex sign off.
text | 39f4e0b7-f06b-5207-b6f6-c54cdd4563a3 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Materials ready to deliver on site
label | 3e471a34-2db7-5671-b768-ad50b35a628f |  | note | Responsibility: Facadex
label | 114f53f2-a443-506c-beab-85de3a61b508 |  | note | – – – – – – – – –
label | b712cedc-8184-5162-946e-4deb4a05865a |  | note | Acceptance Criteria: Facadex sign off.
text | 4bdc97c8-2bf1-5335-932c-ef68c52c7dbf |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | c9e8c455-409e-581a-876b-c5088da17c6d |  | note | Responsibility: Facadex / Builder
label | 6bf987e1-83bd-5ec1-bd6f-cdf5645e8af3 |  | note | – – – – – – – – –
label | 9d417330-3847-5189-9cd5-24e323888d08 |  | note | Acceptance Criteria: Defect notification via email or chosen correspondence
label | 25177711-effd-55fd-b7e4-f925cf24cab0 |  | note | ○ Evidence of close out / rectification
label | ef8ad8ca-c782-5b31-b3b8-722b2bb686f8 |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | 3058a16a-dd42-588b-aaeb-90e85cc42ffb |  | note | ○ Sign of only once agreed that wall is defect free
text | db85c688-156a-5e4a-9932-805476e9540c |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | a48ccd02-1fe4-5e59-8a05-888b991b5cc8 |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | 81afdb02-d04e-514f-977c-2d95f0515545 |  | textbox | Foreman – Checklist Completed:
text | f3acbebf-dc8e-519e-ae81-66985c1fb278 |  | textbox | Date / Time:
text | d94fea19-ce1f-5b98-bd3c-65303427e8d5 |  | textbox | Coordinator – Checklist Completed:
text | 9a6143ab-c74e-5231-8795-d0e43627c302 |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLG-514 Bridge Factory ITP | itp |  |  |  | Yes | CLG-514 Bridge Factory ITP | fdf1bd05-918e-4474-94a3-a65c6b38a6ed
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC shop drawings approved for fabrication
label | 3472d786-3577-5339-893e-00d264086464 |  | note | Responsibility: MPX
label | 52e8877a-7a94-5368-9280-9c96b35cf427 |  | note | – – – – – – – – –
label | 5c225f3d-0a70-5371-a353-81b5f7cf7841 |  | note | Acceptance Criteria: MPX / Architect sign off
label | 55065371-5271-562a-be35-192a667fa702 |  | note | – – – – – – – – –
text | 97727bcf-286d-531f-96fc-0ab574f135da |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 83472bb3-50af-5768-a2c8-69f0f1c65103 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | b5186b0a-1ce0-5d47-941c-a6039bb48f80 |  | note | Responsibility: MPX
label | fe82d1b2-ac63-5a27-9318-edb2973ebd61 |  | note | – – – – – – – – –
label | e074db5b-9cf7-5624-a05b-5e5c03070ea8 |  | note | Acceptance Criteria: MPX / Architect sign off
label | 2a8336f5-8148-58bf-bd85-3553f483ab18 |  | note | – – – – – – – – –
text | 68bdba1c-79b0-55d4-9585-2acc6d21a22b |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | afee839d-cb9c-5919-9969-dedb9cf5d080 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Confirm and check finish as per approved IFC drawings
label | e32315e8-125a-5244-8f93-09e0908a7245 |  | note | Responsibility: Facadex
label | c900e971-7434-58ff-8d39-ec5753cadd4c |  | note | – – – – – – – – –
label | 0930aed9-4b0b-5f75-876e-3077704b9558 |  | note | Acceptance Criteria: Facadex sign off.
label | 18afb700-892f-5632-952d-ff054c733c32 |  | note | – – – – – – – – –
text | 216fee86-3f93-5202-b8a0-f73237e72a90 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | d86e04e1-353a-509c-8556-24a514bd3574 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check panel size and dimensions against IFC drawings
label | 4576243d-aa3e-5164-b411-5f917ff46f9e |  | note | Responsibility: Facadex
label | c010f2fa-29e9-5535-93fb-41d82884745c |  | note | – – – – – – – – –
label | b91f5714-4c8a-5dfb-9e7f-497d5c728cd1 |  | note | Acceptance Criteria: Facadex sign off.
label | 1d719952-714a-5683-8d8a-a765e81ba49d |  | note | – – – – – – – – –
text | f75a716a-76fa-5fb2-bca4-5bb7d4dc1662 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 7f2b62b7-cd7f-5127-96e7-8c9cb03b6d67 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check diagonal dimension to ensure odd shape panel are done correctly
label | abc549ad-b369-50b2-a1c8-b704ac8421ea |  | note | Responsibility: Facadex
label | ba993840-e52f-5521-8253-a881be337c5d |  | note | – – – – – – – – –
label | 3515fff1-f180-58f4-8866-a49e3f20f435 |  | note | Acceptance Criteria: Facadex sign off.
label | 2f8d1ba2-06df-519e-8dbb-90688ff42aec |  | note | – – – – – – – – –
text | f2c8fad0-733a-5fed-aafa-dd9f39515429 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 06558924-62c3-599e-9650-dcdad531a9c6 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | QA has checked delivery docket and receipt from powder coater
label | dd19dfba-85a1-5f84-b29b-fab7ba6e3811 |  | note | Responsibility: Facadex
label | a595deb6-5a83-5275-b579-aefe3d39e0e0 |  | note | – – – – – – – – –
label | d088346c-623f-5147-9d12-f7b5e657e6aa |  | note | Acceptance Criteria: Facadex sign off.
label | aa72cd7d-d3a3-5c5a-b11a-b6638f9b8e45 |  | note | – – – – – – – – –
text | 9a591110-f7d1-58ad-a69d-483286c55ef7 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 21796ba6-e575-5cc4-b365-ddf89420d06d |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Is fabricated item labelled as per drawing?
label | 0083a231-1587-5614-80be-97a5d4fe5a37 |  | note | Responsibility: Facadex
label | f8121108-f7c7-51f9-ad3c-97fe6edee3be |  | note | – – – – – – – – –
label | 21fe6a80-a6de-59e9-8fac-544d0f417a04 |  | note | Acceptance Criteria: Facadex sign off.
label | 2eeccd4f-a8ec-5ee3-9b7a-4af8826e9cc3 |  | note | – – – – – – – – –
text | 853098a6-c5be-5519-bcc7-9d0d2231ea2a |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 4e8a4b00-f091-5814-b93b-4f64d89c38f4 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Fabrication complete
label | 6efe71d3-420a-5ae2-ada3-60ef9b1b8385 |  | note | Responsibility: Facadex
label | 181a4dad-d213-5541-ba02-6e393b21ccbe |  | note | – – – – – – – – –
label | d8396307-1bbe-51d3-988d-1bf566166af0 |  | note | Acceptance Criteria: Facadex sign off.
label | 698c3664-22fd-592c-a4e1-3b9be2854f85 |  | note | – – – – – – – – –
text | 8e088db0-2d33-5eeb-a207-9bf788d22d75 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 5f2b8c56-9e86-5995-9c03-f9c04536df3a |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Prevent direct contanct between incompatible materials
label | bfc817d2-c9ed-5e3f-bb57-6d4f4b148ad7 |  | note | Responsibility: Facadex
label | 3e2675cd-327d-5384-a2b4-f648df7e983d |  | note | – – – – – – – – –
label | 2d6ad526-9161-5908-912e-a05210dc1d94 |  | note | Acceptance Criteria: Facadex sign off.
label | d4075b0d-1191-52e5-b750-46dc45e6c218 |  | note | – – – – – – – – –
text | ecffe366-095a-5c03-9742-ce0c0d9feead |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 867286b3-f8a2-5c6c-a518-473f39fe533a |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Materials ready to deliver on site
label | d0e11353-d060-57e3-bb8a-0bd8fc9ef84b |  | note | Responsibility: Facadex
label | 974f4781-c7cb-5505-82e3-3b5235615711 |  | note | – – – – – – – – –
label | 57b26c75-4c8f-5e86-8bcc-b603e226eb9a |  | note | Acceptance Criteria: Facadex sign off.
label | 7dee31e7-8e35-5ba3-808a-0cc7f33b2b1c |  | note | – – – – – – – – –
text | 68955439-61d1-54e5-94b3-ab080b443087 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 924e8b2d-fb1a-5d80-8895-5658f9bd0ea1 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | dd4252fa-a12b-5c93-877a-9356ffde3132 |  | note | Responsibility: Facadex / Builder
label | 7a419d16-8286-5c9f-ba8b-bb2e348847a4 |  | note | – – – – – – – – –
label | 6e01c34a-d655-5735-80a5-0bfc986c1df5 |  | note | Acceptance Criteria: Defect notification via email or chosen correspondance
label | ef9264ee-c3ac-512d-91c1-2e3a9296be4a |  | note | ○ Evidence of close out / rectification
label | c555d2e1-8d27-58aa-a9de-bde35bf71544 |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | e25b5ede-4678-57cf-a85c-71a440e94d38 |  | note | ○ Sign off only once agreed that wall is defect free
label | 4c304724-7c51-516f-8611-51ff66c429d7 |  | note | – – – – – – – – –
text | 6aa057a6-7cdf-531f-ac4d-97383e89bebb |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | dbdaea4d-42c4-55ce-a69e-458bd50a4ba6 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | d431e8d1-5ea1-535f-9f9a-73256256b245 |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | 0874111d-0197-52d3-a070-07efa067cbed |  | textbox | Foreman – Checklist Completed:
text | 79470d1f-4f68-5c94-bc57-22f0ba418feb |  | textbox | Date / Time:
text | 68f300b9-4dec-58c7-b5af-3ce4a88573b6 |  | textbox | Coordinator – Checklist Completed:
text | 57c88e2a-a3b4-5dc2-9001-06709efcbffc |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed