## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | SCN-117 3mm Alum Capping and Shroud (Building A) Panel site ITP | itp |  |  |  |  | SCN-117 3mm Alum Capping and Shroud (Building A) Panel site ITP
section | Details
checkpoint | IFC Shop Drawings Approved
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
label | – – – – – – – – –
textbox | Date:
checkpoint | Material Approval
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
label | – – – – – – – – –
textbox | Date:
label | Comments: Check colour is correct as per shop drawings
checkpoint | (Panels/Bolts/Screw/Washers) delivered to site free of damage and deformation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Date:
label | Comments: Check colour is correct as per shop drawings
checkpoint | Parapet wall has been installed for cladding
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Date:
label | Comments: If installed off site no gridline available
checkpoint | 25x50x1.15 BMT galvanied Z450 top hat has been fixed to the back of the Parapet with M6 anchors @500mm CTS
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Date:
checkpoint | 3mm alum panel planter gap cover has been installed where there is a planter at the back of the parapet
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | Expansion & Contraction:
label | ○ +/- 3mm @ every 1000mm in length & height
label | – – – – – – – – –
textbox | Date:
checkpoint | 15x50 1.15BMT galvanized Z450 top hat has been installed with blue screws at top of the parapet for the capping
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Date:
checkpoint | 3mm alum capping (dulux electro bronze flat) has been installed to the top of the parapet
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | Expansion & Contraction:
label | ○ +/- 3mm @ every 1000mm in length & height
label | – – – – – – – – –
textbox | Date:
checkpoint | 3mm Alum back pan in dulux electro bronze flat has been installed to the back of the parapet
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | Expansion & Contraction:
label | ○ +/- 3mm @ every 1000mm in length & height
label | – – – – – – – – –
textbox | Date:
checkpoint | Bottom shroud has been installed to the bottom with M8x60 anchor bolts @500mm CTS
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Date:
checkpoint | All silicone joint has been caulked uniformly
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Date:
checkpoint | Panel has no scratches/dents/damages to the finish
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Date:
holdpoint | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | Responsibility: Facadex / Builder
label | – – – – – – – – –
label | Acceptance Criteria: Defect notification via email or chosen correspondence
label | ○ Evidence of close out / rectification
label | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | ○ Sign of only once agreed that wall is defect free
textbox | Date:
checkpoint | AUTHORITY TO PROCEED
label | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
textbox | Foreman – Checklist Completed:
textbox | Date / Time:
textbox | Coordinator – Checklist Completed:
textbox | Date / Time:
holdpoint | Checklist Completed
checklist | SCN-117 3mm Alum Capping and Shroud Factory ITP | itp |  |  |  |  | SCN-117 3mm Alum Capping and Shroud Factory ITP
section | Details
checkpoint | IFC shop drawings approved for fabrication
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect sign off
label | – – – – – – – – –
textbox | Date:
checkpoint | Material Approval
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect sign off
label | – – – – – – – – –
textbox | Date:
checkpoint | Confirm and check finish as per approved IFC drawings
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Date:
checkpoint | Check panel size and dimensions against IFC drawings
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Date:
checkpoint | Check diagonal dimension to ensure odd shape panel are done correctly
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Date:
checkpoint | Check the bottom Shroud extrusion has been procured without damages/dents/scratches to the surface
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Date:
checkpoint | QA has checked delivery docket and receipt from powder coater
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Date:
checkpoint | Is fabricated item labelled as per drawing?
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Date:
checkpoint | Fabrication complete
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Date:
checkpoint | Prevent direct contanct between incompatible materials
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Date:
checkpoint | Materials ready to deliver on site
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Date:
checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | Responsibility: Facadex / Builder
label | – – – – – – – – –
label | Acceptance Criteria: Defect notification via email or chosen correspondence
label | ○ Evidence of close out / rectification
label | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | ○ Sign of only once agreed that wall is defect free
textbox | Date:
checkpoint | AUTHORITY TO PROCEED
label | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
textbox | Foreman – Checklist Completed:
textbox | Date / Time:
textbox | Coordinator – Checklist Completed:
textbox | Date / Time:
holdpoint | Checklist Completed