## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP028 - AGL MAG Signs | itp |  |  |  |  | FH-ZU2-QU-ITP028 - AGL MAG Signs - Rev 0
section | 1.0 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Ensure that all employees and subcontractors are using the latest and complete set of drawings
label | Reference Documents - IFC Drawings
label | Inspection/Test Method - Verify
label | Record of conformity - Drawings
label | IP
label | Responsibility - Project Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing any activities
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is PSP, EMP, TMP, SWMS & WP.
label | Reference Documents - PSP, EMP, TMP, JSEA, SWMS, WP
label | Inspection/Test Method - Verify
label | Record of conformity - Site and office Inspection
label | HP*
label | Responsibility - Project Engineer / Site Supervisor
date | Date Completed:
checkpoint | 1.3 - Material/Equipment Approvals
label | Frequency - Prior to start
label | Acceptance Criteria - All materials shall be proven to meet contractual requirements prior to acceptance.
label | ○ MAGS shall be from ATG Airfield guidance signs range.
label | ○ Any deviation from the above suppliers shall be submitted to the Contract Administrator for approval prior to ordering.
label | Reference Documents - ZULU- BECA-001- SPC-00003 cl 2.3
label | Inspection/Test Method - Verify
label | Record of conformity - Aconex reference(s)
label | HP*
label | Responsibility - Project Engineer
date | Date Completed:
section | 2.0 - Installation of MAG Sign Footing
checkpoint | 2.1 - MAG Sign Base
label | Frequency - Each lot
label | Acceptance Criteria - Position of rectangular base to be as per set out coordinated listed in MAG schedule.
label | ○ 150mm thick class 2 crushed rock base layer compacted to 98% STD on prepared subgrade.
label | ○ Subgrade Bearing strength of 130kPA confirmed by a qualified geotechnical engineer on behalf of the contractor before placing membrane, reinforcement or concrete.
label | ○ 50mm blinding concrete between subgrade and foundation.
label | ○ Slab thickness to be 300mm for all H<900mm signs, min. 32 MPa concrete.
label | ○ Footing to be placed flush with FSL when placed in pavement surfaced areas.
label | ○ N12-200 top and bottom reinforcing bars with minimum 50mm cover from edge of concrete.
label | ○ Sign mounting brackets and frangible coupling as per manufacturers guidelines
label | Reference Documents - ZULU-BECA-023-DWG-07502
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed, DCP test result, Concrete test certificate, Avionics Installation of New MAG Slab and Sign checklist
label | IP
label | Responsibility - Project Engineer
date | Date Completed:
section | 3.0 - Installation of MAG Sign
checkpoint | 3.1 - Luminaire Circuit
label | Frequency - Each lot
label | Acceptance Criteria - Each luminaire fitting shall be installed on the appropriate circuit as specified in the AGL schedule.
label | Reference Documents - ZULU-BECA-024-DWG-09001-16
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed, As-Built Documentation
label | IP
label | Responsibility - Project Engineer
date | Date Completed:
checkpoint | 3.2 - MAG Sign Face
label | Frequency - Each lot
label | Acceptance Criteria - All MAGS that are to be mounted on frangible couplings. The provision of internal illumination of the MAGS shall be as detailed on the Drawings.
label | ○ Bird spikes provided with MAGS Chain tether installed on side further from taxiway and installed as per manufacturer’s recommendations
label | ○ Where multiple panels are required, the inscription shall appear continuous over any joint and shall only include a bar if the bar is part of the inscription.
label | Reference Documents - ZULU-BECA-001-SPC-00003 cl 4.7.1
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed, Avionics Installation of New MAG Slab and Sign checklist
label | IP
label | Responsibility - Project Engineer
date | Date Completed:
section | 4.0 - Post Construction
checkpoint | 4.1 - As-Built
label | Frequency - Each lot
label | Acceptance Criteria - Submission of surveyed luminaire position to superintendent prior to practical completion
label | Reference Documents - WP-001-09
label | Inspection/Test Method - Verify
label | Record of conformity - SCP
label | IP
label | Responsibility - Project Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
date | Work Completed On:
date | Date: