## SWMH08
INSPECTION TEST PLAN
CONSTRUCTION
Foreman |  | Daryl Banks |  | Action | Arthur St SW Manholes
Manager |  | Kate Gentle |  |  | W | Witness | SWMH08 - DN1800 RCMH WITH SCRUFFY DOME
Divisional Manager |  | Jay Arthur |  |  | H | Hold Point
Engineer |  | Callum Feely |  |  | M | Monitor | Job Number: |  | 4811 | Version: | 1
No: | Detail | Specification / Standard | Inspection / Test Point | ACTION | Conformance Criteria (Whats Required) | Frequency | Inspection / Test Method | Verification Records | Signatory | Comments | Date | Signature
1 | PRE-CAST BASES AND RISERS |  | Sign off | H | Inspection of concrete product upon delivery to site. Ensure there is no damage or cracking to the precast unit. | Prior to commencement | Visual | Sign This ITP | Site Foreman, Engineer's Representative
2 | RCRRJ PIPE AND FITTINGS | SR10.103 SR10.105 | Sign off | H | Class 2 RCRRJ pipe, pipe to be inspected upon delivery and have no damage or deformities | Prior to installation | Visual | Sign This ITP | Site Foreman, Engineer's Representative
3 | BENCHING AND OTHER MASS POURS FOR MANHOLE | Contract Document | Sign off | H | Minimum 1:4 crossfall grade towards formed channel, all surfaces finished smooth, no benching shall hold water | During Installation | Visual | Sign This ITP | Site Foreman
4 | BASE PREPARATION FOR MANHOLE | Contract Document | Sign off | M | A level 150mm AP65 compacted base. | Prior to installation | Review | Sign This ITP | Site Foreman
5 | BACKFILLING AND COMPACTION ROADWAY | Contract Document | Sign off | M | All backfilled material shall be compaction tested at a maximum of 20m intervals longitudinally with an NDM. | During Installation | NDM | Sign This ITP | Site Foreman

## SWMH07
INSPECTION TEST PLAN
CONSTRUCTION
Foreman |  | Daryl Banks |  | Action | Arthur St SW Manholes
Manager |  | Kate Gentle |  |  | W | Witness | SWMH07 - DN1800 RCMH WITH HINGED LID
Divisional/Regional/General Manager |  | Jay Arthur |  |  | H | Hold Point
Engineer |  | Callum Feely |  |  | M | Monitor | Job Number: |  | 4811 | Version: | 1
No: | Detail | Specification / Standard | Inspection / Test Point | ACTION | Conformance Criteria (Whats Required) | Frequency | Inspection / Test Method | Verification Records | Signatory | Comments | Date | Signature
1 | PRE-CAST BASES AND RISERS |  | Sign off | H | Inspection of concrete product upon delivery to site. Ensure there is no damage or cracking to the precast unit. | Prior to commencement | Visual | Sign This ITP | Site Foreman, Engineer's Representative
2 | RCRRJ PIPE AND FITTINGS | SR10.103 SR10.105 | Sign off | H | Class 2 RCRRJ pipe, pipe to be inspected upon delivery and have no damage or deformities | Prior to installation | Visual | Sign This ITP | Site Foreman, Engineer's Representative
3 | BENCHING AND OTHER MASS POURS FOR MANHOLE | Contract Document | Sign off | H | Minimum 1:4 crossfall grade towards formed channel, all surfaces finished smooth, no benching shall hold water | During Installation | Visual | Sign This ITP | Site Foreman
4 | BASE PREPARATION FOR MANHOLE | Contract Document | Sign off | M | A level 150mm AP65 compacted base. | Prior to installation | Review | Sign This ITP | Site Foreman
5 | BACKFILLING AND COMPACTION ROADWAY | Contract Document | Sign off | M | All backfilled material shall be compaction tested at a maximum of 20m intervals longitudinally with an NDM. | During Installation | NDM | Sign This ITP | Site Foreman

## SWMH06
INSPECTION TEST PLAN
CONSTRUCTION
Foreman |  | Daryl Banks |  | Action | Arthur St SW Manholes
Manager |  | Kate Gentle |  |  | W | Witness | SWMH06 - DN1800 RCMH WITH HINGED LID
Divisional/Regional/General Manager |  | Jay Arthur |  |  | H | Hold Point
Engineer |  | Callum Feely |  |  | M | Monitor | Job Number: |  | 4811 | Version: | 1
No: | Detail | Specification / Standard | Inspection / Test Point | ACTION | Conformance Criteria (Whats Required) | Frequency | Inspection / Test Method | Verification Records | Signatory | Comments | Date | Signature
1 | PRE-CAST BASES AND RISERS |  | Sign off | H | Inspection of concrete product upon delivery to site. Ensure there is no damage or cracking to the precast unit. | Prior to commencement | Visual | Sign This ITP | Site Foreman, Engineer's Representative
2 | RCRRJ PIPE AND FITTINGS | SR10.103 SR10.105 | Sign off | H | Class 2 RCRRJ pipe, pipe to be inspected upon delivery and have no damage or deformities | Prior to installation | Visual | Sign This ITP | Site Foreman, Engineer's Representative
3 | BENCHING AND OTHER MASS POURS FOR MANHOLE | Contract Document | Sign off | H | Minimum 1:4 crossfall grade towards formed channel, all surfaces finished smooth, no benching shall hold water | During Installation | Visual | Sign This ITP | Site Foreman
4 | BASE PREPARATION FOR MANHOLE | Contract Document | Sign off | M | A level 150mm AP65 compacted base. | Prior to installation | Review | Sign This ITP | Site Foreman
5 | BACKFILLING AND COMPACTION ROADWAY | Contract Document | Sign off | M | All backfilled material shall be compaction tested at a maximum of 20m intervals longitudinally with an NDM. | During Installation | NDM | Sign This ITP | Site Foreman

## SWMH05
INSPECTION TEST PLAN
CONSTRUCTION
Foreman |  | Daryl Banks |  | Action | Arthur St SW Manholes
Manager |  | Kate Gentle |  |  | W | Witness | SWMH05 - DN1800 RCMH WITH HINGED LID
Divisional/Regional/General Manager |  | Jay Arthur |  |  | H | Hold Point
Engineer |  | Callum Feely |  |  | M | Monitor | Job Number: |  | 4811 | Version: | 1
No: | Detail | Specification / Standard | Inspection / Test Point | ACTION | Conformance Criteria (Whats Required) | Frequency | Inspection / Test Method | Verification Records | Signatory | Comments | Date | Signature
1 | PRE-CAST BASES AND RISERS |  | Sign off | H | Inspection of concrete product upon delivery to site. Ensure there is no damage or cracking to the precast unit. | Prior to commencement | Visual | Sign This ITP | Site Foreman, Engineer's Representative
2 | RCRRJ PIPE AND FITTINGS | SR10.103 SR10.105 | Sign off | H | Class 2 RCRRJ pipe, pipe to be inspected upon delivery and have no damage or deformities | Prior to installation | Visual | Sign This ITP | Site Foreman, Engineer's Representative
3 | BENCHING AND OTHER MASS POURS FOR MANHOLE | Contract Document | Sign off | H | Minimum 1:4 crossfall grade towards formed channel, all surfaces finished smooth, no benching shall hold water | During Installation | Visual | Sign This ITP | Site Foreman
4 | BASE PREPARATION FOR MANHOLE | Contract Document | Sign off | M | A level 150mm AP65 compacted base. | Prior to installation | Review | Sign This ITP | Site Foreman
5 | BACKFILLING AND COMPACTION ROADWAY | Contract Document | Sign off | M | All backfilled material shall be compaction tested at a maximum of 20m intervals longitudinally with an NDM. | During Installation | NDM | Sign This ITP | Site Foreman

## SWMH04
INSPECTION TEST PLAN
CONSTRUCTION
Foreman |  | Daryl Banks |  | Action | Arthur St SW Manholes
Manager |  | Kate Gentle |  |  | W | Witness | SWMH04 - DN1800 RCMH WITH HINGED LID
Divisional/Regional/General Manager |  | Jay Arthur |  |  | H | Hold Point
Engineer |  | Callum Feely |  |  | M | Monitor | Job Number: |  | 4811 | Version: | 1
No: | Detail | Specification / Standard | Inspection / Test Point | ACTION | Conformance Criteria (Whats Required) | Frequency | Inspection / Test Method | Verification Records | Signatory | Comments | Date | Signature
1 | PRE-CAST BASES AND RISERS |  | Sign off | H | Inspection of concrete product upon delivery to site. Ensure there is no damage or cracking to the precast unit. | Prior to commencement | Visual | Sign This ITP | Site Foreman, Engineer's Representative
2 | RCRRJ PIPE AND FITTINGS | SR10.103 SR10.105 | Sign off | H | Class 2 RCRRJ pipe, pipe to be inspected upon delivery and have no damage or deformities | Prior to installation | Visual | Sign This ITP | Site Foreman, Engineer's Representative
3 | BENCHING AND OTHER MASS POURS FOR MANHOLE | Contract Document | Sign off | H | Minimum 1:4 crossfall grade towards formed channel, all surfaces finished smooth, no benching shall hold water | During Installation | Visual | Sign This ITP | Site Foreman
4 | BASE PREPARATION FOR MANHOLE | Contract Document | Sign off | M | A level 150mm AP65 compacted base. | Prior to installation | Review | Sign This ITP | Site Foreman
5 | BACKFILLING AND COMPACTION ROADWAY | Contract Document | Sign off | M | All backfilled material shall be compaction tested at a maximum of 20m intervals longitudinally with an NDM. | During Installation | NDM | Sign This ITP | Site Foreman

## SWMH03
INSPECTION TEST PLAN
CONSTRUCTION
Foreman |  | Daryl Banks |  | Action | Arthur St SW Manholes
Manager |  | Kate Gentle |  |  | W | Witness | SWMH03 - DN1050 RCMH WITH HINGED LID
Divisional/Regional/General Manager |  | Jay Arthur |  |  | H | Hold Point
Engineer |  | Callum Feely |  |  | M | Monitor | Job Number: |  | 4811 | Version: | 1
No: | Detail | Specification / Standard | Inspection / Test Point | ACTION | Conformance Criteria (Whats Required) | Frequency | Inspection / Test Method | Verification Records | Signatory | Comments | Date | Signature
1 | PRE-CAST BASES AND RISERS |  | Sign off | H | Inspection of concrete product upon delivery to site. Ensure there is no damage or cracking to the precast unit. | Prior to commencement | Visual | Sign This ITP | Site Foreman, Engineer's Representative
2 | RCRRJ PIPE AND FITTINGS | SR10.103 SR10.105 | Sign off | H | Class 2 RCRRJ pipe, pipe to be inspected upon delivery and have no damage or deformities | Prior to installation | Visual | Sign This ITP | Site Foreman, Engineer's Representative
3 | BENCHING AND OTHER MASS POURS FOR MANHOLE | Contract Document | Sign off | H | Minimum 1:4 crossfall grade towards formed channel, all surfaces finished smooth, no benching shall hold water | During Installation | Visual | Sign This ITP | Site Foreman
4 | BASE PREPARATION FOR MANHOLE | Contract Document | Sign off | M | A level 150mm AP65 compacted base. | Prior to installation | Review | Sign This ITP | Site Foreman
5 | BACKFILLING AND COMPACTION ROADWAY | Contract Document | Sign off | M | All backfilled material shall be compaction tested at a maximum of 20m intervals longitudinally with an NDM. | During Installation | NDM | Sign This ITP | Site Foreman

## SWMH02
INSPECTION TEST PLAN
CONSTRUCTION
Foreman |  | Daryl Banks |  | Action | Arthur St SW Manholes
Manager |  | Kate Gentle |  |  | W | Witness | SWMH02 - DN1050 RCMH WITH HINGED LID
Divisional/Regional/General Manager |  | Jay Arthur |  |  | H | Hold Point
Engineer |  | Callum Feely |  |  | M | Monitor | Job Number: |  | 4811 | Version: | 1
No: | Detail | Specification / Standard | Inspection / Test Point | ACTION | Conformance Criteria (Whats Required) | Frequency | Inspection / Test Method | Verification Records | Signatory | Comments | Date | Signature
1 | PRE-CAST BASES AND RISERS |  | Sign off | H | Inspection of concrete product upon delivery to site. Ensure there is no damage or cracking to the precast unit. | Prior to commencement | Visual | Sign This ITP | Site Foreman, Engineer's Representative
2 | RCRRJ PIPE AND FITTINGS | SR10.103 SR10.105 | Sign off | H | Class 2 RCRRJ pipe, pipe to be inspected upon delivery and have no damage or deformities | Prior to installation | Visual | Sign This ITP | Site Foreman, Engineer's Representative
3 | BENCHING AND OTHER MASS POURS FOR MANHOLE | Contract Document | Sign off | H | Minimum 1:4 crossfall grade towards formed channel, all surfaces finished smooth, no benching shall hold water | During Installation | Visual | Sign This ITP | Site Foreman
4 | BASE PREPARATION FOR MANHOLE | Contract Document | Sign off | M | A level 150mm AP65 compacted base. | Prior to installation | Review | Sign This ITP | Site Foreman
5 | BACKFILLING AND COMPACTION ROADWAY | Contract Document | Sign off | M | All backfilled material shall be compaction tested at a maximum of 20m intervals longitudinally with an NDM. | During Installation | NDM | Sign This ITP | Site Foreman

## SWMH01
INSPECTION TEST PLAN
CONSTRUCTION
Foreman |  | Daryl Banks |  | Action | Arthur St SW Manholes
Manager |  | Kate Gentle |  |  | W | Witness | SWMH01 - DN1050 RCMH WITH HINGED LID
Divisional/Regional/General Manager |  | Jay Arthur |  |  | H | Hold Point
Engineer |  | Callum Feely |  |  | M | Monitor | Job Number: |  | 4811 | Version: | 1
No: | Detail | Specification / Standard | Inspection / Test Point | ACTION | Conformance Criteria (Whats Required) | Frequency | Inspection / Test Method | Verification Records | Signatory | Comments | Date | Signature
1 | PRE-CAST BASES AND RISERS |  | Sign off | H | Inspection of concrete product upon delivery to site. Ensure there is no damage or cracking to the precast unit. | Prior to commencement | Visual | Sign This ITP | Site Foreman, Engineer's Representative
2 | RCRRJ PIPE AND FITTINGS | SR10.103 SR10.105 | Sign off | H | Class 2 RCRRJ pipe, pipe to be inspected upon delivery and have no damage or deformities | Prior to installation | Visual | Sign This ITP | Site Foreman, Engineer's Representative
3 | BENCHING AND OTHER MASS POURS FOR MANHOLE | Contract Document | Sign off | H | Minimum 1:4 crossfall grade towards formed channel, all surfaces finished smooth, no benching shall hold water | During Installation | Visual | Sign This ITP | Site Foreman
4 | BASE PREPARATION FOR MANHOLE | Contract Document | Sign off | M | A level 150mm AP65 compacted base. | Prior to installation | Review | Sign This ITP | Site Foreman
5 | BACKFILLING AND COMPACTION ROADWAY | Contract Document | Sign off | M | All backfilled material shall be compaction tested at a maximum of 20m intervals longitudinally with an NDM. | During Installation | NDM | Sign This ITP | Site Foreman