## SWMH08 - SWMH07
INSPECTION TEST PLAN
CONSTRUCTION
Foreman |  | Daryl Banks |  | Action | Arthur St SW Pipelines
Manager |  | Kate Gentle |  |  | W | Witness | SWMH08-SWMH07 - 825 CLASS 2 RCRRJ - 77.4M @ 1.31%
Divisional Manager |  | Jay Arthur |  |  | H | Hold Point
Engineer |  | Callum Feely |  |  | M | Monitor | Job Number: |  | 4811 | Version: | 1
No: | Detail | Specification / Standard | Inspection / Test Point | ACTION | Conformance Criteria (Whats Required) | Frequency | Inspection / Test Method | Verification Records | Signatory | Comments | Date | Signature
1 | CLASS 2 RCRRJ PIPE AND FITTINGS | Contract Document | Sign Off | H | Class 2 RCRRJ pipe, pipe to be inspected upon delivery and have no damage or deformities | Prior to commencement/upon delivery of materials | Visual | Sign this ITP | Site Foreman Engineer's Representative
2 | BEDDING MATERIAL | AS/NZS 2566.2 | Aggregate Certification | M | Clean granular non-cohesive material with a maximum particle size of 20mm | Continuous for pipe length | Clegg Hammer | Sign this ITP | Site Foreman
3 | OPEN TRENCHING ALIGNMENT, DEPTH AND ACCURACY | Contract Document | Witness & Record | M | Installed within +/- 10mm accuracy from design datum. Installed as per design grade and recorded on pipe laying form. Daily checks to make sure pipe is laid to design. | Prior to commencement and every two lengths | Review | Sign this ITP | Site Foreman
5 | BACKFILLING AND COMPACTION ROADWAY | Contract Document | Sign off | M | Trench backfill to be carried out with imported AP65 gravel in 250mm lifts. The subbase material shall achieve an average of 95% of the MDD. All backfilled material shall be compaction tested at a maximum of 20m intervals longitudinally and 1m vertically with an NDM. All basecourse material shall be M4AP40. | During Installation | NDM | Sign This ITP | Site Foreman
5 | CCTV | Contract Document | CCTV Footage | H | Clear new pipeline of any debris prior to CCTV. CCTV inspection of gravity to be as per the New Zealand Pipe Inspection manual. | Once pipeline is installed | CCTV | Sign this ITP | Site Foreman

## SWMH07 - SWMH06
INSPECTION TEST PLAN
CONSTRUCTION
Foreman |  | Daryl Banks |  | Action | Arthur St SW Pipelines
Manager |  | Kate Gentle |  |  | W | Witness | SWMH07-SWMH06 - 825 CLASS 2 RCRRJ - 81.2M @ 0.50%
Divisional Manager |  | Jay Arthur |  |  | H | Hold Point
Engineer |  | Callum Feely |  |  | M | Monitor | Job Number: |  | 4811 | Version: | 1
No: | Detail | Specification / Standard | Inspection / Test Point | ACTION | Conformance Criteria (Whats Required) | Frequency | Inspection / Test Method | Verification Records | Signatory | Comments | Date | Signature
1 | CLASS 2 RCRRJ PIPE AND FITTINGS | Contract Document | Sign Off | H | Class 2 RCRRJ pipe, pipe to be inspected upon delivery and have no damage or deformities | Prior to commencement/upon delivery of materials | Visual | Sign this ITP | Site Foreman Engineer's Representative
2 | BEDDING MATERIAL | AS/NZS 2566.2 | Aggregate Certification | M | Clean granular non-cohesive material with a maximum particle size of 20mm | Continuous for pipe length | Clegg Hammer | Sign this ITP | Site Foreman
3 | OPEN TRENCHING ALIGNMENT, DEPTH AND ACCURACY | Contract Document | Witness & Record | M | Installed within +/- 10mm accuracy from design datum. Installed as per design grade and recorded on pipe laying form. Daily checks to make sure pipe is laid to design. | Prior to commencement and every two lengths | Review | Sign this ITP | Site Foreman
5 | BACKFILLING AND COMPACTION ROADWAY | Contract Document | Sign off | M | Trench backfill to be carried out with imported AP65 gravel in 250mm lifts. The subbase material shall achieve an average of 95% of the MDD. All backfilled material shall be compaction tested at a maximum of 20m intervals longitudinally and 1m vertically with an NDM. All basecourse material shall be M4AP40. | During Installation | NDM | Sign This ITP | Site Foreman
5 | CCTV | Contract Document | CCTV Footage | H | Clear new pipeline of any debris prior to CCTV. CCTV inspection of gravity to be as per the New Zealand Pipe Inspection manual. | Once pipeline is installed | CCTV | Sign this ITP | Site Foreman

## SWMH06 - SWMH05
INSPECTION TEST PLAN
CONSTRUCTION
Foreman |  | Daryl Banks |  | Action | Arthur St SW Pipelines
Manager |  | Kate Gentle |  |  | W | Witness | SWMH06-SWMH05 - 825 CLASS 2 RCRRJ - 89.1M @ 0.50%
Divisional Manager |  | Jay Arthur |  |  | H | Hold Point
Engineer |  | Callum Feely |  |  | M | Monitor | Job Number: |  | 4811 | Version: | 1
No: | Detail | Specification / Standard | Inspection / Test Point | ACTION | Conformance Criteria (Whats Required) | Frequency | Inspection / Test Method | Verification Records | Signatory | Comments | Date | Signature
1 | CLASS 2 RCRRJ PIPE AND FITTINGS | Contract Document | Sign Off | H | Class 2 RCRRJ pipe, pipe to be inspected upon delivery and have no damage or deformities | Prior to commencement/upon delivery of materials | Visual | Sign this ITP | Site Foreman Engineer's Representative
2 | BEDDING MATERIAL | AS/NZS 2566.2 | Aggregate Certification | M | Clean granular non-cohesive material with a maximum particle size of 20mm | Continuous for pipe length | Clegg Hammer | Sign this ITP | Site Foreman
3 | OPEN TRENCHING ALIGNMENT, DEPTH AND ACCURACY | Contract Document | Witness & Record | M | Installed within +/- 10mm accuracy from design datum. Installed as per design grade and recorded on pipe laying form. Daily checks to make sure pipe is laid to design. | Prior to commencement and every two lengths | Review | Sign this ITP | Site Foreman
5 | BACKFILLING AND COMPACTION ROADWAY | Contract Document | Sign off | M | Trench backfill to be carried out with imported AP65 gravel in 250mm lifts. The subbase material shall achieve an average of 95% of the MDD. All backfilled material shall be compaction tested at a maximum of 20m intervals longitudinally and 1m vertically with an NDM. All basecourse material shall be M4AP40. | During Installation | NDM | Sign This ITP | Site Foreman
5 | CCTV | Contract Document | CCTV Footage | H | Clear new pipeline of any debris prior to CCTV. CCTV inspection of gravity to be as per the New Zealand Pipe Inspection manual. | Once pipeline is installed | CCTV | Sign this ITP | Site Foreman

## SWMH05 - SWMH04
INSPECTION TEST PLAN
CONSTRUCTION
Foreman |  | Daryl Banks |  | Action | Arthur St SW Pipelines
Manager |  | Kate Gentle |  |  | W | Witness | SWMH05-SWMH04 - 825 CLASS 2 RCRRJ - 119.6M @ 0.20%
Divisional Manager |  | Jay Arthur |  |  | H | Hold Point
Engineer |  | Callum Feely |  |  | M | Monitor | Job Number: |  | 4811 | Version: | 1
No: | Detail | Specification / Standard | Inspection / Test Point | ACTION | Conformance Criteria (Whats Required) | Frequency | Inspection / Test Method | Verification Records | Signatory | Comments | Date | Signature
1 | CLASS 2 RCRRJ PIPE AND FITTINGS | Contract Document | Sign Off | H | Class 2 RCRRJ pipe, pipe to be inspected upon delivery and have no damage or deformities | Prior to commencement/upon delivery of materials | Visual | Sign this ITP | Site Foreman Engineer's Representative
2 | BEDDING MATERIAL | AS/NZS 2566.2 | Aggregate Certification | M | Clean granular non-cohesive material with a maximum particle size of 20mm | Continuous for pipe length | Clegg Hammer | Sign this ITP | Site Foreman
3 | OPEN TRENCHING ALIGNMENT, DEPTH AND ACCURACY | Contract Document | Witness & Record | M | Installed within +/- 10mm accuracy from design datum. Installed as per design grade and recorded on pipe laying form. Daily checks to make sure pipe is laid to design. | Prior to commencement and every two lengths | Review | Sign this ITP | Site Foreman
5 | BACKFILLING AND COMPACTION ROADWAY | Contract Document | Sign off | M | Trench backfill to be carried out with imported AP65 gravel in 250mm lifts. The subbase material shall achieve an average of 95% of the MDD. All backfilled material shall be compaction tested at a maximum of 20m intervals longitudinally and 1m vertically with an NDM. All basecourse material shall be M4AP40. | During Installation | NDM | Sign This ITP | Site Foreman
5 | CCTV | Contract Document | CCTV Footage | H | Clear new pipeline of any debris prior to CCTV. CCTV inspection of gravity to be as per the New Zealand Pipe Inspection manual. | Once pipeline is installed | CCTV | Sign this ITP | Site Foreman

## SWMH04 - SWMH03
INSPECTION TEST PLAN
CONSTRUCTION
Foreman |  | Daryl Banks |  | Action | Arthur St SW Pipelines
Manager |  | Kate Gentle |  |  | W | Witness | SWMH04-SWMH03 - DN300 SN8 PVC - 75M @ 0.72%
Divisional Manager |  | Jay Arthur |  |  | H | Hold Point
Engineer |  | Callum Feely |  |  | M | Monitor | Job Number: |  | 4811 | Version: | 1
No: | Detail | Specification / Standard | Inspection / Test Point | ACTION | Conformance Criteria (Whats Required) | Frequency | Inspection / Test Method | Verification Records | Signatory | Comments | Date | Signature
1 | uPVC MAINS AND FITTINGS | Contract Document | Sign Off | H | Shall be SN8 and rubber ring jointed, with no damage or deformities. | Prior to commencement/upon delivery of materials | Visual | Sign this ITP | Site Foreman Engineer's Representative
2 | BEDDING MATERIAL | AS/NZS 2566.2 | Aggregate Certification | M | Clean granular non-cohesive material with a maximum particle size of 20mm | Continuous for pipe length | Clegg Hammer | Sign this ITP | Site Foreman
3 | OPEN TRENCHING ALIGNMENT, DEPTH AND ACCURACY | Contract Document | Witness & Record | M | Installed within +/- 10mm accuracy from design datum. Installed as per design grade and recorded on pipe laying form. Daily checks to make sure pipe is laid to design. | Prior to commencement and every two lengths | Review | Sign this ITP | Site Foreman
5 | BACKFILLING AND COMPACTION ROADWAY | Contract Document | Sign off | M | Trench backfill to be carried out with imported AP65 gravel in 250mm lifts. The subbase material shall achieve an average of 95% of the MDD. All backfilled material shall be compaction tested at a maximum of 20m intervals longitudinally and 1m vertically with an NDM. All basecourse material shall be M4AP40. | During Installation | NDM | Sign This ITP | Site Foreman
5 | CCTV | Contract Document | CCTV Footage | H | Clear new pipeline of any debris prior to CCTV. CCTV inspection of gravity to be as per the New Zealand Pipe Inspection manual. | Once pipeline is installed | CCTV | Sign this ITP | Site Foreman

## SWMH03 - SWMH02
INSPECTION TEST PLAN
CONSTRUCTION
Foreman |  | Daryl Banks |  | Action | Arthur St SW Pipelines
Manager |  | Kate Gentle |  |  | W | Witness | SWMH03-SWMH02 - DN300 SN8 PVC - 71.8M @ 1.42%
Divisional Manager |  | Jay Arthur |  |  | H | Hold Point
Engineer |  | Callum Feely |  |  | M | Monitor | Job Number: |  | 4811 | Version: | 1
No: | Detail | Specification / Standard | Inspection / Test Point | ACTION | Conformance Criteria (Whats Required) | Frequency | Inspection / Test Method | Verification Records | Signatory | Comments | Date | Signature
1 | uPVC MAINS AND FITTINGS | Contract Document | Sign Off | H | Shall be SN8 and rubber ring jointed, with no damage or deformities. | Prior to commencement/upon delivery of materials | Visual | Sign this ITP | Site Foreman Engineer's Representative
2 | BEDDING MATERIAL | AS/NZS 2566.2 | Aggregate Certification | M | Clean granular non-cohesive material with a maximum particle size of 20mm | Continuous for pipe length | Clegg Hammer | Sign this ITP | Site Foreman
3 | OPEN TRENCHING ALIGNMENT, DEPTH AND ACCURACY | Contract Document | Witness & Record | M | Installed within +/- 10mm accuracy from design datum. Installed as per design grade and recorded on pipe laying form. Daily checks to make sure pipe is laid to design. | Prior to commencement and every two lengths | Review | Sign this ITP | Site Foreman
5 | BACKFILLING AND COMPACTION ROADWAY | Contract Document | Sign off | M | Trench backfill to be carried out with imported AP65 gravel in 250mm lifts. The subbase material shall achieve an average of 95% of the MDD. All backfilled material shall be compaction tested at a maximum of 20m intervals longitudinally and 1m vertically with an NDM. All basecourse material shall be M4AP40. | During Installation | NDM | Sign This ITP | Site Foreman
5 | CCTV | Contract Document | CCTV Footage | H | Clear new pipeline of any debris prior to CCTV. CCTV inspection of gravity to be as per the New Zealand Pipe Inspection manual. | Once pipeline is installed | CCTV | Sign this ITP | Site Foreman

## SWMH02 - SWMH01
INSPECTION TEST PLAN
CONSTRUCTION
Foreman |  | Daryl Banks |  | Action | Arthur St SW Pipelines
Manager |  | Kate Gentle |  |  | W | Witness | SWMH02-SWMH01 - DN225 SN8 PVC - 60.3M @ 0.50%
Divisional Manager |  | Jay Arthur |  |  | H | Hold Point
Engineer |  | Callum Feely |  |  | M | Monitor | Job Number: |  | 4811 | Version: | 1
No: | Detail | Specification / Standard | Inspection / Test Point | ACTION | Conformance Criteria (Whats Required) | Frequency | Inspection / Test Method | Verification Records | Signatory | Comments | Date | Signature
1 | uPVC MAINS AND FITTINGS | Contract Document | Sign Off | H | Shall be SN8 and rubber ring jointed, with no damage or deformities. | Prior to commencement/upon delivery of materials | Visual | Sign this ITP | Site Foreman Engineer's Representative
2 | BEDDING MATERIAL | AS/NZS 2566.2 | Aggregate Certification | M | Clean granular non-cohesive material with a maximum particle size of 20mm | Continuous for pipe length | Clegg Hammer | Sign this ITP | Site Foreman
3 | OPEN TRENCHING ALIGNMENT, DEPTH AND ACCURACY | Contract Document | Witness & Record | M | Installed within +/- 10mm accuracy from design datum. Installed as per design grade and recorded on pipe laying form. Daily checks to make sure pipe is laid to design. | Prior to commencement and every two lengths | Review | Sign this ITP | Site Foreman
5 | BACKFILLING AND COMPACTION ROADWAY | Contract Document | Sign off | M | Trench backfill to be carried out with imported AP65 gravel in 250mm lifts. The subbase material shall achieve an average of 95% of the MDD. All backfilled material shall be compaction tested at a maximum of 20m intervals longitudinally and 1m vertically with an NDM. All basecourse material shall be M4AP40. | During Installation | NDM | Sign This ITP | Site Foreman
5 | CCTV | Contract Document | CCTV Footage | H | Clear new pipeline of any debris prior to CCTV. CCTV inspection of gravity to be as per the New Zealand Pipe Inspection manual. | Once pipeline is installed | CCTV | Sign this ITP | Site Foreman