## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | Capping Beams ITP | itp |  |  |  |  | Capping Beams ITP
checkpoint | 1. Drawing # / Revision
label | Australian Standards: AS3610
textbox | Architectural:
textbox | Structural:
textbox | Precast:
label | Point Type: Witness
checkpoint | 2. Reference (Use gridlines)
label | Point Type: Witness
checkpoint | 3. Surveyor to Check Position of Capping beam
label | Point Type: Witness
checkpoint | 4. Top Blinding / Top Beam (Termination Height)
textbox | Top Blinding:
textbox | Top Beam (Termination Height):
label | Point Type: Witness
checkpoint | 5. Waterproofing
textbox | 5.1 CETCO/Bravada Inspection:
label | 5.2
textbox | – Sheet Membrane Cut Around Each Pile
textbox | – Membrane Application:
textbox | – 450mm Overlap Sheet Membrane:
textbox | – Waterstop Around Each Pile:
label | 5.3 Photos of Waterproofing detail executed
label | Point Type: Hold
holdpoint | HOLD POINT
checkpoint | 6. Reo
textbox | Reo placement:
textbox | Pile Reo Length:
textbox | Reo Size/Configuration:
label | Refer to Schedule
label | Cover: 50mm
label | Photos Taken (attached with engineer sign off)
label | Engineers Inspection (attached engineer sign-off)
label | Point Type: Hold
holdpoint | ENGINEER SIGN OFF
checkpoint | 7. Commencement of Pour
label | OK to Pour. Shotcrete methodology attached
label | Point Type: Hold
holdpoint | HOLD POINT
checkpoint | 8. Concrete
textbox | Concrete Strength:
textbox | Concrete dockets/test Docket: |  |  | (Attach to ITP)
label | Point Type: Witness
checkpoint | Signed off / Handed Over