## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP003 - Asphalt Production of Surface Mixes | itp |  |  |  | Yes | ITP003 - Asphalt Production of Surface Mixes | 02b2f3e6-0f9d-401a-b0c6-ca4db6fe40fe
checkpoint-group |  |  | section | 1 Mix Production
checkpoint-status |  |  | checkpoint | 1.01 - Asphalt production plan
label | c7447511-5375-51c4-885d-52e103fa6c87 |  | note | Frequency: Not less than 48 hours prior to the commencement of a work period.
label | b39388fc-7894-56f0-abf1-dd574cd33b2c |  | note | Acceptance Criteria:
label | a16294fb-9258-5b82-906e-3c4bbffc3f98 |  | note | • Plan demonstrates that the hot storage capacity and production capacity of the mixing plant is capable of supplying asphalt to complete the work proposed to be undertaken within that work period on time and to make the runway suitable for aircraft operation in the event of an asphalt plant breakdown.
label | c99a245c-d81a-55d4-bcfc-a206c985322d |  | note | Reference Documents: GHD-DD-SPC-002 5116(e) HP5116-1
label | 53cedb96-e973-5f3d-b1d1-d3167297ba9e |  | note | Inspection/ Test Method: N/A
label | cb7910eb-5674-570e-a9e1-c232172196a3 |  | note | Record of conformity: Production plan
label | 81a8eb08-1c41-5b6a-a497-239dc0c1961b |  | note | HP
label | e229e7b3-6e24-50a3-ad67-acfb339d0365 |  | note | Responsibility: Production Supervisor
text | f20791da-2971-55a1-81f6-a8b71ffac5aa |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.02 - Temperature of bitumen
label | c8dabe28-5ed7-57f7-9e31-ac59cbf80047 |  | note | Frequency: Not less than once per work period. To be recorded at the time of taking bitumen volumetric readings.
label | 69ff44bb-80b7-5373-8721-bd013cc42607 |  | note | Acceptance Criteria:
label | 412c7ded-216c-5412-9120-0f2c0c330040 |  | note | • Temperature to be within the below range for the relevant bitumen type when introduced into the mixer:
label | 79d397f7-1bcc-57e3-a351-29f68efe6cda |  | note | – Residual bitumen: 140-165°C
label | 95d2b7d0-ab44-5d91-8aa2-29e84d993316 |  | note | – Polymer modified bitumen: 160-175°C
label | 41770db8-5c2d-5005-aa68-8424150c0b71 |  | note | – Polymer modified bitumen with warm mix additives: 140-175°C
label | f30929b1-71c0-57a9-a8ac-22b77b6dc11e |  | note | Reference Documents: GHD-DD-SPC-001 5116(f)
label | 7cbb66cd-1dc3-5054-9a04-72277c571b95 |  | note | Inspection/ Test Method: Asphalt plant temperature probe
label | 6d404193-9429-5904-ab47-5e2dea929ffd |  | note | Record of conformity: Production records
label | 5a7400c1-75ca-558b-964e-c812f448b727 |  | note | IP
label | 8550eaa8-9bcb-5c6f-b517-efe472df9c8f |  | note | Responsibility: Plant Operator
text | 1bfb5457-d453-571f-bd61-ba106e94cef7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.03 - Temperature of aggregates
label | 0abbf69e-d082-503e-93a5-29a568750c7e |  | note | Frequency: Not less than once per work period.
label | 1450bb9e-10a4-5209-a9e0-5c8adaab6f2e |  | note | Acceptance Criteria: Temperature to be not more than 10°C above or more than 15°C below the temperature of the bitumen.
label | 0b5a8e59-53da-5b87-b4f2-0ca009ffe5f5 |  | note | Reference Documents: GHD-DD-SPC-001 5116(f)
label | 442a6f56-c44c-560d-b24d-a556378010c6 |  | note | Inspection/ Test Method: Asphalt plant temperature probe
label | 381d4ea4-10b0-5571-aff2-c9a7f915a528 |  | note | Record of conformity: Production records
label | 9bd55efd-c87b-58b0-a65c-1bce1d1a2b42 |  | note | IP
label | 4b1fe4e8-cbcc-5bf8-aab2-8c17b3c8a5f9 |  | note | Responsibility: Plant Operator
text | 97fca832-5b89-599f-a22a-0246fbc4245f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.04 - Temperature of asphalt
label | c3742e4b-ade3-5af1-809a-3a8ec3521816 |  | note | Frequency: Not less than once per work period.
label | 3f74eeb0-cc63-578a-8836-ab83780b480d |  | note | Acceptance Criteria: Temperature to be within 10oC of the job mix temperature
label | 34795ccb-02a7-5145-9d48-7c85d9483469 |  | note | Reference Documents: GHD-DD-SPC-001 5116(f)
label | 84fe70bf-c9bf-580d-bc20-17083fb948de |  | note | Inspection/ Test Method: Asphalt plant temperature probe
label | 6d736823-61ed-59e4-8637-1a7e974e7b7c |  | note | Record of conformity: Production records
label | d63796ac-f051-5aa8-bf1a-66c705e8039b |  | note | IP
label | 4c30a41e-c2cf-532c-993e-960b671a727d |  | note | Responsibility: Plant Operator
text | e068a066-d2f3-59a4-9aec-2ec6e61c13ca |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.05 - Daily bitumen usage
label | 2f93870a-be9f-5db6-a32c-b70493da1a15 |  | note | Frequency: Once per work period for each production run for each nominal size of asphalt mix.
label | c77f85cd-2f66-5ed1-8034-60ea963eff02 |  | note | Acceptance Criteria: To be reported.
label | e211db16-047d-50f2-8e2c-e74a90f4a01b |  | note | Reference Documents: GHD-DD-SPC-001 5131(e)
label | 791f3a69-39da-55b5-8aea-f736f0835fc1 |  | note | Inspection/ Test Method: Inspection of plant digital readouts before and after each production run
label | e0549d88-1c49-5d72-9bee-101c523f31fa |  | note | Record of conformity: Production records
label | 36282e64-81a9-56c4-9aab-4befbd685f5d |  | note | IP
label | d9d476a8-bd4d-5ba4-9b32-d200d5d27b00 |  | note | Responsibility: Plant Operator
text | 61e195d2-b853-5c6b-95b0-5522be157dd0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.06 - Supplementary bitumen content determination
label | 3139313c-9fc0-508c-a629-09016879918e |  | note | Frequency: Once per work period for each nominal size of asphalt mix.
label | 03cb3108-663d-5374-9b96-553e7b84d4e6 |  | note | Acceptance Criteria: Not less than the job bitumen content.
label | 033b35d3-a17b-578e-b687-bf31d99bcca0 |  | note | Reference Documents:
label | a95d14d9-c961-5513-96a1-c08adad9e63a |  | note | • GHD-DD-SPC-001 5131(e)
label | 28658dd2-8cb0-5ab2-8f7f-c5f54c55c58c |  | note | • Table 5116-7
label | 43e06781-b0ff-51ae-9674-9e4184f5b67a |  | note | Inspection/ Test Method: Calculation: Daily bitumen usage divided by mass of asphalt produced for each mix type.
label | 1575af13-7e29-56a9-8a94-d7e73f2fa8e8 |  | note | Record of conformity: Production records
label | 9d0e40b4-4de5-5e65-8958-6d795dbad96d |  | note | IP
label | 2610ccde-0281-5b08-a509-54762eeeeb96 |  | note | Responsibility: Plant Operator
text | bc8b4184-1c55-53da-bb4b-7c7a1f83304f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.07 - Mass of asphalt produced
label | 5bdd7072-6a21-5554-b481-3691783f2921 |  | note | Frequency: Once per work period for each nominal size of asphalt mix.
label | 341e0dbf-6776-5799-867b-083fc31d5ae2 |  | note | Acceptance Criteria: To be reported.
label | 0f0c2076-0886-5262-a24a-ed22ae3cb1ff |  | note | Reference Documents: GHD-DD-SPC-001 5131(e)
label | 7f51da74-5522-5f14-bcb9-456b1463ac45 |  | note | Inspection/ Test Method: Inspection of plant digital readouts
label | 1a0a2836-8781-55e5-aced-418ab10e7a64 |  | note | Record of conformity: Production records
label | 7a81e02c-2b93-59bf-859b-e46054ef9eee |  | note | IP
label | c5159df9-16cf-5264-ac87-4c248af560fc |  | note | Responsibility: Plant Operator
text | 89257a8d-8e18-5a29-930d-7fbb60ddcb7c |  | textbox | Date Completed:
checkpoint-group |  |  | section | 2 Bitumen properties
checkpoint-status |  |  | checkpoint | 2.01 - Sampling from storage tank at the asphalt mixing plant.
label | e36812ef-6228-5d87-b30c-1e3dbb95f544 |  | note | Frequency: Not more than four hours prior to the scheduled production start time for each work period.
label | 51e60040-e7ca-549d-bf13-b087aed084ff |  | note | Acceptance Criteria:
label | d04905b7-3e4e-59cf-90dd-de0ed4d3ff47 |  | note | • Duplicate samples are taken from the storage tank at the asphalt mixing plant.
label | 93606da9-6d56-5445-a811-456b657a4561 |  | note | • Containers are labelled appropriately so that samples are traceable to asphalt lots, manufacturing batch records and conformance reports.
label | 47f4df82-967b-5343-b444-41309d01c2f0 |  | note | • One sample is provided to Contract Administrator immediately after sampling; one sample is tested as per Section 2 of this ITP.
label | 7fa07cf5-f483-5b3d-af6c-992a00a260c7 |  | note | Reference Documents: GHD-DD-SPC-001 5131(c)
label | 78a4a7e4-b436-569f-8999-d1766073c589 |  | note | Inspection/ Test Method: AS 2008 (Appendix B)
label | 2a2be1f4-2651-5298-9a11-99f65823caae |  | note | Record of conformity: ITP
label | 1c03a313-c1ad-5dae-945c-f0a69cce65cb |  | note | IP
label | 1f446026-a477-5cc9-ba90-0051d9fd2a26 |  | note | Responsibility: Laboratory Technician
text | 0563e1a7-bdad-5df4-b872-5194154c520c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.02 - Viscosity at 165°C
label | b5bf69c1-91ff-5caa-8cb7-8af993e37f5a |  | note | Frequency: One test prior to each work period, completed no later than 1 hour prior to start of asphalt production.
label | f8e80c54-f8d2-50fc-9729-5750811ae1ff |  | note | Acceptance Criteria: To be reported.
label | b1941a64-8402-5be3-bda3-aba411376bb1 |  | note | Reference Documents:
label | 708ae000-6db4-54c2-bba5-b29cb357a807 |  | note | • GHD-DD-SPC-002 5131(c)
label | 83d8fc93-d207-5bed-a9cd-e4bd7f41f192 |  | note | • Table SP5131-3
label | 29eafe90-81ae-5718-90d3-f844bd6dd8c2 |  | note | Inspection/ Test Method: AG:PT/T111
label | a98b20d2-f01e-5f75-ba02-9097011bb52f |  | note | Record of conformity: NATA-accredited test certificate
label | aa3824e3-1a5b-507d-bba7-0766e104ce7d |  | note | TP
label | 362dc6c3-1e6a-5261-b68c-032b38b8f6b0 |  | note | Responsibility: Laboratory Technician
text | b8f5845c-bca6-5f0e-9277-6c049c3d4883 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.03 - Torsional recovery at 25oC, 30 s
label | 1399427d-2ace-57c0-bdfe-d733f44dc2bb |  | note | Frequency: One test prior to each work period, completed no later than 1 hour prior to start of asphalt production.
label | 815feaf9-e832-5efc-abb0-a3c717be4ed6 |  | note | Acceptance Criteria: To be reported.
label | d65cb637-bc66-5ea1-8548-ab7df09e57ca |  | note | Reference Documents:
label | c57899ee-962d-538e-a321-6672b37f0565 |  | note | • GHD-DD-SPC-002 5131(c)
label | f6e7d27c-b58c-5d19-b3cc-e045d3f576b9 |  | note | • Table SP5131-3
label | 91172221-a6e5-5e4b-9abd-4e50bed3504c |  | note | Inspection/ Test Method: AG:PT/T122
label | 1692b6ec-6e65-5362-9205-c30d261620e1 |  | note | Record of conformity: NATA-accredited test certificate
label | aaee1b2c-6e2e-5be2-9a95-f63dcfc3b488 |  | note | TP
label | 5f5b4afb-e6e3-5379-84ec-f9dab75847e2 |  | note | Responsibility: Laboratory Technician
text | b9604f63-25be-5bb5-b5d6-fd50ab9f9c77 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.04 - Softening point
label | d21e1ad3-bd24-50c1-86f3-ebf7a0e171ae |  | note | Frequency: One test prior to each work period, completed no later than 1 hour prior to start of asphalt production.
label | d8684b3e-c3c1-5b67-92a7-e5af3da4e001 |  | note | Acceptance Criteria: To be reported.
label | 25e125a9-e3fb-5f51-ba1d-a0c6f8da23f0 |  | note | Reference Documents:
label | c4e1cf6f-7000-5137-9a28-4feb4f5f2c68 |  | note | • GHD-DD-SPC-002 5131(c)
label | 21f224ec-69fa-5acd-9743-433d37e69c02 |  | note | • Table SP5131-3
label | d34529db-a0f4-55ec-bccd-73a26fd55b08 |  | note | Inspection/ Test Method: AG:PT/T131
label | 178bf1d3-2188-5bb3-a4e1-d9111ca9ed97 |  | note | Record of conformity: NATA-accredited test certificate
label | 3e6e813e-40b1-5bb0-9ccf-f8b3efa5c95d |  | note | TP
label | 860784ef-4f25-5a5a-9154-a5d1d5c11b18 |  | note | Responsibility: Laboratory Technician
text | f7806156-0a8e-5c23-a290-f9e073352189 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.05- PG MSCR
label | bf796fc9-1d39-58a1-b99e-6725e63da153 |  | note | Frequency: One test weekly conducted on a Monday sampled from storage tank, regardless of whether work proceeds that day or not.
label | 97bec41b-bcc6-59df-9426-f29092abdddd |  | note | Acceptance Criteria: To be reported.
label | 1d83bec6-e871-5846-b8d0-ecc6f696f081 |  | note | Reference Documents:
label | 48fde1ab-a564-5e2c-bb71-67db48d89ebf |  | note | • GHD-DD-SPC-002 5131(c)
label | 898d8fa9-ebb3-538b-8445-5f19ef953cb4 |  | note | • Table SP5131-3
label | 55157d2b-cc4d-5834-b967-3683e1fd401a |  | note | Inspection/ Test Method: AASHTO T350
label | f16f78e5-66ed-5f28-b714-eff8731c29dc |  | note | Record of conformity: NATA-accredited test certificate
label | f295527e-10e3-5892-9087-be6647067d6f |  | note | TP
label | fdfa0e63-e789-587f-bd0b-5a1d7450ce89 |  | note | Responsibility: Laboratory Technician
text | 9d4014db-2375-589c-abe1-ae6dd6eb3007 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.06 - Submission of binder test results.
label | cb8576f3-0d69-50e0-b5b7-801bcc160225 |  | note | Frequency: No later than 1 hour prior to the scheduled start of asphalt production for each work period.
label | 7f872593-daaf-5de2-8769-3c4c78fa6a93 |  | note | Acceptance Criteria:
label | c2c9a8eb-328e-5ca2-8195-13ea92032f2e |  | note | • Completion of the specified set of tests on polymer modified binder.
label | 90ad3ceb-4c2b-5437-bcb4-f93130f0ef72 |  | note | • Submission of test results and a statement to the Contract Administrator regarding the compliance of the binder in the tank.
label | 848ada2f-0a4a-53f0-a9c4-887814056e77 |  | note | Reference Documents: GHD-DD-SPC-001 5131(c) HP5131-2
label | 597d1287-09d8-5899-9e35-e28c7fac73ee |  | note | Inspection/ Test Method: N/A
label | 06ea5316-2443-5fe1-a72e-efecd0425456 |  | note | Record of conformity: ITP
label | 74fd5afa-4be5-5555-93fd-5818d70e09a5 |  | note | HP
label | 2009be83-6869-52a3-8be7-53bc3baf7bc7 |  | note | Responsibility: Laboratory Technician
text | d9fc0e8c-cf9a-58e7-9b31-84c53d8019e3 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 Asphalt properties
checkpoint-status |  |  | checkpoint | 3.01 - Mixing efficiency
label | 62b2caab-8cea-5f3b-9471-81f5ccbf6cb2 |  | note | Frequency: Not less than once per work period.
label | 234db886-ef5c-53bb-82c8-e5df8ee9ade9 |  | note | Acceptance Criteria:
label | 4b99233a-0045-5195-967e-d2a93a5df323 |  | note | • Percentage of coating of particles in the mix, when sampled at the point of loading, must not be less than 97% and a homogeneous mixture must be obtained.
label | 81079eb3-0ad8-54a8-947b-a74f13d7c124 |  | note | Reference Documents: GHD-DD-SPC-001 5116(g)
label | 98ab6c8e-c06d-5866-b4e3-555e68d48cc9 |  | note | Inspection/ Test Method: Visual inspection as per ASTM D2489 methodology
label | acf9c80b-85dc-5d2f-8980-42775e85dea5 |  | note | Record of conformity: Inspection record
label | 88e50bae-bd60-50b1-a8d0-a3c8fa6170b1 |  | note | IP
label | e843266e-c0b1-59df-8401-e491c18a2dad |  | note | Responsibility: Plant Operator
text | a2db56ac-6f04-5a9c-83c8-4fa5772fa9e5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.02 - Stability
label | c3ee6680-3d47-57aa-a4bd-954947a75b7b |  | note | Frequency: Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency.
label | ca0d834d-28dc-5269-83b8-207c4938581a |  | note | Acceptance Criteria: ±3.0 compared to job mix but not less than 12.0 kN (for 14mm NMS) or not less than 10.0 kN
label | 01d7fa0e-d780-5ca0-980b-9fe594f6f0a0 |  | note | Reference Documents:
label | edc2ffb2-3e90-5609-aef6-75e29741acc2 |  | note | • GHD-DD-SPC-001 5116(j)
label | 8454c709-8ce0-59fd-a3d4-a3ac544ef85f |  | note | • Table 5116-4
label | 1fa5aae2-f166-5e34-9601-82df8477622c |  | note | • HP5116-2
label | ba97f618-8fca-5592-aae9-3ba142c04a92 |  | note | Inspection/ Test Method: AS/NZS 2891.5 (75 blows)
label | 62c74dd3-a2ad-57bf-b6b1-e7d15d49b798 |  | note | Record of conformity: NATA-accredited test certificate
label | 1ee7cbb9-d161-5cc4-b426-d45c6fb63d70 |  | note | TP
label | 4804a9be-c7d9-50da-9689-59ef50661840 |  | note | Responsibility: Laboratory Technician
text | c4489f55-8b71-521c-9783-a8b8438b6a0e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.03 - Flow
label | 88720f6d-1f69-585a-9894-c6d597b657dd |  | note | Frequency: Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency.
label | 48af0f1d-f1e9-5893-a0b7-c5c39234332a |  | note | Acceptance Criteria: Max 3.0 mm for unmodified binder; max ±1.0 mm compared to job mix for PMB
label | 481baaaa-3b4d-57dd-b11f-9c06c223ae05 |  | note | Reference Documents:
label | a380cf57-6995-546d-9cf0-33dd4cc98242 |  | note | • GHD-DD-SPC-001 5116(j)
label | bced9d27-75cb-5520-a1cf-87bead31a88e |  | note | • Table 5116-4
label | 556dc30b-2dce-51ac-bc4b-09f308bf7993 |  | note | • HP5116-2
label | 2023c085-3d20-5ffb-9a45-a589168111a7 |  | note | Inspection/ Test Method: AS/NZS 2891.5 (75 blows)
label | 7a862aaa-40d3-5473-8430-b086f0ab8b22 |  | note | Record of conformity: NATA-accredited test certificate
label | 034c002f-c545-5ff4-8c85-3a25782dfa95 |  | note | TP
label | ce361085-e5e3-5a7b-9045-a2f68c64a912 |  | note | Responsibility: Laboratory Technician
text | e68dbea9-a2c9-5e5d-8366-7794d2e21196 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.04 - Minimum voids in mineral aggregate
label | 8d0b5c9c-aa84-5409-a51f-1fd095156453 |  | note | Frequency: Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency.
label | 4281719a-81db-526b-b673-eecd9576ac0c |  | note | Acceptance Criteria: 14.0% (for 14mm NMS) or 15.0%
label | d2bdc235-2018-5f4b-814f-6b3152e7b34f |  | note | Reference Documents:
label | 083e2519-1f98-5b42-a3f2-89534d043174 |  | note | • GHD-DD-SPC-001 5116(j)
label | b838b03e-46c1-5865-b972-4830b4ef1151 |  | note | • Table 5116-4
label | 686921ef-c87f-5628-a477-41afa710efc0 |  | note | • HP5116-2
label | dcf52227-7d17-50fc-bed3-187d389be918 |  | note | Inspection/ Test Method: AS/NZS 2891.5 (75 blows)
label | d8122f18-5677-5a0b-92ce-f4ed330d4442 |  | note | Record of conformity: NATA-accredited test certificate
label | 0d040b46-a6b7-5d48-94b5-9af1623d9352 |  | note | TP
label | 51e9c540-6d7b-5b43-8cd6-32f9037bde43 |  | note | Responsibility: Laboratory Technician
text | b3d87ab0-36a8-5b0f-a1ab-90bea46072db |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.05 - Minimum and maximum air voids
label | 498ffa4d-bd91-54c9-9c65-ccb7b0ce0462 |  | note | Frequency: Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency.
label | 80444f34-4cec-54ee-a7fd-be99d5c2cefc |  | note | Acceptance Criteria: 3.0-5.0%
label | 68c17c94-0c6f-5788-8c72-ea72757ea5b6 |  | note | Reference Documents:
label | d35880a9-a235-5470-bd00-b9fe5cd58a43 |  | note | • GHD-DD-SPC-001 5116(j)
label | 450b5740-4663-564c-8c52-5467d790ba9a |  | note | • Table 5116-4
label | cc8239af-a89a-5233-8409-910a312147cf |  | note | • HP5116-2
label | ef5b2a1a-8543-51a2-a68d-f68fd1a042a4 |  | note | Inspection/ Test Method: AS/NZS 2891.5 (75 blows)
label | 75a00843-ceb8-51cb-8599-0c4d22b5a16c |  | note | Record of conformity: NATA-accredited test certificate
label | ac570a34-bf16-569f-94f2-1e4942f585d5 |  | note | TP
label | bfc2277b-b3f3-5429-a54b-d972ea166cc0 |  | note | Responsibility: Laboratory Technician
text | 23b9e8d5-13ec-5fad-9cd6-7c26438edfda |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.06 - Minimum and maximum voids filled with bitumen
label | 7918d784-a8ed-5526-a861-28186f0219b3 |  | note | Frequency: Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency.
label | 45fd2d4e-e7d5-52b8-a412-f45f99589bff |  | note | Acceptance Criteria: 70.0-80.0% (for 14mm NMS) or 75.0-85.0%
label | 427c4159-6ac7-5386-b454-fb0719037a28 |  | note | Reference Documents:
label | f854aff8-5cd3-5b42-b0b6-6e499ec7ab51 |  | note | • GHD-DD-SPC-001 5116(j)
label | ded794a1-8988-56e3-832f-eacd333f4abc |  | note | • Table 5116-4
label | e11f32fb-9958-5034-98dd-a8f27aa42a32 |  | note | • HP5116-2
label | 8b4ea5a1-2556-5ccc-81a2-6836faea33cf |  | note | Inspection/ Test Method: AS/NZS 2891.5 (75 blows)
label | 14693842-b130-5418-97e6-3514066fd117 |  | note | Record of conformity: NATA-accredited test certificate
label | b951d660-15d8-5d60-97e7-7e6936db58cc |  | note | TP
label | dbfd8bbd-c055-57be-9947-9d064b334294 |  | note | Responsibility: Laboratory Technician
text | 4ae32db1-fe59-5167-bb46-3089214fcaaa |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.07 - Combined aggregate particle size distribution
label | f956beed-5c5a-5d10-8b7c-f8c48b84332a |  | note | Frequency: Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency.
label | 61f87c27-f7aa-5a8e-96f8-eeeb50d39b12 |  | note | Acceptance Criteria:
label | 796e533f-7b30-502f-a82e-bc610e40f1dd |  | note | • Within acceptable range of deviation from job mix aggregate particle size distribution:
label | de675087-6748-5c4d-a82c-fccad2800ddb |  | note | 13.2: ±6 ¦¦ 1.18: ±4
label | ff8721d0-2902-531e-91a7-1109f501d983 |  | note | 9.5: ±6 ¦¦ 0.6: ±3
label | 55ed992a-309b-5147-b280-e2136591248f |  | note | 6.7: ±6 ¦¦ 0.3: ±2
label | 331e6284-358a-5363-b2cd-d1a8092870af |  | note | 4.75: ±5 ¦¦ 0.15: ±2
label | 8fac9b40-e112-551e-82bb-22d3643803fc |  | note | 2.36: ±5 ¦¦ 0.075: ±1.5
label | 85787ba9-9c88-5813-8fe9-5f0efaa0d69a |  | note | Reference Documents:
label | 814767c8-7f20-5206-9bcd-cac192a79217 |  | note | • GHD-DD-SPC-001 5116(j)
label | 1d1bf0e0-4b24-5547-b424-83947a971276 |  | note | • Table 5116-7
label | 8a58598c-ba6c-5cd6-97f0-ffb1b40e9eae |  | note | Inspection/ Test Method: AS/NZS 2891.3.3
label | 9c30da60-f5ce-5fc7-acef-698abdf0e6ca |  | note | Record of conformity: NATA-accredited test certificate
label | 46af8787-7325-5185-a8f9-f698001afad9 |  | note | TP
label | 7b23d0d8-1c32-5ba9-87b6-ad31a213e90a |  | note | Responsibility: Laboratory Technician
text | c819ce53-517d-5ed4-b495-f2f651111fa1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.08 - Bitumen content in asphalt
label | 0959a425-2cfa-5eec-8300-b592353fec41 |  | note | Frequency: Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency.
label | b390a304-e3b1-59be-b2ad-be8075dc98c9 |  | note | Acceptance Criteria: Within ±0.3 of job bitumen content by mass.
label | 2e2109b4-957f-5be1-a4eb-be321643a677 |  | note | Reference Documents:
label | 6c4e00a2-a3e2-5c3a-b329-d41b0348ef0f |  | note | • GHD-DD-SPC-001 5116(j)
label | 450b27a7-5a67-54da-97bf-0c8a47cf5cf6 |  | note | • Table 5116-7
label | deead141-d4b7-5fcc-adcd-5e155187ea16 |  | note | Inspection/ Test Method: AS/NZS 2891.3.3
label | 5d89badf-d51b-568f-84b8-4637a968789c |  | note | Record of conformity: NATA-accredited test certificate
label | 5840ef38-6dc1-5377-b84f-cdd69df0b431 |  | note | TP
label | d8f62764-e95b-5391-b15b-77e18e16e472 |  | note | Responsibility: Laboratory Technician
text | 2e08a047-ec9e-52ee-b0ac-cdc7ae12bd3f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.09 - Maximum density
label | 6155a149-1c92-5043-8ca0-ad45769fcf7b |  | note | Frequency: Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency.
label | 9430ef16-6563-5668-9428-dc6e4f44b5f9 |  | note | Acceptance Criteria: To be reported.
label | 3b06caa7-cb8d-51ba-8f27-bc7639e65036 |  | note | Reference Documents: GHD-DD-SPC-001 5132(a)
label | 65d1f9f5-6ef2-5831-a49d-b3bd47d58b83 |  | note | Inspection/ Test Method: AS/NZS 2891.7.1
label | 240407ed-4958-5c78-9987-4e5df5b3372b |  | note | Record of conformity: NATA-accredited test certificate
label | 99b799b7-c541-589f-be59-2b8cc19bede9 |  | note | TP
label | c38078dc-b3e9-57fd-a29f-58cb8a9e32d0 |  | note | Responsibility: Laboratory Technician
text | 7c60f689-352a-5510-87e2-581e03c75170 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Note 1: Sampling frequency
label | a0cab129-82de-573e-9361-0b6b63e5ad10 |  | note | • Number of test sets on asphalt of each nominal size in work period:
label | 94460686-9284-56ee-90b9-03d56a7d7e17 |  | note | Quantity of asphalt produced ¦¦ Number of sets of tests
label | bbb45ba0-3471-5fac-9f07-a7e64a70c720 |  | note | First 50t (0-50t) ¦¦ 1
label | 2b68096f-f742-5778-88b0-c1e06199c79e |  | note | Next 100t (50-150t) ¦¦ 1
label | b588aaff-2fbf-59ff-b0fc-14115a5d618b |  | note | Next 200t (150-350t) ¦¦ 1
label | 2f5da9f6-7dcd-571a-9428-a7540b3f7f95 |  | note | Next 250t (350-600t) ¦¦ 1
label | 3dfb1782-b721-5403-9520-0e935186aae8 |  | note | Every 250t thereafter ¦¦ 1
label | aa97af4d-6f7f-5243-a3a5-85df15272fba |  | note | • Minimum number of tests per work period regardless of tonnes produced: 3
checkpoint-status |  |  | checkpoint | Final Inspection
label | 952f4daf-0d9b-5631-acd3-e5f8cb502f7c |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 6b50041b-3f81-52a5-bd37-a8bb1640e08a |  | textbox | Print Name:
text | 13b2ec50-512b-5822-bf9c-97dc7b698af7 |  | textbox | Position:
text | d43cf99e-142c-5550-b513-3708338c6556 |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP005 - Cold Planing - Main Works | itp |  |  |  | Yes | ITP005 - Cold Planing - Main Works | 082903a8-2854-44ce-bbc7-54ed69feb810
checkpoint-group |  |  | section | 1 Preliminary
checkpoint-status |  |  | checkpoint | 1.04 - Plant verification checklist
label | b6a0ef1f-1857-5016-acfd-7108775a7928 |  | note | Frequency:
label | 9762a032-7697-5dd0-91e4-803d68c0065b |  | note | Prior to the commencement of cold planing operations in each work period. Prior notice (60 minutes) of commencement time of cold planing plant verification process to be given to the Contract Administrator."
label | d1b42cfc-e7e1-5b55-8040-82dc374dca7b |  | note | Acceptance Criteria: Verification that plant is in full working order and free from leaks of oil, hydraulic fluid, fuel and water.
label | d5e8ec42-bb9c-5a80-aa52-ffbd313aed4e |  | note | Reference Documents:
label | e30eb77c-e031-55ba-b614-47560906361c |  | note | GHD-DD-SPC-001 3903(f)"
label | 6f4f8c17-07b6-5f62-bcd6-529be2acacea |  | note | HP3903-1"
label | f4953f77-8637-5b12-9970-d8acab56a811 |  | note | Inspection/ Test Method: Inspection
label | 47457fd5-3c9f-5831-819c-d7b5bcad94f5 |  | note | Record of conformity: Plant verification checklist
label | 541b34a4-8cce-5343-a7c2-27f9c8aca261 |  | note | HP
label | 744c879b-9ffe-5ceb-b318-dfea5cc17ea3 |  | note | Responsibility: Site Engineer
text | 193b3640-f2be-5997-9913-a5fdd18ede05 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.05 - Plant performance check
label | 1c64fe87-e2f2-555d-963c-b3b515cff325 |  | note | Frequency:
label | 61f5e7e3-f87d-5ae6-95b7-e42c823daad3 |  | note | At the commencement of cold planing operations in each work period. Prior notice (30 minutes) of commencement time of cold planing to be given to the Contract Administrator."
label | 369bab0f-60c9-5155-afbf-5b1dbf6d9a7c |  | note | Acceptance Criteria:
label | fb483194-948c-528b-9f5c-c05edfff6813 |  | note | Verification that the machine cutters producing the required surface texture and leaving a cold planed surface free of ridges. forward speed and method of operation are removing asphalt to the required depth
label | c306b188-e41a-544f-824a-05ce08b7f7e1 |  | note | Reference Documents:
label | b8c6748b-56d6-56fc-829d-f4e718d1ae56 |  | note | GHD-DD-SPC-001 3906"
label | 00826d6a-6829-5501-a737-7e60849b0a87 |  | note | WP3906-1"
label | b4d828f8-9e44-50eb-9de0-ed38b2e47927 |  | note | Inspection/ Test Method: Inspection
label | 60a7b470-d948-51be-be9b-8cde89c06ccd |  | note | Record of conformity: ITP
label | 17aabeb9-f082-5422-ba32-0d07826509c8 |  | note | WP
label | 4c943a23-ac8a-503e-b06e-946b2985aff4 |  | note | Responsibility: Site Engineer
text | 481d6146-7d10-55eb-b6fa-02d5d8db364d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.06 - Commencement of cold planing works
label | 74649a61-1f5f-59a6-972b-a6b506656247 |  | note | Frequency:
label | 4a37a677-9ab5-5be1-ad56-6ecc46158c0f |  | note | Prior to the commencement of cold planing operations in a work area that must be covered with asphalt before the end of the work period."
label | 231b3ac6-f276-57c0-8a95-283587618142 |  | note | Acceptance Criteria:
label | 855df592-5a5a-5d49-8850-165c63377532 |  | note | Written notice to the Contract Administrator that all plant equipment labour including that required for the placing compaction and finishing of asphalt are available and ready on-site and supply of asphalt for the work is confirmed even in the event of an unexpected breakdown of the asphalt mixing plant."
label | 15ca959f-2181-59b8-bc26-8ef728ea7136 |  | note | Reference Documents:
label | 3a189d04-fd81-52ca-bbd3-4a340eda1405 |  | note | GHD-DD-SPC-001 3905"
label | b4214aa4-4c87-5030-8787-1ef3b4d91111 |  | note | HP3905-1"
label | 46558038-718c-590d-910b-e8c2280ffc88 |  | note | Inspection/ Test Method: Notification
label | 5d3a89eb-b8db-54b5-a323-bb9b3509d7bb |  | note | Record of conformity: ITP
label | 9179eb99-543f-54a0-914f-65acea07a5d9 |  | note | HP
label | 94b6dbab-0270-5778-ba1f-bee559421502 |  | note | Responsibility: Site Engineer
text | 0cca0eb2-f787-538d-b919-996373503415 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 Texturing
checkpoint-status |  |  | checkpoint | 3.01 - Removal of asphalt from the existing asphalt surface by texturing to required depth.
label | f5318b3d-00da-50db-8442-38965d18218d |  | note | Frequency:
label | ff122877-0948-54fa-81b6-3a94471dd1c7 |  | note | At the completion of texturing in each work period and prior to the application of tack coat and asphalt paving."
label | e078c5bb-7a26-521a-a8e8-6870f9a7401b |  | note | Prior notice (60 minutes minumum) of inspection to be given to the Contract Administrator."
label | 8af52cce-812a-5fce-8ba4-c191098e7bda |  | note | Acceptance Criteria: Depth of asphalt removed not less than 7mm and not more than 12mm
label | e6e40723-1554-5a3e-a985-36a5de75155d |  | note | Reference Documents:
label | 4314a7e2-549a-505c-a487-65638b61ee90 |  | note | GHD-DD-SPC-001 3907(b)(f)"
label | 6f535c7c-1d44-5a7b-bda9-da8eb2fd9bd1 |  | note | HP3907-4"
label | 5da94cd5-d472-55a6-a906-be2581664076 |  | note | Inspection/ Test Method: Inspection
label | 149d602a-6048-5c98-b5ff-dc8c1aae38c4 |  | note | Record of conformity: ITP
label | 57666b8e-ac00-5b5f-9339-a5b08856689e |  | note | HP
label | bba547cc-7138-5a2b-9ba6-fbacc900281e |  | note | Responsibility: Site Engineer
text | 8c541dca-9e9d-537f-86e9-c9049857ea26 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.02 - Removal of asphalt from the existing asphalt surface by texturing to achieve sufficiently coarse texture.
label | f9f11944-e4f2-5178-b714-43d353410bad |  | note | Frequency:
label | 20109cc8-138d-5c30-b2e0-26fc4690a534 |  | note | At the completion of texturing in each work period and prior to the application of tack coat and asphalt paving."
label | f5980bc7-a911-5828-be0c-dd3a071879ef |  | note | Prior notice (60 minutes minumum) of inspection to be given to the Contract Administrator."
label | 6a738d39-ba45-5a53-a034-12337df24ca4 |  | note | Acceptance Criteria:
label | b380bd67-9c09-577d-b4f6-2a99aca42596 |  | note | Textured surface is sufficiently coarse:"
label | 47851fbc-1550-5c17-a84f-f66f5bdc0a46 |  | note | Transverse spacing of deepest tooth cuts is 45mm (�15mm)
label | 3e0ffae4-a5e8-5bd2-8c29-8b6a7de4b7ee |  | note | Longitudinal overlap of adjacent teeth of not more than 25% of the average length of two adjacent cuts
label | 692f0cdd-8079-5f20-a46e-8d03e9117732 |  | note | No deviation >15mm under a 300mm straight-edge
label | 98e2dc1e-5837-5231-aa09-71d96ab57b6c |  | note | Irregular surface between deepest tooth cuts; at least one point between cuts deviates >5mm from the deepest point.
label | f576735c-2290-5e1f-81a7-4ab62f87530d |  | note | Reference Documents:
label | 138b2572-5cc9-51fc-85da-bd11d5757e96 |  | note | GHD-DD-SPC-001 3907(c)(f)"
label | 561b8645-82c4-5b3e-a84d-a488118cc5d0 |  | note | HP3907-4"
label | 6f7fce4b-1a7f-5d8c-8f09-264794bafdcb |  | note | Inspection/ Test Method: Inspection
label | b409a8c5-6a69-538d-9c72-00df5ed49682 |  | note | Record of conformity: ITP
label | 8b8e8989-b66f-5cc3-a95d-a8d1c9322bcf |  | note | HP
label | 5a14c8aa-80d4-5209-b348-68027bb52159 |  | note | Responsibility: Site Engineer
text | 3418a89d-794d-55f0-9088-35cde241358a |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.03 - Removal of asphalt from the existing asphalt surface by texturing to achieve a uniform surface.
label | 1be059ef-9b4a-5f77-9db8-077cc21f12fc |  | note | Frequency:
label | 207b8fb9-1f1f-5d4e-91f2-0b5ed1f81269 |  | note | At the completion of texturing in each work period and prior to the application of tack coat and asphalt paving."
label | af321452-1a82-5592-968e-93152028f41f |  | note | Prior notice (60 minutes minumum) of inspection to be given to the Contract Administrator."
label | 4193b751-2930-5da8-a2ba-94064f39bffd |  | note | Acceptance Criteria:
label | b6747d83-8444-505b-9999-87dd2aa46640 |  | note | Texture is uniform continuous without steps or abrupt changes in grade free draining apart from water retained in cuts and breaks of textured surface."
label | b77e1ccb-0931-54be-bbac-90baabdf1da6 |  | note | There are no visible grooves and all existing pavement markings have been completely removed."
label | c4a76182-72f3-593d-a51e-efa85236208b |  | note | Reference Documents:
label | 094675d2-a27e-5a97-b0b7-91d17d756346 |  | note | GHD-DD-SPC-001 3907(c) (f)"
label | fbab4d51-c74e-546a-8305-8ab3a5fa3aec |  | note | HP3907-4"
label | 318054ac-14ce-5b9f-9c0f-0f6a46d491eb |  | note | Inspection/ Test Method: Inspection
label | 3497ead1-003b-5c29-8d3b-0a4bff0e0b4b |  | note | Record of conformity: ITP
label | fa1f1d45-3e74-575d-8030-f1239753481b |  | note | HP
label | 3367aea0-0410-57ad-a7a2-77477196e1ed |  | note | Responsibility: Site Engineer
text | 77107249-9ad0-5839-bfad-fa5923cbb104 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.04 - Removal of delaminated asphalt
label | f503c3d6-383f-5fd2-a29c-c6f25a0f7202 |  | note | Frequency:
label | 8f3730c6-adf1-5660-9b32-3baf3005d8a8 |  | note | In the event that asphalt that is delaminated or exhibits evidence of delamination or lack of bond to the underlying layer is observed in the work area after texturing."
label | 862f5193-24a1-5693-8e51-84580c0f4d49 |  | note | Acceptance Criteria:
label | e4594ca6-5d39-512f-be63-e7a92d29fa97 |  | note | All delaminated or debonded asphalt is profiled to a sufficient depth to remove all delaminated or poorly bonded asphalt and patched with asphalt at least 40mm deep."
label | e4e3a22a-1d9a-5dd8-a41b-3a0dfac6f196 |  | note | Reference Documents: GHD-DD-SPC-001 3907(e)
label | 4e907d9e-942c-51ed-8199-aa3c1e1e0cfd |  | note | Inspection/ Test Method: Inspection
label | a511ceff-4cee-5be7-84a4-7551785b9c37 |  | note | Record of conformity: ITP
label | 53b29dc3-df1e-574c-a844-10cbb9908b70 |  | note | IP
label | ae2850b2-7222-52d1-a159-860225c62310 |  | note | Responsibility: Site Engineer
text | 4997ed76-0980-5d2b-965f-476d3328c1c5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.05 - Removal of cold planing and asphalt paving equipment from site.
label | d8c51ac3-e141-5fdc-af48-31962a05680c |  | note | Frequency:
label | f1f095a8-9835-58b7-a6c8-3ef1aba838cb |  | note | At the completion of texturing in areas open to aircraft operations between work periods prior to the removal of cold planing and asphalt paving equipment from the work area."
label | fa644c3d-a6de-568a-9a39-407c9a037885 |  | note | Acceptance Criteria:
label | a119bcbb-115d-5470-a70b-da022df79b28 |  | note | Absence of any possible deficiencies delaminations poor asphalt or any deficiency that may present a risk to aircraft."
label | eeef2b45-a289-56ce-a0c2-2bf59587b246 |  | note | Reference Documents:
label | 0abc5f05-9c7d-5eff-900f-1c0d894a069c |  | note | GHD-DD-SPC-001 3904(b)"
label | 0f8d4b20-aef8-5a5b-9f42-9e4b083fed6d |  | note | HP3904-3"
label | c188ed3d-423a-5f0d-813d-8a1a77e73182 |  | note | Inspection/ Test Method: Inspection
label | b3b67666-91c8-5bbb-97fb-87d66855741c |  | note | Record of conformity: ITP
label | 4be3da7d-e14e-563a-9a8f-357a338cf9b8 |  | note | HP
label | 1d299f58-eec3-532d-a959-46f0f1ebeaaf |  | note | Responsibility: Site Engineer
text | 6d4930d5-044e-51d2-86e9-b84ba3c64b6e |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.06 - Reinstatement of pavement markings.
label | 436b4bd0-923f-5cfd-971a-d41bb384a8bf |  | note | Frequency: At the completion of texturing in areas open to aircraft operations between work periods.
label | 8bc6f4dd-6415-5c59-bc4d-6008c723e40c |  | note | Acceptance Criteria: All removed pavement marking is reinstated as shown on the Drawings and specified Section 7100.
label | 97d548c9-7690-5286-8c57-dbeef5cca344 |  | note | Reference Documents: GHD-DD-SPC-001 3904(b)
label | 07402019-b43e-5322-a7ae-396437cffc6a |  | note | Inspection/ Test Method: Inspection
label | 3ac72f18-5c8a-50cf-93a6-27f2ef4e1e8e |  | note | Record of conformity: ITP
label | 7bd70fe9-89c3-5cf9-a0d1-7a138a88bb0b |  | note | IP
label | 86bbe54d-fc48-5105-b0ed-caebd075e50d |  | note | Responsibility: Site Engineer
text | 07c430f5-654c-50ab-8d58-2f65a062b425 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 4 Profiling
checkpoint-status |  |  | checkpoint | 4.01 - Removal of asphalt from existing asphalt surface by profiling to required depth.
label | 5fe64d47-fceb-5fc2-b566-9c5eac9965d7 |  | note | Frequency:
label | afd43dec-b381-5c8f-8e71-f1f6d21b4fc0 |  | note | At the completion of profiling in each work period and prior to the application of tack coat and asphalt paving."
label | 48eef436-caf1-50b9-872d-1c03f6dad24d |  | note | Prior notice (60 minutes minimum) of inspection to be given to the Contract Administrator."
label | bc4e8bd3-1ae1-58ee-9775-098c285652ce |  | note | Acceptance Criteria:
label | 45cb27f5-a2cc-542e-a36b-ca440155dfad |  | note | Depth of asphalt removed not less than depth shown on Drawings and not more than depth shown on Drawings plus 10 mm."
label | e27d6ddf-8fe1-5f03-aca6-2344187975c4 |  | note | Reference Documents:
label | 24c902a8-4126-5d6f-ba9b-aeb453b84ea2 |  | note | GHD-DD-SPC-001 3908(a)(b)(f)"
label | 1ff6a4a1-f285-5ed6-9de8-9d8c14ee0b2f |  | note | HP3908-1"
label | 9af90cef-6410-5ea8-a3d2-d2c01233879c |  | note | Inspection/ Test Method: Inspection
label | e6ab8301-47d3-5209-9d67-a55d8be948cc |  | note | Record of conformity: ITP
label | cc674aa0-1082-50b3-a1bb-bc66c8f400bb |  | note | HP
label | c0ec1126-8499-5edf-b335-d386c0781675 |  | note | Responsibility: Site Engineer
text | 896ba2e4-ff01-554e-8d08-91d5863231f7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.02 - Removal of asphalt from existing asphalt surface by profiling to achieve a uniform surface.
label | f8989762-4262-5bb9-b646-7271253da5b1 |  | note | Frequency:
label | e5c7b15a-f6aa-582c-8aca-f67846da93a2 |  | note | At the completion of profiling in each work period and prior to the application of tack coat and asphalt paving."
label | 96bee6c4-0c38-5ebc-8e7f-3c5dd0aac740 |  | note | Prior notice (60 minutes minimum) of inspection to be given to the Contract Administrator."
label | d689664c-98e6-564c-bf71-578017a81c4c |  | note | Acceptance Criteria:
label | 289ef800-bc7c-5843-8a67-8f8ef9b4b009 |  | note | Surface is uniform continuous without steps or abrupt changes in grade except at steps and edges of work and free draining."
label | fa85cdda-4c93-5a29-ad30-4c59df86eec4 |  | note | There are no visible grooves and all existing pavement markings have been completely removed."
label | b3fe7a78-9822-59c9-afce-f0af7ce8a428 |  | note | Reference Documents:
label | c1009901-b7a0-5947-a8fc-dff2dc105008 |  | note | GHD-DD-SPC-001 3908(c)(f)"
label | 54a146ed-a40b-5774-b20c-eff25f0ff26c |  | note | HP3908-1"
label | 985bdfbd-09fd-5f2c-a8d2-798efb41c5be |  | note | Inspection/ Test Method: Inspection
label | 67832fe8-4667-5692-bd4b-9fd4ba60c298 |  | note | Record of conformity: ITP
label | 9411feb4-d4f2-5e70-80a9-2ab399c55343 |  | note | HP
label | bb26e736-421b-565e-95ef-47c91ebffe39 |  | note | Responsibility: Site Engineer
text | 203a1bed-a8a1-5fda-bdbf-c0f3344570ec |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.03 - Removal of asphalt from existing asphalt surface to produce neat cut edges.
label | f0c02210-e6c4-5e9d-a4bc-400bc74729ee |  | note | Frequency:
label | e6cd75ed-bd85-5aaa-bf52-318f110274aa |  | note | At the completion of profiling in each work period and prior to the application of tack coat and asphalt paving."
label | 5e3cf769-33a3-590e-8bb9-9fe90b6ea4a8 |  | note | Prior notice (60 minutes minimum) of inspection to be given to the Contract Administrator."
label | b1d0d472-0c24-5821-844c-2c2432af8150 |  | note | Acceptance Criteria: Edges of cut are clean, not frayed and asphalt layer is not lifted.
label | 7fe5e275-8fb0-5014-abc8-5c11f76e4cac |  | note | Reference Documents:
label | 2d4f5b97-2ff4-5310-86cb-4d5928f80552 |  | note | GHD-DD-SPC-001 3908(e)(f)"
label | 051d1a11-2b30-5b83-9d42-8bb3b18a2711 |  | note | HP3908-1"
label | 17204573-c16a-57a6-91b5-2a59bb8c5ab5 |  | note | Inspection/ Test Method: Inspection
label | 6501d208-b12f-52c0-ade1-9f4455167267 |  | note | Record of conformity: ITP
label | 7cab6614-7c8b-5e73-b50c-1782c668f383 |  | note | HP
label | e222a78f-703e-5e88-856e-1a566165a608 |  | note | Responsibility: Site Engineer
text | eb026e23-8638-56a1-a4fb-91f3dfb31158 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.04 - Removal of delaminated asphalt
label | 144e18c3-0546-579a-a039-ad5b2c5bc106 |  | note | Frequency:
label | 79eff9c3-64cf-5697-8a32-6bd1c4ce0a02 |  | note | In the event that asphalt that is delaminated or exhibits evidence of delamination or lack of bond to the underlying layer is observed in the work area after texturing."
label | 16498cd2-0794-5d2f-90e6-dab7eca6ee1d |  | note | Acceptance Criteria:
label | 217d0348-ee13-5008-af67-48d344d0aee0 |  | note | All delaminated or debonded asphalt is profiled to a sufficient depth to remove all delaminated or poorly bonded asphalt."
label | 8ae0f0ed-7c39-5b2e-a369-9f59c3943f82 |  | note | Reference Documents: GHD-DD-SPC-001 3908(d)
label | 3e9b8ca0-ea48-5238-8c4c-e96534c23e6f |  | note | Inspection/ Test Method: Inspection
label | f51f5056-e327-5a37-812b-acae20979737 |  | note | Record of conformity: ITP
label | 12ce2910-4448-5f27-883e-e9258adfbcd6 |  | note | IP
label | 865cb107-d98f-5c95-bd43-ebbea6c80072 |  | note | Responsibility: Site Engineer
text | 118f0f8d-d627-5f1a-b470-45c3b3705d7d |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5 Milling
checkpoint-status |  |  | checkpoint | 5.01 - Removal of asphalt from existing asphalt surfacing by milling to required depth.
label | 78675548-f0fe-5f3f-b1aa-938147a76f5c |  | note | Frequency:
label | e90fc43e-5d0b-51d4-a61f-c631a7de6d86 |  | note | At the completion of milling in each work period and prior to the application of tack coat and asphalt paving."
label | 0e619cf3-9815-58cc-aaa2-08010d8dd460 |  | note | Prior notice (60 minutes minimum) of inspection to be given to the Contract Administrator."
label | 8f6b875b-aef5-59e1-b1e6-a30c20cea64f |  | note | Acceptance Criteria:
label | 7983c9a0-41ba-5dab-9c73-fbe2c7e91086 |  | note | Depth of asphalt removed not less than depth shown on Drawings and not more than depth shown on Drawings plus 10 mm."
label | edeb66f5-7173-545d-aa9f-b9ab132cdec4 |  | note | Reference Documents:
label | 0d68bc18-78d6-56f6-8f25-cba6a3f0ee47 |  | note | GHD-DD-SPC-001 3909(a)(b)(f)"
label | 5953ddb2-484a-50d0-a4aa-2b07ceaaee43 |  | note | HP3909-1"
label | 0e7505ce-6d42-5f12-bd8e-994d979d5a3e |  | note | Inspection/ Test Method: Inspection
label | bfd77d5b-25fe-52c9-8512-99a1e83e85a2 |  | note | Record of conformity: ITP
label | 858c973d-4aab-5f8d-b35e-42292f001f4f |  | note | HP
label | 2d1daa0e-d826-5461-aa41-7321f744a682 |  | note | Responsibility: Site Engineer
text | 55666393-9614-551e-b318-6fdc78729590 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.02 - Removal of asphalt from existing asphalt surface by milling to achieve a uniform surface.
label | 55861269-ed5f-523b-bae5-219a787ff70c |  | note | Frequency:
label | bb9db0d1-dc29-5717-bf0c-ac4e58e0b49e |  | note | At the completion of milling in each work period and prior to the application of tack coat and asphalt paving."
label | ec54fa2d-9abd-5ea1-9a0d-7c858def8c45 |  | note | Prior notice (60 minutes minimum) of inspection to be given to the Contract Administrator."
label | 6945be73-20a3-5cdf-8f91-ed3be775b4bd |  | note | Acceptance Criteria:
label | caae0c91-b3d7-50ee-91cb-806433630bf9 |  | note | Surface is uniform continuous without steps or abrupt changes in grade except at steps and edges of work and free draining."
label | 62cb3c9b-f2c0-545f-a1a7-1e186b39306e |  | note | There are no visible grooves and all existing pavement markings have been completely removed."
label | 12f37b0c-7b9d-5434-9447-5fbe2e462e97 |  | note | Reference Documents:
label | 182cf6af-784a-5b13-92e6-ca475053e8ee |  | note | GHD-DD-SPC-001 3909(c)(f)"
label | c2d116bd-c9cc-5512-91c4-b8c6a01c98f3 |  | note | HP3909-1"
label | d48380d9-5bc9-5f7a-8366-234e1b9205f1 |  | note | Inspection/ Test Method: Inspection
label | 2445ad06-d5ff-5633-b140-da74a4ccabcd |  | note | Record of conformity: ITP
label | 31b4334a-f8d2-5b49-9501-152540cd2d0b |  | note | HP
label | 06bc8f34-6a4f-5242-9562-bd012711d7b0 |  | note | Responsibility: Site Engineer
text | d1e8ee75-3936-55ed-aab0-e6cf7217c62a |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.03 - Removal of asphalt from existing asphalt surface to produce neat cut edges.
label | 8c34012b-0caf-501f-9880-e79cc68ad05c |  | note | Frequency:
label | 084738fe-bb3c-555b-bad0-cb786b2bd63e |  | note | At the completion of milling in each work period and prior to the application of tack coat and asphalt paving."
label | 1a656527-fe45-5330-bf1c-56588d744a15 |  | note | Prior notice (60 minutes minimum) of inspection to be given to the Contract Administrator."
label | 1827b172-0239-5662-8170-e689dcc78e28 |  | note | Acceptance Criteria: Edges of cut are clean, not frayed and asphalt layer is not lifted.
label | 8812c68f-84c7-52e7-9e28-79e64c62a3dd |  | note | Reference Documents:
label | 9823c28d-ed07-5b84-9281-4fcf98fbfe3e |  | note | GHD-DD-SPC-001 3909(e)(f)"
label | fda3e023-86ee-5359-bff3-21386004621c |  | note | HP3909-1"
label | 818804fa-f8a1-5bbb-a3d6-9de347f794d8 |  | note | Inspection/ Test Method: Inspection
label | 4624e760-bbf7-5b84-ac37-1eaead44c56b |  | note | Record of conformity: ITP
label | cfa23656-7f4c-54ac-92f6-a906d025b7bf |  | note | HP
label | a2db89a6-c8d1-58a5-8ce1-751e8b774dbc |  | note | Responsibility: Site Engineer
text | 96bf2056-052c-5631-a32a-adf9a041c9bc |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.04 - Removal of delaminated asphalt
label | 57d38bee-705b-5785-93aa-181589a40590 |  | note | Frequency:
label | 4fdb1a80-46d2-55fb-8dea-7485e7cca5ab |  | note | In the event that asphalt that is delaminated or exhibits evidence of delamination or lack of bond to the underlying layer is observed in the work area after texturing."
label | 18ab0851-0dbc-5c0c-ba47-f8b7744072dc |  | note | Acceptance Criteria:
label | 657f7e2d-7895-5f54-b315-89564399d0e0 |  | note | All delaminated or debonded asphalt is milled to a sufficient depth to remove all delaminated or poorly bonded asphalt."
label | 6603e1b3-045d-50be-a583-b8078948a2bd |  | note | Reference Documents: GHD-DD-SPC-001 3909(d)
label | 6a0aabf2-65d1-5473-97f2-722a5c46595e |  | note | Inspection/ Test Method: Inspection
label | 712bffc4-64e1-5062-8c02-6536c4ebb713 |  | note | Record of conformity: ITP
label | 95dbabd5-698c-5d09-83d9-3611e6327208 |  | note | IP
label | da525703-8002-5d53-840b-d32ca048c4ef |  | note | Responsibility: Site Engineer
text | 49a7ade3-1032-5247-906d-83881e4d9a43 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 6 Cleaning of cold planed surfaces
checkpoint-status |  |  | checkpoint | 6.01 - Commencement of cleaning of cold planed surfaces
label | 84ac9b6e-fb59-57b6-91f9-f066177eb0be |  | note | Frequency:
label | fde0a097-147c-5a87-9831-a375b26fe4f2 |  | note | At the commencement of cleaning of cold planed surfaces in each work period. Prior notice (30 minutes minimum) of commencement of cleaning to be given to the Contract Administrator."
label | cc1aa38d-1818-5f2d-9e2d-e6945665a1d5 |  | note | Acceptance Criteria: Witness the cleaning of the entire cold planed surface of asphalt.
label | b1115a45-5877-55e7-abf6-349ed4fc016e |  | note | Reference Documents:
label | e2975947-2713-51a1-8f43-817c04226067 |  | note | GHD-DD-SPC-001 3911"
label | 2b35be45-ed17-5186-a3ef-e8bff67953fa |  | note | WP3911-1"
label | 15939a4c-5cf6-5378-a116-e66b3fb2b235 |  | note | Inspection/ Test Method: Inspection
label | aa48c21d-0d7c-5a06-8c64-e6db96ad0ad3 |  | note | Record of conformity: ITP
label | 6effa266-3d48-5acf-a5e5-5a60ea3776b9 |  | note | WP
label | f114f22a-555f-5399-80a1-295c7babd307 |  | note | Responsibility: Site Engineer
text | fdb7f33b-d936-5a2d-8859-04d32f415860 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.02 - Cleaning of cold planed surfaces
label | 8cef65e6-a3e8-54b4-8b3e-2f29c45a6dae |  | note | Frequency: At the completion of cleaning of cold planed surfaces.
label | f849da58-758c-52d8-97c0-451534594bdb |  | note | Acceptance Criteria:
label | 6d4f3f0f-7036-5aa1-af81-365aa5be3911 |  | note | Cold planed surface is free from all loose material; excess dust water or slurry; and pieces of milled asphalt."
label | 26a03220-2b7e-58d3-bfb3-36cedd1087db |  | note | Cutting residue fully removed from the recesses in the surface in corners and at the edges of the cut."
label | ae4a6421-ece0-5b74-9ae6-0f0f5b907d05 |  | note | Areas of oil or fuel spillage cleaned with detergent flushed with water and dried."
label | d130a54e-bdce-5ceb-b4e8-52ccd55c7699 |  | note | Reference Documents:
label | 96e4a934-c21a-5d86-bdb7-22add87f623c |  | note | GHD-DD-SPC-001 3911"
label | 9da9093b-154e-50e8-a593-3921ac9cd963 |  | note | HP3911-1"
label | 10798b66-da54-59b4-8f6e-ca5b556f0548 |  | note | Inspection/ Test Method: Inspection
label | 3c05b167-864e-598a-9178-0dd0bd12ee87 |  | note | Record of conformity: ITP
label | 7a6d6fc7-031f-560d-8b84-70dcf51e3dde |  | note | HP
label | 8a2287d4-eda8-5a4d-bc55-11440ab51521 |  | note | Responsibility: Site Engineer
text | 879f7fa2-596b-54be-88db-aa501241e5d4 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 7 Survey of cold planed surfaces
checkpoint-status |  |  | checkpoint | 7.01 - Survey of cold planed surfaces
label | 119366b7-38a7-5e07-8dad-72a1858a1e2f |  | note | Frequency:
label | 8f7c7b40-f4c4-5437-b4e2-20043f49ddc2 |  | note | Progressively as cold planing work is completed in the work period."
label | 46384b88-27bb-59c1-ba42-9fdae4431cca |  | note | Prior notice (30 minutes minimum) of commencement of survey to be given to the Contract Administrator."
label | 3fa4dcb5-4308-53bb-b3bc-bc7eee7327cb |  | note | Acceptance Criteria:
label | 8a3c8c3c-b91e-5753-8de5-f44f1eabad19 |  | note | Compacted thickness of asphalt at each survey grid point location is calculated and inputted into computer controlled thickness control device on the asphalt spreader."
label | 8884780f-aebf-5a4f-b9ba-c8683655986b |  | note | Reference Documents:
label | 7f855aa3-428b-5a45-9003-745ac321ac57 |  | note | GHD-DD-SPC-001 3913"
label | 76fe5013-8cc5-5338-9116-318047d7944e |  | note | HP3913-1"
label | 1655cdc2-51d4-59c0-bfef-d48baffcd434 |  | note | Inspection/ Test Method: Inspection
label | 5cb31b62-d941-524a-a686-b9e00f9e2ae3 |  | note | Record of conformity: ITP
label | d503f2f7-7a05-5bdb-b65c-32e3d3ab0df9 |  | note | HP
label | fc42623e-92f1-58ff-bea0-150d55a8aabe |  | note | Responsibility: Site Engineer
text | 147e4b23-7dd2-541f-8aab-efdb75230a50 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | a46a9b2b-b7a5-533e-b9e2-6fac7c40953b |  | note | The signature below verifies that this ITP has been completed in accordance with the FHs Quality system Procedures and verifies lot compliance with specifications.
text | 5e487079-6a34-5b4a-b999-b7b32f7a14eb |  | textbox | Print Name:
text | ce838c37-7d38-5910-b5a1-fb9b1c7277eb |  | textbox | Position:
text | 8e50f68e-89b5-58b3-87dc-68af7f31ceb6 |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP010 - Prime Coats and Primer Seals | itp |  |  |  | Yes | ITP010 - Prime Coats and Primer Seals | 08a316af-f681-4575-8df0-7835a02fb26e
checkpoint-group |  |  | section | 1 Preliminary
checkpoint-status |  |  | checkpoint | 1.01 - Calibration of bitumen sprayers.
label | 5e932fbf-d2cb-5be1-a7ed-54744b2352e5 |  | note | Frequency: Prior to the commencement of works.
label | 23ccb059-57f6-56ed-b94c-79fcaeff27bf |  | note | Acceptance Criteria: Each bitumen sprayer used on the works has a current certificate of calibration.
label | 445c8aa9-8a64-5876-b786-6331bbac9266 |  | note | Reference Documents: GHD-DD-SPC-002 5004(b)
label | 912a924e-617d-5dbd-ba86-dd697c9059a7 |  | note | Inspection/ Test Method: AP-T181/11, AGPT/T530-536
label | 1400e159-0242-5337-8a07-dc815c0b452d |  | note | Record of conformity: Calibration certificate
label | c0664a56-aa36-5d81-bc8e-934677e59d64 |  | note | IP
label | 15c4cfaf-ffa5-5dea-955a-452ee72c9544 |  | note | Responsibility: Quality Manager
text | b8e85cc1-d7d2-55c8-a419-6a75f18f52d8 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 2 Compliance certification
checkpoint-status |  |  | checkpoint | 2.01 - Blinding sand.
label | 27e993f5-9726-5038-a95b-d4fe45253d05 |  | note | Frequency: Within thirty (30) days of notification of the award of the Contract.
label | 031a1cf7-fb48-58fb-b095-b4bf98a8c5c4 |  | note | Acceptance Criteria:
label | 93599c09-4e51-59ff-8a1b-d7a6fa42712b |  | note | • Sand is crushed or natural sand free from significant amounts of clay, organic matter, water or other foreign material and is non-plastic.
label | be825710-be85-5a07-8a99-4eeaf093e954 |  | note | • The sand contains only sound, hard, dense, durable and clean particles. The particle size distribution of sand is within the below limits:
label | f9afbdd6-a8e3-5e30-966e-af9ec17d7a61 |  | note | 6.7: 100
label | 1845c51b-16c8-56bd-9bee-e4cd05ed71f7 |  | note | 4.75: 85-100
label | d1e7e2b1-f07a-52f0-ac22-ad89c5f6dce0 |  | note | 1.18: 40-100
label | 0bd57de4-3614-565c-a246-8996f48065e1 |  | note | 0.425: 10-50
label | eaccc994-6d2d-5900-93a0-61a7c45b0c61 |  | note | 0.075: 0-5
label | f6e10393-b34e-5499-b864-746a71d122c1 |  | note | Reference Documents:
label | cd084281-d94c-5fef-9538-adf3e1278da9 |  | note | • GHD-DD-SPC-002 5003(e), Table 5003-2
label | 87fe9ede-6f3f-5bac-976e-0c344344ae94 |  | note | • HP5013-1
label | debb1c11-79c4-5554-833b-95add4ce6cee |  | note | Inspection/ Test Method: Inspection, AS 1289.3.3.1 (wet preparation)
label | 56ee9e9a-56e2-5ec9-99e6-5f0a51695bae |  | note | Record of conformity: NATA accredited test certificate
label | a85645ab-7d1f-585c-9a93-3538556b8f74 |  | note | HP
label | e784fc5f-387b-5bfc-930a-bf42bb878232 |  | note | Responsibility: Site Engineer
text | f0c1624f-5024-5576-8e49-d6424fc87306 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.02 - Aggregates: wet strength
label | 7f33ff8b-92ff-5cae-be7a-e2e65f3bf5fd |  | note | Frequency: Within thirty (30) days of notification of the award of the Contract.
label | 18f4c81a-ef79-5ae8-b660-bb049073b01e |  | note | Acceptance Criteria: 150 kN minimum
label | b9384d21-0a6e-5729-8ffe-920a3c57bb86 |  | note | Reference Documents:
label | 977c7b07-1824-5aca-a708-76b21a3ce476 |  | note | • GHD-DD-SPC-002 5003(f), Table 5003-3
label | 257857cf-2d08-5572-9896-917a826fdc49 |  | note | • HP5013-1
label | fa501e0e-d513-50a6-a533-abdab8d9b39e |  | note | Inspection/ Test Method: AS 1141.22
label | 0ae442c0-85c8-5c1d-ae55-a8e33e02cb2f |  | note | Record of conformity: NATA accredited test certificate
label | f6e949c4-d921-52be-9757-9b1051e523eb |  | note | HP
label | cef658a9-e7f8-5afc-a638-e856361abf85 |  | note | Responsibility: Site Engineer
text | 31774abc-8bce-5622-8a46-ddb8a432c7aa |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.03 - Aggregates: wet/dry strength variation
label | 84b51dab-9419-51e2-87b8-4fcf246153e9 |  | note | Frequency: Within thirty (30) days of notification of the award of the Contract.
label | 0fc62589-c44a-5ebe-91ef-fdbf0aa7101c |  | note | Acceptance Criteria: 35% maximum
label | fc20e288-f15a-55ca-b413-a31e449b2d5b |  | note | Reference Documents:
label | 07112f7e-73f3-5851-8317-8b643614d0a0 |  | note | • GHD-DD-SPC-002 5003(f), Table 5003-3
label | 6bb3d657-b536-533b-b8ba-ab2bf61b33fc |  | note | • HP5013-1
label | 94c2ee4b-2a82-506e-8043-ef8dcf692d2b |  | note | Inspection/ Test Method: AS 1141.22
label | 2bd50199-0d21-559a-aca6-65439ef5db02 |  | note | Record of conformity: NATA accredited test certificate
label | d6309d6d-2999-5be9-b953-80bfd69c8f31 |  | note | HP
label | 016099f4-8a58-50fb-9e8f-1ad1334f2612 |  | note | Responsibility: Site Engineer
text | 4866e983-d9cb-51db-94ec-3c3a51b84f31 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.04 - Aggregates: sulphate soundness
label | 8c1b43da-a674-54b6-9631-43653a62c6e6 |  | note | Frequency: Within thirty (30) days of notification of the award of the Contract.
label | 577dbffc-7fd9-54fb-97d8-ce01d7d9211b |  | note | Acceptance Criteria: 10% maximum, and 3% maximum for weighted average percentage loss after 5 cycles
label | bdcbcb54-22e0-50ee-b6f5-c3e22dacdc5c |  | note | Reference Documents:
label | 122446c6-8739-5e9b-8486-a40b908e073a |  | note | • GHD-DD-SPC-002 5003(f), Table 5003-3
label | 5525340d-c5fc-5f29-a3f9-6f38df569590 |  | note | • HP5013-1
label | 7abaf8b8-f59c-50bd-be21-50f827affee3 |  | note | Inspection/ Test Method: AS 1141.24
label | 7aef6781-42d4-5135-ae37-e39fbe7be29b |  | note | Record of conformity: NATA accredited test certificate
label | a3f6353f-3fba-5cd4-afb5-4d86c579fd5a |  | note | HP
label | 168b6a76-39e0-50d3-9a11-162117c8b95f |  | note | Responsibility: Site Engineer
text | c7bbb6b7-4963-5a84-8648-f68f5c954ad2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.05 - Aggregates: flakiness index
label | 548c414a-91be-5c34-b3ba-3802172e62f4 |  | note | Frequency: Within thirty (30) days of notification of the award of the Contract.
label | 98d644b5-8e60-52fc-8782-9b1c9aab81fb |  | note | Acceptance Criteria: 25 maximum
label | c3f1e03f-7974-5032-bdea-4d1ed01c166b |  | note | Reference Documents:
label | de1d9272-168d-5d18-b60b-567f93fdd7d2 |  | note | • GHD-DD-SPC-002 5003(f), Table 5003-3
label | cd9920a6-4b1f-56e8-8161-a21a74132454 |  | note | • HP5013-1
label | 5c1bd45e-4fdc-5306-9177-3c56f7c24fdd |  | note | Inspection/ Test Method: AS 1141.15
label | 42e73841-a9f9-50df-b1b4-de2262bfa986 |  | note | Record of conformity: NATA accredited test certificate
label | c7b97b62-2397-5e2d-a179-3cf9a2a90aae |  | note | HP
label | 4ee35f7a-2cc9-55f6-b2eb-f5ed7a40db13 |  | note | Responsibility: Site Engineer
text | 80aeb84f-771a-568c-b0df-bbd2057d9ef9 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.06 - Aggregates: fractured faces.
label | b8ba07ac-dc4c-5f87-86ee-7fa6c0325b86 |  | note | Frequency: Within thirty (30) days of notification of the award of the Contract.
label | 5122c8a2-fd5d-56ee-bbf0-df900ac1ccc0 |  | note | Acceptance Criteria: Not less than 100% by mass of particles must have 2 or more fractured faces
label | cc4d3260-d384-573e-a796-8ba05f28be92 |  | note | Reference Documents:
label | 845b8f38-3cd1-54f4-9068-f5835934c577 |  | note | • GHD-DD-SPC-002 5003(f), Table 5003-3
label | 8694d2a2-91d3-5dd7-a993-1257db74a3a6 |  | note | • HP5013-1
label | 8dd71b49-ed14-50c6-bd02-cbdaa412e9e0 |  | note | Inspection/ Test Method: RMS NSW Test Method T239 or approved equivalent
label | 75a68e93-0cca-5805-a983-134cf63cc861 |  | note | Record of conformity: NATA accredited test certificate
label | 99e31771-04b9-55a3-a485-6e195271dbf0 |  | note | HP
label | 6d1b6ad0-eb98-52ad-96b7-29f41d5ca34d |  | note | Responsibility: Site Engineer
text | 362b68c1-4135-5782-ac14-66fd7c260314 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.07 - Aggregates: degradation factor (igneous rock only)
label | ec5131ec-2dab-5a1f-987a-95cff9649ab9 |  | note | Frequency: Within thirty (30) days of notification of the award of the Contract.
label | 94790aa8-5a71-5c7f-a869-a25386451b84 |  | note | Acceptance Criteria: 50 minimum
label | 574bce97-58dc-594e-8a94-0f3679f8ed82 |  | note | Reference Documents:
label | cbdc51ff-391c-526b-aa98-aa1ba1abb64f |  | note | • GHD-DD-SPC-002 5003(f), Table 5003-4
label | 2b47f94c-60b5-5750-a573-81c8e02110b5 |  | note | • HP5013-1
label | 63a879e8-e061-5c65-9dba-3e0945b62813 |  | note | Inspection/ Test Method: AS 1141.25.1
label | a009c36a-e0de-53fc-8523-92142ee53d7f |  | note | Record of conformity: NATA accredited test certificate
label | 401937ca-86ac-5b4d-9b60-6dcbb77249d6 |  | note | HP
label | 6da71519-be1b-5aa5-bc70-264b1ea825a9 |  | note | Responsibility: Site Engineer
text | c9729945-e2d2-55ac-b90e-b4fba2ff13e3 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.08 - Aggregates: secondary minerals content (igneous rock only)
label | 8fa46fc8-1081-5dcd-a7cd-ffe3b06ff05f |  | note | Frequency: Within thirty (30) days of notification of the award of the Contract.
label | c8fc414f-8fdb-560d-b28c-b8474eaab904 |  | note | Acceptance Criteria: 25% maximum
label | 2ac76933-5689-5673-9c75-1a1e2f2a43c3 |  | note | Reference Documents:
label | ec5b8476-162c-59a1-9f2c-4203912960ef |  | note | • GHD-DD-SPC-002 5003(f), Table 5003-4
label | c9ae4d03-0dd8-5467-9e20-b447cb50dd47 |  | note | • HP5013-1
label | 1171d933-a7e9-51aa-b606-3121a899934a |  | note | Inspection/ Test Method: AS 1141.26
label | 59fec4d1-d87f-5515-b172-7a2686cc8047 |  | note | Record of conformity: NATA accredited test certificate
label | 82c404c4-6888-5a24-ac95-363b70963d10 |  | note | HP
label | 328c31f3-9eb8-5c83-b0d9-02cd1e1f902f |  | note | Responsibility: Site Engineer
text | 1088f15f-77d1-51bb-b850-57489c05d8c8 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.09 - Aggregates: accelerated soundness index by reflux (igneous rock only)
label | 649f5594-95a7-5037-a2e9-db193c00dc4f |  | note | Frequency: Within thirty (30) days of notification of the award of the Contract.
label | 2682989d-ed61-582d-8dfc-a8716b4d88f3 |  | note | Acceptance Criteria: 94 minimum
label | 1b33f788-b502-5b7b-9c9d-f9419ce85245 |  | note | Reference Documents:
label | a8337a33-dee8-53b1-b710-4ec44fb185b8 |  | note | • GHD-DD-SPC-002 5003(f), Table 5003-4
label | 80f7ee7f-bac5-5f85-8691-eef10612d686 |  | note | • HP5013-1
label | 4c9da715-4e11-51fd-9a65-109da8501c9e |  | note | Inspection/ Test Method: AS 1141.29
label | 20169573-c854-588b-9378-0f3d2b4440ae |  | note | Record of conformity: NATA accredited test certificate
label | 3529cb38-1793-5ca8-8d68-e09a1937c92a |  | note | HP
label | d0dcd135-ca5a-5bc1-9867-f8a3fc944db5 |  | note | Responsibility: Site Engineer
text | e9c091bf-a134-5325-beb8-02d5de535af6 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.10 - Aggregates: particle size distribution
label | f7acc70f-480c-5f20-a094-ecf32c029012 |  | note | Frequency: Within thirty (30) days of notification of the award of the Contract.
label | f529743c-e376-55cc-9c01-44447ae29755 |  | note | Acceptance Criteria: The particle size distribution is within the specified range for the relevant nominal size aggregate shown in Note 1.
label | 79de9f17-cc0d-5ffa-bb23-da0e72a907c7 |  | note | Reference Documents:
label | 8df7a65f-8941-5d58-a50a-381fc7479f06 |  | note | • GHD-DD-SPC-002 5003(f), Table 5003-5
label | ddfb4211-9305-5f6a-8fe9-3e8facc57a4b |  | note | • HP5013-1
label | 0a9f850d-5960-5ac4-95fb-b62b9de7e12d |  | note | Inspection/ Test Method: AS 1289.3.6.1
label | 54e0d1d8-f3fa-5672-afc6-1d8056cd0e84 |  | note | Record of conformity: NATA accredited test certificate
label | a84c3dc4-1d03-51b6-8d59-f455ca890e47 |  | note | HP
label | 76f5f790-a9c8-5cce-8d1b-ab8a9fb0bc54 |  | note | Responsibility: Site Engineer
text | 1389dfb1-decb-57ed-942d-25e7b358638d |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.11 - Aggregates: average least dimension
label | 17daf1c5-2a93-5684-a612-20886230d420 |  | note | Frequency: Within thirty (30) days of notification of the award of the Contract.
label | 336aaafd-3681-5ff6-96a1-2d20144245de |  | note | Acceptance Criteria:
label | 4e03f4c7-4a12-5147-b838-751757f0757e |  | note | • Nominal 10 mm: 5-6 mm
label | 407579ed-dd0e-5d9e-a725-5c42c44cb974 |  | note | • Nominal 7 mm: 3.5-4.5 mm
label | a9586da7-e1ba-5704-8866-97d5735d55ae |  | note | • Nominal 5 mm: Report only
label | ff677bea-d3d3-55c1-9e28-5695fb994337 |  | note | Reference Documents:
label | aabdf87a-4eda-5ad8-97bf-bdcf3a1a31af |  | note | • GHD-DD-SPC-002 5003(f), Table 5003-6
label | 7fdba52c-f041-544b-a011-c298f1a7801a |  | note | • HP5013-1
label | 4ea16b21-fbc5-5e0d-87ed-fabffb81de78 |  | note | Inspection/ Test Method: AS 1141.20.1 or AS 1141.20.2
label | c539cfdf-aa12-5ae5-9595-21d2d02e34de |  | note | Record of conformity: NATA accredited test certificate
label | 0c2d2bbb-490a-5fab-8541-e8516265f09c |  | note | HP
label | 1f5eb606-9574-506d-af69-d69ff748e0ae |  | note | Responsibility: Site Engineer
text | 7131606a-65ac-5362-8507-f456f016f834 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.12 - Proprietary prime products.
label | fea987dc-1c0b-5730-8379-f0ecd88431ce |  | note | Frequency: Prior to the use of proprietary prime products.
label | ee62f9a3-a426-5fda-bcff-f14abf254ecc |  | note | Acceptance Criteria:
label | 63fd1d1c-4841-57a3-974e-81d5f7515d0b |  | note | • Proprietary products have proven performance on similar airport or heavy duty pavement applications for at least 5 years.
label | 7bdb2623-7bbc-5dd8-9ba9-e7182ec1e683 |  | note | • Material data sheet, record of proven performance and specification has been submitted to the Contract Administrator.
label | 8d19a29c-2243-5f1c-809c-de9625356315 |  | note | Reference Documents:
label | 8951b290-7afd-58a2-b600-0daf50a39e81 |  | note | • GHD-DD-SPC-002 5003(h)
label | af09b99e-e2d2-5308-b0fd-0b97d014d44b |  | note | • HP5003-1
label | 2ce9209b-7910-5429-a474-0f33d4281e67 |  | note | Inspection/ Test Method: Document
label | 7edce12f-44ff-5d79-9499-7905c72302dd |  | note | Record of conformity: Materials data sheet, record of proven performance
label | f2420703-92cd-588a-8134-afa0aff517a0 |  | note | HP
label | a9602a9a-55d4-5d07-a0db-83bf2a34e3b9 |  | note | Responsibility: Quality Manager
text | 4c344db4-4606-53dc-ad59-559a393e13a0 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 Materials
checkpoint-status |  |  | checkpoint | 3.01 - Storage temperature of primer.
label | a008e884-fbfd-5756-9ae8-6876ddddec08 |  | note | Frequency: Each delivery of bituminous primer.
label | 25ff61c2-f153-5de7-8385-6aca564540d2 |  | note | Acceptance Criteria:
label | a74012f9-b1c2-50c2-ab5d-2d2aec793abb |  | note | • Primer has not been held at storage temperatures greater than the limits below for more than 6 hours:
label | e927a02d-b6cf-51b7-bb75-dce62cca3780 |  | note | – AMC00: 40°C
label | dc6ebaf2-0c4f-5167-84a1-98aca4f6acd1 |  | note | – AMC0: 60°C
label | 637f7ac5-d15e-5b3c-b7ae-1e2f6819acc1 |  | note | – AMC1: 80°C
label | c2522c75-6e3e-5083-b1c1-4a6c02c1bf0a |  | note | Reference Documents: GHD-DD-SPC-002 5003(d), Table 5003-1
label | bfe8ba44-955b-5a7e-96e2-1cd4a1d7ed60 |  | note | Inspection/ Test Method: Inspection
label | 37db7d47-20ec-58ef-b3fb-168540632585 |  | note | Record of conformity: ITP
label | 405a9176-9d0a-5aec-bd5e-9588a4388fc9 |  | note | IP
label | 3ae4219a-162b-520d-821b-9b56f3721b7f |  | note | Responsibility: Site Engineer
text | 3e097aab-436e-5da2-98d8-37961ae6a2c1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.02 - Sand: particle size distribution.
label | 98df3d1e-dd64-5b9b-8b33-c63607294079 |  | note | Frequency:
label | f4453800-b48d-54de-83b8-59d3497bf0d0 |  | note | • Each stockpile of sand proposed to be used for absorbing excess primer.
label | 835eeb5e-b420-5917-967e-a69992d851ee |  | note | • Test certificates to be submitted to Contract Administrator at least fourteen (14) working days before proposed commencement of priming.
label | 4d4841d1-6bef-55fe-a14f-94413bb8e26f |  | note | Acceptance Criteria: Material complies with Item 2.02 of this ITP.
label | 79fe29a1-2653-5a79-8fe2-12e15db60777 |  | note | Reference Documents:
label | a8d78131-0609-58df-8ca3-1945aececa26 |  | note | • GHD-DD-SPC-002 5013(c)
label | 5accaf2f-e7c1-5dd0-90d6-b9fea697e192 |  | note | • HP5013-2
label | bc98b019-adb9-55e4-8aa1-0d2140a5423a |  | note | Inspection/ Test Method: AS 1141.3, AS 1289.3.6.1
label | d13e744d-6ed7-5102-85a9-482a04dd9afe |  | note | Record of conformity: NATA accredited test certificate
label | bb5895b7-e5da-53ef-a292-0c0d102a5b5d |  | note | HP
label | ee12f38e-4634-5bd4-9bb4-70fb94ec9b91 |  | note | Responsibility: Site Engineer
text | 6a66bc8b-937d-504a-811c-b73e9b64ef54 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.03 - Sand: plasticity index.
label | b5d6c9a6-04d3-5808-9a65-fb6e012d71b7 |  | note | Frequency:
label | c444291f-7290-5ede-bfe3-3d507826e9d3 |  | note | • Each stockpile of sand proposed to be used for absorbing excess primer.
label | 9777e289-e533-5916-9368-ffc2318e0f2d |  | note | • Test certificates to be submitted to Contract Administrator at least fourteen (14) working days before proposed commencement of priming.
label | 5746f542-1838-5c85-a0b3-7e9dd73e263e |  | note | Acceptance Criteria: Non-plastic
label | 07ac81f6-01ae-5abf-9bfc-7686532fbc9e |  | note | Reference Documents:
label | 9da12a9d-a9c2-54af-8d57-20602892192b |  | note | • GHD-DD-SPC-002 5013(c)
label | 20c4596d-aee8-59a5-8025-3332f1198799 |  | note | • HP5013-2
label | 2ee1348a-d5fb-5ac5-82ff-2623e77abbe1 |  | note | Inspection/ Test Method: AS 1289.3.3.1 (wet preparation)
label | 63d08d35-f101-5e12-8547-1d4e8af916ee |  | note | Record of conformity: NATA accredited test certificate
label | c672cfa2-ad78-5222-a324-9e326af65480 |  | note | HP
label | 11b39566-f285-50e8-b102-013af78e4cba |  | note | Responsibility: Site Engineer
text | dd8ac74a-d867-5703-baff-520f0f8302f7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.04 - Aggregates: particle size distribution
label | 98d92b4c-1efa-5be7-aa04-f8a66390b267 |  | note | Frequency:
label | 77f2c4e9-1bd5-5ca1-bfde-2e85a3a0e360 |  | note | • Each stockpile of aggregates to be used in primer seals.
label | c10dcace-21b4-594e-9809-6e7ebfc3b924 |  | note | • Test certificates to be submitted to Contract Administrator at least fourteen (14) working days before proposed commencement of priming.
label | 169cbc92-02bb-5a51-b64d-03b9badcea9e |  | note | Acceptance Criteria:
label | 38d1fba5-b899-5936-b744-68325c3632bd |  | note | • The particle size distribution is within the specified range for the relevant nominal size aggregate shown in Note 1.
label | f7c12ebd-980a-5c7d-8163-a0d062d60dba |  | note | Reference Documents:
label | 32f7bf85-3fcf-5ff4-a12b-59839fbb8881 |  | note | • GHD-DD-SPC-002 5013(d)
label | 4257528f-0d14-5b3c-9783-6ed74082d0a9 |  | note | • HP5013-2
label | 29124da2-6fcf-59f5-b027-15d423cee37f |  | note | Inspection/ Test Method: AS 1141.11.1
label | 183852a5-12b6-5efe-a6ed-0a9a31bae9a4 |  | note | Record of conformity: NATA accredited test certificate
label | 1cb77825-99ff-58d0-b622-fc20352059dd |  | note | HP
label | 8a9e975e-b554-59a1-b02d-0afd3d4a9a87 |  | note | Responsibility: Site Engineer
text | edc9a86e-3c50-50df-a23a-c40da723c0fb |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.05 - Aggregates: apparent particle density.
label | 63add3d1-638a-5e0c-8d2f-852a74c5bfb8 |  | note | Frequency:
label | 42b7c2cf-45c5-58c3-bb16-c3bda9c55dad |  | note | • Each stockpile of aggregates to be used in primer seals.
label | df0adbd1-a5b1-5108-bcde-5212be9a6aed |  | note | • Test certificates to be submitted to Contract Administrator at least fourteen (14) working days before proposed commencement of priming.
label | 9085707c-3650-5c58-b6dd-fb599b7e82ed |  | note | Acceptance Criteria: To be reported.
label | 1e3a81d9-434f-5ca8-8178-ea69778625af |  | note | Reference Documents:
label | 6a5618c9-b3f0-5143-b1f9-50990d86212a |  | note | • GHD-DD-SPC-002 5013(d)
label | 9fbe6108-63da-5dcf-b8cd-394dbfb56c5d |  | note | • HP5013-2
label | ce9a45bc-4d94-5fe3-a1dc-5be8d73310a4 |  | note | Inspection/ Test Method: AS 1141.6.1
label | 150c3748-8c6d-5d34-a1f6-3e1ae95058d1 |  | note | Record of conformity: NATA accredited test certificate
label | b5f09ddd-d692-5733-a603-5cb55afbe332 |  | note | HP
label | e7e800c4-9bab-5502-b352-9e11bff1a04d |  | note | Responsibility: Site Engineer
text | 78f0ccdb-3c11-5b5b-959e-07df24327c9c |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.06 - Aggregates: flakiness index.
label | 9eb80aeb-8df5-5f99-a832-829f25aa865b |  | note | Frequency:
label | 4d02033a-328d-5a00-be35-e72ba07a4627 |  | note | • Each stockpile of aggregates to be used in primer seals.
label | 949692e4-6a4c-545a-ab60-276bce533217 |  | note | • Test certificates to be submitted to Contract Administrator at least fourteen (14) working days before proposed commencement of priming.
label | 8eac231e-af16-5d8d-9f45-2aec66f123c7 |  | note | Acceptance Criteria: 25 maximum
label | 3fa5c01b-bc4d-515a-95ea-3f3480539bab |  | note | Reference Documents:
label | 99184b15-cb3b-590a-b470-b9b3003b7d72 |  | note | • GHD-DD-SPC-002 5013(d)
label | d074ddef-c315-5e28-b709-76a3fcb5d48d |  | note | • HP5013-2
label | aafdb3ba-01da-580c-8b2d-46dded131749 |  | note | Inspection/ Test Method: AS 1141.15
label | 721d2b28-3cf3-598a-bd72-f4cbbeee632e |  | note | Record of conformity: NATA accredited test certificate
label | 09b9b114-f160-5336-a13e-2ec351178ac3 |  | note | HP
label | c2302a54-6521-5b67-a627-8647ee7b03ad |  | note | Responsibility: Site Engineer
text | 332fbe05-7f96-5a50-a6e7-65ea90535f84 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.07 - Bituminous prime: material properties.
label | c6b74daa-90b6-54cf-af07-fde3bfac5a11 |  | note | Frequency: Each homogenous lot of primer.
label | 82e66867-f46b-5571-9150-528073a2076f |  | note | Acceptance Criteria: Material complies with AS 2157 specification.
label | 657fc6f5-6f5e-56b8-b833-b403d59af5ee |  | note | Reference Documents:
label | 0cc6dbd3-7015-5202-8230-6c3d4b25c0c6 |  | note | • GHD-DD-SPC-002 5013(f)
label | dbd31b04-b8a1-53ad-8d00-0de4144a935a |  | note | • HP5013-3
label | 83b9a600-b6ee-52eb-80e5-d7bad37181d1 |  | note | Inspection/ Test Method: AS 2157
label | 646da4a8-3fcd-5ae8-9b08-19c2efcf92a9 |  | note | Record of conformity: NATA accredited test certificate
label | 232947cc-5535-5521-828c-b1455974fd44 |  | note | HP
label | 602c214e-6954-52d6-a347-e019daa1f753 |  | note | Responsibility: Site Engineer
text | 0aae202f-7061-5ae7-b14e-efb97f3872e0 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.08 - Bituminous prime: temperature.
label | 103a960e-5e91-58a7-bda2-e87051424d82 |  | note | Frequency:
label | 89a0889e-3028-5a25-89d9-4aea4b88da26 |  | note | • For each delivery of primer, immediately prior to the transfer of primer to storage tanks from the delivery vehicle, and at least once per day that the primer is being stored, or at least once per hour when the primer is being heated.
label | 940e83d2-05f6-507f-a10b-549992fa20e7 |  | note | Acceptance Criteria: To be reported.
label | 2c15a2ca-0be6-54bc-9791-d99b1f34e626 |  | note | Reference Documents: GHD-DD-SPC-002 5013(i)
label | 4a758eba-d25a-5656-8aac-9ba6d6aa1415 |  | note | Inspection/ Test Method: Thermometer
label | 924bb283-46f6-5aef-917b-1c152b32979e |  | note | Record of conformity: Temperature log
label | 7c76f10a-f366-5f02-bd87-8e75d76f40c7 |  | note | IP
label | 4d623754-17d6-56f5-b046-1793b240f324 |  | note | Responsibility: Site Engineer
text | 4d21317e-458a-53af-9689-bc0e3f2becd9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.09 - Reference samples.
label | 7c972ebb-b55f-5706-a857-aafb674826ec |  | note | Frequency: At least one (1) day prior to commencement of work.
label | e1f5157d-ecd1-53d9-a13a-3b674515a2fa |  | note | Acceptance Criteria:
label | 77c27716-cd35-5236-9770-07e5a932480d |  | note | • The reference sample is representative of the material to be used in the works and complies in all respects with the requirement of the specification.
label | 9e7f5564-6f9b-5f74-97f9-f5ad14e149d4 |  | note | • The sample is dividied into two representattive portions. Each portion is not less than one litre.
label | 16864671-c30e-526c-9d9f-c2a4bb21729c |  | note | Reference Documents:
label | 1ac51557-ee70-50b8-8b97-3f4653832f2c |  | note | • GHD-DD-SPC-002 5013(h)
label | 51d01c15-7cdc-5c61-9c9f-1c0beea3719c |  | note | • HP5013-4
label | 29e2d8de-cb50-589d-8bfe-f360a38c1a76 |  | note | Inspection/ Test Method: AS 2157
label | 0ea553f5-4d85-5dfa-9c3e-4ba335cf8978 |  | note | Record of conformity: Sample receipt
label | 70c2dbf5-fa2c-579b-93c6-97589a264d12 |  | note | HP
label | 2d35a58f-40d1-50ee-a682-540e874ccf53 |  | note | Responsibility: Site Engineer
text | 7f878e01-fe18-5fe7-abfe-ed5d8400800b |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4 Trials
checkpoint-status |  |  | checkpoint | 4.01 - Construction trial of primer.
label | c209b8b2-d2ca-5169-a729-c48090021342 |  | note | Frequency:
label | 4b68a51b-1801-5ea9-84d2-3d85accb13a3 |  | note | • At least three (3) working days prior to the proposed commencement of the initial application of prime coat or primer seal.
label | 7952f6d3-dde1-5c98-b824-4d0aad853b36 |  | note | • Prior notice (minimum two (2) working days) of intention to construct the test area to be given to Contract Administrator.
label | d44f43e0-2f04-5851-9934-56f64ffb2111 |  | note | Acceptance Criteria:
label | d0afb063-66e2-515f-a8f4-95aac398835c |  | note | • Approximately 1000 L of primer and all necessary plant, labour and equipment is available to perform a construction trial of prime coat and/or primer seal.
label | 8aee2fa8-6a68-5565-b55e-237ddc13f876 |  | note | Reference Documents:
label | a7485a7e-4b12-5208-9003-23268b2f1513 |  | note | • GHD-DD-SPC-002 5009
label | 9e326aec-2ce7-5830-97dc-1afe3eef7a47 |  | note | • HP5009-1
label | c89da2d3-2e62-5f7a-a122-9e8adffb538c |  | note | Inspection/ Test Method: Notification
label | 310206ee-7646-5009-89fb-4b45a6b3399a |  | note | Record of conformity: ITP
label | 06bdf4b9-8ae4-5986-a8f1-dba5edfe6ea1 |  | note | HP
label | b34cae9f-d62a-5fb4-bb77-13d5f0c4cd6a |  | note | Responsibility: Quality Manager
text | 91cb3da4-0dfa-5a72-9462-1adf19e04240 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 5 Application of Primer
checkpoint-status |  |  | checkpoint | 5.01 - Surface preparation.
label | 5ffb424a-6ef4-5f23-a03b-6456eb072867 |  | note | Frequency:
label | de658065-fa36-5986-a991-270d03ab1b73 |  | note | • Immediately prior to application of primer.
label | f5b0c58a-26c5-5e1c-b7af-a1aac820ce96 |  | note | • Prior notice (minimum 2 (two) working days) to be given to Contract Administrator of intention to commence con
label | 2307ebb3-2303-56b6-aa23-e38359ac3821 |  | note | Acceptance Criteria:
label | 3918153d-cab2-55f9-939c-3767c2b8576c |  | note | • All loose material, excess aggregate, dirt, clay, dust, oil, or any other deleterious substance has been removed from the surface to be primed.
label | 87259026-f56c-55bf-b3b3-54c98fffbd6c |  | note | Reference Documents:
label | 80e76fc6-199e-5428-b01c-09583920fe67 |  | note | • GHD-DD-SPC-002 5006(b)
label | a844f042-91eb-5039-8d61-26980ac8efbf |  | note | • WP5006-1
label | cd6c3753-4b84-525a-9836-d421171a7d96 |  | note | Inspection/ Test Method: Inspection
label | 97c6046e-5d77-559c-bb90-16718b53ad6f |  | note | Record of conformity: ITP
label | 1bed2ca1-b2e0-5eb1-882d-4c3fb152ae9d |  | note | WP
label | ee7f1c14-5644-50d6-995e-a50f93bf78f5 |  | note | Responsibility: Site Engineer
text | 51641d0d-b68b-584a-ab31-662b2fc154ee |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.02 - Moisture content of surface to be primed.
label | 052bc761-4f92-533f-9c43-8aa4a9a7ac76 |  | note | Frequency: Immediately prior to application of primer.
label | 689d19f6-291b-562b-96b1-4eac2003ac7e |  | note | Acceptance Criteria:
label | 35a7843f-ecba-5e67-bad0-c8a454d0ea32 |  | note | • The prepared surface is dry and the moisture content within the top 25 mm of the base material is 2% or more below the Modified Optimum Moisture Content.
label | ddd4817e-c907-550a-b656-c0ac952a52c2 |  | note | Reference Documents: GHD-DD-SPC-002 5007
label | 49fe9d80-c65c-5635-960a-fa33f23cfb24 |  | note | Inspection/ Test Method: AS 1289.5.2.1
label | 9cfcbfb6-bad2-5aba-b0d6-950a41f86e52 |  | note | Record of conformity: ITP
label | cecd5c4a-9871-5577-bc49-b3d1400d1059 |  | note | IP
label | cd6aed02-9093-53e0-aff2-34c1c71cfef0 |  | note | Responsibility: Site Engineer
text | e086b83c-8694-5dc4-85b1-7fb5d56aa3c8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.03 - Weather conditions.
label | 78467eee-8118-5d59-bb45-e89b2f79f43f |  | note | Frequency: Immediately prior to application of primer.
label | b29b6c13-85eb-5150-a7da-12327102a4ba |  | note | Acceptance Criteria:
label | 188c2036-0794-5017-82f1-cc82bec0744f |  | note | • The pavement temperature is in excess of 15°C and is likely to remain in excess of 15°C during the entire priming operation.
label | 05d8db70-52f4-5f6f-a868-ff3dcf12665e |  | note | • The surface is not moist or wet, it is not raining, and rain is not imminent.
label | 3b09f296-650e-5101-8c07-0235e5954f8f |  | note | Reference Documents: GHD-DD-SPC-002 5008
label | bd0904b2-9a95-544d-999b-f7c3e9727d62 |  | note | Inspection/ Test Method: Inspection
label | 2bd585cd-835d-57ed-a5a3-7938205ad8c2 |  | note | Record of conformity: ITP
label | c6ed752a-abee-5b23-9366-540e4d297668 |  | note | IP
label | d8c22e5e-5d55-5736-96ee-b17078dc5cf4 |  | note | Responsibility: Site Engineer
text | 4bbf4965-0a08-5946-b582-328971ef916d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.04 - Temperature of primer.
label | 55120a6d-7478-52c8-8d7e-a8732b240766 |  | note | Frequency: Immediately prior to the commencement of each spray run.
label | 9d326856-c4ad-5513-a7e3-dcb1b98ff2bc |  | note | Acceptance Criteria:
label | f9972178-06e6-54ef-b2bf-646270068854 |  | note | • The temperature of the primer is at or above the temperatures specified below and has been recorded:
label | 094fead1-9334-5fd5-b44e-0597216f3e12 |  | note | – AMC00: 10°C
label | d954751f-4f89-5f88-ae9c-3a440e7a43cc |  | note | – AMC0: 35°C
label | b85c1285-4fa5-5641-ba1c-3871d4bb557d |  | note | – AMC1: 60°C
label | 7e80ff88-175b-56a6-a0a3-b4ff8713e1fc |  | note | Reference Documents: GHD-DD-SPC-002 5010(a), Table 5010-1
label | 825189f6-29df-5642-a69e-c7be8f610522 |  | note | Inspection/ Test Method: Thermometer
label | c7a272ff-17d1-5be8-ab3a-6b965624af0f |  | note | Record of conformity: Spray run sheet, ITP
label | 46e78b8d-d05f-51b7-becc-6efd14bdd67b |  | note | IP
label | f8f2b597-24ab-5e9e-9a58-2f4fbc8d9092 |  | note | Responsibility: Site Engineer
text | a3f5cc7a-2cb1-5a77-a302-f3e9e64f77fc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.05 - Spray nozzle check.
label | 0d391f48-9735-5aa0-9834-42198ea0e857 |  | note | Frequency:
label | 295d5a2b-9441-5d42-b6a2-e0b6c055ec9a |  | note | • Upon filling or refilling the mechanical sprayer with primer and prior to commencing or recommencing spraying.
label | 01a8f484-9ad3-5df6-89ee-428e053ba150 |  | note | Acceptance Criteria:
label | 75cf5c90-fcb2-5c57-8632-a3aaad130e7a |  | note | • Spray nozzles are working correctly and distributing primer evenly when tested on an area other than the pavement to be primed.
label | 8786b378-3a32-5fdb-8bba-acee3b0d1597 |  | note | Reference Documents: GHD-DD-SPC-002 5010(a)
label | 6f6972ae-43e4-571b-96b7-26940e4c1bd3 |  | note | Inspection/ Test Method: Inspection
label | 463d95d1-7bc4-59d4-84d1-83e665a41803 |  | note | Record of conformity: ITP
label | aed8be55-9fa2-5634-bf86-7b654705d90b |  | note | IP
label | bf2979aa-09b6-51e3-9cd4-c2af55e4c453 |  | note | Responsibility: Site Engineer
text | 024a340b-de51-5133-9f9d-3c308bbf33c7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.06 - Marking up.
label | c2f03cd8-d30a-5855-aab4-a89c5794488a |  | note | Frequency: Before each spray run.
label | 3206794d-c1a0-520a-9104-95015497623b |  | note | Acceptance Criteria: The pavement to be primed has been marked with paint to indicate the line along which the sprayer will drive.
label | ddf2e7bd-72ec-5f34-bc1d-a9cfeddd1c5c |  | note | Reference Documents: GHD-DD-SPC-002 5010(a)
label | c2f5f648-fe9f-5a0d-9538-6603ce7a3fc5 |  | note | Inspection/ Test Method: Inspection
label | c80ce460-0ca4-59a8-a0a8-4da32a896b0c |  | note | Record of conformity: ITP
label | f6ac62e6-53a2-5a4d-885c-ccb99dbf6d35 |  | note | IP
label | c75aa58a-2c87-5c25-ae94-a52bfc854ab6 |  | note | Responsibility: Site Engineer
text | f1eb00ca-ce42-5436-8b03-cdd59d917319 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.07 - Application rate: cutback primer.
label | d0f79e29-eb3f-5ccd-823f-0bef5d736e47 |  | note | Frequency: Each spray run.
label | 7e63b674-80fe-50d4-bbc1-bc953b7f40fe |  | note | Acceptance Criteria: The application rate is 1.3 L/m2 of surface area, measured at 15°C.
label | 9644f249-8cf7-5488-a914-a665b3fcd2e8 |  | note | Reference Documents:
label | 90b3eaf1-a93a-50b4-88df-474c10281f45 |  | note | • GHD-DD-SPC-002 5010(b)(c)(d), Table 5010-2, 5013(k)
label | d7f7a254-af8f-50b3-afa8-dcf56847ed53 |  | note | • HP5010-1
label | 95f0c00e-c9f0-50e5-bf31-bd580a39c6db |  | note | Inspection/ Test Method: Sprayer dippings
label | 69586db3-f835-5f4c-9100-ff007680a530 |  | note | Record of conformity: Certificates indicating binder application rate
label | 247d3c74-ad83-5f9d-8e5c-4dae7fd4d835 |  | note | HP
label | d1c66390-b860-5a48-b423-c8e5cc99c165 |  | note | Responsibility: Site Engineer
text | db8c75ae-2bb3-57ed-aa3e-d009b935f4bf |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.08 - Application and spread rates: primer seals.
label | a0fe64f9-5c95-591a-9b91-a35e5da67091 |  | note | Frequency:
label | fba5f061-bb81-5f0f-855e-93150202ddcb |  | note | • After each spray run and before the commencement of any subsequent spray run.
label | 3f20616c-1883-57ac-bcb4-5527b8ad3870 |  | note | Acceptance Criteria:
label | 36ecd686-7d4c-56f9-bbe3-54f9a3683105 |  | note | • Dippings of the sprayer tank indicate an average application rate of primer on any spray run not less than 92.5% or more than 107.5% of the application rate specified in Note 2.
label | 448a3a14-a03f-544b-a14b-850600997cf3 |  | note | Reference Documents:
label | db7ce16f-6e81-5154-b9b5-2dab75d6551c |  | note | • GHD-DD-SPC-002 5010(b)(c)(d), Table 5010-2, 5013(k)
label | b8d141bb-719d-5d50-a308-5a081195e51d |  | note | • HP5010-1
label | 9f2c7514-8961-5904-a1c4-cfac58fb61c9 |  | note | Inspection/ Test Method: Sprayer dippings
label | a29ca0a4-eea2-5ef6-87c6-81d1fbd9b900 |  | note | Record of conformity: Certificates indicating binder application rate
label | 1969c2a7-cd6c-5d7b-91bd-33c43e5aedc1 |  | note | HP
label | ab32f965-dbd1-53af-b836-880f500e57b6 |  | note | Responsibility: Site Engineer
text | 2d6cbdb7-4eca-52b7-99e3-71de1222603c |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.09 - Location of spray runs.
label | 14c7a5ac-c59b-5cc7-8f3c-f2bd91bf502c |  | note | Frequency: Each spray run.
label | bce73fea-1dd9-5458-a960-6a2134fbdfcc |  | note | Acceptance Criteria:
label | ed3b198e-4e58-5573-96a5-da3926c72cb9 |  | note | • The location and date of each spray run, together with the actual average application rate of primer, is recorded on a plan of the works and in as-built documentation.
label | 0603b1d8-0a56-5b98-9940-3a1dbb24a65d |  | note | Reference Documents: GHD-DD-SPC-002 5013(l)
label | 2fff134a-14aa-5aee-a86c-bf5d2d38f7a3 |  | note | Inspection/ Test Method: Document
label | 900171a6-65c4-56ae-a095-e2c1ff23f0ca |  | note | Record of conformity: As-built documentation
label | 53478d22-35b4-5e75-a730-46dcdb458e57 |  | note | IP
label | 7b221e71-ea6d-5245-a7c6-8d92d76669c8 |  | note | Responsibility: Site Engineer
text | 0903b10a-6f2c-5707-bbce-328555f7382c |  | textbox | Date Completed:
checkpoint-no-status |  |  | checkpoint | Notes
label | 7ad583ae-ac1b-5070-9560-1514f85bcff8 |  | note | Note 1: Table 5003-5 Primer seal Aggregate Particle Size Distribution
label | e53ba69e-72d7-5d0b-a614-1ffc0f2717e6 |  | note | Note 2: Table 5010-2 Primer Seal Spread Rates
checkpoint-status |  |  | checkpoint | Final Inspection
label | 1c0dfe82-a11d-58ba-a7e1-3074fdf0516e |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 5ebbf0a8-fea7-5a7b-9be6-1b24ee0541a3 |  | textbox | Print Name:
text | e6a6e007-8eec-57d4-9745-e6a86cfe82dc |  | textbox | Position:
text | e06aca46-d976-5b34-97b5-c9e827528573 |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP012 - Asphalt Placement - Main Works | itp |  |  |  | Yes | ITP012 - Asphalt Placement - Main Works | 1fd2dc3e-26e5-4078-ab16-de8d008d3c72
checkpoint-group |  |  | section | 2 Asphalt Placement
checkpoint-status |  |  | checkpoint | 2.01 - Design of temporary ramps
label | c66c9ca6-4efd-5cf4-9e29-1231f02096ad |  | note | Frequency: Prior to the commencement of a shift.
label | f5cad097-7191-5613-a869-e2ead9d8c78d |  | note | Acceptance Criteria:
label | 8221c356-a18a-54f9-b97e-59547083f745 |  | note | Ramps are planned for all discontinuities greater than 25 mm in height.
label | c9955c70-4aaa-50a6-94a7-57a1e35c6172 |  | note | The maximum gradient is between 0.5% and 1.0% for discontinuities d50 mm in height and d0.5% for discontinuities >50 mm in height.
label | 0da81cba-0356-5858-b6ed-9a3db3b6ace3 |  | note | The distance between successive transverse ramps is not less than 60 m.
label | 2bea0202-0f84-5c2c-a1b8-9ab55a3047fe |  | note | Planned ramps on taxiways are no shorter than 4 m and have slope not exceeding 1.5% relative to the current slope.
label | c26236ef-50f7-5336-a4ed-f780cbd773a8 |  | note | Reference Documents:
label | be13fd41-3ca7-55ea-8f7c-fb353696701f |  | note | GHD-DD-SPC-001 5123(b)
label | 8122aace-6983-5aaa-a5d2-77e0bf8b9c83 |  | note | HP5123-1
label | a4421419-8827-5692-9a6f-f61005af3e4e |  | note | Inspection/ Test Method: Document
label | c9f7953e-980f-5099-86d4-b50a9d82cb40 |  | note | Record of conformity: Temperary ramp design
label | 09a28917-81a9-5df3-b0f7-552ab527a84c |  | note | HP
label | f0774910-04a1-566d-aeb2-4fa09944d9aa |  | note | Responsibility: Site Engineer
text | 851ff433-00b4-5bbb-bdca-db43cd93c0c9 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.02 - Commencement of asphalt placement processes.
label | b21cae73-8a15-571d-965b-cda9a68bbdb4 |  | note | Frequency: Prior to the commencement of asphalt placement works in each work period.
label | 74b360ac-9bef-5638-8ece-6fcf143d0134 |  | note | Acceptance Criteria:
label | a45bfb1b-2dae-53f6-ac69-6a488a69d03b |  | note | All paving plant tools and equipment including standby plant and equipment are in working condition and are free from leaks of oil water hydraulic fluid and fuel.
label | 452218b0-5e52-5121-a49d-8fb5ba01f68d |  | note | Tyres and tracks of all equipment are clean and any build-up of bitumen or other material has been removed.
label | 9b48d696-201d-5d4f-9dec-ba2f41aa75ce |  | note | Reference Documents:
label | 33f3945b-6c30-530d-8a1e-7b3cf8542126 |  | note | GHD-DD-SPC-001 5113(a)
label | 5b1a06a3-41d1-518e-978a-5de666ab6d0f |  | note | HP5113-1
label | 1edcee3b-15ef-5e6d-aee7-b0bd06351f7e |  | note | Inspection/ Test Method: Inspection
label | d6fc8dd9-67d7-5b13-96d5-acb5b3802a9d |  | note | Record of conformity: Daily plant inspection verification checklist
label | eafa8dd1-380b-50ff-b320-7db4633f3a4e |  | note | HP
label | ed4f9353-02be-5206-ad0c-33250af27ca5 |  | note | Responsibility: Site Engineer
text | 94b37148-c466-5722-837d-17ffe74c2733 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.03 - Weather conditions.
label | 4fd372d3-59ad-56ac-ab65-5bb302acbb67 |  | note | Frequency: Prior to the commencement of asphalt placement works in each work period.
label | 7e397713-a723-55ca-b898-278bc2d0576e |  | note | Acceptance Criteria:
label | 9e78d3e2-5ad8-5ef9-886b-fc96bbd98353 |  | note | Surface to be paved is essentially dry and free from surface water.
label | a03804d8-bda7-5e4b-84e8-463c93911068 |  | note | It is not raining and no rain is imminent.
label | d8754b6c-f839-52c8-98d3-074b3425d5e4 |  | note | The surface temperature is at or above the minimum specified in Note 1.
label | 25ae8611-350d-5864-9dd6-cbf55183b12b |  | note | If the surface temperature is <15°C the layer thickness is <30 mm or the winde speed is >20 knots the cold weather paving plan has been implemented.
label | 40f1855b-ccf7-520a-85d7-81ab9d6be266 |  | note | Reference Documents: GHD-DD-SPC-001 5115, Table 5115-1
label | 7fb6557f-dcc2-56c6-be83-31920a536221 |  | note | Inspection/ Test Method: Inspection
label | 5e0f7645-5f59-50cb-bded-35cf04d298dd |  | note | Record of conformity: ITP
label | 232423e1-9a08-5424-be55-6edafa092f22 |  | note | IP
label | 477935f4-e2d2-5e76-8b22-468c1ac103b8 |  | note | Responsibility: Site Engineer
text | cb9c368a-e4d3-57b0-87f8-cd0e9c5db0ea |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.04 - Surface preparation.
label | d2db862f-caad-5b03-b7f5-6c08c05df366 |  | note | Frequency: Immediately before applying tack coat.
label | ed83037a-5010-5f1e-af13-6bdb175115e6 |  | note | Acceptance Criteria:
label | 06457b46-7edc-513f-9f0d-260f25a208a2 |  | note | All loose and foreign materials have been removed from the surface to be paved to a distance of approximately 300 mm beyond the edge of the area.
label | e01e839f-6e80-549e-8689-4001c2ab332c |  | note | Any areas of oil or fuel spillage have been cleaned with detergent and flushed with clean water.
label | e0240b55-0d56-5bef-b4c9-ac5ec16e53c6 |  | note | Reference Documents: GHD-DD-SPC-001 5118
label | 9195990c-6b2a-54fa-81f1-8d28613e0499 |  | note | Inspection/ Test Method: Inspection
label | 88d3a7a9-9624-52df-8ee0-f53d4846aae2 |  | note | Record of conformity: ITP
label | 70c1c3b5-d809-53f3-9521-6f5ec52816d5 |  | note | IP
label | 8c1312d7-a13d-5e1c-b512-ac478e4e5192 |  | note | Responsibility: Site Engineer
text | 183efc11-3ae9-5877-8ec5-8dc7853abee8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.05 - Tack coating.
label | ea2f5415-d1ce-5198-800c-170176746f18 |  | note | Frequency: Prior to the commencement of asphalt placement in each work period.
label | 22171612-cc75-546c-91b0-606c9def4870 |  | note | Acceptance Criteria:
label | f8e573d0-3833-58b5-b3ab-5984dbdf10ea |  | note | A uniform cover of tack coat has been applied to all existing surfaces on or against which asphalt is to be placed, unless the surface is freshly placed asphalt not greater than 3 days old. Any vertical faces and edges have received 2 full applications. The residual bitumen is within the range 0.15-0.25 L/m2 and at least 80% of the surface has turned from brown to black. Any pooled tack coat has been brushed out prior to breaking. If proprietary tack coat is used, the viscosity and softening point of the tack coat is tested weekly at the point of manufacture, and a sample has been obtained from each delivery to site.
label | 6d102b2b-d564-55ef-ba05-cfd17ec0f652 |  | note | Reference Documents: GHD-DD-SPC-001 5119
label | 4b09871d-277f-500a-9a36-b265df318abc |  | note | Inspection/ Test Method: Inspection, AGPT/T111, AGPT/T131
label | be5f559d-f4d8-5471-b381-d3dbb3768035 |  | note | Record of conformity: ITP, NATA accredited test certificate
label | 41a99ecb-4c20-5cac-9aff-800eb0d0d120 |  | note | IP/TP
label | 2749e7da-4d70-5cfd-bebc-ebd0333ba291 |  | note | Responsibility: Site Engineer
text | 8d7e4266-a729-5a43-8dd4-57912c430225 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.06 - Commencement of paving.
label | 19f5a61f-2608-5666-b971-89ad880e8b03 |  | note | Frequency: Prior to the commencement of asphalt placement in each work period.
label | 3a6d4204-e386-53b9-a7c4-90ef98123c69 |  | note | Acceptance Criteria:
label | 1d53708a-a1ce-5fde-a46b-526277c0eff1 |  | note | All necessary surface preparation and treatments within the paving lane and adjacent paving lane have been completed and inspected by Contract Administrator.
label | 2042031a-c135-54d4-9b24-8740d8f1eef3 |  | note | Reference Documents:
label | 0f9f61fd-23a4-5582-99f1-e2f29554b6ff |  | note | GHD-DD-SPC-001 5120(a)
label | 0812b83b-8be4-55df-8899-9ad3a66459c4 |  | note | HP5120-1
label | 9795ac1d-f5c4-5fcb-9c88-2adeb760e289 |  | note | Inspection/ Test Method: Inspection
label | ac5c5ab9-5c56-56d3-97ef-0d6010b40847 |  | note | Record of conformity: ITP
label | 8560a8cf-da2f-5d4a-839e-acb9cf1d817d |  | note | HP
label | 7513c7b6-f163-5913-a5ff-9ee791a22618 |  | note | Responsibility: Site Engineer
text | d7833a8a-6591-5dae-8881-9d90ecfc602f |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.07 - Longitudinal joints.
label | 3a2a4a6d-d0bd-587a-9bd3-7146f53ae009 |  | note | Frequency: During asphalt placement works.
label | 6df412f9-d457-5726-802c-4b4c59bf796f |  | note | Acceptance Criteria:
label | 12cdba7b-8c4b-5b6d-8dc8-5e523b71a615 |  | note | Cold joints are kept to a minimum.
label | 946a9787-ae83-5e7a-9681-a410bbbdc959 |  | note | All joints are smooth true dense free from segregation and have the same texture and smoothness as elsewhere on the finished surface.
label | 9f84e9bb-64ac-509c-abcc-a75af0205c83 |  | note | Reference Documents: GHD-DD-SPC-001 5120(d), 5122(a), 5124(e)
label | f95fe758-f74b-5342-ae9e-e5e7dc6043a5 |  | note | Inspection/ Test Method: Inspection
label | 3bb5f80d-faec-5890-b9c6-f48daa44ebb8 |  | note | Record of conformity: ITP
label | 8c4b8acf-0c7a-5373-b54d-4026c910870a |  | note | IP
label | 0f625187-60d7-5c47-ba4a-98eb70388356 |  | note | Responsibility: Site Engineer
text | 0733edee-82be-5cce-8b00-7824405b1833 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.08 - Delivery of asphalt.
label | 70872344-0b66-59ee-977c-b08b8b80cc21 |  | note | Frequency: Each load of asphalt delivered to site.
label | 1640fad7-6f39-56aa-906d-f9b2f3125acb |  | note | Acceptance Criteria:
label | 1d95e8e6-0935-5db5-bb5d-176d49918406 |  | note | Asphalt temperature is ≥140°C for PMB or e150°C for residual C320 at point of delivery to paver.
label | bf7c5ca8-893d-5b2e-ba41-d247dafeb143 |  | note | Load does not contain cold unworkabout material is not contaminated with foreign material and has not been wetted by rain.
label | 9b0c2047-c836-5c38-8e34-195cb3832825 |  | note | Reference Documents: GHD-DD-SPC-001 5117(c) Table 5117-1, BecaCPL-CONTIN-000104
label | 7e600b3f-e9d8-568b-a75b-085e14ecc1a0 |  | note | Inspection/ Test Method: Inspection, infrared thermometer
label | ed027ffe-1940-53f0-ba90-0efc4302ff72 |  | note | Record of conformity: ITP
label | 285cd6d4-217c-519e-8ed3-a0b5de133111 |  | note | IP
label | 96fcac0d-e192-51dd-a9f2-274b4ea66137 |  | note | Responsibility: Site Engineer
text | 94404e21-afea-515e-bc3e-f5f5ddcd6bc6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.09 - Layer thickness.
label | efefe422-6f27-5a93-b04e-4562614abe1d |  | note | Frequency:
label | 1941b33d-3927-55f3-9f9d-b5a60625e206 |  | note | During asphalt placement works at intervals not exceeding 10 m (except at the commencement of transverse joints where the interval must be not less than 5 m).
label | 9c2c70b4-6a8c-5467-8c26-cc9ca4528881 |  | note | Acceptance Criteria: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications.
label | a85fce3a-b8db-5a4d-8fa8-009044d19716 |  | note | Reference Documents: GHD-DD-SPC-001 5120(b)
label | 5d35ee70-4d20-5446-94d1-0a70bcfe0809 |  | note | Inspection/ Test Method: Dipstick and ruler
label | 8121ea2d-3ca7-58f0-a0d9-9c88e0ed1e7e |  | note | Record of conformity: ITP
label | b3f6e53f-0e53-5682-bb61-924e0baa2817 |  | note | IP
label | 5ffc4880-e31c-565b-a102-a35b778b5065 |  | note | Responsibility: Asphalt Foreman
text | c0e0eecf-ef13-5536-93ac-9ab96e64f45a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.10 - Compaction with vibratory steel wheel roller.
label | 4fdc016e-9eaa-56cc-a0e7-584cfc1d0e53 |  | note | Frequency: During asphalt placement works.
label | b2841f53-af89-5df1-9709-a45a94912cec |  | note | Acceptance Criteria:
label | 0c001843-8357-5aaa-83bc-0dfa0c98af18 |  | note | The temperature of the asphalt mat is ≥110°C for PMB or e95°C for residual C320 at the commencement of rolling with steel drum roller.
label | 22bfb8fd-729d-5d98-9446-ac5f49348a9a |  | note | Rolling is conducted as per defined rolled rolling pattern. The number of roller passes applied to each paving run has been recorded.
label | 7a7b0eaa-42ca-57e6-ade3-559a00085692 |  | note | Reference Documents: GHD-DD-SPC-001 5121(b), Table 5121-1, BecaCPL-CONTIN-000104
label | e1e8b329-356b-58a6-ac36-e99144a9a0b0 |  | note | Inspection/ Test Method: Infrared thermometer
label | 7b85b2e9-1dd6-5864-98e2-6ba2496213ee |  | note | Record of conformity: Shift report, ITP
label | 93866990-929c-5d6a-bf3d-2bc0572b5669 |  | note | IP
label | 15124ae5-d7d6-50c7-9967-c90b408b450a |  | note | Responsibility: Site Engineer
text | 93c821b8-c0eb-574a-ac23-89a842556b9e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.11 - Compaction with pneumatic tyred roller.
label | e172b56c-dec2-598c-9aa4-c424bbb10a78 |  | note | Frequency: During asphalt placement works.
label | e6111a76-d003-525d-9ffe-46acc387f9d9 |  | note | Acceptance Criteria:
label | 6929ad01-1529-5159-b82f-a1f804a68e3c |  | note | Six (6) roller passes are completed prior to the temperature of the asphalt mat falling below 85°C for PMB or 70°C for residual C320.
label | 00b2b6ba-44a1-5422-8082-00f884c01f39 |  | note | Reference Documents: GHD-DD-SPC-001 5121(b), 5121(f) Table 5121-1, BecaCPL-CONTIN-000104
label | 68c543bc-63fb-5942-a6d7-c0e460e150d7 |  | note | Inspection/ Test Method: Infrared thermometer
label | c07b7d0f-c050-5a13-94fd-db05ffaabcf3 |  | note | Record of conformity: ITP
label | 94f40d30-9845-5273-8fc7-969b85a9cce3 |  | note | IP
label | 82e70d06-88c1-5381-b2db-6984362ffdeb |  | note | Responsibility: Site Engineer
text | 608c2a28-d8c0-5313-b2d9-5a36eafea9c5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.12 - Finished layer thickness.
label | e15b03e3-06fe-54e7-9f7c-212205997534 |  | note | Frequency:
label | f7b4130b-bb81-527f-b081-f7faf8fddcd8 |  | note | As soon as possible or within one working day after the completion of asphalt placement works in each work period and prior to the next work period following completion of the course.
label | b8f238ea-0b13-5c97-9a97-4eac9f30246b |  | note | Acceptance Criteria:
label | 16c7d61a-81de-51aa-9cba-2377fca1bef3 |  | note | The average thickness of a nominal thickness layer is not more than 10% above or 6% below that specified and has no part less than 85% of the specified thickness.
label | 71afb45c-8799-50b7-9d16-a5ee13b18180 |  | note | The thickness of a variable thickness course complies with the specified finished surface levels.
label | 0e87537c-1ce8-56ff-9a8f-9d1bdad48175 |  | note | The average compacted layer thickness of a minimum of 4 cores is within the accepted range of:
label | 29f1cd72-191b-5e78-a84d-8d6c14a4eb04 |  | note | Minimum of 40 mm and maximum of 85 mm for 14mm NMS asphalt, or
label | 2ea37520-7837-5e4f-9ba9-d6d4f2849de4 |  | note | Minimum of 75 mm and maximum of 110 mm for 20mm NMS asphalt.
label | 5e913462-0545-541c-918a-3fb5e1e30b29 |  | note | Reference Documents:
label | 1135a3c2-99ba-57f4-9772-c156c30805bb |  | note | GHD-DD-SPC-001 5124(b)
label | a9706a4a-106f-59d1-a16a-63b43df9809c |  | note | HP5132-1"
label | ef261d29-2b02-59c5-a692-3514918e1b35 |  | note | Inspection/ Test Method: AS 2891.1.2
label | 489de956-0403-5765-8e1d-1fd7fe75d559 |  | note | Record of conformity: NATA accredited test certificate
label | da971e5e-7e3e-550e-bad3-e48f5c52158f |  | note | HP
label | b165f1ea-f790-52b6-952e-efea9cba5c08 |  | note | Responsibility: Site Engineer
text | d8c0766e-c54b-559c-ac4a-ff2d0dcf3e5c |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.13 - Finished surface level.
label | 084c03bd-5c29-5853-aaed-63b03593b629 |  | note | Frequency:
label | 19d8992a-9554-57ee-96ab-5c3a611d7cee |  | note | As soon as possible after the completion of asphalt placement works in each work period and prior to the next work period following completion of the course.
label | f255fa36-6906-566c-ab0e-8a64812b015a |  | note | Record of finished surface levels to be submitted to Contract Administrator within one (1) working day of the completion of the level survey.
label | 1606bba3-aefe-5d2f-aeb4-ee61a93db100 |  | note | Acceptance Criteria:
label | ce9ba8cf-aed9-5095-92a0-f333de897fae |  | note | The finished surface coincides with the surface of abutting pavements except where rolled over edges are specified.
label | 781ad87a-b836-58b5-b911-fd846c14c39f |  | note | The finished surface level is not more than 7 mm above and 5 mm below the design finished surface levels shown on the Drawings.
label | 371c5d04-da19-5a4d-9637-b94cf1d010a9 |  | note | The absolute difference between the design surface level and the final surface level between two adjacent survey points in the longitudinal direction is not be more than 7 mm.
label | 3824ba0d-33a7-58d6-923c-1de613c61064 |  | note | A compliance rate of 97.5% of all the survey points has been achieved and no deviation in excess of 10 mm has been measured.
label | afb20b4e-a934-5966-bbdb-f8e7a783874a |  | note | Reference Documents:
label | 19a23c6e-92db-586a-b837-1838e6029509 |  | note | GHD-DD-SPC-001 5124(b)
label | c662f7c6-8d9b-5b40-938b-a41e3ca404c3 |  | note | HP5124-1 HP5132-2
label | e511ea7e-22f2-54b2-a695-f90bca535656 |  | note | Inspection/ Test Method: Inspection and survey
label | ae263a78-7ae9-5049-81a9-a8f54e2c1a88 |  | note | Record of conformity: Record of finished surface levels
label | 09a85853-ad71-53d5-8d25-18a7bafc9dc3 |  | note | HP
label | ec69d57a-a967-535f-992c-139279f7d37f |  | note | Responsibility: Site Engineer
text | fe6b2040-4f28-51c8-94b1-10ac0e8ff23f |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.14 - Surface smoothness.
label | 03aa69e6-71c8-5d89-a059-f407625a5a3b |  | note | Frequency: After completion of compaction of asphalt with a pneumatic tyred roller and prior to back rolling.
label | 9a2515c4-7098-53d9-a4aa-1470b73a255c |  | note | Acceptance Criteria:
label | d7ada400-4bbd-541c-a665-868125c06e3a |  | note | The finished surface of all asphalt surfacing courses does not deviate from the testing edge of an approved 3.5 m straight edge by more than 3 mm (longitudinally) and 5 mm (transversely) on aircraft pavements and 5 mm (longitudinally) and 7 mm (transversely) on shoulders.
label | dd0bb433-5427-5408-99d6-be03e0f20b3c |  | note | Reference Documents:
label | bad9d602-03be-5aea-aa37-2e72b6abb79d |  | note | GHD-DD-SPC-001 5124(c)
label | a3d581f4-acb6-5a9b-bb53-bc4dbcd9e383 |  | note | HP5132-3
label | 347c6bcc-6191-53be-957b-2a62804ecd83 |  | note | Inspection/ Test Method: Straight edge
label | 467cfa88-06db-5dc0-a715-b0367946fc29 |  | note | Record of conformity: Record of location and extent of any surface irregularities
label | 125470b4-c136-5ebf-9614-9ce1bc96723c |  | note | HP
label | c435cee5-f14f-55a1-a932-1ecff3482d29 |  | note | Responsibility: Site Engineer
text | 3c27f260-ae40-5701-8c12-107791833d1c |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.15 - Finished surface appearance.
label | b3dc4c78-78a8-5d58-8578-b9a10b682db8 |  | note | Frequency: As soon as possible after the completion of asphalt placement works.
label | e6333a7e-99f3-5a1d-89fc-74350a6ec506 |  | note | Acceptance Criteria:
label | e175b735-51c3-5324-9503-8549cc938add |  | note | The finished surface is free from roller marks vertical discontinuities dragged areas cracks segregation open textured patches and has a tightly bonded closed surface of uniform appearance.
label | 5d63f481-e3e3-5d78-94b6-afdde5a15863 |  | note | Reference Documents: GHD-DD-SPC-001 5124(d)
label | 5e23b9f2-254c-5f3a-8793-40fd1a230efc |  | note | Inspection/ Test Method: Inspection
label | 86e40e5c-ca93-5610-80e5-34919ef7f2a5 |  | note | Record of conformity: Shift report, ITP
label | 731f4ade-9338-54d8-902a-72bda7a2321c |  | note | IP
label | 0b9aa91f-cc46-559f-885b-ae2224e4bf94 |  | note | Responsibility: Site Engineer
text | 7c5da4fb-128d-57de-a573-9bbd9681ba3c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.16 - Pavement cleaning.
label | 1a7acebc-657d-5e6d-9393-a0848f1e7d5d |  | note | Frequency: Not less than 60 minutes prior to the scheduled time for opening pavements to aircraft operations.
label | 8a85fdb5-71c0-58ee-ba3d-67abb8f16071 |  | note | Acceptance Criteria: Pavement surfaces are completely free of all loose material.
label | 003269d4-6e56-5e86-8f0d-014833575b49 |  | note | Reference Documents: GHD-DD-SPC-001 5126
label | e68bb4c9-364a-51ff-86c5-41fcc0779232 |  | note | Inspection/ Test Method: Inspection
label | a61f8afa-29e5-565c-ba2e-e2526d1666c5 |  | note | Record of conformity: ITP
label | 1f3bbc9e-ca8a-5100-a9e4-65583d286728 |  | note | IP
label | b4e68586-b0cc-52a4-a25d-91cc92960540 |  | note | Responsibility: Site Engineer
text | 7d1c989d-3332-5033-8b1c-dd6732619dbb |  | textbox | Date Completed:
checkpoint-group |  |  | section | 3 Compaction Testing
checkpoint-status |  |  | checkpoint | 3.01 - Extraction of cores.
label | b8efd54b-13af-58c1-a374-f7f4c3dd5a56 |  | note | Frequency:
label | 6c71d352-2a1f-5842-a64d-a84b5dbfdc47 |  | note | At the completion of asphalt placement works after the asphalt has cooled to ambient temperature throughout and not more than 24 hours after the lot was constructed.
label | 6d9247ae-742b-5dc7-9192-30268ccbdca6 |  | note | Acceptance Criteria:
label | 92f4222d-1353-5ba8-8081-6eb32f4a176f |  | note | From each lot of aircraft pavement cores are cut at a rate of not less than one core per 500 m2 or a minimum of 6 cores within lanes (whichever yields the greater number of cores) and not less than one core every 150 m of joint or a minimum of 4 cores on joints (whichever yields the greater number of cores).
label | e07805b4-5127-5d83-94eb-aea4b0d9c62f |  | note | Cores are not less than 100 mm diameter and are cut from the finished lot after the asphalt has cooled to ambient temperature and not more than 24 hours after construction."
label | 29bc2b93-f929-5adc-aa93-d1cd0513e7c6 |  | note | Reference Documents: GHD-DD-SPC-001 5111(c), 5132(b)
label | 1dfe6e95-659e-5f03-9859-2b57e360b89e |  | note | Inspection/ Test Method: AS 2891.1.2, AS 1289.1.4.2
label | 34c024db-a224-567b-a2a9-eef057385d4b |  | note | Record of conformity: ITP
label | d9069427-c17e-53bf-b5c0-3a6500c35942 |  | note | IP
label | eb41380f-873d-5731-8eb6-5b873c9b2f00 |  | note | Responsibility: Site Engineer
text | c35a5b9d-6179-569f-acec-1525255157b9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.02 - Repair of core holes.
label | fde1d782-ea8f-5341-a7a5-b2fbe90c500e |  | note | Frequency: At the completion of core extraction.
label | 49f7540d-6d31-553e-a2a6-09bfe55038ef |  | note | Acceptance Criteria:
label | 4a6e7965-4fe3-5f3a-a7d8-38c4cb7908fe |  | note | All debris slurry and water has been removed from the core hole and the core walls and floor are completely dry prior to reinstatement.
label | d7a2cb32-0f5f-5511-bf77-4aa1317158a0 |  | note | Tack coat has been applied to the walls and floor of core hole and the hole reinstated with hot mix asphalt approved for use in this project and placed and compacted in lifts not more than 50 mm compacted thickness.
label | 6e4abff2-aba9-54de-bc9f-abb358dcb63f |  | note | The filled hole is flush to the surrounding pavement surface.
label | 30eed1e4-890d-5966-9568-4a236e2ab891 |  | note | Reference Documents: GHD-DD-SPC-001 5111(c), 5132(b)
label | ce58142f-1fdd-5cbb-b0f4-3ebcbf8661f9 |  | note | Inspection/ Test Method: Inspection
label | b5b1bd49-f2e1-5f41-9101-bebc802220a0 |  | note | Record of conformity: ITP
label | c83fbde2-7288-5743-bbde-6ffe15c61e67 |  | note | IP
label | 4c65421e-01c8-5d7e-b7cc-3603f5838dd0 |  | note | Responsibility: Site Engineer
text | ca13aec8-01ea-5b7f-b34c-06b9b571e7c9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.03 - Compaction testing.
label | f08c59d8-b5d1-5c05-93f5-9f0959beee70 |  | note | Frequency: Within 24 hours after the construction of the lot.
label | 6316ae9e-23e1-55b6-878c-e623e1e0ef3f |  | note | Acceptance Criteria:
label | a3ca5fe0-2337-5953-bef0-1af86a9647b9 |  | note | Characteristic value of air voids are within the range of:
label | 517103dc-a3c2-56a5-85d2-01968417a340 |  | note | Surfacing layers: 3.0-6.5% inclusive for mat and 3.0-8.0% inclusive for joints, or
label | 8e66874e-9ad2-5f77-b596-bcd852fa2bb1 |  | note | Base layers: 3.0-7.0% inclusive for mat.
label | 700da85a-1b54-5917-917e-22e2b351c5f0 |  | note | Reference Documents: GHD-DD-SPC-001 5111(c), 5121(c), 5132(c)(d)
label | 03fde7c0-d7b5-588e-8fa9-858f8f9bae3b |  | note | Inspection/ Test Method: AS 2891.14.2 (mat locations) or AS 2891.9.2 (joint locations)
label | 432a20b2-061c-524a-9a59-43249c802946 |  | note | Record of conformity: NATA accredited test certificates
label | 39e987b2-3331-5325-9bf4-da5a3eb8e164 |  | note | TP
label | 5218d8f0-d552-5763-a608-d9d273ff25c8 |  | note | Responsibility: Site Engineer
text | 2784b427-9783-5a9f-ba1c-ba4d04a48c0e |  | textbox | Date Completed:
checkpoint-no-status |  |  | checkpoint | Notes
label | 32709450-1dc5-5f2d-9447-a723f1f0685b |  | note | Note 1: Table 5115-1 Minimum Surface Temperature for Asphalt Placement, BecaCPL-CONTIN-000104
label | be15b86e-bfc5-5c73-a0d8-e6c62668df9c |  | note | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
label | 77995e25-cb0a-554e-8def-b77d7e9afc5b |  | note | Target layer thickness (mm) ¦¦ Minimum surface temperature for asphalt placement (°C)
label | fe869c2e-a2cf-533b-9115-dcf82e55308b |  | note | C320 and M1000/320 multigrade bitumen :: Polymer modified bitumen
label | 5d518494-f7c5-5f1b-9c6f-c645515dbd88 |  | note | < 30 mm ¦¦ 20°C :: Specific procedures and an additional roller required regardless of pavement temperature
label | 48d5f257-15a5-573b-b764-7a8567b61786 |  | note | 35 mm ¦¦ 10°C :: Specific procedures and an additional roller required regardless of pavement temperature
label | ae9a3cca-539d-5c01-9499-a548dfc12ec6 |  | note | 40 mm ¦¦ 2°C :: 20°C
label | 48247fd4-b9ab-595e-924e-7d011846ef8e |  | note | 40 mm ¦¦ 2°C :: 20°C
label | 9974d58b-6049-56f1-9656-850798e346ac |  | note | 45 mm ¦¦ 2°C :: 10°C
label | 7aabe0a5-c7b4-5c0a-9b47-56b63525a717 |  | note | e 50 mm ¦¦ 2°C :: 2°C
label | 0dcaced0-7db4-52b4-860b-cecbd94c0fc1 |  | note | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
checkpoint-status |  |  | checkpoint | Final Inspection
label | d1ca8b5c-f33b-5fb3-9310-772df153c35e |  | note | The signature below verifies that this ITP has been completed in accordance with the FHs Quality system Procedures and verifies lot compliance with specifications.
text | f8c7ab4d-356b-5468-aeca-5a577fd3d155 |  | textbox | Print Name:
text | 8fde444d-bc49-56ce-80b9-47d040d444ea |  | textbox | Position:
text | ae0b6113-62de-56dc-9e42-197f7bffa021 |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP002 - Stripping, Bulk Exc, Fill and Subgrade Prep | itp |  |  |  | Yes | ITP002 - Stripping, Bulk Exc, Fill and Subgrade Prep | 427e7b74-c12e-4f9b-8149-bda0d88529b3
checkpoint-group |  |  | section | Preliminary Activities
checkpoint-status |  |  | checkpoint | 1.1 - Inspection and Test Plan
label | f6244a74-88d1-5d0d-bc84-b46733f7106b |  | note | Frequency - Prior to commencing works
label | 8aed7d3a-3eb3-5ac3-92ff-d5dea5f40e6e |  | note | Acceptance Criteria - Hold Point The Contractor must submit an Inspection and Test Plan to the Principals Representative for review, outlining the tests, frequencies of tests, certifications and Hold Points
label | 6240eaac-d1ba-5891-8bb2-82a481b43c1b |  | note | Inspection/ Test Method - Verify
label | 3a658c65-2b42-59e6-9005-b0ce198944eb |  | note | Record of conformity - This ITP signed
label | cbc2fa8e-9b0e-532f-8aa5-b1e52a3b19a9 |  | note | HP
label | f05bf0e8-948f-5b25-b81d-fc949e9cb40b |  | note | Responsibility - Project Engineer/ Principals Representative
text | a3a95746-54b2-5dd8-89b0-dc6439c84d3b |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.2 - Current Drawings being utilised
label | f8df6eee-287b-5e8b-b95e-cce5fb438f3f |  | note | Frequency - Prior to commencing works
label | 94579cb3-649b-5181-9a6d-c65ba2d2799b |  | note | Acceptance Criteria - Current revision drawing is being used including the subcontractors copy. Current Revision to be obtained via Aconex
label | 2f1ed0cf-b7ad-53a1-8b7c-62a9620a638e |  | note | Reference Documents - Aconex
label | aa39c52b-a29a-54dc-9a4d-554807e24aff |  | note | Inspection/ Test Method - Visual Inspection
label | 198b219c-7392-54b6-8f64-665d48089e6f |  | note | Record of conformity - This ITP signed
label | a58969e8-7b0b-55c0-bdde-c51192b5743f |  | note | IP
label | 3006dfde-1f56-548b-b593-d3e25ad47467 |  | note | Responsibility - Project Engineer
text | 73f9e000-b762-528a-a8fa-3a631dcc439e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 - Survey
label | 3a19b86a-2f76-50b4-b875-fe122ae248dc |  | note | Frequency - Prior to commencing works
label | a39bdb2d-eea7-54b2-af70-b0d9b1dff42b |  | note | Acceptance Criteria - Area has been surveyed, highlighting any areas where excavations should not occur (e.g. exclusion zone)
label | 6822302a-4dde-5216-8d27-860d7736c682 |  | note | Reference Documents - Drawings Permits
label | 1baab3f9-a89e-564f-ae87-77a14f06d04d |  | note | Inspection/ Test Method - Visual Inspection
label | fd0618b1-ebc2-5463-94d4-7ff8dee2201d |  | note | Record of conformity - This ITP signed
label | a261bb21-faf5-5eaf-9c31-7dde969bad43 |  | note | IP
label | a016ad59-8ba4-56ea-ad0c-2fc6a3d3b057 |  | note | Responsibility - Project Engineer
text | 08e9857e-fe95-5a05-9710-ca192d610764 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 - Native grass
label | 48a4e9bb-c14a-5f4d-9ea0-ac37e0d62b2d |  | note | Frequency - Prior to commencing works
label | d30a2bd3-e6e5-54be-aa1c-2b9a542a79d6 |  | note | Acceptance Criteria - APAM to confirm native grass permit. Surveyor to mark out the native grass area and place bollards/fencing along the boundary.
label | 7d24543c-30f4-592d-82f4-e9f897a916c4 |  | note | Reference Documents - EMP Native grass ITP No.29
label | 8433a4eb-3214-56d2-be35-bd6b3b423d06 |  | note | Inspection/ Test Method - Visual Inspection
label | 8b4f907b-54c7-5456-9913-2cd8558434dd |  | note | Record of conformity - This ITP signed
label | 2edfb0ad-9c04-540d-80be-3c047cf8d2c7 |  | note | HP*
label | 62594bdb-0894-527c-98a1-611ebfe4cc30 |  | note | Responsibility - Project Engineer
text | 55f20b9b-a9ff-5614-a13e-7a2a26ac702f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.5 - Implementation of all measures and controls
label | 6dd6d704-7a39-5fde-8a4d-d531200f236d |  | note | Frequency - Prior to works
label | e3683ce2-91aa-5b07-8dde-f8d860d30b45 |  | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS and WP
label | 01094ea3-c0f8-5123-99d1-fbb97791db67 |  | note | Reference Documents - PSP, EMP, TMP, SWMS, WP
label | a8437edc-f5a8-5da9-9969-b074296a10a1 |  | note | Inspection/ Test Method - Visual Inspection
label | 426fe64e-50ec-539b-8527-9a33e8755a70 |  | note | Record of conformity - This ITP signed
label | 6479fc70-c962-5075-bed9-c113dff5d803 |  | note | HP*
label | b72f6079-3a21-5960-b37b-028031cdcea8 |  | note | Responsibility - Project Engineer
text | 3ef9ee65-28ea-5395-9def-48c8dfc2419d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.6 - APAM permits
label | 17d1d11e-b603-5b9e-8d33-83769820c0d4 |  | note | Frequency - Prior to commencing works
label | c6ab6f4c-d84d-5be7-8fc3-b3cf166ec188 |  | note | Acceptance Criteria - Excavation permit and if working near HV electrical. An Electricity supply Isolation form and cabling permit has been issued from Melbourne Airport Fulton Hogan Excavation permit issued to plant operators prior to excavation works
label | ae959147-34d5-5789-a219-d79b76abf303 |  | note | Reference Documents - Excavation permit
label | d0a5129c-a5ba-59df-bc95-c1324adcf777 |  | note | Inspection/ Test Method - Approved permits
label | 440bae51-9c56-5d25-ad44-06f768b0ebbd |  | note | Record of conformity - This ITP signed
label | f2493058-bcc3-5373-8ed1-275af52b6064 |  | note | HP*
label | 3affde3c-531a-5da6-98b7-e1c7db665d3a |  | note | Responsibility - Project Engineer
text | 95f0770d-a8d4-5f2c-ae87-ec994e7cea89 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.7 - Maintenance of Pavements
label | beddc1b1-a7af-53d4-adae-8ebaa9c7fd7b |  | note | Frequency - Prior to Commencing Works
label | c7958d5c-ebb6-5791-9d74-dc6a47b5023e |  | note | Acceptance Criteria - Hold Point Prior to the use of any existing roads within the airport boundary and site access roads, the contractor shall carry out a site inspection and provide a dilapidation report.
label | c566430a-29b1-5731-b938-890a614670b0 |  | note | Reference Documents - Aconex
label | eb19be34-125b-58db-8098-69a5355da6fe |  | note | Inspection/ Test Method - Verify
label | b1511a0f-dc68-5f6f-9470-a2ed07742e25 |  | note | Record of conformity - This ITP signed
label | 36e4dd7b-bcd1-5fa1-a268-7659b80bb06e |  | note | HP
label | 21786b56-e949-5793-b9a8-db0474eb9526 |  | note | Responsibility - Project Engineer/ Principals Representative
text | 54cd5293-c95f-5028-9ebf-b91ee4b778ba |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.8 - Drainage of Earthworks
label | db385ce8-eb7d-599a-84b7-e4670e6a389c |  | note | Frequency - Prior to Commencing Works
label | 390fd2e8-5fb6-5f5f-982e-da5aa4f14fee |  | note | Acceptance Criteria - Fulton Hogan to submit dewatering plan for each area of the works prior to carrying out any excavations for pavement design subgrade level. As safely practical the contractor must keep all earthworks free from standing water and must provide sufficient pumps at low points and other special dewatering equipment for the disposal of all water encountered in the excavations. Including the installation of any design or temporary drainage works to allow for preparedness of pavement construction.
label | b7c32022-66e0-511d-9c2c-0a5c1f276d7a |  | note | Inspection/ Test Method - Verify
label | 3627ce16-5e53-5f73-a515-3baa2d5f255f |  | note | Record of conformity - This ITP signed
label | 6ff5ed5c-246b-555c-b689-5035fca28299 |  | note | HP*
label | d4f0e805-dcd8-5ce0-9fca-2e13598ab515 |  | note | Responsibility - Project Engineer
text | 37f4a390-129e-5ab6-8477-eabed952c4d3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.9 - Plant and Equipment
label | b650e8ad-6e0d-544a-a716-893d0dbd8ed8 |  | note | Frequency - Prior to Commencing Works
label | 3647f8f7-9a4e-5673-8d4b-09b5512e56a6 |  | note | Acceptance Criteria - Plant and Equipment used in the works are appropriate to achieve specifications requirements. All plant inducted and inspected as per Fulton Hogans plant safety guidelines.
label | 08fd4fb0-f229-540c-bbb2-e3d3ad35a9e3 |  | note | Inspection/ Test Method - Visual Inspection
label | ca4e82a6-505c-5fd4-8dfb-f49fc32b195f |  | note | Record of conformity - This ITP signed
label | 0bbcfeef-6526-5df5-a9b5-6c1782265f03 |  | note | HP*
label | 7219da15-241d-55d5-842a-27c468c6a62c |  | note | Responsibility - Project Engineer
text | fd6237c1-e69d-5a24-a2e6-347b5d26dfcd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Stripping/Excavation to Subgrade
checkpoint-status |  |  | checkpoint | 2.1 - Site Preparation
label | 351c05f6-a3ad-5881-a3c5-ccc2b7159077 |  | note | Frequency - Each lot
label | 1a606b51-4e37-559c-88df-98ce3fa744a1 |  | note | Acceptance Criteria - All excavation and filling will be free draining to low points clear of the Works at all times; Sufficient pumps, well-points or other equipment for work area de-watered during the works shall be provided where required. Existing drainage lines and water mains found to be traversing the site must be removed as shown on drawings. Contractor must provide temporary pollution control devices or ponds in existing drainage systems and receiving waters.
label | e93aa5e1-2216-5c3d-a208-be0b644b05f3 |  | note | Inspection/ Test Method - Visual Inspection
label | f03e8491-0dba-5f63-977d-2bd0dfd77f61 |  | note | Record of conformity - This signed ITP
label | 135d3dfb-6d9b-5e5a-bcb4-a759c5c1c138 |  | note | IP
label | 13b3b5e0-0225-5267-8a2b-78a0372efcc1 |  | note | Responsibility - Project Engineer
text | 2a4bce63-c663-5394-b6cd-93c8a9fc8929 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Dust control
label | 33599175-82af-531e-802c-73486030115c |  | note | Frequency - Each Lot
label | 9c569a86-c643-5eb5-9f0f-cb47ac353e40 |  | note | Acceptance Criteria - Prevention of dust during earthworks and subgrade preparation (Water Cart, tarps etc.); Truck mounted water sprayer keeping dust moist to allow for reliable operation 24 hours per day.
label | a4ce34ed-8b0c-5715-920c-8931a0812c8a |  | note | Inspection/ Test Method - Visual Inspection
label | 05b95915-1561-52c3-a4d0-54eeb17dc981 |  | note | Record of conformity - This signed ITP
label | eb212a24-0584-536b-8d68-494ca31405ad |  | note | IP
label | 158c9ebb-a64b-530b-abe9-fd3c446ef1a6 |  | note | Responsibility - Project Engineer
text | fbe15c3f-c84a-564d-af01-dd1e711f4cf1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - Excavation
label | 92c7608e-906c-57fb-97a0-4ec7d500f149 |  | note | Frequency - Each Lot
label | d2c85328-51db-5b79-b2cd-5176d09d19ee |  | note | Acceptance Criteria - Contractor shall excavate every type of material encountered within the limit of earthworks to the lines and levels indicated on the drawings. Where over-excavation occurs or filling is required the area must be filled with Class 3/4 crushed rock or profilings. All materials removed from excavations are to be classified by the contractor as topsoil, fill, concrete (for recycling) or unsuitable material.
label | aacc83d0-2f67-5a4e-8d2f-8c5f5d5a6015 |  | note | Inspection/ Test Method - Inspection Point
label | 2d23f5f2-8e3a-56a1-be62-79325fce05c1 |  | note | Record of conformity - This signed ITP
label | 5b40fcd1-829c-55c7-8077-44d25510ec27 |  | note | IP
label | c0199fe8-e3e4-5a28-a2f9-01bfabece901 |  | note | Responsibility - Project Engineer
text | 3c5904f5-0da7-5a55-853f-95fbcaf17a00 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 - Test Rolling
label | 7f964682-60e1-5cd6-9612-2aa6360aeddb |  | note | Frequency - Each Individual Location
label | 0997744d-407b-5759-a2d0-f703b69d6a15 |  | note | Acceptance Criteria - Areas upon which fills are to be constructed, all layers of fill, and material within 150 mm of the cut floor level in cuts, shall be test rolled.
label | 869853f6-9ab0-5a03-9d8e-41bab86c314c |  | note | Inspection/ Test Method - Visual Inspection
label | 324054ce-c3df-5c7e-b965-277777ffdfb4 |  | note | Record of conformity - This ITP signed
label | 5256e64a-9b09-52fd-a5a0-2fb3eb9b9d50 |  | note | WP/HP*
label | 6525acc4-bd0e-566f-8d79-0958c7e331ff |  | note | Responsibility - Project Engineer/ Principals Representative
text | ad2e6733-c164-517c-a43f-dd6a863d89a1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 - Moisture Content and Compaction Testing
label | 190202b4-08c7-5e7f-82dd-8e753ded0ba9 |  | note | Frequency - 3 days a week
label | c8b569e0-b28c-5097-9cc8-5e54f6bd9e73 |  | note | Acceptance Criteria - Moisture content and compaction testing requirements as per VicRoads section 304. Frequency of tests will occur subject to the availability of the tester (3 days a week).
label | ceb6abf9-0cba-54df-81fb-fd28fcae0a15 |  | note | Reference Documents - VicRoads section 304
label | c77fa7e2-a8bb-518e-9a79-640fe7c97db4 |  | note | Inspection/ Test Method - Test result certificate
label | 0c6329d7-aef7-58f9-a50e-a00e378fce25 |  | note | Record of conformity - This ITP signed
label | 8c1bf8d5-1205-5bcd-94e2-72af601ff28f |  | note | TP
label | 940d4cb9-0148-50a4-8770-6bb450642274 |  | note | Responsibility - Project Engineer
text | 0b55df8b-bdd1-5dfe-80bf-36ad2b57a6c7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 326c871f-f98c-5178-ae83-3de4c5e57161 |  | note | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 16173cf8-86bd-5f40-84b4-96512d17f7bd |  | textbox | Name:
text | 0ecef53f-b3b7-5cf9-a4fa-e0237d3624d8 |  | textbox | Position:
holdpoint |  |  | signoff | Add Signature
checklist-flat |  |  | checklist | ITP009 - Runway Grooving of Asphalt Surfacing - Prelim Works | itp |  |  |  | Yes | ITP009 - Runway Grooving of Asphalt Surfacing - Prelim Works | 431d9f02-201f-4b14-9916-c66b2474092c
checkpoint-status |  |  | checkpoint | 1.01 - Trial section of grooving in new asphalt surfacing
label | d2f5386d-af9b-5345-8baa-ac823d41354b |  | note | Frequency: Prior to the commencement of grooving works.
label | bca1989e-4cda-5288-a364-5f377f723361 |  | note | Acceptance Criteria: Construction of a trial section of grooving that complies with the requirements of Sections 2 and 3 of this ITP.
label | 69ef65ed-c3cd-5a6e-afc2-9b53ac1a5317 |  | note | Reference Documents:
label | 9771f7d5-e2fb-59a0-ab85-664888dbe860 |  | note | GHD-DD-SPC-001 7005"
label | 2c01875a-7d43-5292-88a7-25ada9ab1ba9 |  | note | HP7005-1"
label | ff85703f-7d88-50cd-ae00-fcf7d054538d |  | note | Inspection/ Test Method: Inspection
label | 4809c7b0-a90f-5283-9b17-3efe6a783098 |  | note | Record of conformity: ITP
label | c741dc38-a602-5884-8a41-8e733e772344 |  | note | HP
label | e4a92412-aee3-5597-b66c-a8bb80d7289c |  | note | Responsibility: Quality Manager
text | 30939d91-5cad-54aa-b1d1-69357861dab9 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP012 - Asphalt Placement - Prelim Works | itp |  |  |  | Yes | ITP012 - Asphalt Placement - Prelim Works | 658fa1c0-784e-4b00-a4a9-467a0f5ec017
checkpoint-status |  |  | checkpoint | 1.01 - Supply of proprietary tack coat for use in asphalt placement works.
label | 1e00aa11-8cf6-57e5-b1a5-380fc9fe276f |  | note | Frequency: Prior to the commencement of asphalt placement works.
label | 3477ac2c-5f24-5c04-bdb8-1e7a64508da5 |  | note | Acceptance Criteria: Submission of the properties, specifications and test requirements for proprietary tack coats.
label | 44207b7f-8a87-5355-8387-42956f935d02 |  | note | Reference Documents:
label | 078d5649-f15f-528a-b679-866472f240e3 |  | note | GHD-DD-SPC-001 5107(g)"
label | bf8b9bec-4c5d-5199-a952-4689f4684ed0 |  | note | HP5107-1"
label | 365f7773-4cf2-54aa-b228-58af9ee37a00 |  | note | Inspection/ Test Method: Document
label | d089cdd7-d88f-591b-8465-1e137e938300 |  | note | Record of conformity: ITP
label | cc9c3775-720b-5021-bd99-2300507773c8 |  | note | HP
label | 7e21dbfc-d428-516c-bd7a-ab019093dc72 |  | note | Responsibility: Quality Manager
text | 4e6fbd3d-aefa-50f3-ab09-c92cb0354306 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT AUTHORITY
checkpoint-status |  |  | checkpoint | 1.02 - Supply of asphalt to a nominated mix design.
label | 4f9000f5-bbc2-5cab-ba65-96d1c0e84abd |  | note | Frequency: Not less than twenty (20) working days prior to the scheduled commencement of asphalt production.
label | bcf77061-4c47-55bf-ae15-7c4ab38b28c4 |  | note | Acceptance Criteria: Submission of the proposed mix design for each nominal size asphalt mix including results of the mix design tests.
label | aafdc6f3-482f-5cd5-a953-67c47beff06e |  | note | Reference Documents:
label | 7d746fac-0d3a-54e2-8d78-1eedea42336f |  | note | GHD-DD-SPC-001 5109(d)"
label | 94a38cf1-5c0d-52ab-bd76-f6d4a5b6aa58 |  | note | HP5109-1"
label | 52acdca0-5cb9-5198-9156-0c0db820c205 |  | note | Inspection/ Test Method: Document
label | b195f8c8-5a8f-58f8-94e1-d9ed63fec3fe |  | note | Record of conformity: NATA accredited test certificates, mix design report
label | 7959af6a-142b-5059-8348-d8b051e0f35f |  | note | HP
label | fff6df6c-90ec-5cd5-804b-5fe85b900393 |  | note | Responsibility: Quality Manager
text | 7fbaf84d-c622-5a27-8108-2784269288b2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT AUTHORITY
checkpoint-status |  |  | checkpoint | 1.03 - Calibration of straight edge.
label | d5013bce-e1fb-5cd5-ace1-d0a800b11030 |  | note | Frequency: Prior to the commencement of asphalt placement works.
label | 7a42747d-1e27-5685-ba86-6b56c8d99e05 |  | note | Acceptance Criteria: Mobile straight edge equipment to be used in the asphalt laying works has been calibrated.
label | 568b3cee-9555-5479-8cda-a9f0291c8aa1 |  | note | Reference Documents:
label | e6ef2530-1c0b-5136-9ed6-19e877f4c4c9 |  | note | GHD-DD-SPC-001 5113(o)"
label | 382e6810-e5b3-5a64-8bd8-d868035019e5 |  | note | HP5113-2"
label | 4049bdf9-a648-5685-9f16-2a1e20c54b9f |  | note | Inspection/ Test Method: Calibration
label | e7fa9a30-1c62-5bb4-b668-4229e55cf7ba |  | note | Record of conformity: Calibration report
label | 5f729319-56a3-5d29-af66-357ed8f1097e |  | note | HP
label | fed2778a-d225-5c8f-829b-34a83fd1bdc8 |  | note | Responsibility: Quality Manager
text | f551af4d-1b9f-51f3-bfec-69aae5414f6d |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT AUTHORITY
checklist-flat |  |  | checklist | ITP008 - Pavement Marking - Prelim Works | itp |  |  |  | Yes | ITP008 - Pavement Marking - Prelim Works | 6e87d1b0-9681-4d91-982b-33f8bbdbd4fb
checkpoint-status |  |  | checkpoint | 1.01 - Supply of paints for pavement marking.
label | c49c0929-b8f9-547f-86b3-0ec828267ddf |  | note | Frequency:
label | 3aea7332-8c13-543b-b981-475a3eff8bbb |  | note | Not less than 1 month prior to the commencement of pavement marking."
label | 234fd0df-0664-58dd-81fe-52169a365bc8 |  | note | Acceptance Criteria:
label | daeb81ed-6796-50e5-9e0e-9e28110febb8 |  | note | Submission of conformance test reports for the proposed paints to the Contract Administrator which demonstrate compliance to Section 2 of this ITP."
label | 64120274-2090-5fea-a71d-964ed41781af |  | note | Reference Documents:
label | 5248d350-8481-5e26-974d-24e6dd165256 |  | note | GHD-DD-SPC-001 7103(b)"
label | d2dffcd0-2902-5b96-88b3-7d4da5c1baf1 |  | note | HP7103-1"
label | 645a17c9-c5e9-5f93-8264-c14e985a3bba |  | note | Inspection/ Test Method: Document
label | 4df9f970-b57a-525e-a811-d133f365b29a |  | note | Record of conformity: ITP
label | 459c2444-dcde-5729-af5b-20cb1d7434f9 |  | note | HP
label | 77518036-41cf-5e4a-99c2-d79e54e7f297 |  | note | Responsibility: Quality Manager
text | 4aadc6e0-fbb9-51d1-aa03-3bf2118941f1 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.01 - Demonstration of process and equipment for removal of pavement paint markings.
label | c39dde36-f219-52ae-818f-5ae50aba4d41 |  | note | Frequency:
label | c7a80d70-119a-5e11-8f26-754a73fd5ad8 |  | note | Not less than 1 working day prior to the commencement of full-scale paint removal works."
label | 8975dcbb-0c10-5ebb-b569-9e52e46c857a |  | note | Prior notice (24 hours minimum) of trial to be given to Contract Administrator."
label | ef66529a-32b4-5014-84ba-6542c66a0b03 |  | note | Acceptance Criteria:
label | 9d26c52d-c124-5e81-a635-b985c74abb80 |  | note | A trial conducted in an area agreed with the Contract Administrator of not less than 5 m2 demonstrates removal of pavement marking without chemical methods without causing disintegration of the pavement surface and in compliance with the requirements of Section 4 of this ITP.
label | c80f99f9-cf90-5c00-847b-e2ffaca3d0a7 |  | note | Reference Documents:
label | ff0547f7-b6b6-517e-a880-04f4e89d9b33 |  | note | GHD-DD-SPC-001 7104(f)"
label | 8b78195b-3394-53fb-b3fe-820929369caa |  | note | HP7104-1"
label | ab28c830-1cd2-53a1-8c0d-f872c6ddf984 |  | note | Inspection/ Test Method: Inspection
label | 66563bb0-d02a-5985-8144-5d2f69fadf64 |  | note | Record of conformity: ITP
label | b344e9cc-4990-5f81-bc13-cb92d91e59e4 |  | note | HP
label | 740be46e-0ae1-5c6e-9357-2eb0f3355210 |  | note | Responsibility: Quality Manager
text | 0804f6d4-7835-504a-ad8a-4510e457cf08 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP008 - Pavement Marking - Main Works | itp |  |  |  | Yes | ITP008 - Pavement Marking - Main Works | 7b1c3b43-68f2-4f13-857f-933f6c29cef4
checkpoint-group |  |  | section | 2 Paint Properties
checkpoint-status |  |  | checkpoint | 2.01 - Runway marking paint and taxiway and apron marking paint type and packaging
label | 12d30a03-81ac-5588-83de-f41992fdea43 |  | note | Frequency: Prior to the commencement of pavement marking works.
label | c06782e5-9ff2-5f8d-b142-cbbab0bc4730 |  | note | Acceptance Criteria:
label | da385304-ec6e-5ebc-886f-cf84ebe259ec |  | note | Paint is pre-mixed acrylic co-polymer water based paint packaged in 20 L containers.
label | e8f386ee-e4e7-5c8d-adb7-fccd9b9903b0 |  | note | Containers are of durable construction and labelled with manufacturer's name and a complete description of the contents.
label | 50b3971d-bd77-5844-832c-5c4e47e8801d |  | note | Paint is of a consistency suitable for application by brushing and spraying and capable of being used as supplied or diluted with water.
label | a53b0fb7-7445-5497-8eab-cd517c352ace |  | note | Dilution information and coverage is stated by the manufacturer on the packaging.
label | 14fbe368-d69e-5877-8a98-fa758b2e60ec |  | note | Reference Documents: GHD-DD-SPC-001 7103(a)(c)(d)(h)
label | fe2b8b44-9874-5301-a121-d1bfc2a8ef38 |  | note | Inspection/ Test Method: Inspection
label | 9cceb3f3-b4cc-5114-9b84-e75d1c6c4df4 |  | note | Record of conformity: ITP
label | f01c0308-00dc-52a4-87bd-3547eb179035 |  | note | IP
label | 10bd0e4a-7fe2-5773-9e46-bf1248659c38 |  | note | Responsibility: Quality Manager
text | 7d4d4df6-978f-5b8f-b52f-f919b6e7bdb6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.02 - Condition upon delivery
label | 9ca27ac3-8450-5f7a-861b-a9cd5c6637bd |  | note | Frequency: Prior to the commencement of pavement marking works, at the time of delivery of paint.
label | 74b1d90a-9320-5410-a901-0d370a998dba |  | note | Acceptance Criteria: Hand stirring of the paint readily produces a smooth uniform product.
label | 47bf73b5-0fa6-5da3-ae40-16c735595bcf |  | note | Reference Documents: GHD-DD-SPC-001 7103(e)
label | 49f1ea7b-7f92-533f-b311-41ffcd03aea1 |  | note | Inspection/ Test Method: Inspection
label | 3654e29d-889e-5ee4-b3b7-db494127c729 |  | note | Record of conformity: ITP
label | b163d6fd-6f00-52bf-a84b-88708180b52b |  | note | IP
label | 97bd2a72-fcae-50ca-9fe9-5413263818cc |  | note | Responsibility: Quality Manager
text | 86763891-9fe5-58ce-8b11-991567603f25 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.03 - Material properties: pick-up time, colour, bleeding, durability, and keeping properties.
label | ff7dab01-bc12-5a6f-a75d-ba3f037f230e |  | note | Frequency: Prior to the commencement of pavement marking works.
label | 07568999-6457-500c-91ec-e237c980500c |  | note | Acceptance Criteria:
label | 63372fb6-3eba-568d-8407-bd9f4b3e875e |  | note | Information provided by the manufacturer or demonstrated by trial indicates:"
label | df9fc902-7795-5423-a96b-3b2f516e47b9 |  | note | The no-pick-up-time of the paint does not exceed 30 minutes.
label | 99422d5e-a8b4-5226-bd6f-5c7cab333caf |  | note | The colour of the paint conforms to AS 2700, shows a high visibility against the pavement, is the correct colour as indicated on Drawings, does not react with bitumen and will not dull, fade or discolour within a period of 6 months after application.
label | 004ab173-1147-5afe-9bc9-ee14aa30671a |  | note | The paint when stored in original sealed containers retains all specified properties for a period of not less than 12 months.
label | 1e225041-4f8a-5f1c-b253-c2418c004746 |  | note | The paint shows resistance to weathering, stripping, abrasion, flaking, erosion, jetblast and scuffing under normal aircraft operations.
label | 5457a83a-9e9f-5fc9-a44c-f2c2a42cd323 |  | note | Reference Documents: GHD-DD-SPC-001 7103(f)(g)(i)(j)(k)
label | e16587dc-ac50-5519-91cd-303b24bc088b |  | note | Inspection/ Test Method: Inspection
label | db579e02-a4e0-5e89-be01-2fdee6410fff |  | note | Record of conformity: ITP
label | 30ed9435-847b-557c-9d34-f762d5ffcfbe |  | note | IP
label | d0064461-77c9-545a-9db2-ea5f3f5932f8 |  | note | Responsibility: Quality Manager
text | 2336a0fc-d0dc-58d6-a0d3-c3e48c444a8e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.04 - Paint surface finish
label | 1058efcb-69dd-5485-9ba8-a33867f230c5 |  | note | Frequency: Prior to the commencement of pavement marking works.
label | 8c6f3d13-9c08-56b7-b234-57d8a6f4f077 |  | note | Acceptance Criteria:
label | 51ab6f73-3319-5ce9-bd08-a534a6a177f3 |  | note | The dried surface of painted areas on aircraft aprons is not slippery under foot."
label | 2510fd92-e4e7-5b67-bac1-f5c2d6bbad45 |  | note | The surface finish of the dried film of paint is a non-gloss matte finish."
label | 58064e8d-4cba-5d38-aa1d-deca6b2ecd6b |  | note | Reference Documents: GHD-DD-SPC-001 7103(l)(m)
label | 1eeb72e0-8b71-547e-90e8-a31eb1033841 |  | note | Inspection/ Test Method: Inspection
label | c72e41f1-2eaf-5ded-b560-e6549a9b9cd8 |  | note | Record of conformity: ITP
label | 948717bc-1245-5121-83e9-23861b46d040 |  | note | IP
label | 319ee390-bb5b-5e44-b561-877f006a39c8 |  | note | Responsibility: Quality Manager
text | 40e0a124-41e3-5383-af9e-32606a507301 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 4 Removal of Pavement Paint Markings
checkpoint-status |  |  | checkpoint | 4.01 - Plant performance check
label | 4a3b0ae9-ebb5-5c80-a3ff-30d502d31340 |  | note | Frequency: Prior to the commencement of paint marking removal work in each work period.
label | 6e42ca88-77c5-5c8a-ae93-9e7fa0116b9e |  | note | Acceptance Criteria:
label | 923551e0-c226-5247-86e9-fd75315e347a |  | note | All plant is in working order free from leaks and capable of removing all paint from the pavement surface without filling voids with debris removing joint sealants or otherwise damaging the pavement surface.
label | 0979f134-ee9e-533c-acb4-b3b0994dd0a5 |  | note | Reference Documents:
label | 7eea2720-8dc8-55e8-9ee5-ce1315c27aad |  | note | GHD-DD-SPC-001 7104(b)(c)"
label | 9df5d98f-d4c0-522c-b6be-68da2d776448 |  | note | WP7104-1"
label | 74ed28d4-d9ce-5dfd-bb4f-7828ac6fb05a |  | note | Inspection/ Test Method: Inspection
label | a33f2333-9cea-5825-a839-cc606e241c63 |  | note | Record of conformity: Daily plant verification checklist
label | 72aa6258-7b1e-563a-a253-51bea1d5979d |  | note | WP
label | add00efe-5c3f-5cb3-9c71-549c327e52ba |  | note | Responsibility: Site Engineer
text | 2bc38304-e4fc-56b3-89dc-116d80beb13f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.02 - Weather conditions
label | 946f5461-155c-58f6-88fd-4cce2c7e4529 |  | note | Frequency: Prior to the commencement of paint marking removal work in each work period.
label | 2aeac528-e8bc-5eb3-af21-55e4df8b8a04 |  | note | Acceptance Criteria:
label | d7102ebb-328b-5839-82b5-6c4bddde6100 |  | note | Pavement surface is free of snow, ice or slush with a surface temperature of at least 5C and rising at the beginning of operations (except for where shot- or sand-blasting is used for which a lower surface temperature may be accepted).
label | 2dcc272f-5b41-5245-8e34-1735000db3bf |  | note | Work is not occurring during a thunderstorm."
label | 2cfb2dbb-6d0a-5d2e-ac00-c01497637e8e |  | note | Work is not occurring during rainfall except for water-blasting and removal of previously applied chemicals.
label | 5da5b605-094c-5a7c-8aa5-568de5420f74 |  | note | Reference Documents: GHD-DD-SPC-001 7104(e)
label | ba0061d3-1267-5247-ae2d-279390b1cb20 |  | note | Inspection/ Test Method: Inspection
label | 09520109-9157-56a2-b114-271da7ae7156 |  | note | Record of conformity: ITP
label | 597590ec-6c78-5d2b-a61d-56505b7a77a0 |  | note | IP
label | 9fef1e15-2b86-5ec7-9dbc-0e093af481ae |  | note | Responsibility: Site Engineer
text | 4c057a3e-8812-50f4-bf10-7076401ccc11 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.03 - Surface texture
label | 807fad53-2dff-5e05-b748-ed82a87bd5b6 |  | note | Frequency: At the completion of paint marking removal work in each work period.
label | 96f63478-ae6a-5d62-b36e-5fdf25e7c9aa |  | note | Acceptance Criteria:
label | a2982576-e104-546e-a0f6-36b17753718a |  | note | The surface texture of the cleaned removal area is comparable to a standard area of pavement in the removal trial area selected by the Contract Administrator."
label | b2920425-3a69-5d9d-9696-8bcd6fd68518 |  | note | Reference Documents: GHD-DD-SPC-001 7104(f)
label | b5f1ef9b-1552-5f51-8fe3-9bc76dca2cdd |  | note | Inspection/ Test Method: Inspection
label | 84266060-4564-5016-87d7-569b5b47e2fa |  | note | Record of conformity: ITP
label | 5f9fe6c0-f74b-5300-a06b-fed5a3f92c26 |  | note | IP
label | c0fa1839-7b50-5280-80b8-0a3eb9231f1b |  | note | Responsibility: Site Engineer
text | 0ae51240-7a10-512a-bc43-353e168de795 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.04 - Clean up and waste disposal
label | 102d83c1-4318-5026-8888-07fd0d43aabc |  | note | Frequency: At the completion of paint marking removal work in each work period.
label | 60544895-a5b9-5cfa-9046-a4d3c5f839f5 |  | note | Acceptance Criteria:
label | fa9f91ab-6bad-500d-988b-3a0ed03bf2d6 |  | note | Debris and waste materials have been collected removed from site and disposed of at an appropriately licensed waste disposal site.
label | b8317443-0738-58b3-93a2-ae1b55f52ecd |  | note | Reference Documents: GHD-DD-SPC-001 7104(f)
label | 41c79429-30fb-5827-a96b-e03d52abcb4b |  | note | Inspection/ Test Method: Inspection
label | 874b197a-1e51-5d62-8d1a-453c46d5b966 |  | note | Record of conformity: ITP
label | aeaeee8b-1de7-5166-824a-6954edbf1d28 |  | note | IP
label | e4325ec3-9484-5c3c-8360-934fc9d15458 |  | note | Responsibility: Site Engineer
text | ff9e984c-233e-5594-98a9-381af9e719ee |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5 Application of Pavement Markings
checkpoint-status |  |  | checkpoint | 5.01 - Setting out of pavement markings
label | 505b29c1-88f7-541c-8565-2cd98e471b91 |  | note | Frequency:
label | 4e87ae10-9591-52ea-bb89-ca0a704af418 |  | note | At the completion of setting out and prior to application of pavement markings.
label | d6cb31c0-08f5-5f7c-9270-bde9cec8acd0 |  | note | Prior notice (minimum 24 hours) of commencement of setting out is given to the Contract Administrator.
label | b8981fc2-abe9-5d01-8dff-cf14f1295698 |  | note | Acceptance Criteria:
label | 35694ada-5dfb-5a7c-8158-0bd437b53b52 |  | note | Survey for setting out new pavement markings has been completed as shown on the Drawings by a suitably qualified surveyor to a horizontal accuracy of 25 mm.
label | 1299c1fb-0a31-5f69-988b-2f0e559648c6 |  | note | Spotting indicates the location and extent of new markings in sufficient detail for the painting of the required markings to the tolerances specified.
label | e78c573f-07c6-5a7c-b381-214bbb97c695 |  | note | Reference Documents:
label | b29525ad-caa9-5883-9fb9-5f5702d0a1a4 |  | note | GHD-DD-SPC-001 7105
label | 551b1cf6-4083-5c87-ab06-1c4747a5e0f4 |  | note | HP7105-1
label | 5623b5a6-99ed-5556-923f-554d2b5a126b |  | note | Inspection/ Test Method: Inspection
label | ba353dff-3821-5890-808f-cd76fbba52e8 |  | note | Record of conformity: ITP
label | 221b8396-0e91-51bd-a345-3be6580752be |  | note | HP
label | 2a54438a-4a3b-5435-b975-280e8ccbbb55 |  | note | Responsibility: Site Engineer
text | c5834b01-ac41-5f44-9d23-f9497c760aef |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.02 - Surface preparation
label | 1ce39ec9-16f5-50f4-9c4e-d255332095ff |  | note | Frequency:
label | ef9c3a3d-606b-5440-a946-39681a786d8f |  | note | Prior to the commencement of pavement marking in each work period."
label | a78f21c3-2e5c-59a4-b82c-cb9ca14f0253 |  | note | Prior notice (minimum 24 hours) of the commencement of pavement marking is given to the Contract Administrator."
label | 9b910aad-e488-5732-b146-f4fcc2e45689 |  | note | Acceptance Criteria:
label | d0fed293-e662-5877-be43-7f06834e3ec4 |  | note | The surface to be painted has been thoroughly cleaned using vacuum sweepers, hand brooming and/or high pressure water jetting as required and all existing paint not strongly adhering to the pavement has been removed.
label | b33154f4-15e1-59b4-84b6-5480c0979af7 |  | note | Reference Documents:
label | de5b7f06-ef81-5cbe-8160-0d5b58152be8 |  | note | GHD-DD-SPC-001 7106(b)"
label | fe93a87e-2c49-554e-8d46-394a74f8f509 |  | note | HP7106-1"
label | 291c9f9f-9750-58f6-8d51-50c614e8e04a |  | note | Inspection/ Test Method: Inspection
label | ffe8a008-e1ee-529a-93fa-44bb6a939b19 |  | note | Record of conformity: ITP
label | e6c7b5a6-a03b-5cc6-b296-0cc51e19589f |  | note | HP
label | 6115a7b0-4774-505f-8f44-356db499e5d1 |  | note | Responsibility: Site Engineer
text | fc724601-8b36-5b45-8a24-a7039ecc0af1 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.03 - Weather conditions
label | 747bce2c-562e-54f6-b78f-452e013d0d91 |  | note | Frequency: Prior to the commencement of pavement marking in each work period.
label | 7d39a7bb-e84f-5811-9d29-ecabdcf2873e |  | note | Acceptance Criteria:
label | 109f445f-93a8-5838-bcb5-4b3a4a33320e |  | note | The pavement surface is not wet and wet weather conditions are unlikely during the work period the air and pavement temperatures are not less than 15C the relative humidity is not greater than 85% the wind speed is not greater than 20km/hr and wind conditions are unlikely to affect the application of the paint.
label | c5c75e09-faaa-5bf2-bb8f-341049f139e8 |  | note | Reference Documents: GHD-DD-SPC-001 7106(c)
label | e9b52c21-48e0-5fda-8a32-d6e302d35f79 |  | note | Inspection/ Test Method: Inspection
label | 4cef60e9-8231-54ac-acfa-bacbfdae8724 |  | note | Record of conformity: ITP
label | 81ded818-c6ae-57b0-af46-1712997c6ea8 |  | note | IP
label | 254bf12f-74b5-5844-a537-06b4aff62b98 |  | note | Responsibility: Site Engineer
text | dd2f4746-f94b-5e20-8169-a9b64de5d583 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.04 - Pavement marking adjacent to in-pavement light fittings
label | 205266d9-ef80-59c2-bdb6-3a08a5f84842 |  | note | Frequency: During pavement marking works.
label | 5644ccae-b8e7-5052-a4d7-4a742c642fb2 |  | note | Acceptance Criteria:
label | 13f103b0-105f-573c-a12f-44eb5d177086 |  | note | Any in-pavement light fittings in the vicinity of pavement marking works have been protected to avoid contamination with paint.
label | 2a54654e-a3d4-5bd5-94fa-aea2249d1ba1 |  | note | Markings in line with light fittings extend to the edge of the fitting but not on to the fitting.
label | f6e011cf-509e-51cc-ac00-f4b7c37f3d09 |  | note | The gap between the end of painted line and edge of a light fitting is not more than 25 mm.
label | e6c54a8e-03a4-5169-9847-534da4d74bd0 |  | note | Reference Documents: GHD-DD-SPC-001 7106(d)
label | ef826500-f1dc-5326-8da0-52fc225b1c12 |  | note | Inspection/ Test Method: Inspection
label | da67edc5-ad3a-5555-894a-6bfb715f5fe7 |  | note | Record of conformity: ITP
label | 918b6bbf-161d-5d15-b809-aa93763fb115 |  | note | IP
label | e00e938d-f8a2-5732-a32f-3183302e3e7f |  | note | Responsibility: Site Engineer
text | 55d98e94-a5ff-508e-b35a-80caca44f42f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.05 - Application of paint
label | 6b9f65e7-fbfe-5c20-bd77-cf83f1fe587d |  | note | Frequency: During pavement marking works.
label | 1d79c8bd-73d5-5506-8b3b-9c079c0a2da3 |  | note | Acceptance Criteria:
label | 490af5e3-7d75-561d-a83f-819a640d8ddc |  | note | Paint is applied by spraying except for small markings isolated repairs and stenciling of letters and numerals where brushing is permitted.
label | 52322e4a-54b8-5db6-bd59-efbe2b67cffb |  | note | Paint is applied in 2 even coats to give a minimum total dry film thickness of 120 m.
label | cdf0b1f6-2012-5813-8b17-a403be7f119e |  | note | The edges of markings are straight or smooth even curves with crisp even lines wihtout side spatter at the edges and ends of markings.
label | f7bf0e0e-60d1-5d17-9374-43e1d65ad876 |  | note | Reference Documents: GHD-DD-SPC-001 7106(d)
label | 096423d9-a5ed-5f9b-9665-cee3b327fa44 |  | note | Inspection/ Test Method: Inspection
label | d246ef14-5e12-582f-8aa6-3f468c4bd7eb |  | note | Record of conformity: ITP
label | daedde47-26dd-5bca-9a58-2b844fb158d5 |  | note | IP
label | 8c7defd7-544e-5a0a-844b-df64272ca321 |  | note | Responsibility: Site Engineer
text | d9248b18-fccc-515b-9279-75ce9de2c7f9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.06 - Application of glass beads
label | cdb7be29-2590-5830-a441-61ef0fff1551 |  | note | Frequency: During pavement marking works.
label | 56e04cd1-cb86-5cba-9e6c-8599cce9d7b2 |  | note | Acceptance Criteria:
label | 5d016e3b-18c7-56d2-842e-56080151a5e7 |  | note | Glass beads are not used on any pavements with the exception of areas specified within standard MAS-CVL-002 for Pavement & Pavement Markings (Airside).
label | 59ce49cb-71ff-5b90-8591-ac96d3083b1a |  | note | Where glass beads are specified on taxiway pavement markings the minimum application rate is 300 g/m2.
label | d16d98d8-845c-5ef0-bb14-7b8fc9e87c17 |  | note | Reference Documents: GHD-DD-SPC-001 7106(d) SP7103(n)
label | 2d48a280-cfcc-514a-b9bf-dfb32dcafd44 |  | note | Inspection/ Test Method: Inspection
label | 9ee8a9ae-b220-5330-a06f-0441e2428707 |  | note | Record of conformity: ITP
label | bef29b36-2371-535c-a68d-10e757b9045e |  | note | IP
label | 4d0744a9-ed62-52e3-b954-19e82009ce83 |  | note | Responsibility: Site Engineer
text | 2964e138-6951-553e-b3c0-0934177f3756 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.07 - Paint application rates
label | b22ba058-1c17-5eaa-8012-bb4b4538bba5 |  | note | Frequency: At the completion of paint marking removal work in each work period.
label | e3d437a0-a977-5bb3-ace1-7947ef17decb |  | note | Acceptance Criteria: Paint usage and area of coverage for each work period are recorded.
label | e2887137-1755-56c2-930e-974df2908e4f |  | note | Reference Documents: GHD-DD-SPC-001 7107
label | 289b1e04-5200-549e-97cb-d575d7d82ee4 |  | note | Inspection/ Test Method: Inspection
label | 73a6c0a5-dcdb-5259-b4a4-f7c5a9da32a9 |  | note | Record of conformity: Shift report
label | 57a08508-406c-5dfe-8101-a9b606fd45b6 |  | note | IP
label | 928a9f3c-2026-5ced-8a33-11e3b21f1d94 |  | note | Responsibility: Site Engineer
text | 6b96c65f-6c3b-510f-94c5-0afe467b96a6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 7539afe2-b661-53d2-b81e-008351ace069 |  | note | The signature below verifies that this ITP has been completed in accordance with the FHs Quality system Procedures and verifies lot compliance with specifications.
text | 58b91a9c-68fd-5d07-863d-a2330639027d |  | textbox | Print Name:
text | d9bcea65-aaeb-5221-a075-3e6f12981389 |  | textbox | Position:
text | 5aad08f9-0924-520a-9b29-602951a23b4e |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP016 - AGL Removal of Luminaires and Install of foundations | itp |  |  |  | Yes | ITP016 - AGL Removal of Luminaires and Install of foundations | 7ce2819b-70f8-465e-aebb-4f3d150b8b95
checkpoint-group |  |  | section | 1.0 Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | 7b92530b-e696-51f6-bd3a-eedb8e8a982f |  | note | Frequency: Prior to commencing any activity
label | 505ba630-e3f2-52c7-ab0e-dbdbea788f02 |  | note | Acceptance Criteria:
label | 20fbf138-51bb-56bd-bdf0-e1bc956cada0 |  | note | • Ensure that all employees and subcontractors are using the latest and complete set of drawings
label | ebe0fa93-f48a-58c7-8c94-3e0c1822175d |  | note | Reference Documents:
label | 119d0512-fdf8-5704-87f8-a941030188a8 |  | note | • IFC Drawings
label | be3fe723-a930-5692-b3d8-d30e2e16034b |  | note | • Appendix K- AGL Specification
label | 95530858-9a26-5059-be6b-766443cf7c33 |  | note | Inspection/ Test Method: Verify
label | cce05c7d-24e4-5e6d-82fc-a3439964a6c0 |  | note | Record of conformity: Drawings
label | e9ffc273-b45c-53a9-8413-4f8d33b94497 |  | note | IP
label | 088f686a-8525-5d7a-8b13-ee015879cef4 |  | note | Responsibility: Subcontractor Representative
text | bef99b6b-152d-5c7e-b265-d05b1b98bc57 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Implementation of all measures and controls
label | ffd457ee-a4ec-5fec-b8a4-7b3eee2a467a |  | note | Frequency: Prior to commencing any activities
label | d64d9626-ceb5-5eab-bc49-d4337ec493c7 |  | note | Acceptance Criteria:
label | b7f04acf-4d2c-519f-97ed-1dc4b2a564a5 |  | note | • All necessary measures and controls are being implemented, that is PSP, EMP, TMP, SWMS & WP.
label | 7457827f-bc21-5cfc-83d7-8b75d47719c2 |  | note | Reference Documents:
label | a4de334e-f842-51bd-bffd-23cda77ad809 |  | note | • PSP
label | 629b15b9-8ae6-5bba-9352-8dabd8c28ff6 |  | note | • EMP
label | ac21505d-d8a2-59c4-80d4-943294ff369c |  | note | • TMP
label | 33a21856-23cf-50d6-b6b9-d2340411402c |  | note | • JSEA
label | de3ea236-6082-520d-9f6a-85d1d9171687 |  | note | • SWMS
label | 91b53f7c-b10c-5b08-9521-4d5eb8f780b4 |  | note | • WP
label | 6cd25c30-3562-57a0-ad42-0eafb522cffc |  | note | Inspection/ Test Method: Verify
label | bbac771a-afb4-570f-a187-f3e56ead34c2 |  | note | Record of conformity: Site and Office Inspection
label | 2293b69b-156b-5c49-a90a-3c4470668958 |  | note | HP*
label | 9f0bbab5-fc24-5315-ab79-9069047745c9 |  | note | Responsibility: Site Engineer / Site Supervisor
text | b26802ab-68e8-5275-a129-db5b61829fe3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 - Material/Equipment Approvals and Certification
label | 71eedcdf-a7f2-5ae1-9aad-4b752d5ed074 |  | note | Frequency: Prior to Start
label | bce7ecbb-aa01-5613-8c63-882eca870925 |  | note | Acceptance Criteria:
label | 01ac754a-58f9-5f0b-adf5-f178e96daa84 |  | note | • All materials shall be proven to meet contractual requirements prior to acceptance.
label | de5e2cd9-1649-59f0-a300-6985a52484a4 |  | note | Reference Documents:
label | 92c467e4-9ba9-5b77-bb36-42c4ba380dd5 |  | note | • Appendix K- AGL Specification Section 2.3.3
label | 8b249099-35c8-5e36-a71a-98b42796afd7 |  | note | Inspection/ Test Method: Verify
label | 7bebe0ed-3b69-5ca1-adf0-51bfff7140fc |  | note | Record of conformity: Datasheet / Material Submission
label | cb5cf4a5-fae5-5a74-9536-ba3aca39f99e |  | note | HP*
label | 74ccc66b-9fc7-5f5e-b2fa-e989f7de376e |  | note | Responsibility: Site Engineer
text | 4b9639c5-f810-55c6-b352-1adbb9b14ddb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 - As-built location
label | d3ad7413-9536-523f-b484-eff2a7ce5059 |  | note | Frequency: Prior to commencing any activity
label | 6d9ebd33-165a-5e67-bc9c-590a1c17fd6e |  | note | Acceptance Criteria:
label | f00cbe9e-072a-5bdb-a46b-167da5d3f038 |  | note | • Surveyor to pick up existing location of all AGL Luminaires and position of foundations are prescribed based on design RL.
label | cece4c77-a280-5e9f-a340-9413f82f4b90 |  | note | Reference Documents: Survey Documentation
label | 2cf7080f-510d-5fb3-806a-57a906476523 |  | note | Inspection/ Test Method: Verify
label | e2478f86-703a-56df-84d0-e4ba5aae065e |  | note | Record of conformity: Survey as Built
label | c0346e9b-a7c0-5431-961b-af7446d5d4a5 |  | note | SCP
label | f8e85c5c-e5d4-51c2-a31d-23fb01907ac1 |  | note | Responsibility: Site Engineer
text | 6544886b-d280-527a-a528-b218dad5c1b0 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 2.0 Removal of AGL Luminaires and installation of Foundation
checkpoint-status |  |  | checkpoint | 2.1 - Confirmation of pre-works
label | 50598412-62aa-58c8-812d-3c89105d16a6 |  | note | Frequency: Each Light
label | 3114d161-3be0-5a4d-bd23-b4fe74be8def |  | note | Acceptance Criteria:
label | 5fae524d-11c7-500a-885a-fda8bbe6cdf2 |  | note | • Ensure that the light to be removed corresponds to project drawings and documentation.
label | 50312c74-1f00-5ca4-a1e6-921f4b82b25a |  | note | Reference Documents:
label | b088fd28-7e38-51c8-803d-e91beb838ae1 |  | note | • IFC Drawings
label | f817a5ed-68da-5836-b15a-12f2498af415 |  | note | • 12554937-E031 to 12554937-E037
label | b4a526f4-86eb-5c66-bf35-f7632d48ffd6 |  | note | Inspection/ Test Method: Verify
label | 6ae21043-580e-58c4-aec8-bee6f4faf634 |  | note | Record of conformity: This ITP Signed & Sub-contractor ITP
label | 142ac3b4-ffb9-51f7-92e3-fef3e8c95345 |  | note | IP
label | 797284f8-9488-56cb-b2fe-1bdff18ab288 |  | note | Responsibility: Site Engineer / Site Supervisor
text | fb6d6637-1820-54a6-9b3a-f87551051923 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - Isolation of lights
label | 0b7d5184-7c67-5550-b541-4a055ad113cf |  | note | Frequency: Each Light
label | d7fa6b11-ef34-56e6-abd8-eba9355a77c2 |  | note | Acceptance Criteria:
label | cba92527-2ce2-5b25-897d-d7fb6b0b80aa |  | note | • Prior to commencement of removal, the subcontractor shall ensure that the light has been isolated from power.
label | 3c444d2d-f7f0-5731-a139-19b2ffce72de |  | note | Reference Documents: APAM Electrical Isolation Standards
label | dbb9f15b-df39-5192-a891-fe9fbd780786 |  | note | Inspection/ Test Method: Verify
label | 6d6307e4-5564-5368-9670-14a23ddd6a86 |  | note | Record of conformity: This ITP Signed & Sub-contractor ITP
label | 9aa972e1-0d8f-5ea7-a872-f6c10a024a03 |  | note | IP
label | 63a8428b-1f4b-52d4-8ff6-c2720cf4dcb5 |  | note | Responsibility: Site Engineer / Site Supervisor
text | 244efa32-bb96-5e67-a4c6-390ff3dcdada |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 - Light removal
label | fffda413-4266-5ae8-91ff-8da1cf289325 |  | note | Frequency: Each Light
label | b0934f8a-64b5-54d6-85cd-51839c740951 |  | note | Acceptance Criteria:
label | cc439537-409b-5c27-8439-2ee6491824d1 |  | note | • Remove light as per Subcontractor checklist for the different methods.
label | 1af797ce-565b-5dbc-bdd4-d74736d6288f |  | note | Reference Documents:
label | 555feb3b-114f-551c-a3ad-be0629a19a42 |  | note | • IFC Drawings
label | 104823cf-0df6-506a-b5f9-1c3225b68dc6 |  | note | • 12554937-E031 to 12554937-E037
label | a76de7ce-b4a5-5c98-b0f8-d757f54b740f |  | note | Inspection/ Test Method: Verify
label | e8890ed0-8d63-58ac-97d6-7ec4c5530866 |  | note | Record of conformity: This ITP Signed & Sub-contractor ITP
label | 17a13baf-57c9-58e4-81d6-edb2fb71ae6b |  | note | IP
label | 7c7d7eab-9e43-5bb1-ab9e-f5e0c3bb5216 |  | note | Responsibility: Site Engineer / Site Supervisor
text | ee6891b9-7b46-51e9-b881-14ddc328bd15 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 - Light storage
label | 43f0ab42-aebd-5e16-9e42-f30246493e1e |  | note | Frequency: Each Light
label | e1e4ec46-8fe6-50c1-8e43-0bcc04299aca |  | note | Acceptance Criteria:
label | def2f620-72a2-50e6-ab12-df83c0748866 |  | note | • After removal of the light, the subcontractor must ensure that the light number and position is recorded and stored accordingly for re-installation.
label | 4f246b2b-32cf-5955-a53e-c9af56c55257 |  | note | Reference Documents:
label | 1a64a7f4-ca83-536e-8cbe-20b9eead2bcf |  | note | • IFC Drawings
label | 0a8793b0-da36-5bc8-ad1b-815d5d9e7a1d |  | note | • 12554937-E031 to 12554937-E037
label | d4c329f2-86b6-5cd7-9c71-b5bf3f6b1334 |  | note | Inspection/ Test Method: Verify
label | 16d96bb6-b79e-56c9-b1f7-21b5cec3a958 |  | note | Record of conformity: This ITP Signed & Sub-contractor ITP
label | 4354307a-1847-5420-ab68-29725361e8bb |  | note | IP
label | df0158c3-737c-52b3-9917-dec84a30fb9f |  | note | Responsibility: Site Engineer / Site Supervisor
text | d6390492-8b10-596c-a889-d93decd46b12 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 3.0 Installation of Light Foundation
checkpoint-status |  |  | checkpoint | 3.1 - Coring
label | 40694520-71d0-5762-adf9-7329fced52b7 |  | note | Frequency: Each Light
label | ed9a30c0-3694-5a81-ab64-0d2b19b40641 |  | note | Acceptance Criteria:
label | 3eeda6c5-e4aa-5c13-a66f-de3188ccef5e |  | note | • Core pavement to required depth as per subcontractor ITC for relevant Method.
label | 98df6de5-1339-5eb3-8a03-4eb7cf9e8caa |  | note | • Remove base and clean void.
label | 5ebd840d-3e98-5db8-8b73-27687461a974 |  | note | Reference Documents:
label | 022ba4b7-2535-58f7-a12b-750c5991ae51 |  | note | • IFC Drawings
label | b731b438-7e2c-52f7-9413-29dfd2e27ba3 |  | note | • 12554937-E031 to 12554937-E037
label | d4be26cc-7f3b-5b44-b362-6f1ddc6d8572 |  | note | Inspection/ Test Method: Verify
label | 9e43977c-7d9b-5d79-b74b-15c299107a12 |  | note | Record of conformity: This ITP Signed & Sub-contractor ITP
label | fb2388ee-7d37-594d-91b1-52e6411f3045 |  | note | IP
label | f6c9d078-6270-5043-9ffc-84a70dd8e9e6 |  | note | Responsibility: Site Engineer / Site Supervisor
text | ce41b239-3b29-5daf-ae77-749d13010968 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Installation of foundation
label | c19534fe-a87a-5605-8a07-e78fb55bd02c |  | note | Frequency: Each Light
label | b3e84b9d-7b35-5b7e-b5ea-ebe9b53ec112 |  | note | Acceptance Criteria:
label | 54748705-7a08-58e3-a392-331eabe3898e |  | note | • Position bung/spacer in 150mm diameter hole of foundation. Ensure cables and conduits are clear and clean.
label | 75d80868-e2ad-5cb3-94d9-27da2974c8e6 |  | note | • Surveyor to provide final design surface level.
label | e0867d61-dcfe-5bad-8a45-0e4967dfd35c |  | note | • Mix and position quick set concrete onto the top of the existing foundation and let cure.
label | 189a37c2-c152-5a84-9cb7-b7a9ded30ae7 |  | note | Reference Documents:
label | 5fb73f6f-338a-573d-a055-b62c020541c4 |  | note | • IFC Drawings
label | 8b986fa6-c0dd-5c48-8473-2ec34c9e7732 |  | note | • 12554937-E031 to 12554937-E037
label | 30aca6f8-981b-5906-988e-2e99a150882c |  | note | Inspection/ Test Method: Verify
label | e509760c-562d-544b-a72f-1b9584146222 |  | note | Record of conformity: This ITP Signed & Sub-contractor ITP
label | 8065aeac-2dde-515d-9624-76c6b83b4363 |  | note | IP
label | 81e7b0e4-45f7-5935-922a-ed9baaff4ad4 |  | note | Responsibility: Site Engineer / Site Supervisor
text | 077b5d8f-4acb-5232-b8b4-64425d82a2ee |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 - Blanking Plate
label | db71c48e-a6a7-50d7-85d0-fae1444ea39c |  | note | Frequency: Each Light
label | 883a9029-46fd-5dc9-83d4-66b30a3196bd |  | note | Acceptance Criteria:
label | 454fc40d-b3c1-5b20-80e3-1cfa1e9f3941 |  | note | • As required, luminaire fittings to be safeguarded to allow for placement of asphalt with a Blanking plate.
label | 8b522931-9246-5eb4-9b2b-92ef4643dfe6 |  | note | Reference Documents:
label | b64d8a1b-1dad-570d-bc35-b86b6a554039 |  | note | • IFC Drawings
label | 8025638a-3797-5508-b806-42af4f89ac0a |  | note | • 12554937-E031 to 12554937-E037
label | f488a1ef-56c4-58c8-9bc0-1b96ea2d2be5 |  | note | Inspection/ Test Method: Verify
label | bd879610-2378-5da6-b121-90b9d90d0dac |  | note | Record of conformity: This Signed ITP & Sub-contractor ITP
label | 35888a1e-3f7f-50ed-9452-1aa2528ed6e4 |  | note | IP
label | 6c353132-b65e-5d22-aa78-4aba2ca59332 |  | note | Responsibility: Site Engineer / Site Supervisor
text | fa93396a-37e5-5e3b-92ef-d03786bff200 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 - Asphalt Backfill
label | 076b2166-8cb8-590a-9d33-2dba10f146c8 |  | note | Frequency: Each Light
label | 851033bf-1a72-59c4-9c1a-15f1880f3771 |  | note | Acceptance Criteria:
label | 0b88f65c-6400-51c5-b2d0-ff2a8afd0262 |  | note | • Place hotmix asphalt in void above new foundation and compact using hand tools.
label | 7e676e9a-07df-5c52-8d13-02a007b8bb7e |  | note | • Ensure asphalt is finished flush with surrounding surface.
label | 66a5ce12-20e4-57ed-83c2-181516521171 |  | note | Reference Documents:
label | 445da681-4042-521d-8232-d9334873759e |  | note | • IFC Drawings
label | 85c349ac-89e0-5cc6-9499-788e55f8260a |  | note | • 12554937-E031 to 12554937-E037
label | fef6a701-d8ad-508d-8189-5b4e04864931 |  | note | Inspection/ Test Method: Verify
label | e77e026d-0f21-5e06-956b-22975f66c3c5 |  | note | Record of conformity: This ITP Signed & Sub-contractor ITP
label | 42458b1d-2b78-5b49-b06b-6210cf18cb27 |  | note | IP
label | fb317f28-54da-5b3d-bad9-a9637f89648b |  | note | Responsibility: Site Engineer / Site Supervisor
text | 19005792-3c75-585c-8b10-c5c55afed940 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 70f46a8f-5621-5395-93a7-9afdf737e70a |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | 6e3a6434-00a9-58dc-acb9-c2efa143306b |  | textbox | Print Name:
text | e332741d-d319-5bd9-b88b-7af8b95cb969 |  | textbox | Position:
text | 41993938-8198-5e36-b887-b4d088abb363 |  | textbox | Date:
checklist-sectioned |  |  | checklist | FHC-ITP-022 Native Grass | itp |  |  |  | Yes | ITP022 - Native Grass | 9ed4997e-b576-433d-b189-3ae3bdb1726b
checkpoint-group |  |  | section | Preliminary Activities
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | 166a7010-cba8-5cf5-8225-cf53eae3de69 |  | note | Frequency - Prior to site establishment
label | 606fc980-1ce4-5cd8-ae27-01f67b887b3c |  | note | Acceptance Criteria - Review whether a preliminary report has been completed for the project which will outline where the Significant native grasses are and what protection has been specified.
label | d8ebe34e-1dad-5140-9083-b0668fc27f7d |  | note | Reference Documents - Consultant reports
label | 046d9d89-1497-5ebe-ab44-37bcbf885bbf |  | note | Inspection / Test Method - Visual inspection
label | 64155c32-706f-5e58-9c7a-a3a4a4b4ac48 |  | note | Record of conformity - This Signed ITP
label | 13704c85-bcb7-5024-8eca-7b47581ea6a8 |  | note | HP*
label | f3a6f4c3-3d20-56a5-8ffc-a1f5e0e61427 |  | note | Responsibility - FH Project Engineer
checkpoint-status |  |  | checkpoint | 1.2 - Check the Google Earth Mapping
label | 770ad89c-6285-5ca4-ad6e-5150bc0d3f14 |  | note | Frequency - During site establishment
label | f75d4038-a2b0-5a05-8f3d-da0ce45cc142 |  | note | Acceptance Criteria - Review the Google Earth mapping which outlines the boundary of the native grasses at the time they were mapped.
label | b97d3304-9721-517d-93b1-623282e17c9e |  | note | Reference Documents - Google Earth Mapping
label | 1bd6d606-59bd-5f54-9ae6-e0eeefdb351f |  | note | Inspection / Test Method - Visual inspection
label | 519fb784-3a9c-5fd4-9034-afa1959f16f6 |  | note | Record of conformity - This Signed ITP
label | 0eded8f9-cee1-5076-a488-d2200ecc9b6d |  | note | HP*
label | c371bf2a-2b92-5d78-9686-dc6fae5ec65b |  | note | Responsibility - FH Project Engineer
checkpoint-group |  |  | section | Implementation of Controls to Protect the Native Grasses
checkpoint-status |  |  | checkpoint | 3.1 - Mark out the exact Significant Native Grass Boundary area
label | d51ccaa0-b121-5ec0-8f99-2a6d89dfd98f |  | note | Frequency - Prior to commencing any activity
label | deed4930-8009-5032-9508-fbf2006af565 |  | note | Acceptance Criteria - Work with the surveyor to mark out the Significant Native grass boundary. Signage will be placed onto the bollards stating ‘Native Grass Boundary Area.’ NTGVVP Nationally Significant Grasses to protect within this area.
label | 74095b11-fed2-5863-a6b6-bd9d55db24c2 |  | note | Reference Documents - EMP
label | a999d5b3-7263-5572-9c2c-44f615b3d4c8 |  | note | Inspection / Test Method - Inspect
label | e85a32c1-953b-5f31-b90a-3fa9d0dc161e |  | note | Record of conformity - This Signed ITP
label | 1ad6e536-a92c-564e-bcb1-83977661ab90 |  | note | HP*
label | cfd56eae-741c-5a40-9f27-0236047abc7b |  | note | Responsibility - Surveyor
checkpoint-status |  |  | checkpoint | 3.2 - Use temporary fencing and signage to block access to the Significant native grasses where we are working in close proximity.
label | 9be47146-547e-5912-8b42-ae12ec26bf86 |  | note | Frequency - Prior to commencing any activity
label | 0fecde4f-5edf-5ca1-be9a-6b3550840cf9 |  | note | Acceptance Criteria - The Botanist report may define what type of protection is required for the Native grasses. For works in close proximity to the native grasses, use temporary fencing to block access with signage stating “Vegetation Protection – No Go Zone.” This fencing will be installed at a distance away from the actual native grass boundary to act as a ‘buffer zone’ but still allows works to progress.
label | 6c12f338-8c85-5d8f-877b-26c86790480d |  | note | Reference Documents - Biosis report, ECP
label | e4ddcfd2-c7be-51e2-914f-68a11f419f0f |  | note | Inspection / Test Method - Inspect
label | 237d846e-2bac-5034-9bb0-9134a714e9d4 |  | note | Record of conformity - This Signed ITP
label | c7999228-d0c2-5ffa-b499-ea0cf43474c7 |  | note | HP*
label | 695d8de3-06b5-572d-86ef-47c3fb26a90f |  | note | Responsibility - FH Project Engineer
checkpoint-status |  |  | checkpoint | 3.3 - Implementation of control measures required to protect the significant native grasses around our project area
label | 2b68405b-5228-5dd2-a6ce-4c7369bda63d |  | note | Frequency - Prior to commencing any activity
label | df11b116-99aa-5d06-89e2-a6140e67f0d5 |  | note | Acceptance Criteria - An exclusion zone will be set up with bollards and signage stating “Vegetation Protection – No Go Zone” between our works area and the native grass boundary area to act as a ‘buffer zone.’ Allow a minimum 2.5m buffer zone.
label | 87617fed-9715-5aaa-aeba-9f3aa509fd21 |  | note | Reference Documents - Biosis Zulu report, EMP
label | 686647ec-dfb7-5a39-8d62-4b021eb88e58 |  | note | Inspection / Test Method - Inspect
label | 79859c6c-c61a-5084-8b7f-5925cd938e5f |  | note | Record of conformity - This signed ITP
label | d54473cd-ca3a-566b-8c11-38842793dd7b |  | note | HP
label | 9638da71-fb02-5577-8bf6-6c997b4648c4 |  | note | Responsibility - FH Project Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | APAM Hold Point Release - Second Inspection
checkpoint-status |  |  | checkpoint | 4.1 - Release of Hold Point for Native grass Protection
label | e0786b23-99ef-5e02-853b-1ee09980e376 |  | note | Frequency - Prior to commencing construction
label | 77d18b07-cf2d-59ff-9118-f4f6871fbb1e |  | note | Acceptance Criteria - Arrange an APAM inspection to confirm that the native grasses are protected with the required temporary fencing or bollards and correct signage where required. All parties are to sign off on this Hold Point Release document
label | 7686c9be-386c-5491-a8b5-4114ad968e9d |  | note | Reference Documents - CEMP, ECP, Botanist report
label | 1dd8e8ca-2d5a-5f1d-b6c6-f164a4be604c |  | note | Inspection / Test Method - Visual
label | 34f33b25-768a-5cf1-ad94-c14ffd41c6d2 |  | note | Record of conformity - This Signed ITP
label | 3546be1c-0167-5da9-a3ed-61c24e067293 |  | note | HP
label | 868df850-0374-51c5-8b18-a3466814ab7c |  | note | Responsibility - APAM Fulton Hogan Environmental Manager or Project Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | 82c8ca0f-10f2-5e53-a7f0-49fcdc3bdc93 |  | note | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed above have been reviewed and implemented in accordance with the Construction Environmental Management Plan and conform in all respects with the requirements of the Contract.
label | b9ab059f-5260-5588-b052-b3bcc1bb9678 |  | note | FH Environmental Team
text | 27db9fd2-a1df-59c7-b315-c5ae910d3d65 |  | textbox | Name:
text | db9e7a0f-6697-509f-b1fe-6114b249f6db |  | textbox | Position:
text | 4ed0cd96-62a7-508d-843d-31bb025edf51 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Add Signature:
checkpoint-status |  |  | checkpoint | Final Inspection
label | eb8c8eec-449d-5769-9269-d869c3d2e57d |  | note | FH Project Manager
text | 3955531e-b3bb-577e-a518-be6edcf6cfed |  | textbox | Name:
text | c766eaba-8f0e-5047-8eed-d1a9f5964635 |  | textbox | Position:
text | f67255c2-c82c-56e5-b26d-a5fbab9ec0c8 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Add Signature:
checklist-sectioned |  |  | checklist | ITP004 - Coarse Aggregates for Asphalt Production | itp |  |  |  | Yes | ITP004 - Coarse Aggregates for Asphalt Production | a5211f37-4160-4b9e-b81e-528f0468f2d1
checkpoint-group |  |  | section | 1 Quality Assurance - Prior to Commencement of Works
checkpoint-status |  |  | checkpoint | 1.01 - Apparent particle density
label | f5f8d351-0493-5df7-a781-85363893f840 |  | note | Frequency: Within 1 month prior to commencement of works
label | 6cefc595-07cd-59a8-a130-60f363a9d328 |  | note | Acceptance Criteria: Not less than 2,300 kg/m3
label | bbae41b7-9c90-524e-8273-872696e49a8a |  | note | Reference Documents:
label | f8713f5d-2fc0-5de1-a505-02d5a7a826d8 |  | note | • GHD-DD-SPC-001 5104(b)
label | 002531e6-865f-5d2f-8aa3-fdf57e08eb60 |  | note | • Table 5104-1, 5130(a)
label | 764f20d6-32f2-506e-bcf7-360b1d4b2bb5 |  | note | • HP5130-1
label | fe5805e3-d178-5802-826e-3e2c0987f3c1 |  | note | Inspection/ Test Method: AS 1141.6.1
label | eacd925c-8688-5272-ab7f-8709d5efd7a9 |  | note | Record of conformity: NATA-accredited test certificate
label | 08d9d383-6dc8-5814-bb9e-aa96fb622171 |  | note | HP
label | a6cb9cad-24ab-5f7e-a500-675af3f99357 |  | note | Responsibility: Technical Manager
text | a81cda13-f5c3-5a92-94e5-dd2c1d2639de |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.02 - Water absorption
label | 09d3e997-0c7f-521e-922f-e654c1ea5470 |  | note | Frequency: Within 1 month prior to commencement of works
label | ee99d408-a8d3-51d4-9cf5-c95577267e65 |  | note | Acceptance Criteria: Not more than 2.0%
label | a39ae797-36fd-5f3d-89b9-fd82d30dfc7f |  | note | Reference Documents:
label | e1474b77-7108-54aa-b913-a9ebd77e3f30 |  | note | • GHD-DD-SPC-001 5104(b)
label | e9fe11df-25f6-54c3-a4e9-18f45cfc6a17 |  | note | • Table 5104-1, 5130(a)
label | d73f396e-4bb9-51da-b930-0e2466b50952 |  | note | • HP5130-1
label | d942b9b8-f388-59e9-b4fb-3dabb1afe1ab |  | note | Inspection/ Test Method: AS 1141.6.1
label | d2482d25-5154-53ce-b337-6064bae6ea21 |  | note | Record of conformity: NATA-accredited test certificate
label | 7e5e720b-6fda-567d-9a59-67a0a15c185a |  | note | HP
label | 3af0734c-6a4e-5013-95c8-6854a93ac2d8 |  | note | Responsibility: Technical Manager
text | ebd4384d-73aa-56b3-afa4-d803b73d34b5 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.03 - Material finer than 0.075mm in aggregates (by washing)
label | 4368835e-a136-5241-86ab-fb5f065a9d25 |  | note | Frequency: Within 1 month prior to commencement of works
label | cb5c104a-97b7-506e-a1b5-f1059b0a88f1 |  | note | Acceptance Criteria: Not more than 2.0%
label | 04fbdd6c-c884-5d3c-921b-e2709db7241c |  | note | Reference Documents:
label | b85bc966-911f-54c3-a6c9-d235b7cb35b7 |  | note | • GHD-DD-SPC-001 5104(b)
label | eacc5978-278e-56c1-9108-7c72f42f8d0e |  | note | • Table 5104-1, 5130(a)
label | 9db238ec-70ec-58e3-ae03-d20ce037381d |  | note | • HP5130-1
label | 171b7f05-a4d5-554d-b5e0-dbf2737154a0 |  | note | Inspection/ Test Method: AS 1141.11.1
label | a05422c9-0ea9-5552-8e6a-b13e86d6fa81 |  | note | Record of conformity: NATA-accredited test certificate
label | 4e034839-74fb-52be-a898-6414c1cc5b7a |  | note | HP
label | 7a9f5f5b-a773-5709-9f88-30f269c272df |  | note | Responsibility: Technical Manager
text | 5bde7a03-4abb-51fd-a7a3-e79d5e992532 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.04 - Flakiness Index (nominal 10mm and larger)
label | 6164fea4-2d2f-58c7-b5ac-c0f40cf334fa |  | note | Frequency: Within 1 month prior to commencement of works
label | 75a8858b-56ce-543c-965d-70e066147017 |  | note | Acceptance Criteria: Max 20%
label | 3d1b51bf-7869-5b45-ba3e-d8df4f01bb30 |  | note | Reference Documents:
label | 37ce773f-3e78-52b6-b928-a699cbb2279f |  | note | • GHD-DD-SPC-001 5104(b)
label | dc9dd172-e610-5141-9a67-8901e5a6c547 |  | note | • Table 5104-1, 5130(a)
label | 5d865773-8649-51ec-ae74-413745d9bddd |  | note | • HP5130-1
label | c8780b81-8719-5810-b7b9-ae8bfeb78a7d |  | note | Inspection/ Test Method: AS 1141.15
label | 4742e18e-9f5c-57d3-b858-1cd5775ba941 |  | note | Record of conformity: NATA-accredited test certificate
label | 244403de-d9f0-5af6-a5e8-450b75ee4e7b |  | note | HP
label | ab554bfb-585c-556c-ba7d-c19b234235cd |  | note | Responsibility: Technical Manager
text | 96edad0e-6b4f-5a02-8f35-45dfc2e7bbf8 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.05 - Soudness (using sodium sulphate)
label | 75738a4d-ed08-51e3-bd96-b34333496808 |  | note | Frequency: Within 1 month prior to commencement of works
label | 4e7d1460-c203-59a0-bef5-d5556e61739e |  | note | Acceptance Criteria: Not more than 3% weighted loss
label | d5ad7fd8-31f9-5a05-8caf-e56a5113e417 |  | note | Reference Documents:
label | f8ff580e-b263-5a18-985b-8906bcc946f6 |  | note | • GHD-DD-SPC-001 5104(b)
label | feee53aa-a953-5c23-a6c0-8e0479d4d850 |  | note | • Table 5104-1, 5130(a)
label | 736be387-8a18-5e2d-962d-440fd3498a39 |  | note | • HP5130-1
label | 8fbb7238-f558-5274-8b62-6e5b21d4ffa5 |  | note | Inspection/ Test Method: AS 1141.24
label | 28694f6b-28ef-59b5-b698-219547e9997f |  | note | Record of conformity: NATA-accredited test certificate
label | d5df5ced-cbd1-5010-bae4-71e3e37f1c5e |  | note | HP
label | 748e0fe6-da85-534b-9ba5-ca3a7f6db888 |  | note | Responsibility: Technical Manager
text | accdbff6-da94-5535-a642-7f3c4aa436d2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.06 - Unsound and marginal stone content
label | 372a078f-8901-5d80-80a0-4c451c735145 |  | note | Frequency: Within 1 month prior to commencement of works
label | a121e962-eefa-56f0-9a06-498de1776cb0 |  | note | Acceptance Criteria: Not more than 5% unsound; not more than 10% marginal and unsound
label | 42de67ce-52b6-57e1-a398-b6578e9e9297 |  | note | Reference Documents:
label | 3497fb78-f24d-55e5-bf72-fa7198a53d79 |  | note | • GHD-DD-SPC-001 5104(b)
label | 3756ad2d-7ee2-579f-81ba-4506243fdc01 |  | note | • Table 5104-1, 5130(a)
label | 3092d631-d9fc-5a15-8598-2faa455a1c60 |  | note | • SP5104-1
label | d75bfadd-f729-5967-90ff-2877605fb3e1 |  | note | • HP5130-1
label | b2b2b9ee-e6f5-5078-8da4-c68550d63e82 |  | note | Inspection/ Test Method: RC372.01
label | 7260e7a5-fd81-578b-b3f6-c12d6659adc4 |  | note | Record of conformity: NATA-accredited test certificate
label | 9a975944-f9ab-5af6-b92a-9c6a3748d7a5 |  | note | HP
label | ee515ace-9568-5d2c-b628-62abe49c4e93 |  | note | Responsibility: Technical Manager
text | f04bb129-016d-5f84-a9ac-d94090b6a4d1 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.07 - Wet strength
label | b4b79d24-c565-5ea3-b485-11d2b267adcf |  | note | Frequency: Within 1 month prior to commencement of works
label | 062ff714-0ee2-543a-b23a-ffe296da788f |  | note | Acceptance Criteria: Not less than 150 kN
label | 80a1876a-c8d0-5881-b97c-3b2cf4531b5f |  | note | Reference Documents:
label | 1c6313c4-81a6-55fd-bf43-d6c0d4604a6b |  | note | • GHD-DD-SPC-001 5104(b)
label | 63883b8d-465a-5ef6-9fe0-1876a24326d6 |  | note | • Table 5104-1, 5130(a)
label | bb40ae47-c59d-5c16-bfd7-bf76677dcc17 |  | note | • HP5130-1
label | e3b987b8-a030-58cf-a447-4aeb0ab0f3bb |  | note | Inspection/ Test Method: AS 1141.22
label | 335c534e-0419-588e-964a-6429cc41bcfc |  | note | Record of conformity: NATA-accredited test certificate
label | 2d07e8a4-053b-5f33-9279-911a33082b15 |  | note | HP
label | 4b6d509a-4d44-5588-b834-5aedebb43bff |  | note | Responsibility: Technical Manager
text | af4fa423-ef22-55e3-951e-52e853eda928 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.08 - Wet/dry strength variation
label | 52112e5a-5472-53ab-b53a-1bc51e2473e8 |  | note | Frequency: Within 1 month prior to commencement of works
label | 6f1de806-0c52-50c0-9e8b-2f90b1dada7b |  | note | Acceptance Criteria: Not more than 30%
label | 54e1090c-157b-57a4-a043-9f912919cb06 |  | note | Reference Documents:
label | bdd90f50-f3b5-57f4-8c8b-bfb1fff65c90 |  | note | • GHD-DD-SPC-001 5104(b)
label | 9a9b8ec2-7f27-5c0a-9253-8e99fd30a457 |  | note | • Table 5104-1, 5130(a)
label | 2ec4a8df-8524-5e68-a1ba-c2c24a4b7ca3 |  | note | • HP5130-1
label | 29a50ee2-9cda-5fe6-bce8-c00a7a979f0b |  | note | Inspection/ Test Method: AS 1141.22
label | 75806cfb-c4b8-5cf5-8528-f42590153e43 |  | note | Record of conformity: NATA-accredited test certificate
label | 8d41aad3-6134-542e-847c-65f440b25140 |  | note | HP
label | 507b869a-39d6-595a-9ea4-6423ba8722a9 |  | note | Responsibility: Technical Manager
text | f60a54eb-17d1-5088-a45d-36cc842b6fc6 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.09 - Los Angeles value
label | 9c71ea93-4d94-57cc-818c-6116aaa20fef |  | note | Frequency: Within 1 month prior to commencement of works
label | 462ea3a1-82d4-57e5-8174-2c9b1e112e87 |  | note | Acceptance Criteria: Not more than 25% loss
label | c166108f-9761-5908-919f-c8e03e2dc1b7 |  | note | Reference Documents:
label | f4f22511-5213-5ef5-8c96-9a6c3317b28d |  | note | • GHD-DD-SPC-001 5104(b)
label | 696c1216-6397-532c-b378-a87adeeb8512 |  | note | • Table 5104-1, 5130(a)
label | c2e9e034-372d-5be2-b6b9-4c65c805915f |  | note | • HP5130-1
label | 8bc2dd08-26b3-5405-9520-4607f0d037f4 |  | note | Inspection/ Test Method: AS 1141.23, B or K Grading
label | 5883d289-1a93-5c90-b4b2-847ad6b5545c |  | note | Record of conformity: NATA-accredited test certificate
label | 389c55c0-9f10-5d84-91dc-69e1b5c942fb |  | note | HP
label | c358188f-5683-53d7-bdc3-73d854741af3 |  | note | Responsibility: Technical Manager
text | ff5e4eab-12c4-54e5-ab51-407dc931c42b |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.10 - Secondary mineral content
label | 6cc4b0d1-a10f-5b20-abff-389b1e8f5452 |  | note | Frequency: Within 1 month prior to commencement of works
label | bd5599b8-686d-54b8-b696-abcfd706c789 |  | note | Acceptance Criteria: Not more than 20%
label | 1195505a-29a5-5042-99a1-2ad7f14b58a0 |  | note | Reference Documents:
label | 3d2e8625-00e9-5db9-a60d-491dc47bd601 |  | note | • GHD-DD-SPC-001 5104(b)
label | 696d335d-c5cb-5ec1-869f-7fbba56def17 |  | note | • Table 5104-1, 5130(a)
label | f5a7e8e1-c848-56f4-b13d-c258ce307f63 |  | note | • HP5130-1
label | b10515da-0d9f-505f-a3d7-5b78c8bee240 |  | note | Inspection/ Test Method: AS 1141.26
label | 2143a0fd-9fdb-5958-b7c5-d39467f38e44 |  | note | Record of conformity: NATA-accredited test certificate
label | 6bf08b46-8f76-57c9-8ebd-ce7b066f6853 |  | note | HP
label | 456d20c7-6f9b-511a-822d-c7538d79b91d |  | note | Responsibility: Technical Manager
text | eb350696-5a4c-5daf-975a-83e3fedc2832 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.11 - Weak particles (including clay lumps, soft and friable particles)
label | e6174eb5-f55f-5b61-8b05-4eabd1e4a0c3 |  | note | Frequency: Within 1 month prior to commencement of works
label | 8c4750ff-0dea-55a4-bd49-2e89cfacceab |  | note | Acceptance Criteria: Not more than 0.2%
label | e3d903fb-0210-5016-80d4-f39774642ac6 |  | note | Reference Documents:
label | d0cab39d-5dab-5b1e-9728-20198aebee4d |  | note | • GHD-DD-SPC-001 5104(b)
label | f5b278bd-a6b3-5cf4-b026-1f284f123dce |  | note | • Table 5104-1, 5130(a)
label | ccf16fb1-5581-53ce-99b1-2e690dfac6e0 |  | note | • HP5130-1
label | 25a684ce-3d33-5e47-b90e-7ae3918d027b |  | note | Inspection/ Test Method: AS 1141.32
label | f3b1d7ce-b3d9-59ba-b49a-a2ad17b647d7 |  | note | Record of conformity: NATA-accredited test certificate
label | 6f76a1af-c172-531c-9505-8e5dfb95f227 |  | note | HP
label | 058044c8-ad91-5beb-b0f2-127f08f37462 |  | note | Responsibility: Technical Manager
text | 3fbbfe4d-44ce-5de7-93cc-20e36b17b5c8 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.12 - Supply of reference samples to the Contract Administrator
label | 52c499d7-2701-535c-91bb-9d525591f2a6 |  | note | Frequency:
label | 9228bf65-00a8-55e2-abf0-923f2fc2972d |  | note | • After acceptance of conformance certification for coarse aggregate properties has been accepted by Contract Administrator.
label | c85d2db1-656c-5f96-9729-891263990cba |  | note | • Prior notice (minimum 48 hours) of time of inspection of sources provided to Contract Administrator.
label | 9cf786e8-2961-5255-903f-ac0283056787 |  | note | Acceptance Criteria:
label | 097c876f-79eb-530a-a310-5fa6fcb8350f |  | note | • Three split samples of each aggregate fraction to be bagged and labelled. Minimum quantities for each aggregate fraction:
label | 108ced1d-5144-5a84-866c-22c026ca343c |  | note | ○ 14mm: 50kg
label | 3bad28c4-0256-5569-88f3-73517f317d98 |  | note | ○ 10mm: 40kg
label | 3eae1ff1-d557-522f-bcde-adb68484e117 |  | note | ○ 7mm: 30kg
label | ce86017e-5acc-5573-8917-0a5946a5bf2b |  | note | Reference Documents:
label | fff3a968-ab93-535e-96e1-5dc14559be8a |  | note | • GHD-DD-SPC-001 5130(b)
label | e23f6d20-e98f-5954-b620-2b2ad0fb424f |  | note | • WP5130-1
label | f4ae7e51-69ac-5d0d-a89e-b4cae6902e41 |  | note | Inspection/ Test Method: Inspection
label | a96b9d59-53d3-55d8-b582-f9f6b43de40d |  | note | Record of conformity: Receipt of samples by the Contract Administrator
label | 8bfc3863-e2dc-554c-b1a2-934c087545f1 |  | note | WP
label | c4eab840-4bd9-5843-bd9b-3b26c86a1336 |  | note | Responsibility: Technical Manager
text | 541ef5f7-b625-5552-8b36-957deae656df |  | textbox | Date Completed:
checkpoint-group |  |  | section | 2 Quality Assurance - Production
checkpoint-status |  |  | checkpoint | 2.01 - Particle size distribution
label | 62efbbe2-5877-53f7-8986-39c425f65548 |  | note | Frequency: 1 test per lot (see Note 1, Note 2) of 1000 tonnes aggregate, not less than 5 days prior to use in production of asphalt.
label | b684e09c-c027-5187-a48f-2bd3f36df279 |  | note | Acceptance Criteria: To be reported.
label | 7e98db3d-e30f-5216-806f-1b49ec4fa2b2 |  | note | Reference Documents:
label | bb1867ed-ec59-58f7-919b-dc41902fe8a8 |  | note | • GHD-DD-SPC-001 5131(a)
label | 62c696dd-6007-5f47-84db-ab6583f44696 |  | note | • Table 5131-1
label | 778f5ab7-83a1-50ba-acfb-fd51e1607263 |  | note | • HP5131-1
label | a638fd69-b1dd-53b4-98a3-a6493ae67200 |  | note | Inspection/ Test Method: AS 1141.11.1
label | c68e70b5-2ec7-5e77-bebe-33f8ff51b7fe |  | note | Record of conformity: NATA-accredited test certificate
label | 4d360fc5-0349-5daf-9547-67bbcf61818d |  | note | HP
label | 55ac4f06-042e-5e0d-bcf8-f6f667708dc5 |  | note | Responsibility: Laboratory Technician
text | 20f0f74c-a813-5264-8d55-02ddc465394a |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.02 - Material finer than 0.075mm in aggregates (by washing)
label | a5a0c340-0a36-53fb-9021-9d00370a5965 |  | note | Frequency: 1 test per lot (see Note 1) of 1000 tonnes aggregate, not less than 5 days prior to use in production of asphalt.
label | f42b04d1-fdc5-5e25-8442-93d9d080d91c |  | note | Acceptance Criteria: Not more than 2.0%
label | 22b7a89b-6713-51ab-ad3a-a91e8098e05e |  | note | Reference Documents:
label | c3a69efe-6224-5ea3-8177-592bbc4e333b |  | note | • GHD-DD-SPC-001 5131(a)
label | ab3226a7-e665-5b06-a302-2372fec325b8 |  | note | • Table 5131-1, Table 5104-1
label | df7993c3-6a60-5213-9178-62e9fc794c9c |  | note | • HP5131-1
label | f6831829-455f-5b55-befe-0d0823c8c25a |  | note | Inspection/ Test Method: AS 1141.11.1
label | 671fc28b-cfd3-5bc1-9149-708ca1dcb82a |  | note | Record of conformity: NATA-accredited test certificate
label | aa1aa113-c54f-5567-b9e3-1c59df3b736a |  | note | HP
label | 891dc0e4-6bce-50c8-b78c-23aa529c1230 |  | note | Responsibility: Laboratory Technician
text | b873d9f3-63c2-5270-baaf-bb282df5f591 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.03 - Flakiness Index (nominal 10mm and larger)
label | 655f0c88-b179-5148-ab66-442994acec81 |  | note | Frequency: 1 test per lot (see Note 1, Note 3) of 500 tonnes aggregate, not less than 5 days prior to use in production of asphalt.
label | e3e99803-c08f-5b83-9dcf-b1d193d0d250 |  | note | Acceptance Criteria: Max 20%
label | a42da3a1-309d-5cae-a010-da0d01c018bb |  | note | Reference Documents:
label | 56eb888d-8eff-5cee-88bf-085f17673221 |  | note | • GHD-DD-SPC-001 5131(a)
label | 7f322623-2e65-5b5f-ae5c-da8e09cc8f22 |  | note | • Table 5131-1, Table 5104-1
label | 3b67dcae-8b79-513f-9651-0d952f976513 |  | note | • HP5131-1
label | e0b4b632-63c9-5151-8e14-a4c57ee3a40e |  | note | Inspection/ Test Method: AS 1141.15
label | 13dc3d28-382b-5de0-bdc9-e493b2002b2c |  | note | Record of conformity: NATA-accredited test certificate
label | 4dfb1337-c7d1-552e-889d-105b6322c4a3 |  | note | HP
label | cc5c331e-5943-5fea-836e-76050db805d6 |  | note | Responsibility: Laboratory Technician
text | 60e339eb-2cb0-52ee-a7f4-1c226b8751fc |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.04 - Weak particles (including clay lumps, soft and friable particles) in coarse aggregate
label | a860765c-8793-5bcf-8396-6587ba33976d |  | note | Frequency: 1 test per lot (see Note 1) of 500 tonnes aggregate, not less than 5 days prior to use in production of asphalt.
label | 9fc425de-483e-5e2d-b007-a6ad1fd5fb61 |  | note | Acceptance Criteria: Not more than 0.2%
label | 52be6e0a-bc4d-5a48-ba9f-3456e9d92689 |  | note | Reference Documents:
label | 952e6859-50a2-58d6-833a-bd6bce615107 |  | note | • GHD-DD-SPC-001 5131(a)
label | 42850213-f3af-5d58-a226-2e3c1e3070d3 |  | note | • Table 5131-1, Table 5104-1
label | 35873edf-aaf5-58b3-b0db-c468527bab9f |  | note | • HP5131-1
label | 0e7792f2-b5b4-535a-b625-dd6ea8e00329 |  | note | Inspection/ Test Method: AS 1141.32
label | e76fd71c-5c03-5345-aebb-b27c7c75cd66 |  | note | Record of conformity: NATA-accredited test certificate
label | 5339e24e-740c-55f1-afd1-7280d0abddb4 |  | note | HP
label | e4b2839f-7409-54b1-8320-13bdae8f95bb |  | note | Responsibility: Laboratory Technician
text | 84c1dfe6-7247-5379-b40f-b395c887885b |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.05 - Apparent particle density
label | 3627f8da-95db-5c1a-afab-8b4d710f2a00 |  | note | Frequency: 1 test per lot (see Note 1) of 1000 tonnes aggregate, not less than 5 days prior to use in production of asphalt.
label | f93dca51-9b24-5397-a300-bd2336e1c7af |  | note | Acceptance Criteria: Not less than 2,300 kg/m3
label | 7229e4af-2308-56ed-a516-293b7cdf69e0 |  | note | Reference Documents:
label | 1fa7536a-8ae8-50cd-ad94-4e7bb0567cee |  | note | • GHD-DD-SPC-001 5131(a)
label | 64754e43-a4e5-539d-986d-6eea256ed4f5 |  | note | • Table 5131-1, Table 5104-1
label | 35543948-9ccc-5eb2-8023-99ec8a704828 |  | note | • HP5131-1
label | 27300600-1c75-5df6-a732-221847424603 |  | note | Inspection/ Test Method: AS 1141.6.1
label | cbf1d5e8-88bd-503d-bb35-5222ab2a88c1 |  | note | Record of conformity: NATA-accredited test certificate
label | 1a1f6f27-bd90-583e-bd26-0e058f88d58f |  | note | HP
label | ec1a0be9-8424-5c7e-a942-130039a9a27d |  | note | Responsibility: Laboratory Technician
text | 870b90f0-ae35-5bd8-9b46-372225cdd8a0 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.06 - Water absorption
label | 812ddbba-db52-5f05-bb67-46baaef10705 |  | note | Frequency: 1 test per lot (see Note 1) of 1000 tonnes aggregate, not less than 5 days prior to use in production of asphalt.
label | b435fffe-90da-5fe0-b407-5872f4c0e630 |  | note | Acceptance Criteria: Not more than 2.0%
label | 69b08208-92f5-5313-ba0b-78f779afad69 |  | note | Reference Documents:
label | 8fcd474b-07a1-5667-9c22-f0bb95a59e58 |  | note | • GHD-DD-SPC-001 5131(a)
label | 2916ab4a-d5b0-551e-89b3-3fd2f5d15c92 |  | note | • Table 5131-1, Table 5104-1
label | 57e349e3-4ff8-5c86-8060-bd9836fee56d |  | note | • HP5131-1
label | 9b38118e-8be6-50e4-ae72-628326705605 |  | note | Inspection/ Test Method: AS 1141.6.1
label | 0a98b1e7-e82a-5246-aa7c-ffd44e55d55c |  | note | Record of conformity: NATA-accredited test certificate
label | 42b2ed69-eec6-586b-9f7b-94ee84d14976 |  | note | HP
label | 4804cae0-4002-5c8f-898f-210c226d73fd |  | note | Responsibility: Laboratory Technician
text | ad24253a-f9b4-5591-b7c7-fade132e9a77 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-no-status |  |  | checkpoint | Notes
label | 0e640cf3-b22a-50ac-863c-2c6862a89a20 |  | note | Note 1: A change in the source rock or face in the quarry will initiate the start of a new lot.
label | 8ad07445-cd86-582f-9858-a0adc5e6618e |  | note | Note 2: A change in the crusher plant screens will initiate the start of a new lot.
label | 90b10de8-0aeb-5f31-a11b-bd9c49231417 |  | note | Note 3: A change in crushing plant parameters will initiate the start of a new lot.
checkpoint-status |  |  | checkpoint | Final Inspection
label | ff0b9f54-6d50-5286-bbc5-cf981f83c03e |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 36638a7e-8c68-578f-bcba-3d75218073ef |  | textbox | Print Name:
text | d1573454-3360-5eb4-a175-4774a6517578 |  | textbox | Position:
text | 4cdd8ee1-a9d0-57b1-9741-21b2ab93c92f |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP011 - Reclaimed Asphalt Pavement (RAP) | itp |  |  |  | Yes | ITP011 - Reclaimed Asphalt Pavement (RAP) | b2987cfa-9588-46a1-92a8-a07f549dd59f
checkpoint-group |  |  | section | 1 Material properties
checkpoint-status |  |  | checkpoint | 1.01 - Material composition.
label | e3c35f0b-284f-533d-a7e6-563980d1f1e7 |  | note | Frequency: Each 1,000 t stockpile.
label | 82f0a875-66b8-58eb-8f0d-a9ed611879a6 |  | note | Acceptance Criteria: The RAP is free from foreign material such as unbound granular base, broken concrete, or other contaminants.
label | 566fbedc-d31e-5f36-a4b4-853ca61ceb5c |  | note | Reference Documents: GHD-DD-SPC-001 5105
label | 2c5d4f52-323a-5955-8c70-9697d05f165b |  | note | Inspection/ Test Method: Inspection
label | 2a37c8f7-d238-56f8-8e89-2f73d733f4be |  | note | Record of conformity: ITP
label | 0b195fb0-b5ce-5d4c-96ac-8e3fe4c9de25 |  | note | IP
label | ab7ec117-666f-57c2-bcde-0113fab85d27 |  | note | Responsibility: Laboratory Technician
text | 5ecc2c58-8c76-5cc6-94fc-cba6f3f58c75 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.02 - Binder content.
label | 15208ce3-76e5-56a6-a60d-488ba402dd2a |  | note | Frequency: Each 1,000 t stockpile.
label | e371a80b-c9c9-52f7-bf31-ad9c6efb8aed |  | note | Acceptance Criteria: To be reported.
label | 88e72bb6-8533-5872-becc-a6a80fd18242 |  | note | Reference Documents: GHD-DD-SPC-001 5105
label | a3b30cc2-d3dc-56f8-a9e4-e4ed361b4187 |  | note | Inspection/ Test Method: AS 2891.3.3
label | 4aecbb35-7d8b-503c-a9c8-25fbd359b6d2 |  | note | Record of conformity: NATA accredited test certificate
label | 1c2a9ec9-9e55-58e5-b87f-b4b2332d0203 |  | note | TP
label | e3053e29-f83c-54a1-a04b-16dad262334d |  | note | Responsibility: Laboratory Technician
text | 34f47a11-bc10-527a-8350-591176b14e12 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.03 - Particle size distribution.
label | c8d52133-f708-5b32-b94a-c73295865e1d |  | note | Frequency: Each 1,000 t stockpile.
label | 317d120f-1d82-5f03-a25e-4d66e2d28b1e |  | note | Acceptance Criteria: 100% passing on 13.2 mm sieve
label | 5ae18186-d80e-509b-82c9-de266204d10f |  | note | Reference Documents: GHD-DD-SPC-001 5105
label | cbe982ed-d53e-5902-a64a-b920e90b6b58 |  | note | Inspection/ Test Method: AS 2891.3.3
label | e1b0609f-e5a1-5ec4-828a-86ef97e1d67b |  | note | Record of conformity: NATA accredited test certificate
label | bcc0f0f5-2701-597d-ab1d-7dde53ac0c60 |  | note | TP
label | fd501dc1-6b87-53f6-9f4c-1b0fbd85b14e |  | note | Responsibility: Laboratory Technician
text | f6896725-8fb2-522b-ab73-4cd3ac183bfe |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.04 - Moisture content.
label | 6f39b249-79ca-500e-9116-5f8898955221 |  | note | Frequency: Each 1,000 t stockpile.
label | 89a787ea-4bf3-55f4-bc6e-8d14a1cd7722 |  | note | Acceptance Criteria: To be reported.
label | 00e19531-a3c0-5869-95a9-8e97b9324a8e |  | note | Reference Documents: GHD-DD-SPC-001 5105
label | cd0c9745-283f-5137-b2dd-6257236801bd |  | note | Inspection/ Test Method: AS 2891.10
label | 71ecc1ed-2bc6-55a4-b76c-935e22a42cfb |  | note | Record of conformity: NATA accredited test certificate
label | 53913fef-780f-588f-b385-bfe4069e3711 |  | note | TP
label | 22ded6dd-1cd0-5a8f-9b00-5bb677a5b51d |  | note | Responsibility: Laboratory Technician
text | 0ad25b53-d520-55b8-9d4d-4c98e2d05bb7 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 2 Binder blend viscosity
checkpoint-status |  |  | checkpoint | 2.01 - Binder blend viscosity (for asphalt mixes containing >15% RAP content only)
label | 5e48f50a-8675-507a-a5d2-ce8cc173bfae |  | note | Frequency: Each 1.000 t stockpile.
label | cb163347-6f5f-5342-98a5-fdd4051c8757 |  | note | Acceptance Criteria:
label | 41bf61c8-f5ba-55d0-90e5-88591bd279c7 |  | note | • The blended binder viscosity is within the range of:
label | 946d6d33-15d1-5bcf-881b-230f72764215 |  | note | – 320-500 Pas for a target binder class of C320,
label | 406feb3c-7cac-5f2b-97c8-df2036a8bebc |  | note | – 450-680 Pas for a target binder class of C450, or
label | fb7a9fba-0bae-57d4-8531-1e9a79bb459a |  | note | – 600-880 Pas for a target binder class of C600
label | 300fea80-bb4d-5bd1-8fd5-7181941bcc4b |  | note | Reference Documents: AfPA RAP Management Plan Section 8.5.2
label | b25fb88c-413b-53c4-8662-65d16ad2ea33 |  | note | Inspection/ Test Method: AGPT/T191, AGPT/T192, AGPT/T193
label | eeeeb0ad-1d75-5645-96b9-cee3e5b25545 |  | note | Record of conformity: NATA accredited test certificate
label | 96943f79-6756-5a5a-bc5f-cef0cf84455f |  | note | TP
label | e362a757-9122-5eff-9e3b-7c66da580a6a |  | note | Responsibility: Laboratory Technician
text | 84d71138-6e23-5281-a05e-4718ac67885f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | fd31fa93-541f-586f-9852-94e7e0e8bc15 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 8f070a1c-2e6e-5543-a630-ef1b4531af2f |  | textbox | Print Name:
text | cf735725-8225-588b-9812-065bc0d30af1 |  | textbox | Position:
text | 4fffbc96-da74-54b4-87f9-b3d59c0b64b0 |  | textbox | Date:
checklist-flat |  |  | checklist | ITP005 - Cold Planing - Prelim Works | itp |  |  |  | Yes | ITP005 - Cold Planing - Prelim Works | b57007be-cc97-423e-b471-81a6c4df3d66
checkpoint-status |  |  | checkpoint | 1.01 - List of plant and equipment
label | d6998cb8-bcad-5cea-a01c-b965af6d6436 |  | note | Frequency: At least ten (10) working days prior to the commencement of cold planing operations.
label | 8bae190f-d3f7-5f4d-9420-29c1d9bb4665 |  | note | Acceptance Criteria: Submission to Contract Administrator of a list of all plant and equipment to be used for the cold planing work.
label | 94d5cc3c-9c6b-556a-8c41-a476aff7a10c |  | note | Reference Documents:
label | 868e6b1c-6830-512c-a9f4-c97e5c2d1ff1 |  | note | GHD-DD-SPC-001 3903(e)"
label | 68626096-34eb-52d9-bec3-7d4036a48d00 |  | note | WP3903-1"
label | 871c35c9-c8b6-5e8e-9f86-6f97af56eb88 |  | note | Inspection/ Test Method: Document
label | cf9d3a42-f46e-540e-9adf-9ee9cd275254 |  | note | Record of conformity: ITP
label | 5b527d6d-4f96-5c15-aa90-df4bfb9d5a84 |  | note | WP
label | 08fcf04c-453a-5d0f-99ca-d44cfd1e804a |  | note | Responsibility: Quality Manager
text | a0c2bfab-6357-583e-8903-c85afc488282 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.02 - Proposal to Contract Administrator to texture, profile and mill in advance of asphalt overlay work in a work area closed to aircraft operations between work periods.
label | cd91bc4f-e839-5247-9193-c218147fa811 |  | note | Frequency: Prior to the commencement of cold planing operations in the work area.
label | 25747f06-952f-5a17-884b-9d2b1367c3a0 |  | note | Acceptance Criteria:
label | 62a12247-b383-5444-9e5a-e43a3837be80 |  | note | Submission to Contract Administor of complete program and plan of texturing profiling and milling and asphalt overlay work proposed in the work area."
label | a489863b-2618-51b0-833e-da09385e1cc5 |  | note | Reference Documents:
label | b11d46d9-3119-5b61-85d6-2bce29721cdc |  | note | GHD-DD-SPC-001 3907(a)"
label | ab6c151f-acf5-54af-9b38-b0f9b312c25c |  | note | HP3904-1"
label | e9e8b959-f390-543b-8997-6fd5a72939ea |  | note | Inspection/ Test Method: Document
label | e7d8e94f-fa2b-5f32-95bb-eb6cf24e58b4 |  | note | Record of conformity: ITP
label | f11cac91-5dda-530d-bf76-d3a7b2e3b6ed |  | note | HP
label | d2dd57d1-efa1-5028-902c-29111c637167 |  | note | Responsibility: Quality Manager
text | 0ed6a0b8-1097-56a3-b426-acf62ddbe1e2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.03 - Proposal to Contract Administrator to texture, profile and mill in advance of asphalt overlay work in a work area open to aircraft operations between work periods.
label | def6ca44-9088-51c3-8498-9e806ab257a8 |  | note | Frequency: At least ten (10) working days prior to the commencement of cold planing operations in the work area.
label | 65ef66c9-95b0-553f-8d73-eb571527ca55 |  | note | Acceptance Criteria:
label | 4b95577e-d2c5-556f-834c-1bf14849ca14 |  | note | Submission to Contract Administrator of a proposal for a full scale demonstration to produce a textured surface safe for aircraft operations in that work area date of the proposed demonstration schedule and plan of texturing and asphalt overlay work proposed in the work area."
label | b4e042d1-e48c-54e2-9d9b-c820a1c7578b |  | note | Reference Documents:
label | 03d65c89-33a2-5e9e-b9de-f4fd5458808d |  | note | GHD-DD-SPC-001 3907(b)"
label | 958d778a-b27d-5463-8ba0-6518e769bd27 |  | note | HP3904-2"
label | c38254e6-5015-5935-93ce-fb145516edab |  | note | Inspection/ Test Method: Document
label | e7df4fec-26ea-5013-abd5-c4d02df8a211 |  | note | Record of conformity: ITP
label | 5d0c1f38-70b7-5fef-8b55-afc670a9cd4e |  | note | HP
label | d69ec4d5-db93-50f7-a99f-b1850c2c9401 |  | note | Responsibility: Quality Manager
text | 2a334651-bf40-55a8-bf07-1f73e16ffd5b |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.01 - Commencement of texturing trial
label | 203a8023-b429-5a92-837c-7b7efd74071a |  | note | Frequency: Prior (48 hours) notice to the Contract Administrator of the commencement time of the texturing trial.
label | 3bedbbae-4bc0-589b-8f6a-e7fb60d7a29e |  | note | Acceptance Criteria: All resources required for the texturing trial are available and all arrangements required for the trial have been made.
label | f09da81d-bbda-55e3-9b4a-1d741dffbd40 |  | note | Reference Documents:
label | 1944fcfa-2e33-553c-8c7f-9441b69c1a87 |  | note | GHD-DD-SPC-001 3907(d)"
label | 6b198d32-1e51-5b33-8afa-361e77b9a788 |  | note | HP3907-1"
label | 0b904c4f-c3be-5c74-845e-4f06483d4745 |  | note | Inspection/ Test Method: Notification
label | 3e1af9e1-92e1-5a84-b8ea-cc55f03d155e |  | note | Record of conformity: ITP
label | 44c1baf3-2343-5d3a-bf70-bfc60ddfce60 |  | note | HP
label | 68b11502-5d5b-57d5-8ec8-928a68cd1f50 |  | note | Responsibility: Quality Manager
text | 3ee067af-17b9-539d-b9a6-10c07192bbb7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.02 - Inspection of texturing trial
label | f126d703-5518-5ef3-9284-22bc343f3e9d |  | note | Frequency:
label | 5933e493-03d8-5930-8439-669f0d55a4a7 |  | note | At the completion of texturing trial prior to the commencement of application of tack coat and asphalt pavement at the trial area. Prior notice (30 minutes) of inspection to be given to the Contract Administrator."
label | 744e7a15-f34c-52e5-b4a2-54b44896e995 |  | note | Acceptance Criteria:
label | 87a70223-313b-5184-b696-d455e113c01c |  | note | Construction of a trial section comprising a single pass of the cold planing machine not less than 25m long that incorporates all cold planing processes to be carried out during the work."
label | 4ed331b1-ac40-5e09-b888-0a83285fa272 |  | note | Demonstration that the cold planing plant operators and method proposed for texturing are capable of producing a suitable textured surface."
label | 7cb2c68f-9fcc-5373-aadd-8dc5a1c9cc83 |  | note | Reference Documents:
label | 9f8e8117-9578-5e0a-a08e-10e49915a327 |  | note | GHD-DD-SPC-001 3907(d)"
label | de12cc30-86e8-5ade-af5a-15b0c3947663 |  | note | HP3907-2"
label | 96b38e9d-8909-5912-aeb7-e9afe1a66a68 |  | note | Inspection/ Test Method: Inspection
label | f4ad3c68-db01-513e-8b51-f9db3107e1fb |  | note | Record of conformity: ITP
label | efb57589-4376-58fc-9dd1-a845d92591c8 |  | note | HP
label | cf7ec1e2-421e-52d8-8e5a-1e9388b4b69b |  | note | Responsibility: Quality Manager
text | ce3f05a6-b33c-5263-90dd-fa696850362e |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.03 - Selection of textured surface reference area.
label | 9baa4d68-1663-593f-827d-3afec2e183a7 |  | note | Frequency:
label | 0a375e9b-e598-547c-90d3-b4deaca5ba18 |  | note | At the completion of texturing trial prior to the commencement of application of tack coat and asphalt pavement at the trial area."
label | b99861ee-08d6-5118-b254-df0e83060452 |  | note | Prior notice (30 minutes) of inspection to be given to the Contract Administrator."
label | 5ba5d413-4913-5227-8954-51f2eaee7c13 |  | note | Acceptance Criteria:
label | 78b528ac-8d71-5c16-b5d6-9488c9327921 |  | note | Close up photographs framed at 300mm incorporating a tape/ruler showing length."
label | 538ae0a8-cbd9-554c-9213-518a2ee00f7e |  | note | One direct overhead view and one view with camera resting on the surface pointing in the direction of the tooth cuts."
label | 825d9f9f-0c5c-52ac-bc86-71fba7fe02d6 |  | note | Reference Documents:
label | 4d41c0ec-3ef7-55d0-b967-83bb97cfeb04 |  | note | GHD-DD-SPC-001 3907(d)"
label | af66cc4d-f6b6-52e6-8921-2e91cafc67a7 |  | note | HP3907-3"
label | 3b0a4ea8-c2e1-5929-8c70-4ac125528466 |  | note | Inspection/ Test Method: Inspection
label | c2824c9b-1500-5880-9dc0-5f337db0862c |  | note | Record of conformity: Photos and typical measurements of the Texture Reference Area
label | 066bde5e-da07-5274-83cb-6489510baf90 |  | note | HP
label | 6e992506-bc90-55e2-9188-955fd66f18d3 |  | note | Responsibility: Quality Manager
text | 655eeed9-703b-59c6-b6e6-d69d01154357 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP031 - AGL Luminaires Installation | itp |  |  |  | Yes | ITP031 - AGL Luminaires Installation | b92cb116-529f-4d5a-91ef-b8d8e72a6715
checkpoint-group |  |  | section | 1.0 Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | 5f7b1c19-8558-5c89-9828-24f96ffedb4f |  | note | Frequency: Prior to commencing any activity
label | 19487d2c-ec47-51d2-9a31-14950bd74ea2 |  | note | Acceptance Criteria:
label | c1be8fb2-6471-5dbc-9d01-daef8250e505 |  | note | • Ensure that all employees and subcontractors are using the latest and complete set of drawings
label | 881f5344-4b22-58d4-b9a8-bd3f8a7dce1f |  | note | Reference Documents:
label | f4ccdddb-a218-56d3-9bbb-6481c2d9b628 |  | note | • IFC Drawings
label | f53f36fe-bf25-5d2e-8a5c-0ff8fbea7779 |  | note | • Appendix K- AGL Specification
label | 45b6dff3-1fea-5803-a45e-5985b43aa3f8 |  | note | Inspection/ Test Method: Verify
label | d172b7c5-0e3a-5c05-9913-e942b8681b21 |  | note | Record of conformity: Drawings
label | 3a09e6ee-405e-571f-af3e-e39d3f3edccc |  | note | IP
label | 9d3b9a2d-d148-5556-8235-c8ee2b3e82c4 |  | note | Responsibility: Site Engineer/Subcontractor Representative
text | 4d8a6bd2-363a-5f18-8ae8-a346a04d9a5d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Implementation of all measures and controls
label | 752e17a3-004d-55bf-bdda-c3c8f3ae61c0 |  | note | Frequency: Prior to commencing any activities
label | 83238235-1300-5157-a05c-a790d6b7c493 |  | note | Acceptance Criteria:
label | 80950af0-f26a-54fe-aa06-cadd4b5dd211 |  | note | • All necessary measures and controls are being implemented, that is PSP, EMP, TMP, SWMS & WP.
label | ee4b8bf8-2857-53bc-b94c-594b169a2bbf |  | note | Reference Documents:
label | 256ecbe2-42e0-5bb6-b446-e8553708d2ff |  | note | • PSP
label | 47ca152a-3463-5ad1-84d4-b6745f6829c4 |  | note | • EMP
label | 31bbfbd3-efbd-558d-9738-d375d47bd467 |  | note | • TMP
label | 719097f9-ae0c-58d4-8b24-42dd6151148c |  | note | • JSEA
label | d3645880-5b01-5007-9931-2292fed6f81d |  | note | • SWMS
label | 6c6b7f2f-f58b-5ee7-a418-43e8a205f962 |  | note | • WP
label | f7945eae-3f99-569a-81c2-4b1332ac22be |  | note | Inspection/ Test Method: Verify
label | 10a14905-c901-5e6e-b8e0-523e23b0c526 |  | note | Record of conformity: Site and Office Inspection
label | a34052d2-fcc6-5290-a7a0-4fb86a362c60 |  | note | HP*
label | 04dca15d-5702-5fcb-824d-50403eb25bd0 |  | note | Responsibility: Site Engineer / Site Supervisor
text | f68c0dd3-6fc1-58e1-9b1c-9afb0dc4af4e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 - Material/Equipment Approvals and Certification
label | 74ad2647-5545-5660-8b3f-3a667dcc64c0 |  | note | Frequency: Prior to Start
label | eb769476-2737-5d8d-b2ba-77b85471ef8a |  | note | Acceptance Criteria:
label | 6414c014-51ac-58d0-b05c-7ac6d37546a9 |  | note | • All materials shall be proven to meet contractual requirements prior to acceptance.
label | a2abb579-eca0-5379-9702-c12870306ccc |  | note | – Light Bases: The inset light bases must be compliant with the mechanical requirements for load and flange torque tests as detailed in FAA AC 150/5345- 42J for Type L-868 Class 1A light bases.
label | fa1e50f1-c8bd-508c-939b-b1ab16dd13fe |  | note | – Secondary cable entry: The cable entry must be arranged to provide side entry of both secondary and earth cables through the base (for termination to FAA style connecting socket and tail within the light base). A separate entry must be provided for each cable.
label | f5e767e0-596c-5053-b8bc-3bd255f76bf0 |  | note | – Earth connection: Bases must be equipped with earth cable connections, supplied with proprietary stainless steel screws.
label | 929350e4-27f8-518e-acc9-0fd0ad3a5ce9 |  | note | – Fixing stud: The shallow bases must incorporate stainless steel fixing studs cast or screwed into stainless steel thread inserts e.g. “helicoil”. The studs must include self-locking nuts and/or “vibration proof” washers.
label | c6c27d17-baae-56a6-a202-c4252d7a0ea5 |  | note | – Anti-rotation pins: The shallow base must incorporate stainless steel anti rotation pins or other fixtures to prevent rotation of the light top assembly.
label | 6bd339e4-9918-58d0-b470-dbd47815a419 |  | note | – Light canisters: Canisters must meet the requirements of the FAA AC 150/5345 – 42J for Type L-868 Class 1A light bases.
label | 8d87fcc7-a36a-5c15-87b1-0b348a08f7a9 |  | note | Reference Documents:
label | 685bc0ac-e8d2-584f-bb52-53e2bf7930ec |  | note | • Appendix K- AGL Specification Section 2.3.3 Section 2.4 Section 2.5
label | 7818cda6-7dc2-5a0a-a174-b6609c92337d |  | note | Inspection/ Test Method: Verify
label | e987c096-10e2-59e4-bb3c-cd1ecb39ae4b |  | note | Record of conformity: Datasheet / Material Submission
label | c828ec30-ad2b-5391-b6f0-9726c4127a8a |  | note | HP*
label | c4bf8f16-8211-55db-b78e-bde8f283c775 |  | note | Responsibility: Site Engineer
text | c8248b1f-b36a-55df-aae0-1ed892c7ae85 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 - Luminaire Foundation Installation
label | 7463ff59-575c-5f6b-bd43-09a61bbe7d34 |  | note | Frequency: Each Lot
label | bcaea0b0-5273-554d-af35-39ef831d9b45 |  | note | Acceptance Criteria:
label | 8344dc72-8a21-5970-9cc8-7c8a0eff71c0 |  | note | • Installed and Backfilled in accordance to drawings.
label | cbac5246-b3fb-5e5f-b5e3-1b3da359aa47 |  | note | Reference Documents:
label | 49120c33-1b69-56da-9d72-9fa674815347 |  | note | • IFC Drawings 12554937-E031 to 12554937-E038
label | 4c9bc506-28e5-551e-a32a-2c2fee2235a7 |  | note | Inspection/ Test Method: Verify
label | 57b8b947-28f4-51cb-8293-2316e23a4364 |  | note | Record of conformity: This ITP Signed & Aconex Reference of ITP submission for Foundation Install
label | 0b650687-a287-5cc0-b943-46641f24cc1a |  | note | IP
label | 4299aac8-9076-520e-89e3-6cf5b01bf5a6 |  | note | Responsibility: Site Engineer
text | 259e1743-380f-5566-8d87-eee3e7cdb707 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 2.0 Installation of AGL Luminaires
checkpoint-status |  |  | checkpoint | 2.1 - Setting out of Airfield Luminaires
label | 3e57990e-3fc1-5373-b84c-d3f1280d1232 |  | note | Frequency: Each Lot
label | faf0b3ed-c170-5a11-92f9-5c127e6dbaea |  | note | Acceptance Criteria:
label | 9ba5d76f-eb1c-5d2a-acc8-72b59be35343 |  | note | • Surveyor to confirm location of AGL with IFC drawings and confirm alignment of luminaires.
label | 4cb332a6-ece3-50c5-b801-e016c25502f7 |  | note | • Existing lights shall be reinstated following the overlay works in their existing location and at their existing orientation utilising the survey data captured prior to their removal before the overlay works commencing.
label | ec4fd0ab-71b7-5bb1-b853-92786e00bd5a |  | note | Reference Documents:
label | c71d07f9-25bc-5988-b44c-13de2103f8f1 |  | note | • IFC Drawings 12554937-E031 to 12554937-E037
label | 4c5b9d5e-c8c7-50b8-ae62-15af47dde4bf |  | note | • Appendix K- AGL Specification Section 2.16.1
label | 08cf912a-75b7-5b4a-801e-99a4c4ea577b |  | note | Inspection/ Test Method: Verify
label | 0fed259a-a87c-5f43-92e0-a3ea0cc962a2 |  | note | Record of conformity: SCP
label | 9c0ebd7d-5237-58d0-96a6-ad76af610502 |  | note | IP
label | 7758b62b-929a-5a51-9dec-c0f6ad31ed5e |  | note | Responsibility: Site Engineer / Surveyor
text | 9629d50d-1c24-51bf-8692-e891929852ae |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Coring
label | aba2f8cd-8735-5f18-96a8-92d7127c78c2 |  | note | Frequency: Each Light
label | a5dfeab5-1ef3-58a1-8d4a-47349a29f151 |  | note | Acceptance Criteria:
label | 140ed901-9ca6-57a0-908c-4ed0e5d8ecb9 |  | note | • The core position must be accurately surveyed and marked before commencement of the core cutting process
label | 235cba6c-1227-50db-9f40-baee534525f0 |  | note | • The core centre must not be removed until immediately prior to installation of the inset light unit base. The core centre must be removed avoiding damage to the surrounding pavement.
label | 2a2216e9-4777-5afe-b3f3-c9967439f012 |  | note | • As required, Core asphalt to depth as per subcontractor ITC for relevant Method.
label | e40d7045-b700-555b-88d5-9ae62f0b8319 |  | note | • Ensure conduits are cleaned after coring of light base and conduit coupling and connections are intact.
label | 96e3a224-d01e-5879-a1ff-99ff35b39a85 |  | note | Reference Documents:
label | 3383a51e-3865-5536-8a3f-e0ddf4fac4d5 |  | note | • IFC Drawings 12554937-E031 to 12554937-E037
label | e6a85749-685e-5fba-8f8e-ce63cc576c2c |  | note | • Appendix K- AGL Specification Section 3.16.3
label | 491d43d5-facd-5eaa-aaa0-e363b52a7555 |  | note | Inspection/ Test Method: Verify
label | d6a9a2c9-719d-56dd-b910-9f5796738bb2 |  | note | Record of conformity: This ITP Signed & Sub-contractor ITC
label | 9b1c5ebf-3c4d-5409-9c6f-e29b404cdbf0 |  | note | IP
label | f423d992-132f-5155-a9b9-6c51b6db8a9e |  | note | Responsibility: Site Engineer / Site Supervisor
text | ef7d4f4b-f094-5938-9ad8-81eeac8f2d6e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - Installation of Inset light
label | b5ddecf3-3798-5f44-ac92-f963d85ac4fa |  | note | Frequency: Each light
label | 1281cf3b-2d06-57b4-a562-23bfd02fc64d |  | note | Acceptance Criteria:
label | 81a407e9-dd6a-5551-b327-98592fd21dac |  | note | • A jig must be used to install, locate and level the inset light unit base in position in the core hole and maintain the base in position during the curing of the epoxy grout.
label | dc2786d2-06ad-5e99-a6cb-6ab1f8fdac18 |  | note | • Ensure correct light is installed in correct position as per the IFC drawings, this ITP and ITC
label | 88b147c1-799f-527d-896c-71dd33db59e9 |  | note | Reference Documents:
label | 2e3ff90f-43cb-5e9c-9fa4-8103f78091a2 |  | note | • IFC Drawings 12554937-E031 to 12554937-E037
label | 034d787a-dfe5-59af-9047-977ea22a396e |  | note | • Appendix K- AGL Specification Section 3.16.3
label | f84bb035-759e-599a-b12c-c2c1e2b556fa |  | note | Inspection/ Test Method: Verify
label | ff8edd87-d158-55e8-b762-8dfc445ab065 |  | note | Record of conformity: This ITP Signed & Sub-contractor ITC
label | f7909a16-e83a-57df-ac37-791666bf3b06 |  | note | IP
label | b180e2f4-8312-5753-9fd9-00f7a9b0fc51 |  | note | Responsibility: Site Engineer / Site Supervisor
text | cb6b1a5e-7990-52d7-a2bd-d9cf357c57f7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 - Installation of light top assembly
label | 08dd160b-d446-5bd3-b54d-adc9cc16b611 |  | note | Frequency: Each light
label | d495a4a4-be59-57ee-b53b-ff53f58c3317 |  | note | Acceptance Criteria:
label | 21dc3fd1-0609-58d0-a558-7fc3403a17ba |  | note | • Base to be cleaned of all materials by vacuum process.
label | 59592d52-6c41-55b1-be3d-7c3947c5a66f |  | note | • Light tops to be installed as detailed on the drawings. Connect the 2 pin FAA style plug and socket as appropriate to connect the secondary conductors.
label | 08b787df-e2ed-5745-8e26-22a3ad55df48 |  | note | • Nuts and screws must be tightened to the torque to 40N.m prior to returning a pavement area back into service. Measure and record the applied torque for each light.
label | 425bf558-5bd6-54fb-b705-8d17d2859436 |  | note | • Records of torque applied to be submitted to Contract Administrator for each installed light prior to returning a pavement area back into service.
label | 18ff453e-2400-5db1-a3cd-b84bef7cdb44 |  | note | Reference Documents:
label | ac6574d6-f86c-594a-8603-c166051c6d7e |  | note | • IFC Drawings 12554937-E031 to 12554937-E037
label | dbd515c4-86c9-5ebb-af59-5891dd724305 |  | note | • Appendix K- AGL Specification Section 3.16.4
label | ff319616-f467-5cd5-975b-0a7589c58373 |  | note | Inspection/ Test Method: Verify
label | 4cce8132-ef36-5af8-9fac-a32b055ef078 |  | note | Record of conformity: This ITP Signed & Sub-contractor ITC with records of torque applied
label | 6e8ce1fb-4572-5397-9aaf-1cc495b27d8c |  | note | HP
label | afaa4226-acb5-560d-a160-a561478b0a4e |  | note | Responsibility: Contract Administrator/Site Engineer
text | bcd5c89d-1dac-535b-ae78-6e50492efe72 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Gap between the light base and pavement
label | b19f74f0-0f26-578a-a666-8f6b5ca86d89 |  | note | Frequency: Each Light
label | 6afffe05-051d-5378-a423-8000380d446d |  | note | Acceptance Criteria:
label | a9780658-90f8-5bcd-8c06-5071c2ac1b3d |  | note | • Gap between light base and pavement to be as per IFC drawings i.e. For Method 3 lights, ensure gap between new light base and pavement not less than 7mm and not more than 19mm (Aconex BecaCPL-CONTIN-000077).
label | a094991f-c18d-566b-acf1-a903a3080338 |  | note | Reference Documents:
label | b7820cde-fccb-5119-acfb-32d4cb1022dc |  | note | • IFC Drawings 12554937-E031 to 12554937-E037
label | fc22ed06-5be0-50cd-aba8-986efb13f65d |  | note | Inspection/ Test Method: Verify
label | bad14b4a-b615-513c-baab-30f97936cda9 |  | note | Record of conformity: This ITP Signed & Sub-contractor ITC
label | 749902b6-bc26-55ff-b97b-e78f97ed2807 |  | note | IP
label | 78941815-b34e-5d9a-b239-a550855ebf19 |  | note | Responsibility: Site Engineer / Site Supervisor
text | 6262115a-e40b-5609-960d-f05b55fbfbad |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 - Grouting
label | 675399c2-93c2-5200-b9f6-748c2402bc7d |  | note | Frequency: Each Light
label | 74c6736b-ce09-587d-b713-5e97884ba938 |  | note | Acceptance Criteria:
label | 39f95280-f2b7-5a68-971e-732b85dd376a |  | note | • The light fitting bases must be fixed using Masterflow 618 epoxy grout or approved equivalent.
label | a2044812-4810-5b33-b38f-6104c3f0f812 |  | note | • The inset light unit base must be maintained properly orientated and level, as specified, throughout the epoxy curing process.
label | 7b5288b3-be65-5a8d-8f3b-33cd7d3604d7 |  | note | • Before opening the work area to traffic the Manufacturer’s recommended epoxy curing time must be allowed.
label | 19569587-3181-5463-bb4a-7c8078f47483 |  | note | Reference Documents:
label | 7c050067-3d65-5e81-b01c-d9f27e6ef052 |  | note | • Appendix K- AGL Specification Section 3.16.3
label | 17d872c5-30c6-5b00-b0c6-c6ad8f0992f7 |  | note | Inspection/ Test Method: Verify
label | 1b3dff00-df2f-5756-b237-fb3c1f685252 |  | note | Record of conformity: This ITP Signed & Sub-contractor ITC
label | 3f5ab9ee-2aaa-5651-b131-ebbe94031ae9 |  | note | IP
label | 218db998-c61d-517f-aecb-581e8171187c |  | note | Responsibility: Site Engineer / Site Supervisor
text | ccb7b74d-c84e-53ea-b3b7-fdc91f640c4f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 - Recess Sealing
label | f924a5dc-0d3c-5106-85a1-374c715fbbb2 |  | note | Frequency: Each light
label | 6d2e5259-956a-5242-91bf-f24cd926d083 |  | note | Acceptance Criteria:
label | 40c03d2c-27e9-5168-a116-e8b8a477a444 |  | note | • The final level of the epoxy is a minimum 10 mm below the level of the pavement.
label | cd7b8f38-b913-52fa-bb5c-5e9012016b8e |  | note | • Seal top of recess around light base with Dowsil 888 in concrete
label | 7f53dbbf-1615-5f25-bc0e-a44682160d3c |  | note | • Sealant in asphalt as detailed in IFC Drawing
label | 890844a5-6620-5111-ba6b-994808b4cd26 |  | note | Reference Documents:
label | 480a6648-12b9-5378-850b-2251df662cff |  | note | • IFC Drawings 12554937-E033
label | 61f99047-a98a-5c6a-a665-da41ae4bb67a |  | note | Inspection/ Test Method: Verify
label | cbdfd40a-bffc-5656-90a7-b98b98267ada |  | note | Record of conformity: This Signed ITP / ITC/As-Built Documentation
label | e0c81073-3961-5e4c-84fd-b304503b6630 |  | note | IP
label | 2ee24707-558c-5f0d-8756-7601c0c14c5e |  | note | Responsibility: Site Engineer / Site Supervisor
text | d1931dce-b629-56f8-bb08-9966f02bdb21 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.8 - Installation of secondary and Earthing Cable
label | 6db06590-e27d-57dc-b32c-f06111dfe697 |  | note | Frequency: Each Light
label | e9594234-3319-5812-8b4c-9a86c76c370e |  | note | Acceptance Criteria:
label | f8e2bb02-dbc0-56c9-9a00-61cc99c9e008 |  | note | • Each fitting shall have earthing cable provided
label | e0b27113-9b64-5a82-96bb-e95c3dbb3ef5 |  | note | – Earthing to be 6mm2 single core green/yellow PVC cable.
label | 11198dd9-5de1-5c3f-82c0-dd2c72b259e2 |  | note | – Twin secondary cable to be 4mm2 each.
label | 6264cfea-9625-59e8-8439-2fd654bdf302 |  | note | Reference Documents: -
label | aedc6551-01bc-5efd-956a-bdfcd6e225cb |  | note | Inspection/ Test Method: Verify
label | adfd94cb-cd9e-59ae-8508-ff6f69bba28a |  | note | Record of conformity: This Signed ITP & Sub-contractor ITC
label | d8d57ab8-7c0e-5720-a9f7-54c630bcbc82 |  | note | IP
label | b2ab7fba-a3e8-5d3a-b73b-8eaa3e55caee |  | note | Responsibility: Site Engineer
text | bf17b5ae-1c48-53ab-970e-2a164e7385f9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.9 - Series Isolation transformer
label | 5e7aa10a-fdf4-5f7d-9ea6-180734d9d20d |  | note | Frequency: Each Light
label | 5387a8c5-e3b6-5e7c-abc9-5c4c057f7b4e |  | note | Acceptance Criteria:
label | 23d7973d-ec66-5449-acdc-ae60ca9be3ab |  | note | • Each luminaire / fitting shall be connected to a series isolation transformer in closest SIT duct pit/ junction can.
label | a5505453-dc4a-5c66-ad64-36c98971c3e3 |  | note | Reference Documents:
label | fa69dc53-2aa6-5bf3-a0b0-556963217784 |  | note | • IFC Drawings 12554937-E031 to 12554937-E037
label | 81a69d69-ae8c-5f16-bb04-24105b715ea3 |  | note | Inspection/ Test Method: Verify
label | 94c48534-0545-5958-91a1-61c2a75cfe52 |  | note | Record of conformity: This Signed ITP & Sub-contractor ITC
label | 2566e9ad-7e56-5bbe-ab7b-271fd7e8bd46 |  | note | IP
label | b0ad1a0f-51da-56d0-92f6-4cb4bfb0967b |  | note | Responsibility: Site Engineer
text | 2174b19c-53f2-5ee4-be15-9c8bba6e831d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.10 - Luminaire Circuit
label | 3ce232ea-aaef-5292-88a4-cea5209741c6 |  | note | Frequency: Each Light
label | bcf3b9a3-1249-53f3-8409-4bc42ed59e6f |  | note | Acceptance Criteria:
label | 09e499cb-f0c5-5e2b-bfed-4112b203ea82 |  | note | • Each luminaire fitting shall be installed on the appropriate circuit as specified in the construction drawings.
label | aa1a1340-fc2c-58a0-8e37-b8981144b89d |  | note | Reference Documents:
label | 6bbc6362-e408-596f-85c7-e63fa1b6a03b |  | note | • IFC Drawings 12554937-E031 to 12554937-E037
label | c4b66852-6ace-577c-abad-3572e7c22f72 |  | note | Inspection/ Test Method: Verify
label | fc7615b9-7666-5da0-a105-8c2382b5f61b |  | note | Record of conformity: This Signed ITP / As-Built Documentation
label | b708e3d1-4f90-5ed3-9e33-9379311476bf |  | note | IP
label | 2796a65f-072a-5940-ac02-5cca1b09b89a |  | note | Responsibility: Site Engineer
text | da2c1b90-305c-5af7-896f-62b726382893 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 3.0 Post Construction
checkpoint-status |  |  | checkpoint | 3.1 - Equipment Survey
label | f07e245c-4169-54f4-895c-b19107e2871c |  | note | Frequency: Each Light
label | efad0d9d-2c2b-5f51-93a7-0eab59393997 |  | note | Acceptance Criteria:
label | e5dcc5dc-3e8b-5be7-b81a-ae939dbf04c8 |  | note | • Accurately survey the location of airfield lighting equipment. The survey plan, endorsed by a registered surveyor, must identify the location of all installed equipment in relation to permanent site features and other underground Services.
label | 6358c707-8e1c-5f46-b5c8-4b9955afed11 |  | note | • The survey must also capture all installation details such as the orientation and rotation of visual aids, colour pattern, constructed foundations, etc.
label | 70849576-e3c9-5f2d-b6db-dafa3cf7eac7 |  | note | Reference Documents:
label | 2c3afefe-bb69-574e-9942-f99667c718d6 |  | note | • Appendix K- AGL Specification Section 3.4
label | 768f8b1c-c105-5767-80c1-9d1c91a8c45f |  | note | Inspection/ Test Method: Verify
label | 4d01a2ec-83ba-502e-a99c-b2f45f77a8f7 |  | note | Record of conformity: This Signed ITP & Sub-contractor ITC
label | e3a3f8dd-1bea-5a8e-b0ac-7542544f5b88 |  | note | IP
label | 5f2a986e-5b07-5ad3-9611-946fb7486d7f |  | note | Responsibility: Site Engineer
text | 87de3c9e-8c3b-5846-927f-70015387083b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - As-Built
label | 72a04f80-b572-5249-96cc-f2a5978491f3 |  | note | Frequency: Each Lot
label | 33ddbda0-42d6-5b56-8faa-73d82a3016ab |  | note | Acceptance Criteria:
label | d4cd5c6e-ce8c-5cea-a21a-c6924c1f1c73 |  | note | • Submission of surveyed luminaire position to superintendent prior to practical completion
label | 0a9dc28f-6dfb-5611-bbcb-8c45cf8c428c |  | note | • The final installed orientation of the centre line of the output beam of the inset light unit must be within plus or minus 0.5 degree of the designed orientation.
label | c457e057-9dac-52bb-ab39-0ff300202857 |  | note | • Light bases must be installed such that the light is installed within 0.25 degrees of level.
label | 7219b767-c0dd-54f1-8890-a724ffb92b89 |  | note | Reference Documents: Specifications Section 3.16.2
label | 83444d59-372c-52d2-92f5-b49753264170 |  | note | Inspection/ Test Method: Verify
label | 3c1d7121-04a8-57f5-8c8f-243442c67189 |  | note | Record of conformity: SCP
label | 88b1714e-98a3-5ee1-8c43-8f0505db5655 |  | note | IP
label | 2514c5d3-ab38-534b-84ce-e46f71acc029 |  | note | Responsibility: Site Engineer
text | ceeade95-e413-5362-be40-5c7d1e7e7197 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 82a0d72f-7492-5aab-af61-40594b0dac4d |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | 404dab08-87bd-5330-a836-52f67498d0ec |  | textbox | Print Name:
text | 2c838ec8-ab7b-5fc6-9548-db8c6c069ce3 |  | textbox | Position:
text | f3f0ac85-3bec-5b5a-bda3-e32634df3fe8 |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP001 - Asphalt Production of Base Mixes | itp |  |  |  | Yes | ITP001 - Asphalt Production of Base Mixes | c66ec477-9003-48fd-9a5d-b1dbeba98b13
checkpoint-group |  |  | section | 1 Mix Production
checkpoint-status |  |  | checkpoint | 1.01 - Asphalt production plan
label | ae0a9c42-aa6e-50e9-b30b-9992c8a3e7e1 |  | note | Frequency: Not less than 48 hours prior to the commencement of a work period.
label | 76585f48-8165-5476-8d92-7982901086a3 |  | note | Acceptance Criteria:
label | a967a0cf-d239-5603-b193-af222a848d87 |  | note | • Plan demonstrates that the hot storage capacity and production capacity of the mixing plant is capable of supplying asphalt to complete the work proposed to be undertaken within that work period on time and to make the runway suitable for aircraft operation in the event of an asphalt plant breakdown.
label | 9cf56db6-226a-5e4d-8a99-69041109c84d |  | note | Reference Documents: GHD-DD-SPC-002 5116(e) HP5116-1
label | 0a907f27-7b35-55b9-ab28-91de2956b4f5 |  | note | Inspection/ Test Method: N/A
label | 8c540b49-31a8-5da4-8b1d-4b05562af970 |  | note | Record of conformity: Production plan
label | eb37336f-c199-5cb1-883c-c247c7833b6d |  | note | HP
label | 5d754ff4-1bda-5cce-b3f8-a3ab541d7eaa |  | note | Responsibility: Production Supervisor
text | 0a8f0fcd-7d6c-5b1b-90cf-604096278f20 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.02 - Temperature of bitumen
label | f703b14e-e3d0-516c-b9bc-78735de325a9 |  | note | Frequency: Not less than once per work period. To be recorded at the time of taking bitumen volumetric readings.
label | c56bc857-152a-5376-983f-f286225b60ae |  | note | Acceptance Criteria:
label | e7e68cc5-a564-5eef-a3d1-163ab69ef74c |  | note | • Temperature to be within the below range for the relevant bitumen type when introduced into the mixer:
label | 721cfa78-a130-5fa0-8089-d34b3c7e4c5e |  | note | – Residual bitumen: 140-165°C
label | 961e82fe-5ca9-5748-98b7-59ce5b64a219 |  | note | – Polymer modified bitumen: 160-175°C
label | 8ab3c20b-f310-51e8-8cfd-df4349b5d94c |  | note | – Polymer modified bitumen with warm mix additives: 140-175°C
label | 78f06aad-a1d0-5df4-89de-c54c6038a0d2 |  | note | Reference Documents: GHD-DD-SPC-001 5116(f)
label | 4f99b342-d83d-5eb7-9ebf-14ff3361951f |  | note | Inspection/ Test Method: Asphalt plant temperature probe
label | 9b395ff1-db1e-5607-b28c-058050675513 |  | note | Record of conformity: Production records
label | 26cf14f6-8074-5c56-88f9-9876b0851ed7 |  | note | IP
label | f7e93768-c4c9-58c3-a441-186e5b8b75d0 |  | note | Responsibility: Plant Operator
text | 351f47a7-5f67-58d0-8969-ed815fe757c6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.03 - Temperature of aggregates
label | bfc31e7f-b237-56c5-a933-2f8c067847df |  | note | Frequency: Not less than once per work period.
label | 663ceedb-426c-5bd6-936f-0f901edc4b17 |  | note | Acceptance Criteria: Temperature to be not more than 10°C above or more than 15°C below the temperature of the bitumen.
label | 38b6d2ad-b41e-5a23-8964-674459ec2c25 |  | note | Reference Documents: GHD-DD-SPC-001 5116(f)
label | 894a049f-59ba-555e-823a-2d704db7b106 |  | note | Inspection/ Test Method: Asphalt plant temperature probe
label | eb1cbf2a-4ada-5fa9-abc7-47a9825acc58 |  | note | Record of conformity: Production records
label | 31c8c625-3edb-58c3-9111-eca2cfa57399 |  | note | IP
label | d70911e7-2b38-580c-88bb-d4fb2eef86c8 |  | note | Responsibility: Plant Operator
text | a9f9db1c-fe36-584b-9cfa-e7be2fb541b4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.04 - Temperature of asphalt
label | a60e6e98-d065-50f5-8052-e66ba8bc61b5 |  | note | Frequency: Not less than once per work period.
label | 6b81a30e-3396-55e6-ba84-2c2226f1bb19 |  | note | Acceptance Criteria: Temperature to be within 10°C of the job mix temperature
label | 2ed5ebb1-40b2-57fd-bd21-52224bea2b99 |  | note | Reference Documents: GHD-DD-SPC-001 5116(f)
label | 9c70a49b-7a10-55b1-9198-dcb91f181faa |  | note | Inspection/ Test Method: Asphalt plant temperature probe
label | a10c1c81-957f-57f6-815a-9dd13c9fca2b |  | note | Record of conformity: Production records
label | 97fdac61-c326-54e7-8dd1-e15e1cc00d56 |  | note | IP
label | b6cd625b-cb2f-5e49-99d4-3cb433e26c9a |  | note | Responsibility: Plant Operator
text | db66d154-a060-5d71-8d62-23f1aad54f76 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.05 - Daily bitumen usage
label | ea996ae0-ee94-5f40-8fd0-422a05833a6c |  | note | Frequency: Once per work period for each production run for each nominal size of asphalt mix.
label | e42d1275-e69e-58e3-b87c-c123ab793e4f |  | note | Acceptance Criteria: To be reported.
label | 65a95bd6-f0ea-574d-9888-aac18434894b |  | note | Reference Documents: GHD-DD-SPC-001 5131(e)
label | c163378f-959d-52e6-b864-e5e42270a098 |  | note | Inspection/ Test Method: Inspection of plant digital readouts before and after each production run
label | 73af4274-9277-5a9b-a523-3f913835b5eb |  | note | Record of conformity: Production records
label | 247aebf0-4c0a-54eb-bfc4-a8198749f143 |  | note | IP
label | 99ab5385-c3f7-5f12-996c-51c8ebb57ee9 |  | note | Responsibility: Plant Operator
text | de4d447b-d7c5-5bac-b8fa-a1811b98fd2c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.06 - Supplementary bitumen content determination
label | bd683574-7453-5833-a1ad-2124a5c5cf5d |  | note | Frequency: Once per work period for each nominal size of asphalt mix.
label | 9ab748a9-d456-5ca8-b50c-5e2349032b89 |  | note | Acceptance Criteria: Not less than the job bitumen content.
label | 8bded84a-a7bc-56e6-b837-e8c084aaa4d0 |  | note | Reference Documents:
label | c6a085a6-2547-5acb-b845-dfbcd7ca011a |  | note | • GHD-DD-SPC-001 5131(e)
label | 2ff064f1-7caf-5774-92f8-e323343b0716 |  | note | • Table 5116-7
label | 8e456fb5-2ec4-59a3-9728-dde1b2be9c1a |  | note | Inspection/ Test Method: Calculation: Daily bitumen usage divided by mass of asphalt produced for each mix type.
label | cf637f6b-c1d1-5995-b014-a3174f5277cc |  | note | Record of conformity: Production records
label | b3fd93ff-8727-5c9d-b278-0a7d9cb057dd |  | note | IP
label | c721c706-3032-5bc6-b9e2-0a06ae33917c |  | note | Responsibility: Plant Operator
text | 3b840928-0196-585f-a3dc-079a22413a3c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.07 - Mass of asphalt produced
label | df16ba69-81a6-52ab-b199-961949d909ef |  | note | Frequency: Once per work period for each nominal size of asphalt mix.
label | ffb3c416-2158-51c5-ba45-9377f1bc837c |  | note | Acceptance Criteria: To be reported.
label | 7729ec92-4c82-599a-a8a4-d783336ccd1b |  | note | Reference Documents: GHD-DD-SPC-001 5131(e)
label | 9c960099-0d22-5778-85d5-ac02faac6982 |  | note | Inspection/ Test Method: Inspection of plant digital readouts
label | 2b0e6334-7a7b-5c4e-bca3-16e05350878c |  | note | Record of conformity: Production records
label | d1870b29-7f39-5870-afe9-13b34796439c |  | note | IP
label | bff85e8b-e577-590b-81a8-233bd49b252a |  | note | Responsibility: Plant Operator
text | 52b84047-88f6-5755-98a9-56f0a3ab0699 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 2 Bitumen properties
checkpoint-status |  |  | checkpoint | 2.01 - Sampling from storage tank at the asphalt mixing plant.
label | 1038678a-bb8e-5601-aae1-70e916054de1 |  | note | Frequency: Not more than four hours prior to the scheduled production start time for each work period.
label | dc2a5e2a-04bc-5027-994a-52f25c653f4b |  | note | Acceptance Criteria:
label | fad40fbc-e419-55cc-a717-037ad867f48d |  | note | • Duplicate samples are taken from the storage tank at the asphalt mixing plant.
label | 2a511efe-8a71-533b-9163-c21ab73d6e79 |  | note | • Containers are labelled appropriately so that samples are traceable to asphalt lots, manufacturing batch records and conformance reports.
label | 6e5d892e-576c-5aac-a620-4d35bfed684b |  | note | • One sample is provided to Contract Administrator immediately after sampling; one sample is tested as per Section 2 of this ITP.
label | c7365215-ec13-5ed7-8f2f-6e7ffc1f805e |  | note | Reference Documents: GHD-DD-SPC-001 5131(c)
label | b69016a3-baa7-5e4b-ab61-77036f1c82cf |  | note | Inspection/ Test Method: AS 2008 (Appendix B)
label | 9f6582b2-cb40-5309-bdd6-b4bcdf41c0d0 |  | note | Record of conformity: ITP
label | 2d49cfa3-e424-5274-92ad-1f1b2a25909f |  | note | IP
label | b7a3f830-928b-5520-8a65-1c93e799dbed |  | note | Responsibility: Laboratory Technician
text | 6edb5c57-8e97-5f41-9604-56f968190325 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.02 - Viscosity at 165°C
label | 55c6ef13-ba8b-5167-afc9-1d7a3797c76b |  | note | Frequency: One test prior to each work period (for PMB) or per 250 t of bitumen used , completed no later than 1 hour prior to start of asphalt production.
label | d7164c9a-29f4-593e-a315-eababb976f6c |  | note | Acceptance Criteria: To be reported.
label | 0540e13a-42e4-51c0-bb5c-c3dac8d46fed |  | note | Reference Documents:
label | 36b48c5c-414a-571e-a312-b0f9fdc245a3 |  | note | • GHD-DD-SPC-002 5131(c)
label | 1ed2ebad-a6ee-5bf7-a143-7962299fed38 |  | note | • Table SP5131-3
label | dc981f8d-0bce-5719-9ea4-1226646191e1 |  | note | Inspection/ Test Method: AG:PT/T111 (for PMB) or AS 2341.2
label | 36bdde55-7737-5cce-9ed4-f0b9da673863 |  | note | Record of conformity: NATA-accredited test certificate
label | 06f6d8ee-2983-54f0-8852-9fd1ddbe4c9b |  | note | TP
label | 2c94d247-c4a7-5079-baec-f9381057ee57 |  | note | Responsibility: Laboratory Technician
text | 67ec4cd8-e0aa-5523-be4e-2b5b3efdba12 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.03 - Torsional recovery at 25°C, 30 s (PMB only)
label | d5c12532-4d06-5391-9a6e-98c0dbfff0d4 |  | note | Frequency: One test prior to each work period, completed no later than 1 hour prior to start of asphalt production.
label | 569852ed-d6d9-5f83-bdc0-943759dd2628 |  | note | Acceptance Criteria: To be reported.
label | af3e41fa-4f3b-595e-ba3b-2108197ee33d |  | note | Reference Documents:
label | 0ea6b44b-c386-556b-9942-7bf2c3446398 |  | note | • GHD-DD-SPC-002 5131(c)
label | 7ebf3735-dd7a-567f-8199-e8042102b247 |  | note | • Table SP5131-3
label | c014d2fe-791f-522d-a808-da48bfbfd86e |  | note | Inspection/ Test Method: AG:PT/T122
label | f014cb47-530d-54fb-be11-30de96177e5e |  | note | Record of conformity: NATA-accredited test certificate
label | 83f70a87-ceac-5698-a633-da8bcd25dc50 |  | note | TP
label | c5d3e77f-227b-5306-b3f9-f5723eeaddcd |  | note | Responsibility: Laboratory Technician
text | 2d9886a7-7a42-574e-b4f7-48c1c70d160e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.04 - Softening point (PMB only)
label | 0aae2bd9-dedd-51ae-9fbb-34339158288d |  | note | Frequency: One test prior to each work period, completed no later than 1 hour prior to start of asphalt production.
label | 47c6ae34-ef46-5738-a61d-42322d9a1c18 |  | note | Acceptance Criteria: To be reported.
label | e08a8c36-e96f-56cb-ba1e-c0c084a526fb |  | note | Reference Documents:
label | bbb8dc9c-72ad-5dec-a287-f33774858d2c |  | note | • GHD-DD-SPC-002 5131(c)
label | c987c855-c8df-53a7-b5e9-1f04e2cc1295 |  | note | • Table SP5131-3
label | 1e5c5d51-a896-5814-8256-13b9bc0a7021 |  | note | Inspection/ Test Method: AG:PT/T131
label | 72ce8e2d-7246-558c-ac65-c76d8ce2c28d |  | note | Record of conformity: NATA-accredited test certificate
label | 7b407ece-1519-5fd7-8a7c-96fce96473ad |  | note | TP
label | f606eff5-6d2d-520e-a8e0-8d0982cb1e7c |  | note | Responsibility: Laboratory Technician
text | d4317710-64ce-5285-871e-ace1065431ae |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.05 - PG MSCR
label | e32c0445-d745-5be0-9c5b-31c50ffcad89 |  | note | Frequency: One test weekly conducted on a Monday sampled from storage tank, regardless of whether work proceeds that day or not.
label | d1a332e7-c1d1-52ad-b002-23cafb4b980a |  | note | Acceptance Criteria: To be reported.
label | 830c7571-d04b-5075-aca8-865349d722a3 |  | note | Reference Documents:
label | 0c1137f6-060b-50a8-a635-aa036cb2c6cd |  | note | • GHD-DD-SPC-002 5131(c)
label | c5a3ab97-45b2-50b9-b5c3-12836aa6a135 |  | note | • Table SP5131-3
label | fdea01e2-5619-5d86-8791-424154999c47 |  | note | Inspection/ Test Method: AASHTO T350
label | c41f77ec-7f1c-53b8-aac1-7df5f22ef096 |  | note | Record of conformity: NATA-accredited test certificate
label | 34b9f1fa-3ede-5069-adcf-1c0e20cd3070 |  | note | TP
label | 30d3f08d-8efe-58b9-998f-24bc01a8f054 |  | note | Responsibility: Laboratory Technician
text | 4ef42135-419f-57f4-a606-727788c25f6a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.06 - Submission of binder test results.
label | 2abeb8e8-9d0f-5c48-a316-33a19969f6c8 |  | note | Frequency: No later than 1 hour prior to the scheduled start of asphalt production for each work period.
label | 04f2d4d5-32c9-5189-a81e-6bf14724fc88 |  | note | Acceptance Criteria:
label | 7fbd9905-51b2-5e5a-aa6e-2aeb1f122586 |  | note | • Completion of the specified set of tests on polymer modified binder.
label | 06375f8b-9241-59ff-83c4-7f4323bdc2c6 |  | note | • Submission of test results and a statement to the Contract Administrator regarding the compliance of the binder in the tank.
label | d57561d0-a1cd-5efe-acb8-114064d732d5 |  | note | Reference Documents: GHD-DD-SPC-001 5131(c) HP5131-2
label | f13c02f4-71d9-5a28-b400-3d1910124b85 |  | note | Inspection/ Test Method: N/A
label | ecef3270-72ca-5f09-8786-a997701d0129 |  | note | Record of conformity: ITP
label | 68b8eae5-f34c-5186-a5cc-8de70b5b4e7f |  | note | HP
label | ee1ca6c7-7e7c-5ccb-b25f-521aa6674bd3 |  | note | Responsibility: Laboratory Technician
text | 0452d4fe-a4b2-5dca-8adc-b831dfbbda72 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 Asphalt properties
checkpoint-status |  |  | checkpoint | 3.01 - Mixing efficiency
label | b27edcbf-0fd5-59a2-a877-d1ec99b44b1f |  | note | Frequency: Not less than once per work period.
label | f9870bb9-f9df-54b5-a182-dd31fd3a27ef |  | note | Acceptance Criteria:
label | a918bd22-015a-5576-a1a2-ad86cba6fabb |  | note | • Percentage of coating of particles in the mix, when sampled at the point of loading, must not be less than 97% and a homogeneous mixture must be obtained.
label | 10d5e79a-6b7e-55d2-8c4e-cf105910ec2a |  | note | Reference Documents: GHD-DD-SPC-001 5116(g)
label | ec79658a-9064-5046-ba62-5a80ea51009a |  | note | Inspection/ Test Method: Visual inspection as per ASTM D2489 methodology
label | 1797a84e-9cd4-579e-9545-4280eeb5292f |  | note | Record of conformity: Inspection record
label | 1b05e733-f056-5fc8-8abd-0fd62d71adac |  | note | IP
label | 748a674e-f352-572d-8e5c-126734838564 |  | note | Responsibility: Plant Operator
text | d862b1e9-628e-5470-acb9-485b6eb69fc7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.02 - Stability
label | 1119a5d2-cb27-55df-bc74-329849e528df |  | note | Frequency: Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency.
label | d14ce65b-bb6b-599e-889d-c451a6c9146e |  | note | Acceptance Criteria: ±3.0 compared to job mix but not less than 12.0 kN
label | 6811081d-8d26-56ca-aae2-abe8d01cb4f3 |  | note | Reference Documents:
label | 1a2f11c2-34f3-518e-8237-da79dac0e090 |  | note | • GHD-DD-SPC-001 5116(j)
label | d7c1ec46-6848-59b4-bbfc-819b6cc0ca31 |  | note | • Table 5116-5
label | 0af93394-b140-56b9-93d5-c57aad78867a |  | note | • HP5116-2
label | 0096de79-5714-54f2-81d0-987cdd649b7b |  | note | Inspection/ Test Method: AS/NZS 2891.5 (50 blows)
label | b3d9c596-ffd4-529f-9636-46647b9c056d |  | note | Record of conformity: NATA-accredited test certificate
label | bbeaa9ce-b432-5caa-b6bc-7a343c6a13b7 |  | note | TP
label | e16c831e-0847-50f7-b9fb-7288061308c5 |  | note | Responsibility: Laboratory Technician
text | 280daa91-4b83-558f-a170-b9ec1672ff74 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.03 - Flow
label | 1fe0af98-8db3-593a-8d30-7ada5e27b4c0 |  | note | Frequency: Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency.
label | 75caf5fe-ee98-562b-892c-55594400f8b7 |  | note | Acceptance Criteria: Max 3.0 mm for unmodified binder; max ±1.0 mm compared to job mix for PMB
label | 4729f8d2-0d38-5972-a0c4-f94fa83054d0 |  | note | Reference Documents:
label | 7e60577c-0644-5823-bd52-ffc1f79a41f1 |  | note | • GHD-DD-SPC-001 5116(j)
label | 71fcb384-61a8-584d-aa66-846d736280e1 |  | note | • Table 5116-5
label | f3be9275-a705-510e-b27c-c4f4006adc57 |  | note | • HP5116-2
label | 0769ca9c-edcb-55e2-af50-db9c247eb967 |  | note | Inspection/ Test Method: AS/NZS 2891.5 (50 blows)
label | 82eb7363-de81-5b02-90e4-9df0aa636948 |  | note | Record of conformity: NATA-accredited test certificate
label | b99af3fb-b725-5c38-a6b8-2afc03135e6d |  | note | TP
label | 8dbf5ef6-9f2e-515b-8570-67e43c1695a7 |  | note | Responsibility: Laboratory Technician
text | d5f4ef46-7d5f-555c-b0a5-be3a78a9a446 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.04 - Minimum voids in mineral aggregate
label | da515340-a4c0-54da-8275-9b7a5fdf0b19 |  | note | Frequency: Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency.
label | ede00fd6-2c6c-51e8-a580-53d9cb400d49 |  | note | Acceptance Criteria: 13.0% or 14.0% (for 14mm NMS)
label | 8c4a84f1-6578-591b-8f79-eef3c44d579b |  | note | Reference Documents:
label | e28c38b7-7b76-5cdb-80a9-dbcf8a91e91d |  | note | • GHD-DD-SPC-001 5116(j)
label | 5a1d50fd-13f0-5789-98ef-8f0821e6d6b9 |  | note | • Table 5116-5
label | 1da49ea0-0d22-5165-b553-4810a9f02493 |  | note | • HP5116-2
label | 8a188807-6d1f-5ba6-bff9-66e5fa1d4d74 |  | note | Inspection/ Test Method: AS/NZS 2891.5 (50 blows)
label | 7291aa11-6c76-5416-9be8-c9dcdb1ba83c |  | note | Record of conformity: NATA-accredited test certificate
label | e220b6e0-4ac3-5ed5-8150-a25f88666954 |  | note | TP
label | e157d5d0-8c12-531c-b796-99cac73976a6 |  | note | Responsibility: Laboratory Technician
text | fb5ba4fa-8be2-5a27-b2af-95a5854b88c7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.05 - Minimum and maximum air voids
label | 74bda88e-610a-560c-80f0-b76397c7daf2 |  | note | Frequency: Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency.
label | a366393a-8cfc-525d-8838-235efff16d3e |  | note | Acceptance Criteria: 4.0-6.0%
label | 9857467d-2a5b-5dc5-8d0d-59f88c136569 |  | note | Reference Documents:
label | 51e82390-ca1c-5da0-9891-cb79a20e4808 |  | note | • GHD-DD-SPC-001 5116(j)
label | a496dccc-c966-533e-808c-00a1f0ccd3e1 |  | note | • Table 5116-5
label | e0db976b-3b37-5019-849a-4bceba88782e |  | note | • HP5116-2
label | f663e4be-cbab-54ac-aa0b-5ccede5783c4 |  | note | Inspection/ Test Method: AS/NZS 2891.5 (50 blows)
label | a646c7bd-abc3-5875-9923-8d61b8230241 |  | note | Record of conformity: NATA-accredited test certificate
label | 2bb8ee5e-b7d8-508f-9b9e-2c42cf62e424 |  | note | TP
label | fa541985-4663-57e2-ad92-d4bb765ff0a0 |  | note | Responsibility: Laboratory Technician
text | 928b8bb2-20fa-5f26-a3ef-4938d474b5d0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.06 - Minimum and maximum voids filled with bitumen
label | cabb13a3-fd84-57e7-9afb-bae82398be27 |  | note | Frequency: Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency.
label | 55aa4658-a111-576e-ba1e-5e060c18a959 |  | note | Acceptance Criteria: 65.0-75.0%
label | 5989067a-155a-5411-a936-b90fda58323f |  | note | Reference Documents:
label | cc3930bf-b6d3-5303-a9bd-3ca0bfd4ad3a |  | note | • GHD-DD-SPC-001 5116(j)
label | ea5d7a08-dcba-5ed5-b489-0b1b82d7f437 |  | note | • Table 5116-5
label | 78dcb928-0a1e-5a52-8592-8b9fd3bb7945 |  | note | • HP5116-2
label | 57be75e2-9594-5f98-9e51-51a7c954a37d |  | note | Inspection/ Test Method: AS/NZS 2891.5 (50 blows)
label | ef302ded-4db9-5703-b5e6-cf1ee2eb479b |  | note | Record of conformity: NATA-accredited test certificate
label | f753ddac-13fb-58e1-bf74-23819552842e |  | note | TP
label | f2b63512-9657-5d16-89cd-3f55eb4516bd |  | note | Responsibility: Laboratory Technician
text | 0ee0f4a0-f0ba-5032-a969-bd0efa5bf4f0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.07 - Combined aggregate particle size distribution
label | acb435bd-7cde-5295-ac06-f1cde3a492f5 |  | note | Frequency: Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency.
label | 5ed4e6f7-7e9d-5e3d-95e9-35665363d7dc |  | note | Acceptance Criteria:
label | 642191ef-73bc-5308-b7d2-22be77939a16 |  | note | • Within acceptable range of deviation from job mix aggregate particle size distribution.
label | 809aa04a-9826-5801-950d-1ca72c50291f |  | note | ○ For 14mm NMS:
label | 335738f6-0ffa-59c3-b6c2-64ca99fa2035 |  | note | 13.2: ±6 ¦¦ 1.18: ±4
label | 11fe6ebc-5ae0-5f42-9edb-75e8c317699f |  | note | 9.5: ±6 ¦¦ 0.6: ±3
label | 816462f8-0904-5b70-8ccb-a039ebd10582 |  | note | 6.7: ±6 ¦¦ 0.3: ±2
label | 5cd9ca5b-80df-5988-b966-1a36063a1718 |  | note | 4.75: ±5 ¦¦ 0.15: ±2
label | 5d1a0ce4-766b-52da-8be0-aa7821cc86ce |  | note | 2.36: ±5 ¦¦ 0.075: ±1.5
label | 7db2c84d-7431-5d39-86b1-ef44551563d5 |  | note | Reference Documents:
label | d27af14c-d227-5559-954c-d6994259d4f0 |  | note | • GHD-DD-SPC-001 5116(j)
label | 69094951-0f50-5f5c-a965-e216e13627e1 |  | note | • Table 5116-7
label | 23bcd65a-735b-5c50-9e9f-a75a3758bc14 |  | note | Inspection/ Test Method: AS/NZS 2891.3.3
label | 53e8bd71-2771-5434-881d-59ff1c4490b3 |  | note | Record of conformity: NATA-accredited test certificate
label | 637f1f31-6e94-57ea-8395-0086170b58ed |  | note | TP
label | ccef3f40-301a-5b64-88a2-b93b25570e6e |  | note | Responsibility: Laboratory Technician
text | b97c9e26-305e-59dc-bcc2-9992d37bcf02 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.08 - Bitumen content in asphalt
label | 8d2d77a0-4329-5eaa-8fc5-6b25784b8d5f |  | note | Frequency: Each test set sampled from asphalt delivery trucks (as per AS/NZS 2891.1.1). See Note 1 for sampling frequency.
label | 164cfc91-67e0-55f5-b282-dea05ea8fefa |  | note | Acceptance Criteria: Within ±0.3 of job bitumen content by mass.
label | e43d3474-0aa4-55a1-b30a-0bbc1829c86b |  | note | Reference Documents:
label | 4bd3075a-0cca-5fae-8d35-05dbd854339f |  | note | • GHD-DD-SPC-001 5116(j)
label | 3a1f03ff-ab3d-5f47-a1fc-58c04604445f |  | note | • Table 5116-7
label | 255a648a-de89-54bc-9f47-403b48515e97 |  | note | Inspection/ Test Method: AS/NZS 2891.3.3
label | f5bdd2a9-32c8-5a64-a741-be572882d555 |  | note | Record of conformity: NATA-accredited test certificate
label | a5bbcbd1-c0bd-5178-8bfd-9716d5837482 |  | note | TP
label | 08f2dbe0-a52e-585c-ae27-24d671c35f2e |  | note | Responsibility: Laboratory Technician
text | 805d97c3-a27f-553c-90bf-86c000c550d0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.09 - Maximum density
label | 9f4483e8-dfe9-572b-a460-7898ec0ad8e2 |  | note | Frequency: Each test set sampled from asphalt delivery trucks (as per AS/NZS 2891.1.1). See Note 1 for sampling frequency.
label | 30bc0e71-de0c-5454-aa79-1c923a80db57 |  | note | Acceptance Criteria: To be reported.
label | ca657ceb-b6c5-54cd-bd1f-ed17faff48c0 |  | note | Reference Documents: GHD-DD-SPC-001 5132(a)
label | 99e3a7a8-3931-57cb-9cb0-a1f55fe95dcf |  | note | Inspection/ Test Method: AS/NZS 2891.7.1
label | fe83c62d-751a-50a6-8fb4-8fb9bbee4388 |  | note | Record of conformity: NATA-accredited test certificate
label | 7bcb6dc8-c9e3-5426-bf9b-01587b6704a2 |  | note | TP
label | 7b930d9e-c3a3-5ba5-ba27-a1e2c7c899b4 |  | note | Responsibility: Laboratory Technician
text | a674dc0f-8315-5c2d-9b18-bdf9c51b1e41 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Note 1: Sampling frequency
label | 3d8e6e76-2195-508e-8535-f508c6c3d013 |  | note | • Number of test sets on asphalt of each nominal size in work period:
label | 6cb97fad-a9ec-5061-a29f-020d6b917b7f |  | note | Quantity of asphalt produced ¦¦ Number of sets of tests
label | cf5b9b55-1659-5372-9809-985facc286d0 |  | note | First 50t (0-50t) ¦¦ 1
label | 727979d8-a190-5b84-a6d8-210c67e00bca |  | note | Next 100t (50-150t) ¦¦ 1
label | 3e9ec84e-32ad-5148-9da3-0ab332450b61 |  | note | Next 200t (150-350t) ¦¦ 1
label | e7971162-5fff-54af-b239-609ecffdacf6 |  | note | Next 250t (350-600t) ¦¦ 1
label | 54257ac3-06ab-5883-9cae-3d67479af32c |  | note | Every 250t thereafter ¦¦ 1
label | 56f3afe0-1c61-5584-acd9-384bfe3af7f9 |  | note | • Minimum number of tests per work period regardless of tonnes produced: 3
checkpoint-status |  |  | checkpoint | Final Inspection
label | 7c4040e9-187d-5786-9c4c-4d41cf99fcfb |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 1a618348-c48b-5e12-8d2a-4031796a2118 |  | textbox | Print Name:
text | 331a4674-0a8b-5d35-ad60-9152ff76280f |  | textbox | Position:
text | 8fb6529a-4463-58a3-afc0-1177b61d446f |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP006 - Fine Aggregates for Asphalt Production | itp |  |  |  | Yes | ITP006 - Fine Aggregates for Asphalt Production | c79ab539-5ad1-438c-909d-f4f627bfec80
checkpoint-group |  |  | section | 1 Quality Assurance - Prior to Commencement of Works
checkpoint-status |  |  | checkpoint | 1.01 - Bulk (particle) density
label | d6cb3ce4-6de6-537f-ab53-ddf38981280b |  | note | Frequency: Within 1 month prior to commencement of works
label | 0d58c93e-0389-5939-8f7c-f4055da72a89 |  | note | Acceptance Criteria: Not less than 2,300 kg/m3
label | f59b1ad7-ff5e-5db4-90e1-8422f9a9102d |  | note | Reference Documents:
label | 66bd3db3-05f4-5e70-8a43-59af7ab80dfb |  | note | • GHD-DD-SPC-001 5104(c)
label | d2153e78-eac1-5847-90eb-e89002bd8c53 |  | note | • Table 5104-2, 5130(a)
label | 92c795f0-949f-5bfe-b408-5a4d13f0c6e4 |  | note | • HP5130-1
label | 7ec38c41-99d8-583b-99f8-98fd3aef24d5 |  | note | Inspection/ Test Method: AS 1141.5
label | ffaa3963-a5fe-5ef6-8672-37bbeb598820 |  | note | Record of conformity: NATA-accredited test certificate
label | 53c78bf2-e9de-58e0-941e-204d7f2d2847 |  | note | HP
label | 3036778f-4233-53c8-9a88-dfde37fbd2aa |  | note | Responsibility: Technical Manager
text | 3eef7caa-c157-5a07-a620-3300c7f9a6d3 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.02 - Water absorption
label | b4dd53df-e18d-535b-8677-0f1da1f1e484 |  | note | Frequency: Within 1 month prior to commencement of works
label | 530fbe38-37c8-5ced-a62e-db36da64371c |  | note | Acceptance Criteria: Not more than 2.5% for crushed aggregate; not more than 2.0% for uncrushed aggregate
label | 0e3b4dbf-8fce-5027-94da-507ee90f10ed |  | note | Reference Documents:
label | 971627fd-274b-538b-9f03-5bf35f234318 |  | note | • GHD-DD-SPC-001 5104(c)
label | 4424598f-0c1c-5153-b976-bfe2c04d41f2 |  | note | • Table 5104-2, 5130(a)
label | 091565bd-a50f-5ff0-b736-5667ce838d8b |  | note | • HP5130-1
label | 075cb748-94d6-50a9-ad5d-b393ca3462bc |  | note | Inspection/ Test Method: AS 1141.5
label | 8495ef6f-da02-54a1-be0e-9dd95e5723bc |  | note | Record of conformity: NATA-accredited test certificate
label | 674686eb-7614-524e-84b3-920ca0b4c20c |  | note | HP
label | 31e95f52-10f5-534d-8498-d3bf10315971 |  | note | Responsibility: Technical Manager
text | 614b85d4-4305-5c30-b465-7045cfe3500b |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.03 - Linear shrinkage
label | 15290377-6329-565c-8cbe-fed2ca2f9631 |  | note | Frequency: Within 1 month prior to commencement of works
label | 3da80d33-0b0d-5379-951f-29556005d256 |  | note | Acceptance Criteria: Not more than 1%
label | cad33a55-f83e-56fc-9300-2b51d0eaa25a |  | note | Reference Documents:
label | 26eda95e-b551-5e24-85f4-b608dc571887 |  | note | • GHD-DD-SPC-001 5104(c)
label | 77d5c959-9c7d-52da-a401-a117c4d00330 |  | note | • Table 5104-2, 5130(a)
label | f0e31f0b-87a8-5281-b654-7b8182959482 |  | note | • HP5130-1
label | 2dcbe8db-91a4-51a1-b4cd-0018ba9f24a5 |  | note | Inspection/ Test Method: AS 1289.3.4.1
label | cd46b4d3-91e0-5f52-bb2a-eee08fc6a217 |  | note | Record of conformity: NATA-accredited test certificate
label | 38482945-114c-516a-97cd-467b4254dfee |  | note | HP
label | 3a71ee9f-6e3d-5515-9f20-3228088cdd75 |  | note | Responsibility: Technical Manager
text | ae296f39-543d-5468-a69a-9da179bd28da |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.04 - Methylene blue adsorption value (MBV mg/g)
label | fb20a91c-2c8e-5d76-b607-65ea2b1efe67 |  | note | Frequency: Within 1 month prior to commencement of works
label | 2f183746-5426-5be5-8b40-184e360a5649 |  | note | Acceptance Criteria: Not more than 10
label | 5a123d61-8a87-5d27-af59-2a48fbfea339 |  | note | Reference Documents:
label | 127793e5-dfbd-5f3e-a8eb-649a76abd082 |  | note | • GHD-DD-SPC-001 5104(c)
label | ade293f2-8a28-525a-bf1f-9928e0d1d1cf |  | note | • Table 5104-2, 5130(a)
label | e37ed9bf-1eaf-5fa9-a736-d1fa8ebceeac |  | note | • HP5130-1
label | d96cac74-1236-5d57-9e3b-1db82d9cbdbc |  | note | Inspection/ Test Method: AS 1141.66
label | 86ab1e21-2ae6-5b75-99ef-b4bd37c36ee2 |  | note | Record of conformity: NATA-accredited test certificate
label | 5855f69f-521f-5971-bb0b-cc2e3a46319d |  | note | HP
label | c44f55e0-dc89-5559-a01e-77a254ffec1a |  | note | Responsibility: Technical Manager
text | f832541c-8fb9-587c-b3f8-bcd7c9585e19 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.05 - Supply of reference samples to the Contract Administrator
label | bdf395ce-c4f4-59a9-b59c-f7720a11ff0b |  | note | Frequency:
label | 1bdc7f93-ae58-5fa3-a389-e0eb0eb020ce |  | note | • After acceptance of conformance certification for coarse aggregate properties has been accepted by Contract Administrator.
label | 8cda7747-5aeb-5448-8735-4117210f4aeb |  | note | • Prior notice (minimum 48 hours) of time of inspection to be given to Contract Administrator.
label | 9941430a-d8c0-5f29-9af4-ee053e353c38 |  | note | Acceptance Criteria:
label | 489efe45-2ac1-51ab-ab97-b574b9fea253 |  | note | • Three split samples of each aggregate fraction to be bagged and labelled. Minimum quantities for each aggregate fraction:
label | 27c60cc7-fd3d-5480-b7cf-0718789d5873 |  | note | ○ Crushed fine aggregate: 20kg
label | de6cb35e-fbec-5035-9739-245586a7c9a5 |  | note | ○ Natural sand: 20kg
label | c9682daf-5f5d-57a6-af71-6ae70d3fddbb |  | note | Reference Documents:
label | bcaf8fe9-6210-5fe2-9c82-55692a4f232c |  | note | • GHD-DD-SPC-001 5130(b)
label | b651d83e-ff0a-56bb-b933-0e92ab561b2a |  | note | • WP5130-1
label | 781e852b-c46d-51f6-a0cd-0a03efd509e0 |  | note | Inspection/ Test Method: Inspection
label | 266f6e8b-52e5-57da-9a9a-cf353fd3960e |  | note | Record of conformity: Receipt of samples by the Contract Administrator
label | 818cbce2-633b-5c31-b2b1-e024542031e2 |  | note | WP
label | 2a828300-2e23-57ce-9e4a-a7f83e0a3cc1 |  | note | Responsibility: Technical Manager
text | 4213cc1e-5ee3-5b00-a44b-d43e605e30d2 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 2 Quality Assurance - Production
checkpoint-status |  |  | checkpoint | 2.01 - Particle size distribution
label | 6febb2b5-24e0-570a-a695-fc37a94f4bfc |  | note | Frequency: 1 test per lot (see Note 1, Note 2) of 500 tonnes aggregate, not less than 5 days prior to use in production of asphalt.
label | 6c600191-56c3-56f5-87ca-21848e694847 |  | note | Acceptance Criteria: To be reported.
label | 4f3e7d2f-9162-526a-b67e-512dcaf876aa |  | note | Reference Documents:
label | f9dab626-3348-56fe-9a17-b56435571ca0 |  | note | • GHD-DD-SPC-001 5131(a)
label | 4e7c14a4-d4c7-5d5a-969f-8ef3e76cf48f |  | note | • Table 5131-2
label | 01340b2d-f880-536b-93dc-4a89b23a6d6b |  | note | • HP5131-1
label | 8747ee98-6f78-576a-9ef9-0035385d7f08 |  | note | Inspection/ Test Method: AS 1141.11.1
label | c5b39c82-600a-5a12-9b7d-f743f4af50a5 |  | note | Record of conformity: NATA-accredited test certificate
label | 54590a88-070c-5347-b04f-6fbeb6aebf05 |  | note | HP
label | 87c1e5c2-33dc-522f-82bf-6f6753b46476 |  | note | Responsibility: Laboratory Technician
text | 2b49dbfe-fe7d-5615-8cf0-5efcf99022d7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.02 - Plasticity Index (wet preparation method)
label | cf1e7a96-dc35-5633-8d8f-535ee475fb68 |  | note | Frequency: 1 test per lot (see Note 1, Note 3) of 1000 tonnes aggregate, not less than 5 days prior to use in production of asphalt.
label | 63c81912-2215-537e-8c7c-485cd0d9c959 |  | note | Acceptance Criteria: To be reported.
label | 2c77b91e-9e4a-52fc-aaf8-8a166ed0b419 |  | note | Reference Documents:
label | 521cf384-5b55-55fc-bafa-2ffe8c6b6ea7 |  | note | • GHD-DD-SPC-001 5131(a)
label | 0ff744ac-0db8-5d02-9be1-11744b4bd0b7 |  | note | • Table 5131-2
label | 5ca7e113-0db9-592f-b06b-a7166aee6a11 |  | note | • HP5131-1
label | 4a0ab7f5-a48f-5f79-a2d0-0d6be8d96d0f |  | note | Inspection/ Test Method: AS 1289.3.3.1
label | d02a123f-19bb-5fd7-8be8-de1bc21b40d0 |  | note | Record of conformity: NATA-accredited test certificate
label | ce2aae7f-b4ed-54fe-9777-bf3c97f559f3 |  | note | HP
label | ada41a48-5e9c-5bf7-adb7-79d5cd00234d |  | note | Responsibility: Laboratory Technician
text | 33a65324-8bb2-527b-a201-4f006f8a44c5 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.03 - Linear shrinkage (wet preparation method)
label | 4d885386-c4a5-5cc9-9977-d92adb3c5b4a |  | note | Frequency: 1 test per lot (see Note 1, Note 3) of 1000 tonnes aggregate, not less than 5 days prior to use in production of asphalt.
label | 3045b694-8dc5-5365-8e77-11ffd384eefb |  | note | Acceptance Criteria: Not more than 1%
label | 2fe57623-ddda-5474-a336-528d69a44099 |  | note | Reference Documents:
label | c3f26277-a228-5866-a579-4bafed2667f3 |  | note | • GHD-DD-SPC-001 5131(a)
label | 0817325a-607f-5a03-88c8-4317cf57029b |  | note | • Table 5131-2, Table 5104-2
label | 019f1c50-91dc-5970-90fe-65ce80c7c582 |  | note | • HP5131-1
label | f9d7f480-39f9-5033-b0a1-31ed5c519eea |  | note | Inspection/ Test Method: AS 1289.3.4.1
label | 249f295e-bed2-560b-9e32-7f599a433583 |  | note | Record of conformity: NATA-accredited test certificate
label | 07d3ceb2-a8a4-53d1-9280-f50bb8224602 |  | note | HP
label | c9e46ce8-56a2-5fd1-b9ff-86fd8a468975 |  | note | Responsibility: Laboratory Technician
text | 0a64ecfe-3cac-5744-82d5-9b2ece8ce3b6 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.04 - Apparent particle density
label | ceaa63e0-e9d1-5186-a700-06c3e7422d6c |  | note | Frequency: 1 test per lot (see Note 1) of 1000 tonnes aggregate, not less than 5 days prior to use in production of asphalt.
label | f08d825d-5399-5ef9-a5bd-3f51ae9d5384 |  | note | Acceptance Criteria: Not less than 2,300 kg/m3
label | 76bed8b6-df11-5902-bd97-697c2ac240e6 |  | note | Reference Documents:
label | a1f4cf08-7f6b-5d74-9564-e1ccb1e28337 |  | note | • GHD-DD-SPC-001 5131(a)
label | a1540135-a194-5e7d-8fbc-10b64d2ac587 |  | note | • Table 5131-2, Table 5104-2
label | b7fcb652-f445-5238-a44b-b926d046332c |  | note | • HP5131-1
label | e1df6acb-07a0-5f9e-bbe8-c68d178390d9 |  | note | Inspection/ Test Method: AS 1141.5
label | d1451974-ca4a-58f0-91e2-462bb86272c9 |  | note | Record of conformity: NATA-accredited test certificate
label | 999d64a5-99ba-5a6d-b925-8bde5e05d400 |  | note | HP
label | 536bbbb1-bf7e-5234-9958-2b39f6cc3f91 |  | note | Responsibility: Laboratory Technician
text | 45295286-8f3c-52ec-8650-78404cfe4458 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.05 - Water absorption
label | 483980b1-28ce-5bb9-8251-d5eee35924ba |  | note | Frequency: 1 test per lot (see Note 1) of 1000 tonnes aggregate, not less than 5 days prior to use in production of asphalt.
label | aeb7428e-5da2-523f-acdb-f9e5752a12ef |  | note | Acceptance Criteria: Not more than 2.5% for crushed aggregate; not more than 2.0% for uncrushed aggregate
label | b3e0be1c-a491-59c8-9d35-115e7312f675 |  | note | Reference Documents:
label | fcbc2b96-3162-54c1-b5b8-957d99e25cbb |  | note | • GHD-DD-SPC-001 5131(a)
label | 2e44d238-01c3-55a4-abdc-f724e34e77c3 |  | note | • Table 5131-2, Table 5104-2
label | c7d7e130-806b-5b06-927f-a441a85b8c05 |  | note | • HP5131-1
label | e4c54c18-3a10-54e8-85ba-2b6210e86fc2 |  | note | Inspection/ Test Method: AS 1141.5
label | 3c721d04-8876-5e2a-b722-0992fbac4cf5 |  | note | Record of conformity: NATA-accredited test certificate
label | 0be48e04-364f-5529-8b68-c08fe3220279 |  | note | HP
label | 198efcbd-3105-5e9b-9662-5a0444ca1b57 |  | note | Responsibility: Laboratory Technician
text | 96a35d3a-0254-5f86-9ce5-9ffd6eff271b |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-no-status |  |  | checkpoint | Notes
label | c391557a-bfc8-5497-9a45-7a205aa32266 |  | note | Note 1: A change in crushing plant parameters will initiate the start of a new lot.
label | 7857f235-5ad3-5b56-9833-e2fb7801a736 |  | note | Note 2: A change in the crusher plant screens will initiate the start of a new lot.
label | 760b3a30-b48b-5d18-831f-a8a5e7bc6719 |  | note | Note 3: Changed from 1 test per 500 tonnes to 1 test per 1,000 tonnes of aggregate as per FHPL-RFI000097
checkpoint-status |  |  | checkpoint | Final Inspection
label | 174c56df-f796-50ec-a6e2-50246dedf8f1 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 8f07ee2b-cc8a-5012-add6-be7d1d12ee21 |  | textbox | Print Name:
text | 75e57e9b-5355-5f21-a3c5-6dbab0d7eb5f |  | textbox | Position:
text | a8e7b5cd-5fb8-5eb9-b9b7-d5a4ebf09e2f |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP017 - Mixing Plant Establishment and Trials | itp |  |  |  | Yes | ITP017 - Mixing Plant Establishment and Trials | cac38fdd-61aa-45a7-803d-114f23725683
checkpoint-group |  |  | section | 1 Preliminary
checkpoint-status |  |  | checkpoint | 1.01 - Bituminous material sources
label | d3dcd67d-0db6-5764-9a79-608b0698ed6f |  | note | Frequency: Not less than 5 days prior to the commencement of asphalt mix design.
label | 9fc1e775-0c5f-5b10-bd19-7b5c2c24809d |  | note | Acceptance Criteria: Submission of source, name and address of manufacturer(s), manufacture information and test certificates for bitumen.
label | 38c7bdeb-cb78-5456-b529-bb5e0432e5f7 |  | note | Reference Documents: GHD-DD-SPC-001 5130(c) HP5130-2
label | e7809b22-bbe8-5145-9df3-4e15655947e8 |  | note | Inspection/ Test Method: N/A
label | f4b1c0a8-c721-5da8-b96a-360f82177996 |  | note | Record of conformity: ITP
label | 11db5755-c314-5bf9-a3ea-1a3ad3130459 |  | note | HP
label | e3d4887d-eadf-5495-acb7-3c99d455888f |  | note | Responsibility: Technical Manager
text | 71dbb70e-e0c1-56f0-9f73-4f151fb70f23 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2 Mixing Plant Establishment
checkpoint-status |  |  | checkpoint | 2.01 - Notification of calibration
label | 2e1fc651-29ef-5f6b-9f05-93b46f00b1e4 |  | note | Frequency: Not less than 48 hours prior to each calibration of mixing plant.
label | 97a88089-1309-52c1-b8a4-a163662d2112 |  | note | Acceptance Criteria: N/A
label | f6b71039-d0d6-54c2-a8b8-ff52b1e5bfd8 |  | note | Reference Documents: GHD-DD-SPC-001 5112(i) WP5112-1
label | d870cc94-55e5-5015-b98e-328d5c811553 |  | note | Inspection/ Test Method: N/A
label | e0f17798-a5ee-5109-a35d-fa7cb1a0fcb1 |  | note | Record of conformity: ITP
label | be3b3514-a5b2-55a1-ae8e-4295ababa272 |  | note | WP
label | d5c531e8-fcca-5798-8344-c839f99b1174 |  | note | Responsibility: Technical Manager
text | 846b7e5c-0fd9-523a-8e19-ef221e168cfa |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.02 - Calibration of mixing plant
label | 6796f78b-0238-5ab1-8c9b-b6b7e25df138 |  | note | Frequency:
label | 1da333ff-c99c-5a55-ac3e-aaa34dbb745a |  | note | • Not less than 48 hours prior to the commencement of production mix trial.
label | 162278aa-c8a6-5b60-baa2-7369a3fa1c37 |  | note | • Must include:
label | 928b2ac2-050a-5156-b040-0eb6797c5aa7 |  | note | – Establishment of cold feeder rates of flow, batch masses, mixing cycle times, plant production rates.
label | ca732381-9eaf-5bc1-a7be-6a9b8f4c5334 |  | note | – Adjustment of the aggregate, filler and bitumen feeder compensators to provide accurate readings for the actual materials used.
label | 9527d87e-3b20-543d-a7c3-6c538c894ce7 |  | note | – Confirmation of the accuracy of the plant recorders by checking actual masses on an independent weighbridge.
label | 7ce5608f-3871-53c0-9672-7f918731cb56 |  | note | Acceptance Criteria: Acceptance of calibration report by Contract Administrator
label | b2a001ca-9867-5a29-8505-6c3ac8d9051d |  | note | Reference Documents: GHD-DD-SPC-001 5112(i) HP5112-3
label | 156e93b6-63e5-5a19-9b85-a63b4d8158d0 |  | note | Inspection/ Test Method: N/A
label | 687b4a25-ddb1-5de4-b98e-cb860077bb78 |  | note | Record of conformity: Calibration report
label | 819b5f4f-0b75-5fe9-b6e3-0509c9cf22b2 |  | note | HP
label | 85661653-4f18-5168-b3c8-1933ad83980a |  | note | Responsibility: Technical Manager
text | 4266c3a7-1c5b-5609-9052-05276441df65 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 Production Trial
checkpoint-status |  |  | checkpoint | 3.01 - Assessment of mixing plant.
label | f1d034e9-b12f-5029-a03b-03ae171b5e57 |  | note | Frequency: Not less than 4 weeks prior to the commencement of a production mix trial.
label | 7f9db29a-a98f-5fcc-b4c9-bca59a7aec7e |  | note | Acceptance Criteria:
label | 02298f67-c6b3-5e47-8dab-a7aa97e11fa6 |  | note | • Submission of production capacity and hot asphalt storage capacity for the primary mixing plant proposed for production of asphalt for the works.
label | 947d64a9-ac84-53f5-9394-527c952ace2c |  | note | Reference Documents: GHD-DD-SPC-001 5112(h) HP5112-2
label | 66690c68-bd6b-5a54-b87b-e280bab094b7 |  | note | Inspection/ Test Method: N/A
label | 32ab7a88-0a8d-5c93-8ccc-ac5a6c054d84 |  | note | Record of conformity: ITP
label | 9255b92b-7fe7-58d4-8a46-5cc9239d705b |  | note | HP
label | 60c0df23-0013-5b8d-b602-987bfc936735 |  | note | Responsibility: Technical Manager
text | 2be3ee72-fd32-5580-99bf-72563d7c7822 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.02 - Mixing plant calibration charts.
label | 5bad8281-a4d0-5cc3-8936-6433e43a8a42 |  | note | Frequency: Prior to each production mix trial.
label | 5e07f82d-0928-58f7-b78b-46afadb6ec4c |  | note | Acceptance Criteria: Submission of mixing plant calibration charts to Contract Administrator.
label | 4e2b80be-3745-5e29-bff0-27f2ce366f3f |  | note | Reference Documents: GHD-DD-SPC-001 5110(b) HP5110-1
label | 9759bb21-9888-5e30-a2a2-6d4fac537325 |  | note | Inspection/ Test Method: N/A
label | da2bf739-5f1c-56dd-8179-a4fe70e28fb8 |  | note | Record of conformity: ITP
label | f3fc258d-1441-5773-b8ca-674feaebdc5a |  | note | HP
label | c6e11899-9b48-5e23-b526-a990d3dc2028 |  | note | Responsibility: Technical Manager
text | 043f8a82-d8e3-5257-9a5d-6a7125d97c24 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.03 - Notification of production mix trial
label | a61599d0-bc70-5792-9ac5-6d85c5ecd1ce |  | note | Frequency: Not less than 48 hours prior to the commencement of a production mix trial.
label | 24eb2b68-0b5d-5215-aeeb-0e09d4e0085b |  | note | Acceptance Criteria: N/A
label | 1ec1c2ed-b5bd-5b90-8a2e-990af4f49484 |  | note | Reference Documents: GHD-DD-SPC-001 5110(c) WP5110-1
label | d63abfd8-08f3-5d2e-abfa-06510acab4c6 |  | note | Inspection/ Test Method: N/A
label | e33ae3bc-ca8e-5d02-a185-aa82d239ccaf |  | note | Record of conformity: ITP
label | 35ca8852-1416-5f3a-8a18-7b15ffd79d76 |  | note | WP
label | 01a7e456-9fbf-5d2f-a231-5275726b1762 |  | note | Responsibility: Technical Manager
text | f9d5c2cf-9d3e-5aa9-9115-c4120da2a98e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.04 - Submission of results for production mix trial.
label | c417e3ef-c6a6-5cc4-b9f4-f0fac8c294df |  | note | Frequency: After each production mix trial for each nominal mix size produced in the trial.
label | a7693641-f1d7-55f0-b71b-17e53489e922 |  | note | Acceptance Criteria:
label | 32911c1e-0bd1-52df-8e3f-63976c2eb080 |  | note | • All test results on each nominal mix size produced in the production mix trial submitted to Contract Administrator, and written advice to the Contract Administrator of any adjustments to the mix which are necessary to achieve the properties of the submitted mix design.
label | 0f813766-4243-52af-8541-1849fe239206 |  | note | Reference Documents: GHD-DD-SPC-001 5110(e) HP5110-2
label | e0c8315d-2b7f-5167-b906-6498db9d04d5 |  | note | Inspection/ Test Method: N/A
label | eeee79f6-ac57-5c6d-bc10-06bec52f9dc3 |  | note | Record of conformity: NATA-accredited test certificates
label | daa40372-3ae3-51ed-a635-1a3043880254 |  | note | HP
label | 11778f90-2fe6-530f-ad98-a38600c8b857 |  | note | Responsibility: Technical Manager
text | 5cfd41f0-11bb-5a21-8079-345f6f9b19e1 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.05 - Submission of results of verification testing of asphalt mixing plant devices against direct measurement of bitumen tank with production trial test results.
label | 69dcf0f5-e3d6-5cb5-8cee-363a9dacdb33 |  | note | Frequency: After each production mix trial.
label | 32c5e045-743d-5bbd-8cbd-7cffe874c0a1 |  | note | Acceptance Criteria: Acceptance of verification test results by Contract Administrator
label | 0c2f4410-9816-5e38-8ebe-2fca5d52bfd0 |  | note | Reference Documents: GHD-DD-SPC-001 5112(g) HP5112-1
label | 88d26204-6481-5e29-87da-7ba36f703040 |  | note | Inspection/ Test Method: N/A
label | 6a12c27e-426c-5d2a-86af-1e6d0b123902 |  | note | Record of conformity: ITP
label | c4e56261-0a40-5603-a43c-6c33a1c70703 |  | note | HP
label | 0fccc9ae-a075-5e3c-9662-f0c8113e5053 |  | note | Responsibility: Technical Manager
text | 1d25ea82-19c5-5f48-8e6c-c5dd06b7cc3f |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4 Construction Trial
checkpoint-status |  |  | checkpoint | 4.01 - Bitumen emulsion.
label | 0784790c-abd7-53ee-b662-db9a21608ea9 |  | note | Frequency: Not less than ten (10) days prior to the commencement of construction trial.
label | 06ff6e90-93ec-5caf-b0d6-1c027ad17f73 |  | note | Acceptance Criteria:
label | 59e676c9-07d0-52df-9d34-c8bd0f1fc5c8 |  | note | • Submission of source, name and address of manufacturer(s), manufacture information and test certificates for bitumen emulsion.
label | 67bfba41-e05b-50f1-a96c-93b5b1703763 |  | note | Reference Documents: GHD-DD-SPC-001 5130(c) HP5130-3
label | 351ae26b-689d-5202-8d4c-1db0c750df2b |  | note | Inspection/ Test Method: N/A
label | fa5a37bf-d5aa-5573-bd35-37b8e798934a |  | note | Record of conformity: ITP
label | 289224e9-4b81-596f-a860-cfcff02a8004 |  | note | HP
label | d2a71c96-a090-5350-85a2-5bd0cca5d596 |  | note | Responsibility: Technical Manager
text | bcaf1704-df27-54cc-b335-58ef36995e84 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.02 - Mixing plant calibration charts.
label | be69fdd1-b5f3-5097-8769-2c2384a148ca |  | note | Frequency: Prior to each construction trial.
label | 807c0a4b-8e48-5b04-98bb-0e9f020be954 |  | note | Acceptance Criteria: Submission of mixing plant calibration charts to Contract Administrator.
label | 58f51d41-9803-588f-8254-1417971bfb56 |  | note | Reference Documents: GHD-DD-SPC-001 5111(b) HP5111-2
label | 52284d09-8d83-580b-a1f4-456e10db3845 |  | note | Inspection/ Test Method: N/A
label | 744cc8f9-2f54-5aec-b267-afdc4103f909 |  | note | Record of conformity: ITP
label | ba7b84f9-076d-5450-9e38-32b21b9b221b |  | note | HP
label | 4e0a5631-07da-58af-97e8-fad4d52d4e60 |  | note | Responsibility: Technical Manager
text | 31549e23-1de6-5ee0-b1bb-46c2d10a81bb |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.03 - Commencement of construction trial.
label | 86068b4f-8a69-567d-bfcf-a568e103b401 |  | note | Frequency:
label | 32af8ed9-4afd-54ea-b392-d5438cd356f1 |  | note | • Not less than five (5) days prior to the scheduled commencement of asphalt paving works.
label | 8f46ea7a-9a17-5d8a-a444-a420d821a689 |  | note | • Prior notice (minimum 48 hours) of commencement of trial to be given to Contract Administrator.
label | acb05cdf-3829-56c8-b87e-ed5f31ba38ec |  | note | Acceptance Criteria:
label | 7838049c-69a1-5af5-a89e-fdafc287d296 |  | note | • All resources required for a trial of minimum tonnage 40 t of each nominal mix size, placed in a minimum of two paving runs, with a joint suitable for testing, are available and all arrangements for the trial have been made.
label | 1438ccfb-f551-53ba-83d6-ee4aa0642598 |  | note | Reference Documents: GHD-DD-SPC-001 5111(a) HP5111-1
label | 5d6da315-2308-595c-abf6-e86f5cc589bd |  | note | Inspection/ Test Method: Inspection
label | 858adbdf-a4d7-577b-9756-33f56df504cc |  | note | Record of conformity: ITP
label | 5e0a63c8-94f4-51b5-bcfc-616f9c7d0545 |  | note | HP
label | 63445017-eae2-5088-992c-1545bcec652e |  | note | Responsibility: Site Engineer
text | c50af8e5-270c-5b50-a53d-91b7acc71bb8 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.04 - Extraction of cores from construction trial sections.
label | 0996c294-705a-54af-a733-346c82471ad2 |  | note | Frequency:
label | 09debee1-8e68-5bb4-8390-7724cf9126ba |  | note | • At the completion of each construction trial, after the asphalt has cooled to ambient temperature and not more than 24 hours after construction.
label | df551e18-8207-5bdd-bfc0-6560aa86d309 |  | note | Acceptance Criteria:
label | fbf7e522-27ab-5df8-a7d4-f4c2440b2106 |  | note | • A minimum of six (6) cores are cut from within lanes, and six (6) cores are cut over a joint. Cores are not less than 100 mm diameter and are cut from the finished asphalt construction trial section.
label | 9c040c37-868b-5e0e-8793-ec1d47b9ff8b |  | note | Reference Documents:
label | 8aa3e270-4fb8-5674-8f8f-316a60ae51eb |  | note | • GHD-DD-SPC-001 5111(c)
label | b217de8a-7db8-5c10-b53d-505eeea150c0 |  | note | • 5132(b)
label | 85e655bc-f163-5af6-a509-49955918f060 |  | note | Inspection/ Test Method:
label | 47e0a0e6-c78d-5503-9b89-5a5c682b5ef6 |  | note | • AS 2891.1.2
label | 347c42d2-5117-56d6-af2b-caa66caea846 |  | note | • AS 1289.1.4.2
label | 8a354d34-57a6-5d8c-8be4-71e7bf310569 |  | note | Record of conformity: ITP
label | 54d84d89-c4f1-5e8e-acc0-951b9f034041 |  | note | IP
label | 590d09d8-ce17-5892-ab63-e757358ff225 |  | note | Responsibility: Site Engineer
text | 1dddfa89-595c-5922-8ff0-38a80e161da9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.05 - Repair of core holes in construction trial sections.
label | 076e2eb3-be47-50c6-8b4e-a6b413289772 |  | note | Frequency: At the completion of core extraction.
label | 912b4836-5b85-5f73-98e1-004e1fd970fb |  | note | Acceptance Criteria:
label | 91fd63f8-bd7b-55e8-841c-2bd11a559284 |  | note | • All debris, slurry and water has been removed from the core hole and the core walls and floor are completely dry prior to reinstatement.
label | 30b7c13b-ff73-5a7c-a5ca-78de97021a67 |  | note | • Tack coat has been applied to the walls and floor of core hole, and the hole reinstated with hot mix asphalt approved for use in this project and placed and compacted in lifts not more than 50 mm compacted thickness.
label | 0f74e5b2-115d-5a8e-a817-cd2c23cc846c |  | note | • The filled hole is flush to the surrounding pavement surface.
label | 00c99ac4-ddce-52b1-9e6f-7ce10187fbc8 |  | note | Reference Documents:
label | c85c58a7-cc6e-5d7f-ac42-623040440d1b |  | note | • GHD-DD-SPC-001 5111(c)
label | 8a7ffab8-c03b-5ba3-ac2a-68d2faf03341 |  | note | • 5132(b)
label | b8648344-184e-5676-8fb5-ae1172ee357b |  | note | Inspection/ Test Method: Inspection
label | 15cd6336-3ae9-52c4-bdd7-87f12607111c |  | note | Record of conformity: ITP
label | ab9dc6e2-be97-545a-972e-569c21329b29 |  | note | IP
label | 4c88c25a-d1ff-5214-bade-d994a5f5dfa6 |  | note | Responsibility: Site Engineer
text | 6054884d-a5ad-5507-bc63-4e362cd4b2b6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.06 - Layer thickness of construction trial section.
label | 4f2d399a-5105-5139-948f-b069066b522d |  | note | Frequency:
label | 30d89cf4-8d38-5124-9437-3635bdb1d0ba |  | note | • At the completion of each construction trial and prior to the commencement of full scale production and placement of asphalt.
label | c0c74b60-b6ef-5d84-828a-93925a89589c |  | note | Acceptance Criteria:
label | 9a9f2a37-d87c-5334-a96f-1ed3fe960b6f |  | note | • The average compacted layer thickness of a minimum of 4 cores is within the accepted range of:
label | 8304ffa1-3a19-5dfa-a5b6-a9753d5d3ca1 |  | note | – Minimum of 40 mm and maximum of 85 mm for 14mm NMS asphalt, or
label | 2814811e-491d-5135-8a00-4819439d761f |  | note | – Minimum of 75 mm and maximum of 110 mm for 20mm NMS asphalt.
label | 20279ddf-6964-58c9-a08a-30416ab23999 |  | note | Reference Documents: GHD-DD-SPC-001 5111(c)
label | 6815714e-61a1-5b11-8217-f3fc06eb849b |  | note | • Table 5120-1
label | 4c6d72fa-fe07-5a64-b738-368d1c28929e |  | note | • 5132(e)
label | e3a317ed-4b32-5094-ab4d-25ea88944c9e |  | note | Inspection/ Test Method: AS 2891.1.2
label | 26ea30a8-4131-570a-b994-6e700eb2220b |  | note | Record of conformity: NATA accredited test certificates
label | b860f769-300b-539f-a1a1-67ded233db12 |  | note | TP
label | 29183ee3-ee13-5026-b613-2a5444c08c67 |  | note | Responsibility: Site Engineer
text | 403e4ae4-0f88-5057-90a9-7da0e558a313 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.07 - Compaction of construction trial section.
label | 122e39eb-ee2e-5302-be0f-95e434e8441c |  | note | Frequency: Within 24 hours after the completion of each construction trial.
label | 2f61df66-9cf3-5fad-bf40-f84451c4e992 |  | note | Acceptance Criteria:
label | 4726050a-07ed-5180-b43e-4da2199f2ad7 |  | note | • Characteristic value of air voids are within the range of:
label | abe94b2f-6927-5817-ab63-3ffd454bd459 |  | note | – Surfacing layers: 3.0-6.5% inclusive for mat and 3.0-8.0% inclusive for joints, or
label | c157e2ab-42ce-526e-9281-840bac941cd1 |  | note | – Base layers: 3.0-7.0% inclusive for mat.
label | d4169b6a-4c5d-59e5-a9c1-46ed497dc71e |  | note | Reference Documents:
label | 1a83fa0e-5ab8-5b23-9194-27be29a5f2f9 |  | note | • GHD-DD-SPC-001 5111(c)
label | fb321463-b0b8-5bdd-9488-0c1ec73e4332 |  | note | • 5121(c)
label | c9ae37a7-ebd2-5cee-ba3b-569d166f71b3 |  | note | • 5132(c)(d)
label | aafec80d-1058-53ff-a280-0cb489ca9142 |  | note | Inspection/ Test Method:
label | 24a2c590-e19e-578e-9043-8c007390a338 |  | note | • AS 2891.9.1
label | 80a80851-205b-59fb-9707-3e58112adee9 |  | note | • AS 2891.9.2
label | 44faf643-5b49-5255-9a56-a6b315490bc6 |  | note | Record of conformity: NATA accredited test certificates
label | e0ff1cea-6bef-5f43-8b4d-8891c092e121 |  | note | TP
label | 7c2a1251-ee5b-5965-829d-723eb5d3b7cd |  | note | Responsibility: Site Engineer
text | 686044d9-6a18-5103-b5b4-e34891f14dcd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.08 - Finished surface levels of construction trial sections.
label | ab0b15f8-2fb7-5202-a57b-19d02d5c9ac9 |  | note | Frequency:
label | 28875bb3-5b58-5c27-8540-c9c0185c6969 |  | note | • At the completion of each construction trial and prior to the commencement of full scale production and placement of asphalt.
label | bc9befa0-fe7d-508d-864d-af484d60253b |  | note | Acceptance Criteria:
label | 32215a1a-d3d3-57ed-b79a-155141027e4d |  | note | • All finished surface levels have been surveyed to an accuracy of 2 mm with readings to 1 mm by a licensed surveyor.
label | 4fdea273-a33a-5e4c-8ad8-a0d55065389c |  | note | Reference Documents:
label | be07854a-bd49-5f9c-a9cc-fc257a9c8241 |  | note | • GHD-DD-SPC-001 5111(c)
label | f94fbe38-22c4-56aa-bccd-9359a205866b |  | note | • 5132(f)
label | c519292f-d09b-50b0-92ef-c3d9de18181f |  | note | Inspection/ Test Method: Survey
label | a69661a9-e802-527f-b3bf-257fbe174596 |  | note | Record of conformity: Record of finished surface levels
label | 86d05bbc-bbe0-5d02-93f8-e6b9311b8853 |  | note | IP
label | df59b096-580f-59f8-80f5-64ff0e6c8676 |  | note | Responsibility: Site Engineer
text | 2bb209df-cf58-5f4b-970b-229a928c60ba |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.09 - Surface smoothness of construction trial sections.
label | 0cfc8479-3f0a-5d70-9cd9-6149366a8c27 |  | note | Frequency:
label | f50b1c58-e475-5963-8f0d-b2cb0198c0c5 |  | note | • At the completion of each construction trial and prior to the commencement of full scale production and placement of asphalt.
label | e32bec6e-541c-53da-8eb9-e63598ff0be6 |  | note | Acceptance Criteria:
label | a7424e79-7551-593e-80c0-51b62d913624 |  | note | • Surface smoothness has been tested in each placing lane in longitudinal direction parallel to the centreline, and in the transverse direction at intervals not exceeding 10 m using a mobile straight edge operated at a speed not exceeding 5km/hr.
label | 02942007-7481-58c4-99a1-0d5cb0586303 |  | note | • The finished surface complies with Item 3.14 of this ITP.
label | c0cd0246-eb89-56f7-ad35-d6b236eb51fc |  | note | Reference Documents:
label | d7b21c6c-e6ef-50ce-b447-db812678eb1f |  | note | • GHD-DD-SPC-001 5111(c)
label | 77da32e8-8a0e-5669-aec1-7254fac3fb70 |  | note | • 5132(g)
label | d65eb679-31d4-5f02-9882-e495490c46af |  | note | Inspection/ Test Method: Straight edge
label | 3bb78f10-c2e3-59d9-8417-066b892c6a6c |  | note | Record of conformity: Record of location and extent of any surface irregularities
label | 2147d4ea-7193-581e-84ae-442fd7588815 |  | note | IP
label | 3fca1753-001c-51d7-bf83-7b133193b1b9 |  | note | Responsibility: Site Engineer
text | 198f8009-c86e-580e-85fe-2b14f7818033 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.10 - Completion of construction trial.
label | e6d45e0b-4591-5f8d-a9bb-09526d30e9ad |  | note | Frequency:
label | 6649cb7f-2a03-5d95-8d57-6fb44bed2ee4 |  | note | • At the completion of each construction trial and prior to the commencement of full scale production and placement of asphalt.
label | b2611eea-35a6-5cdb-be55-35a1efafbdfd |  | note | Acceptance Criteria:
label | 7e9dbdf5-7a92-58bb-bd5f-8e24d61bddeb |  | note | • Submission of all test results and written advice to Contract Administrator regarding any alterations in procedures or adjustments to plant and equipment as necessary to produce asphalt in accordance with specified requirements.
label | 1f03c3a6-97de-5654-9917-a6b49926b8c3 |  | note | Reference Documents: GHD-DD-SPC-001 5111(c) HP5111-3
label | 00fd5ddf-223e-59b6-95f4-aa54d2b86761 |  | note | Inspection/ Test Method: Inspection
label | 38cfdad9-82af-55eb-82d2-5c0be2d61cb5 |  | note | Record of conformity: ITP
label | b1152234-962f-534a-8e6b-ddf2933a9b5a |  | note | HP
label | 205230ce-7e9b-523e-8162-b8948007c804 |  | note | Responsibility: Quality Manager
text | e7f95f6e-d041-5c5c-839a-03fe750b8075 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.11 - Selection of reference area for surface finish.
label | c1b68b6b-16dd-5adb-814b-c55f8a8b9800 |  | note | Frequency: After the completion of construction trials.
label | ccf3544f-2619-55ad-b40e-d5f5c044fc81 |  | note | Acceptance Criteria:
label | 68a8c34b-0b0c-5578-9390-5d532f671cb6 |  | note | • Agreement with Contract Administrator of reference area/s for each nominal size mix and photographs of each reference area.
label | 950b6285-a179-5695-9300-a4523b2fcf39 |  | note | Reference Documents: GHD-DD-SPC-001 5111(e) HP5111-5
label | ff434cb7-491c-5de5-bae5-d976fab4c439 |  | note | Inspection/ Test Method: Inspection
label | 31734273-4606-5af8-9298-e1cef57ee3f8 |  | note | Record of conformity: Photographs of reference areas
label | c113b760-ab4f-5683-add4-5a14fa2532a8 |  | note | HP
label | 8f0e997e-ce30-503d-8259-429b763196ec |  | note | Responsibility: Quality Manager
text | 7d90e333-e529-5b16-b697-08f4b7c8457f |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.12 - Supply of asphalt as per job mix.
label | 5a11e04b-a081-54f5-b9b4-c0f5251851bd |  | note | Frequency:
label | a7ea0540-4b5b-5696-8923-49788f7aee1c |  | note | • After the completion of construction trials and not less than two (2) working days prior to the planned commencement of full scale asphalt works.
label | e0180857-e4de-5dde-a1a5-537305431d3d |  | note | Acceptance Criteria:
label | 9f2a9ad1-0662-5bd6-bbcf-2b9a1edfb983 |  | note | • Submission of the complete details of the job mix, job aggregate particle size distribution, job bitumen content, and job mix temperature for each nominal mix size.
label | b39258df-83d5-5b60-bad8-f6c3c89002a6 |  | note | Reference Documents: GHD-DD-SPC-001 5111(e) HP5111-4
label | 57105467-871b-5a69-bf13-e2f8696a41f7 |  | note | Inspection/ Test Method: Document
label | 3636e6e8-75a6-599f-85a9-c8270953cb7b |  | note | Record of conformity: Job mix report
label | 0f681164-7104-5cf4-a3c1-82b2a8b59f34 |  | note | HP
label | 1b57be4c-c41c-5c80-bfd1-412056105b57 |  | note | Responsibility: Quality Manager
text | 6019cd58-8934-5205-9d19-83ca75decc5e |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | a8f0d013-d857-5df9-9a89-98ca9d70e7dd |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | cb822864-f256-5242-9fa3-a3465b0a9f54 |  | textbox | Print Name:
text | 50ed5783-8f3d-5ddc-b504-307ed1c7a2dd |  | textbox | Position:
text | c11f3d20-8d4d-50a1-9de7-31bf70f9d755 |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP007 - Unbound Pavements | itp |  |  |  | Yes | ITP007 - Unbound Pavements | e0f59918-f1ad-489c-b56e-6f0477244c35
checkpoint-group |  |  | section | 1.0 Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
checkpoint-status |  |  | checkpoint | 1.1 - The current revision drawings are being used including subcontractors copy.
label | 5fb72059-bdec-519d-83e6-36855aa307ea |  | note | Frequency: Prior to works
label | a86df616-42e9-5351-907a-fd122004714a |  | note | Acceptance Criteria:
label | 39dbc0b7-f7aa-52f1-98c0-b931c4449399 |  | note | • Current revision drawing is being used including the subcontractors copy.
label | c3675433-df0c-572d-9fe4-02024d80417b |  | note | • Current Revision to be obtained via Principal’s Representative
label | 4ffbc9c4-105a-5def-a747-7f78d6674aa8 |  | note | Reference Documents: ACONEX
label | 178a0ee2-eddf-5a19-abea-7e106edd56d4 |  | note | Inspection/ Test Method: Visual Inspection
label | 7d3518e6-a6e9-51d4-b320-d76b35fe74b1 |  | note | Record of conformity: Current drawings
label | 702b4bc0-9753-5010-b58b-1fa2a3c26991 |  | note | HP*
label | def6b54f-a8b4-5067-a778-892f5dd47a22 |  | note | Responsibility: Fulton Hogan
text | 60508d98-46f1-57d3-89a7-91c49b788803 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - ITP and Construction procedure documentation
label | f8ebfa7f-e876-5f7d-8f81-3d25b2c5d234 |  | note | Frequency: Prior to works
label | 3f7d9c62-5f39-5cb3-a9c5-799db0565661 |  | note | Acceptance Criteria: ITP and Construction procedure for unbound pavement material placement to be provided to Principal’s Representative for review.
label | 123a8682-7cc7-5e40-aa79-ffe065e16a27 |  | note | Inspection/ Test Method: Verify
label | 2352d67b-53f1-5082-a0f6-32ed8b3a3ee3 |  | note | Record of conformity: Approved Work procedure report
label | 72c19a68-923f-589b-bdba-2c19aaddb5fb |  | note | HP
label | 720b6d34-c335-5c8e-a20d-703770f99129 |  | note | Responsibility:
label | 7f77fb01-836e-5cfe-8c42-006ac864b1fe |  | note | • Fulton Hogan
label | 968297ff-57b5-5f2a-bd6d-712d8d322550 |  | note | • Principal’s Representative
text | 792f2f60-a61d-5c13-a32b-897f6108ddc0 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Material classification.
label | 38fb984d-7a06-55a0-924b-82ef2ecff6e2 |  | note | Frequency: Prior to works
label | d9e65db5-43fa-5c96-8f89-1be5fae16029 |  | note | Acceptance Criteria:
label | 07a1ac3f-1c77-5637-b49f-d37affefbe41 |  | note | • Proposed material source information and samples to be submitted to Principal’s Representative.
label | 1e2510f3-6592-5ef2-ab51-0a177de279af |  | note | Reference Documents: VicRoads section 812
label | 85ff3126-13f2-5a08-bc33-967b46db6db2 |  | note | Inspection/ Test Method: Verify
label | db8aba19-8178-55e7-bc05-0ab3b43beac0 |  | note | Record of conformity: Approved rock mix design report
label | e13190c6-6f3d-5798-ae84-115822eb63d1 |  | note | HP
label | b2ab80cf-51b0-5cac-8718-0ff4851eb523 |  | note | Responsibility:
label | 92601a78-9af8-504e-8fc6-f191a2eb093d |  | note | • Fulton Hogan
label | edc19ddc-3742-563a-b199-5f93df928d7d |  | note | • Principal’s Representative
text | cb28f626-104b-5580-a715-84972bd406ab |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.4 - Production testing
label | 114b23df-b509-50bf-9954-ed5da9429066 |  | note | Frequency: Prior to works
label | 32b3e666-abdf-5802-8d3e-25b00ed78278 |  | note | Acceptance Criteria: Supply of information with respect to production testing.
label | 2388d791-2d92-5204-b3de-b5adf3b1e9d1 |  | note | Reference Documents: VicRoads section 812
label | c468f3f3-abeb-581d-9e27-7051b175bbbb |  | note | Inspection/ Test Method: Verify
label | 08783c2f-6956-530f-b66c-99d43a70cc11 |  | note | Record of conformity: Approved production testing results
label | d55acf2b-4f5b-5f92-a454-d3dfb9b601c2 |  | note | TP
label | 76364b95-a9d8-5319-8473-cfc99feaa396 |  | note | Responsibility:
label | 7b41e287-9afd-5ec7-936d-11b12662f70b |  | note | • Fulton Hogan
label | eec93cb0-3229-519e-9b2e-5d34f83201a4 |  | note | • Principal’s Representative
text | c6d3239f-eae5-5ab2-9d75-5b3d385234ce |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.5 - Implementation of all measures and controls.
label | 8afdff1c-3d6b-5619-9b7a-4636a188f19a |  | note | Frequency: Prior to works
label | ade83d52-e14d-53d6-8ba2-eef1459ec090 |  | note | Acceptance Criteria:
label | 80ae3022-bf37-599a-bced-967af5452202 |  | note | • All necessary measures and controls are being implemented including:
label | f121cce1-4432-50d3-bb13-bec3cccd14e4 |  | note | ○ PSP, EMP, TMP, SWMS and WP.
label | a3d0b944-9aca-579b-9ceb-960d66e457fc |  | note | Reference Documents:
label | 3ddd4349-ce49-5155-97e1-6626954eafaa |  | note | • PSP
label | 7e046a71-b4c1-5b8d-acbf-262cf2b959a4 |  | note | • EMP
label | 8a276207-7a09-57c5-8c58-9c5ffdeb4995 |  | note | • TMP
label | d4b745c4-f4ab-51e6-aa66-1aaf401f3447 |  | note | • SWMS
label | 8c80d64a-e25f-5c6c-9280-17b86e0c115d |  | note | • WP
label | 6a9de13c-30d0-59d0-8cd9-7b04aaf43054 |  | note | Inspection/ Test Method: Visual inspection
label | 30bc1335-5f1a-519b-940b-ff63af732d63 |  | note | Record of conformity: Site inspection
label | 0f0f9958-04d5-5e16-b71f-cbdd84094187 |  | note | HP*
label | 25ca562a-b24d-57b3-9b00-1e7657761923 |  | note | Responsibility: Fulton Hogan
text | 53055d6c-0e07-598b-9787-2c4b538ba5fb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.6 - Plant and Equipment
label | 86615659-083b-52f7-9497-4138535aa7c4 |  | note | Frequency: Prior to works
label | de30d32f-87b9-5ab7-a04d-660d746641ba |  | note | Acceptance Criteria: Plant and Equipment used in the works are appropriate to achieve specification requirements.
label | b2e7100d-870f-5845-a0bc-b5a4d8aa154d |  | note | Inspection/ Test Method: Visual Inspection
label | 55b0afdd-4abd-5836-af0f-b6f15b7071c6 |  | note | Record of conformity: Finalised ITP
label | 9109a9b7-52d9-5aa7-8a6e-46cb8a9c8991 |  | note | HP*
label | d5e8cc06-a0f3-5971-b97c-985fa33bbdca |  | note | Responsibility: Fulton Hogan
text | d8383cd0-6786-5bb7-a4d8-9767671edf13 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.7 - Stockpile material on site
label | d2e54f32-8f3a-5d58-9984-58dc4bd57538 |  | note | Frequency: Prior to works
label | 3251eb68-1bc3-596a-9197-41b1af3aee59 |  | note | Acceptance Criteria: Material stockpile locations approved by the Principal’s Representative.
label | 99639137-ed8c-570f-b8a6-559b630e98d9 |  | note | Reference Documents: Stockpile Map
label | ec77cdf7-3f66-5cd3-b991-689888bbcd51 |  | note | Inspection/ Test Method: Visual Inspection
label | 44f3e5a3-3c75-58d8-8aca-8846a838f418 |  | note | Record of conformity: Material receivables checklist (Dockets)
label | 01366522-b21e-5ac0-bfc4-53d38279745e |  | note | AP
label | be022a20-669e-5c4b-a1ac-bd13e2b7368f |  | note | Responsibility: Fulton Hogan
text | ebdcdde0-6b2e-5739-9b60-d6ea572df1c3 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 2.0 Placement of crushed rock base and sub-base
checkpoint-status |  |  | checkpoint | 2.1 - Commencement of construction of the base (Class 3/4/profiling) and sub base (Class 3/4/profiling).
label | 73e8d841-e6ec-5fbd-a442-095e5c50487e |  | note | Frequency: Each lot
label | 692d3800-c0dc-5b70-9dba-6fd02c968a84 |  | note | Acceptance Criteria:
label | 5cbc741d-a57b-51f9-a718-7c85371049f7 |  | note | • The underlying layer shall be clean of all foreign matter.
label | 162cb249-5746-5e68-8136-f1941cbc89b7 |  | note | • All edges of previously placed material must be water conditioned prior to placement continuation.
label | 9f6caf77-4cba-5977-8718-027c15aadf3d |  | note | Reference Documents: VicRoads section 204
label | 96086d4a-9ce1-536b-94fb-3d6e263b0f10 |  | note | Inspection/ Test Method: Visual inspection
label | e684d454-2e02-57c0-b94b-d5354b619a1f |  | note | Record of conformity: Site Inspection
label | 4868e50e-713a-51ab-8b84-cc6aa3338c3a |  | note | HP*
label | f2da1026-373b-5fc2-879b-e2b975771369 |  | note | Responsibility: Fulton Hogan
text | e42f8f4a-e7e9-5ebc-9b93-13ebc96384cb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Placing Crushed rock
label | 4bc364b7-d060-5011-8608-b12c103722cf |  | note | Frequency: Each lot
label | 40b7340b-acce-5a09-b283-9650308f2f79 |  | note | Acceptance Criteria:
label | ca6853b0-f3f3-5ed0-a4d4-996013d78007 |  | note | • The maximum lot size for surface levelling is to be half the size of the working area.
label | bea1aa93-18bf-5d32-a517-083f8a56232c |  | note | • Surface tolerances per layer is as follows;
label | a8d96545-66e0-586e-9403-58c33fc468e3 |  | note | ○ Class 3/4 Crushed Rock/profiling: +0, -10mm
label | 1d0c796f-e57b-5455-8260-bdfb64618ced |  | note | ○ Crushed Rock Working Platform: +0, -10mm
label | 5f2d9cac-933c-5311-b753-4e3d5720619a |  | note | • Pavement layer thickness tolerances as follows;
label | e15de9e2-9714-5dc3-9945-5e44b9a07707 |  | note | ○ Class 3/4 rock/profiling (Base): -10mm. The average thickness over every 100m shall be no less than the specified thickness. Max thickness of any base layer shall not exceed 200mm and be no less than 80mm.
label | 83c1ec9a-a8de-59cf-a0a3-2efda7288fca |  | note | ○ Class 3/4 rock/profiling (subbase): -15 mm. Max thickness of any subbase layer shall not exceed 150mm and be no less than 80mm.
label | 547dcf61-f035-54a7-9b06-1fb8cb5164bb |  | note | ○ The combined thickness of subbase and base course shall be no less than the specified thickness by more than 15mm.
label | d37b8109-219f-589b-aefe-ba348aa689bf |  | note | Reference Documents: VicRoads section 304
label | c94beb86-4b5e-5f55-b627-9d1b28a8da60 |  | note | Inspection/ Test Method: Visual Inspection
label | a4e17d38-1b3f-5a67-8676-7d8041989760 |  | note | Record of conformity: Survey day and Visual inspection
label | 9333b81a-44b6-5a03-b07e-8d7081fcd319 |  | note | HP*
label | 97946913-93a8-5732-b693-3f4cafee110a |  | note | Responsibility: Fulton Hogan
text | a8dfb6dd-8f78-57f7-bdbc-0efe051f4e34 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - Compaction and Post Compaction Testing
label | bf7da061-083a-579f-af2a-e16d78004a0c |  | note | Frequency: Each Individual Location
label | 03107659-fc13-5bac-a532-af1eac1ad6b1 |  | note | Acceptance Criteria:
label | 95d9ec1c-4e60-5f10-a624-948af20303fa |  | note | • Full compaction of each course shall be achieved in all areas including the interfaces between successively placed lanes and sections; Compaction is achieved whilst material is within desired moisture range.
label | 81a81126-471b-5bbf-91d8-e0ce517093bd |  | note | • Compaction to be completed with a 16T smooth roller.
label | 8556671e-d904-55dd-a416-74225ad85f72 |  | note | • Compaction testing requirements and frequency as per Table 304.082.
label | 1720e5f9-a484-5323-a673-1e85b07b00ab |  | note | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
label | e62ae8e7-6871-5090-9028-77fabc1e19a3 |  | note | ¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯
label | 5edf180e-329e-5a11-acbd-734b70422032 |  | note | Table 304.082 Acceptance Limits for Scale C Standard of Compaction
label | 9105e717-ce37-5c60-a03b-e6ea8c87c118 |  | note | ¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯
label | 620ff2a6-50e0-5a7c-ac96-e49a05ccc2d7 |  | note | Compaction Scale ¦¦ Mean Value of Density Ratio % (three tests)
label | 1ef5e11a-4b8f-50ed-9046-a434a990bd22 |  | note | C ¦¦ Subbase Layers (Not less than 98.0) ¦¦ Base Layers (Not less than 100.0)
label | c3139c7d-7005-54d0-b6c4-fcfbb408acf8 |  | note | ¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯
label | 11878d50-4108-52ea-af70-3e607a8dec31 |  | note | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
label | b035845b-8282-5f99-be17-caa32d4b3991 |  | note | • Material requirements as per Tables 820.072, 820.041.
label | 00188313-d603-5d00-bc2f-852c70d702e3 |  | note | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
label | 76a2a048-0332-5b86-9c01-8b4b294b9e62 |  | note | ¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯
label | 9ddb4546-d7bd-5644-8928-d5fc3cc97099 |  | note | Table 820.072 Grading Requirements for Class CC4 Crushed Concrete
label | b6f371de-9348-58f4-93f0-d4e0ffeef285 |  | note | ¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯
label | c7735189-8ada-5be1-a9f4-bb310cff127d |  | note | Sieve Size AS (mm) ¦¦ Limits of Grading - Test Value before Compaction (% Passing)
label | 0645195b-5576-5a53-8138-d9d069d29be4 |  | note | Nominal Size (mm) :: 50 ¦¦ 40 ¦¦ 30 ¦¦ 25 ¦¦ 20 ¦¦ 14
label | 10b9df78-e171-5948-a0e6-3bba35f00fd2 |  | note | ¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯
label | 1fa5b06d-4db3-559e-82d0-4354f9776933 |  | note | 75.0 ¦¦ 50mm :: 100%
label | ba2a840a-d714-51ec-ac71-4be9471ab4d6 |  | note | 53.0 ¦¦ 40mm :: 100%
label | 1ab4d418-8b90-5001-a498-3e15d3f519ee |  | note | 37.5 ¦¦ 30mm :: 100%, 25mm :: 100%
label | 24a36069-0bec-5cb1-aaad-68e175651206 |  | note | 26.5 ¦¦ 20mm :: 100%
label | ac4136df-4918-5fcf-bdf6-d0812d57604b |  | note | 19.0 ¦¦ 50mm :: 54-75%, 40mm :: 64-90%, 14mm :: 100%
label | 86dcb181-9597-5a5f-982e-90cada670139 |  | note | 9.50 ¦¦ 30mm :: 48-70%, 25mm :: 54-75%
label | 4365e94c-33a2-5e89-bdcb-6ca2852ec89b |  | note | 4.75 ¦¦ 20mm :: 42-76%, 14mm :: 54-75%
label | 2efd1d4b-a724-50fc-a1f2-261ef1d47b6b |  | note | 0.425 ¦¦ 50mm :: 7-21%, 40mm :: 7-23%, 30mm :: 9-24%, 25mm :: 10-26%, 20mm :: 10-28%, 14mm :: 15-32%
label | 00606117-3a3f-570e-ae4d-d769653f7d31 |  | note | 0.075 ¦¦ 50mm :: 2-10%, 40mm :: 2-12%, 30mm :: 2-12%, 25mm :: 2-13%, 20mm :: 2-14%, 14mm :: 6-17%
label | 9b30c562-3c4b-557d-add0-4977b16203e5 |  | note | ¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯
label | d55d4288-e6e2-5a7e-8827-6804d1eac551 |  | note | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
label | aacb7c94-5efb-5959-9d48-76bea22901b2 |  | note | ¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯
label | e1355e5f-2974-596b-bc44-a52c3e5dc2fd |  | note | Table 820.041 Physical Properties
label | 8efd9d2f-9ac3-5033-8a61-a81219d3d10f |  | note | ¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯
label | 2790c92d-bbe9-50dd-9e46-7ee6e4ce6582 |  | note | Test ¦¦ Test Value (Class CC2, Class CC3, Class CC4)
label | 46d86728-ffb5-5703-873e-b5a0c042c3dd |  | note | ¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯
label | 9e8453a7-0153-50b4-8e49-d2ddad3ea61f |  | note | Liquid Limit % (max) ¦¦ 35, 35, 40
label | 2e8092bc-e23f-5814-bd17-cf1277edb391 |  | note | Plasticity Index (max) ¦¦ 6, 10, 20
label | 58cd3c97-510b-5c8d-bd99-df490686221c |  | note | California Bearing Ratio (%) (min) ¦¦ 100, 80, 20
label | 6a4f81e6-6de9-5c58-ba9b-7122631dee5c |  | note | Los Angeles Abrasion Loss (max) ¦¦ 35, 40, 45
label | 5925d06b-688f-5c25-8ed9-a0aa971f8c61 |  | note | Flakiness Index ¦¦ 35, - , -
label | cc3d7ccb-3386-5334-a1a2-8f4b80531a8c |  | note | ¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯¯
label | 35cfd9ea-f928-5a92-99a4-14d03728cbae |  | note | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
label | f0a24ec7-0e76-5006-99c9-febc5c31c5cc |  | note | • Nominated frequency of testing for Compaction, Post-compaction Grading and PI, once per individual location (section 304.11).
label | a2cccf93-ebfa-5c5c-bb8d-1ef08748bbd4 |  | note | • Result requirements to conform to VicRoads section 304.
label | ce388ce5-6e76-5b88-8ad8-fa88b4e627dc |  | note | Reference Documents: VicRoads section 304, 820
label | 3b4a212e-656a-5e7a-b87d-a45b363569b1 |  | note | Inspection/ Test Method: Testing
label | d4a301ba-58f6-56f2-8d45-f89b870f3580 |  | note | Record of conformity: Test result certificate
label | 7216d978-6db9-5f17-abba-c44c3640d64e |  | note | TP
label | 25841413-95cb-5903-8e8f-802bf3148960 |  | note | Responsibility: Fulton Hogan
text | c8eaaa52-1d1c-5c12-8de2-8c92604c411c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 - Proof rolling
label | 5a6cd2ad-5ab5-5344-aad1-cd863ecc5418 |  | note | Frequency: Each Lot
label | 52184111-2b4e-5e4d-80d5-728436c31926 |  | note | Acceptance Criteria:
label | ddc80754-762c-5edf-af56-5519e2220ba0 |  | note | • Proof Roll will occur once compaction has been completed, as part of the final sequence of compaction.
label | 25a1d877-38fb-5aaf-887e-339a58a212fa |  | note | • Proof Roll to be systematic and in a manner that covers the entire area.
label | 74bbbaf9-ae32-57ea-b5e4-5e47765a1e7c |  | note | • Vibrating Plant travel at speed less than 4km/h and less than 6 km/h for pneumatic rollers;
label | d0436e64-9715-5421-8e26-aa67e656043d |  | note | • Rollers operated as close as practicable to unsupported edges.
label | 0469f17b-ccf5-5120-88b1-4d7e0040d104 |  | note | • Contractor shall provide for the Principal's Representative to be present after all test rolling.
label | 48336158-c6d9-5fd3-a408-b6fcc9f17510 |  | note | • Proof rolling of the Crushed Rock Working Platform to be completed with a watercart or smooth drum.
label | dd1952ea-c71e-5b80-a8fa-6433139dd199 |  | note | Reference Documents: VicRoads section 173
label | ba812ffd-bd2f-5734-a517-dcfef98b7382 |  | note | Inspection/ Test Method: Visual Inspection
label | 10a25070-cf31-5ed1-bbfa-4966921b0a60 |  | note | Record of conformity: Visual inspection and mapping data
label | 036c67e5-476d-5d3f-ae54-f8f3cdc055f4 |  | note | WP / HP*
label | fd46c512-6279-50b9-9d31-f01df6f9dac2 |  | note | Responsibility:
label | d033931e-895f-5cb2-93b3-13bb00628f5b |  | note | • Fulton Hogan
label | ab9f85ac-3961-5bcc-8452-42a91f69d6e3 |  | note | • Principal’s Representative
text | 10d855ae-2bf3-5125-a2d8-57a3f864f108 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 - Identification and treatment of unsuitable areas.
label | 4392bc8b-ad7a-5cef-831d-9a992264ef5d |  | note | Frequency: Each Lot
label | 5fb8da32-e18f-56f3-8d74-532571b49b45 |  | note | Acceptance Criteria:
label | 36e3bd1c-abd2-5372-b965-de9f9d3bd24a |  | note | • Should any area crushed rock be disturbed or become unstable during proof rolling, the Principal’s Representative should be advised immediately and proof rolling of the area ceased.
label | a92cf3d7-d142-581e-9da6-0faa843a927f |  | note | • Any areas of crushed rock layer that rut, yield or become unstable under the proof rolling must be investigated in the presence of the Principal’s Representative.
label | f09c34c0-5c30-518a-a276-5905598dbed4 |  | note | Reference Documents: Spec cl 3.6.3. & VicRoads Section 204
label | 8ac6fd64-c4b0-5cc6-8911-b3dd28f475bc |  | note | Inspection/ Test Method: Visual Inspection
label | db43286b-1719-5a51-9526-02147048c4e8 |  | note | Record of conformity: Site Inspection
label | 6f0848d5-686b-550a-8844-0f7ac3d6527d |  | note | HP
label | c9b72cb8-b9ba-5700-bf8c-a7f63cf04fdc |  | note | Responsibility:
label | da2d409a-7edf-5289-bba6-30fef4ae843e |  | note | • Fulton Hogan
label | a178b785-00fb-58c3-a725-008b9c339afc |  | note | • Principal’s Representative
text | 6d9a4006-dd16-5e4e-a17b-8560bd36c72e |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | cdf2e525-3171-5f64-85bb-53fdcebd7d92 |  | note | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 27b3cdb6-027a-5d0d-96f6-27553a2755e8 |  | textbox | Print Name:
text | 2647c552-4e99-5d23-90a2-353facdaf6db |  | textbox | Position:
text | c95a2627-6085-5183-89fc-9aedd709f92f |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP009 - Runway Grooving of Asphalt Surfacing - Main Works | itp |  |  |  | Yes | ITP009 - Runway Grooving of Asphalt Surfacing - Main Works | e26a5e55-e697-45b3-9ee5-2c24a5316115
checkpoint-group |  |  | section | 2 Grooving
checkpoint-status |  |  | checkpoint | 2.01 - Commencement of grooving in new asphalt surfacing.
label | fa40773c-e97c-5c5c-8006-d8771e8e410d |  | note | Frequency: Prior to the commencement of grooving works.
label | 56dc63e3-4937-5ec9-a7b9-aff9d99e9ad8 |  | note | Acceptance Criteria: Grooving of asphalt surfacing commenced no less than 8 weeks after the completion of the construction of the asphalt surfacing.
label | 877b8a09-d3ea-5a8c-baff-97ccbb9306a7 |  | note | Reference Documents: GHD-DD-SPC-001 7004(a)
label | 5b82bf4f-94a6-5638-9442-336372c00351 |  | note | Inspection/ Test Method: Inspection
label | ccb91318-0192-5b98-a76b-3f460451248c |  | note | Record of conformity: ITP
label | ef9ff3b4-6c06-582b-a7e6-88a037041631 |  | note | IP
label | 564d8e9c-438c-5c53-bc45-75098ce9e617 |  | note | Responsibility: Site Engineer
text | cdb34c9f-4c1f-584a-bc00-c0c548e1d522 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.02 - Grooving of new asphalt surfacing as per specified dimensions, length, extent and shape.
label | 9e3fdbff-330c-559a-991c-a756b2ac5919 |  | note | Frequency:
label | dd18a520-4527-5dbe-aedb-9d385e862752 |  | note | During grooving works on at least 15 randomly selected grooves within a lot. Submission of groove lots to be within 48 hours of completion of a lot.
label | f410cc8a-f585-51e6-8f0c-de0cd9aacb41 |  | note | Acceptance Criteria:
label | 2317c953-af3c-5a56-a8db-16785483ac99 |  | note | Width on at least 15 randomly selected grooves within a lot. Submission of groove lots to be within 48 hours of completion of a lot.
label | e471797c-437f-5c86-a51e-1b04a536522b |  | note | Floor of grooves are parallel to the finished surface of the pavement."
label | 88c7068a-9931-5449-8cc7-2e38653a66a8 |  | note | Square grooves are square with sides perpendicular to the surface of the runway; trapezoidal grooves are a consistent trapezoidal shape and not round or semi-circle.
label | c10aab5d-9762-574f-8cd1-35d7e0df0fbf |  | note | The deviation from specified groove shape is not more than specified in Note 1."
label | cc83d62a-2835-5677-961e-f26dcbb628f2 |  | note | Grooves are cut continuously across the width of the pavement and are cut to extend over the length of the pavement as shown on the Drawings.
label | 0c0597c9-23cf-522b-a221-b339c45b9b68 |  | note | Reference Documents:
label | 04db7278-c02c-5059-9ff9-7382ded5ceb5 |  | note | GHD-DD-SPC-001 7004(c)(d)(f)(g)"
label | bbfcfce7-e491-5d8e-896d-f3b4888019b1 |  | note | Table 7007-1"
label | 5a2c18fc-794a-5538-837d-acf58e8808e1 |  | note | WP7007-1"
label | 8f51293e-6655-5130-ae08-793fda00f747 |  | note | Inspection/ Test Method: Inspection; random selection in accordance with AS 1289.1.4.2
label | fbfa0915-9783-5ae6-a187-aeb3d95e4040 |  | note | Record of conformity: Conformance report
label | 742e1fda-2cb4-518c-a4f3-e8202221fa26 |  | note | WP
label | faa06e1b-1c90-518a-a3e6-c4c66fb89e1a |  | note | Responsibility: Site Engineer
text | 448e2648-6a44-525c-b6fe-ea37f7fddb94 |  | textbox | Date Completed:
label | 74e0602d-ac27-53c7-98b4-a08ea3b981eb |  | note | Note 1: Table 7007-1 Groove Tolerances and compliances requirements.
label | e837901f-00e4-538e-ac4f-a6e1080db9f0 |  | note | Property ¦¦ Tolerance ¦¦ Compliance requirement (minimum % of compliant measurements in lot sample)
label | 74aff294-d724-5fd1-b932-f1b0e4c01c35 |  | note | Perpendicularity ¦¦ Maximum 80 mm deviation of groove from a line drawn perpendicular to the runway centreline. ¦¦ 90%
label | 154036f1-cf70-59ad-9c1e-33496dcb0e24 |  | note | Straightness ¦¦ Maximum 80 mm deviation of groove from a line drawn between two end points of the groove. ¦¦ 80%
label | 9ca663f7-8b14-5074-96ea-ef535b3117e9 |  | note | Square grooves
label | 4da8aebb-ba44-56a0-ba2c-7038587c1b4f |  | note | Width ¦¦ -0 mm + 1.6 mm ¦¦ 85%
label | 1968826f-4935-5a64-b8dc-ff99aae0651b |  | note | Depth ¦¦ -1.6 mm + 1.6 mm ¦¦ 80% deeper than tolerance, 95% shallower than tolerance
label | e81ac9c0-cf65-5e48-a533-5dc4c9a74b83 |  | note | Spacing ¦¦ �2 mm between selected groove to the groove on either side ¦¦ 90%
label | da54823d-4c0b-560b-8f34-e755ef6b9279 |  | note | Shape (difference between width at top and bottom of groove) ¦¦ max 0.2 mm ¦¦ 95%
label | a3245f7b-734a-55d0-897f-58af51b4f75c |  | note | Trapezoidal grooves
label | d3e8b997-c62a-5921-8a87-7f40fb554dc8 |  | note | Width at top ¦¦ -0.5 mm, +1.6 mm ¦¦ 85%
label | 2ceb7d24-41b4-50c1-8954-e31d13368694 |  | note | Width at bottom ¦¦ -0.5 mm, +1.6 mm ¦¦ 85%
label | 205afa88-4529-50f2-a4bb-73c45b1f8a64 |  | note | Depth ¦¦ -1.6 mm + 1.6 mm ¦¦ 80% deeper than tolerance, 95% shallower than tolerance
label | 0e35039b-1deb-56a7-80a0-1f3973542c6d |  | note | Spacing ¦¦ �2 mm between selected groove to the groove on either side ¦¦ 90%
label | 8d67e406-4279-5c3e-99e4-77bdbfb89865 |  | note | Shape (maximum deviation of any side of trapezoid groove from template) ¦¦ Max 0.6 mm ¦¦ 80%
checkpoint-status |  |  | checkpoint | 2.03 - Grooving of new asphalt surfacing as per specified alignment.
label | 094c6eed-b082-547a-a251-44e0c6246a66 |  | note | Frequency:
label | af3cb3ef-698e-55bb-8fe8-6efba2a21d14 |  | note | During grooving works on at least 15 randomly selected grooves within a lot.
label | ccf2e319-3344-5afb-bca4-73ac8ea15f55 |  | note | Submission of groove lots to be within 48 hours of completion of a lot."
label | a9adb84a-1728-5efa-b738-c72cd2b85f6d |  | note | Acceptance Criteria:
label | cc14fad4-48f6-595b-be05-542ed2330b13 |  | note | Alignment of grooves reset to truly perpendicular to the runway centreline at 150 m intervals along the runway.
label | afe0c97d-288f-53f6-b9c1-f56101963d5e |  | note | Grooves are cut in parallel straight lines perpendicular to the runway centreline and comply with the requirements of Note 1.
label | cbbc99ed-55c0-5d4e-807d-c03cb9552abe |  | note | Grooves on rapid exit taxiways are in straight lines and oriented as indicated on Drawings.
label | b235ac2d-c147-5035-be81-fef5f35bd530 |  | note | Reference Documents:
label | a30bc3dc-a0a7-5c6d-9feb-cf8d62dfc936 |  | note | GHD-DD-SPC-001 7004(e)"
label | 2fdecaaa-7310-5fb6-8611-40fe5407526b |  | note | Table 7007-1"
label | 5f8a5b1a-3172-5bfc-8504-34a10dc71821 |  | note | WP7007-1"
label | 86129547-a4c9-5c9f-b6bb-cc1ecd51183a |  | note | Inspection/ Test Method: Inspection; random selection in accordance with AS 1289.1.4.2
label | 145832f5-1e62-50a1-a545-cd88ed6bc26c |  | note | Record of conformity: Conformance report
label | 8ffd2f9d-afbf-523d-a39e-369e3af80bd8 |  | note | WP
label | 18da4d32-d592-5adf-b25e-0e5d4bdb0422 |  | note | Responsibility: Site Engineer
text | 85fe44e4-6bcd-542a-8576-701f51ab5b05 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.04 - Grooving of new asphalt surfacing near inset light fittings.
label | 34d6bbbc-b28f-55cb-a823-b073e0ac25b0 |  | note | Frequency: During grooving works adjacent to inset light fittings.
label | f2c4e35a-12dc-5150-bec5-c67f0000a4e4 |  | note | Acceptance Criteria:
label | a6b3c83a-d22a-5af1-ab8f-a158859863cc |  | note | Grooving is stopped to leave a regular (rectangular or square) ungrooved area symmetrically surrounding the light fitting.
label | 42c9478d-8023-5703-896c-3855d8fa8086 |  | note | Grooves are not sawn closer than 150 mm and not more than 900 mm from the edge of any inset light."
label | bf62f4fb-8499-5747-b30f-fd5fd6302c4f |  | note | Reference Documents: GHD-DD-SPC-001 7004(h)
label | df6a12ae-a8a0-5d98-b1ed-18f866d1958b |  | note | Inspection/ Test Method: Inspection
label | ed398fa8-9c0b-5470-b1ec-f5fc4b2ee033 |  | note | Record of conformity: ITP
label | 13995823-1f1e-5595-b484-34567fd3a4ea |  | note | IP
label | 947fe133-f69f-52e9-8d84-3c20eef76dd7 |  | note | Responsibility: Site Engineer
text | 247010f1-4489-50b8-b18b-0d3ab7d85d51 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.05 - Grooving of new asphalt surfacing near cable slots.
label | 7fa25185-892d-58c7-adf3-ab8b71e91a7c |  | note | Frequency: During grooving works adjacent to cable slots.
label | 3851abb2-dde8-5674-9d2b-d01030ca05dc |  | note | Acceptance Criteria: Grooves are not sawn closer than 150 mm and not more than 900 mm from the edge of any cable slots.
label | f099dbf3-4751-548f-b9f8-a0d0c4bccd63 |  | note | Reference Documents: GHD-DD-SPC-001 7004(i)
label | d1d78e46-76c2-5bfe-9c68-4c4b184c6946 |  | note | Inspection/ Test Method: Inspection
label | 1444dde1-f199-5fff-a15b-2e668a576078 |  | note | Record of conformity: ITP
label | 5207af00-46d9-5a2a-9f3a-f24b3d112740 |  | note | IP
label | 779b5a95-ad22-5154-81aa-ec4b977555e8 |  | note | Responsibility: Site Engineer
text | c5593d0f-fd9d-5fbc-947f-332b8c8d2c11 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.06 - Grooving of new asphalt surfacing near cable arrestors.
label | 51d18424-5c16-5a96-b089-caa8098996b0 |  | note | Frequency: During grooving works adjacent to cable arrestors.
label | 934b87c4-3f50-520c-8fc1-c35d22452a38 |  | note | Acceptance Criteria: Grooves are not sawn closer than 3,000 mm each side of a cable arrestor system.
label | a2731a50-f351-5223-a8f9-314b0064934a |  | note | Reference Documents: GHD-DD-SPC-001 7004(j)
label | e22a8e55-8608-537d-bad5-2d94b63fed8a |  | note | Inspection/ Test Method: Inspection
label | 1196fd3f-4a6c-558f-873e-3d649476ae52 |  | note | Record of conformity: ITP
label | 9abcb0d8-f2c3-5f07-b115-27377b40f2a1 |  | note | IP
label | 18a5ab8d-dfe6-5c1b-89f3-e0ed2d6859fd |  | note | Responsibility: Site Engineer
text | 1aaa3d1b-54b6-57cf-a00c-ab10885fd475 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 3 Slurry Removal
checkpoint-status |  |  | checkpoint | 3.01 - Cleaning of grooved surface.
label | 05515b46-4f85-5585-9be9-cc2976783847 |  | note | Frequency: Progressively during grooving and at the completion of grooving works.
label | 236eb4c7-87aa-5073-a17a-660189cbd635 |  | note | Acceptance Criteria:
label | 5caf50f4-8f73-5aa7-a94f-8a46bdb29495 |  | note | Slurry produced by grooving equipment is flushed from grooves as it is produced and removed by suction into a mobile container."
label | 141e1c72-9d0d-532b-b08c-26392f0d99e3 |  | note | Residual slurry is removed to produce a clean pavement free from all material arising from the cutting of grooves."
label | 1cace156-51a4-5cfb-bb05-cb6b7101bddd |  | note | Reference Documents: GHD-DD-SPC-001 7006
label | a874085c-d6bb-5bd5-accc-269337badbe6 |  | note | Inspection/ Test Method: Inspection
label | 3d188729-1578-59fc-a999-19195a474468 |  | note | Record of conformity: ITP
label | b0957668-de22-5442-b265-d7e3f8f50fd2 |  | note | IP
label | 6917aca7-6318-5167-8771-0487f80ee5b0 |  | note | Responsibility: Site Engineer
text | c7c0ea5d-9f4a-5c28-9188-a77c1e3d775c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.02 - Notification of completion of cleaning of pavement surface.
label | 7199dad1-148e-5e6f-8ad6-6b6510e002fb |  | note | Frequency: At the end of each work period in which grooving works have been undertaken.
label | 71d1f905-6c6e-547b-a427-6077b8aa4b24 |  | note | Acceptance Criteria: Contract Administor is notified of completion of cleaning of pavement surface.
label | bc118254-55f7-5f51-a1e4-ed1c75fd61b8 |  | note | Reference Documents:
label | a76992cc-90f0-575b-8619-8e44c69729ab |  | note | GHD-DD-SPC-001 7006"
label | b619fc20-0cee-512a-899b-e11688d93728 |  | note | WP7006-1"
label | 710366fa-b12d-5896-80ab-3b078ca81a56 |  | note | Inspection/ Test Method: Inspection
label | 2f1c0596-f440-5ed4-9c46-03bdbbeb32d5 |  | note | Record of conformity: ITP
label | 5e31995b-84d7-5c6e-b1c0-8b1d0e11a13b |  | note | WP
label | 01f31de8-d851-5b10-bb62-9f2a3a768c3d |  | note | Responsibility: Site Engineer
text | c7fb9f77-eb53-5cd5-b621-791840514558 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | ba06e050-c917-5db7-bccf-9450cf81d712 |  | note | The signature below verifies that this ITP has been completed in accordance with the FHs Quality system Procedures and verifies lot compliance with specifications.
text | 1e1272cf-7b5a-5b74-953e-aebe855de5ae |  | textbox | Print Name:
text | cba146d9-6658-5116-a1ce-d0df7ff83800 |  | textbox | Position:
text | e7e0674c-2676-5fb7-8638-2d17aca83834 |  | textbox | Date: