## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP Blockwork | itp |  |  |  |  | ITP Blockwork
checkpoint | 1 - MATERIALS
label | ACCEPTANCE CRITERIA: Blocks – correct block size and type for wall
label | Type of: Witness
label | Comments / Records: Photo required signature
textbox | Date Completed:
checkpoint | 2 - SET OUT
label | REFERENCE: (ST-0091) [A]
label | ACCEPTANCE CRITERIA: Ensure CJs are set out and align with criteria in Mott Macdonald
label | Type of: Hold Point – Wall set out
textbox | Date Completed:
holdpoint | HOLD POINT – WALL SET OUT
checkpoint | 3 - MSDS
label | REFERENCE: Mortar to be class M3 to AS3700 (ST-0091) [A]
label | ACCEPTANCE CRITERIA:
label | ○ Mortar – do not use bush sand
label | ○ Ensure sand clean and free from impurities
label | ○ Cement : Lime : Sand = 1:1:6
label | Type of: Witness
label | Comments / Records: Signature
textbox | Date Completed:
checkpoint | 4 - RE-INFORCEMENT (1)
label | REFERENCE: (ST-0091) [A]
label | ACCEPTANCE CRITERIA:
label | ○ (Vertical) N16-800 Dowel Embedment 125mm min. (600mm min. lap)
label | ○ Dowel to be installed 2nd to last block core either side of CJ – correct ties used
label | ○ Hilti HIT RE-500 – Chemical Injection
label | Type of: Hold Point – Embedment depth
label | Comments / Records: Signature
textbox | Date Completed:
holdpoint | Hold Point – Embedment depth
checkpoint | 5 - RE-INFORCEMENT (2)
label | REFERENCE: (ST-0091) [A]
label | ACCEPTANCE CRITERIA: Joint reinforcement in first bed above slab
label | Type of: Witness
label | Comments / Records: Photo required
textbox | Date Completed:
checkpoint | 6 - RE-INFORCEMENT (3)
label | REFERENCE: (ST-0091) [A]
label | ACCEPTANCE CRITERIA: N12-400 Horizontal in wall (500mm min. lap) bars tied in
label | Type of: Witness
label | Comments / Records: Photo required
textbox | Date Completed:
checkpoint | 7 - RE-INFORCEMENT (4)
label | REFERENCE: (ST-0091) [A]
label | ACCEPTANCE CRITERIA: N16-800 Vertical Lap bars tied in – Bar heights marked on wall
label | Type of: Witness
label | Comments / Records: Photo required
textbox | Date Completed:
checkpoint | 8 - RE-INFORCEMENT (5)
label | REFERENCE: (ST-0091) [A]
button | ACCEPTANCE CRITERIA: Bond Beam Lintel/Penetration Detail (Y/N) | Y,N
label | Type of: Witness
label | Comments / Records: Photo required
textbox | Date Completed:
checkpoint | 9 - INSPECTION
label | ACCEPTANCE CRITERIA: Notify engineer to inspect prior to pour
button | Type of: Engineer required for inspection Y/N | Y,N
label | Comments / Records: Signature
textbox | Date Completed:
checkpoint | 10 - REINFORCEMENT
label | REFERENCE: (ST-0091) [A]
label | ACCEPTANCE CRITERIA: All reinforcement installed as per spec
label | Type of: Witness
label | Comments / Records: Signature
textbox | Date Completed:
checkpoint | 11 - BLOCKFILL (1)
label | ACCEPTANCE CRITERIA: 20mPa blockfill, slump 225mm, maximum agg size 10mm or grout
label | Type of: Supplier Compressive Strength Test
label | Comments / Records: Test report required
textbox | Date Completed:
checkpoint | 12 - BLOCKFILL (2)
label | ACCEPTANCE CRITERIA: Base cleaned out, core to be rodded to ensure wall is properly filled
label | Type of: Surveillance
textbox | Date Completed:
checkpoint | 13 - RE-INFORCEMENT (1)
label | REFERENCE: (ST-0091) [A]
label | ACCEPTANCE CRITERIA: N16-800 Vertical Lap bars tied in and extend min 100mm into last block
label | Type of: Witness
label | Comments / Records: Photo required
textbox | Date Completed:
checkpoint | 14 - RE-INFORCEMENT (2)
label | REFERENCE: (ST-0091) [A]
label | ACCEPTANCE CRITERIA: MFA 4/1 Head Restraint tie at 800 ctrs
label | Type of: Witness
label | Comments / Records: Photo required
textbox | Date Completed:
checkpoint | 15 - BLOCKFILL
label | ACCEPTANCE CRITERIA: 20mPa blockfill, slump 225mm, maximum agg size 10mm
label | Type of: Test Report – Supplier test cylinder
label | Comments / Records: Signature
textbox | Date Completed:
checkpoint | 16 - FINAL INSPECTION (1)
label | ACCEPTANCE CRITERIA: All bedding pointing up, mortar droppings removed, work area cleaned
label | Type of: Surveillance
textbox | Date Completed:
checkpoint | 17 - FINAL INSPECTION (2)
label | ACCEPTANCE CRITERIA: All nonconformances closed out
textbox | Date Completed: