## QA Folder Structure
QA Folder Structure |  |  |  | Checklists
Fabrication & Site QA
Toorak Rd
| Cunningham St | Panel Number (T)
| Laneway | Panel Number (C)
Panel Number (L)
Removal of Non-Compliant ACP Panels
Fabrication Checklist
Receival of panels onsite Checklist
Base framing Checklist
Installation of Solid Alum. Panels

## ITPs Checklist ACP Panels
type | name | values | prefix | postfix
checkpoint | Document type selected and uploaded below
select | document type uploaded | Butterfly Test Record,Sealant Inspection Record,Sealant Deglazing Checklist,Sealant Silicone Application Checklist
text | date
Removal of Non-Compliant ACP Panels
Check Latent condition
Photo's lodged to CONQA - pre removal
Photo's lodged to CONQA - post removal
Fabrication
Panel delivery & material finish
Cutting flat sheet & Flat panel folding
Paper version of ITP uploaded
Receival of panels onsite Checklist
Check deliveries of materials for damage that may have occurred in transportation on truck prior to unloading
Delivered panels have protective film and are free of damage
Delivery Docket lodged to CONQA
Base framing Checklist
Check Latent condition / Alignment of existing panel prior to installation of panel
Base framing observed on site consistant with documentation
Check to see if addational framing is needed
Photo of location regarding additional framing lodged to CONQA
Installation of panels Checklist
Check Latent condition / Alignment of existing panel prior to installation
Fixing and fixtures are installed as documented
Panel installed in accordance with documentation
Check for damages / scratches
Photo's lodged to CONQA
Paper version of ITP uploaded - if panel fails ITP

## Panel Numbers
T | C | L
T-1 | C-1 | L-1
T-2 | C-2 | L-2
T-3 | C-3 | L-3
T-4 | C-4 | L-4
T-5 | C-5 | L-5
T-6 | C-6 | L-6
T-7 | C-7 | L-7
T-8 | C-8 | L-8
T-9 | C-9 | L-9
T-10 | C-10 | L-10
T-11 | C-11 | L-11
T-12 | C-12 | L-12
T-13 | C-13 | L-13
T-14 | C-14 | L-14
T-15 | C-15 | L-15
T-16 | C-16 | L-16
T-17 | C-17 | L-17
T-18 | C-18 | L-18
T-19 | C-19 | L-19
T-20 | C-20 | L-20
T-21 | C-21 | L-21
T-22 | C-22 | L-22
T-23 | C-23 | L-23
T-24 | C-24 | L-24
T-25 | C-25 | L-25
T-26 | C-26 | L-26
T-27 | C-27 | L-27
T-28 | C-28 | L-28
T-29 | C-29 | L-29
T-30 | C-30 | L-30
T-31 | C-31 | L-31
T-32 | C-32 | L-32
T-33 | C-33 | L-33
T-34 | C-34 | L-34
T-35 | C-35 | L-35
T-36 | C-36 | L-36
T-37 | C-37 | L-37
T-38 | C-38 | L-38
T-39 | C-39 | L-39
T-40 | C-40 | L-40
T-41 | C-41 | L-41
T-42 | C-42 | L-42
T-43 | C-43 | L-43
T-44 | C-44 | L-44
T-45 | C-45 | L-45
T-46 | C-46 | L-46
T-47 | C-47 | L-47
T-48 | C-48 | L-48
T-49 | C-49 | L-49
T-50 | C-50 | L-50
T-51 | C-51 | L-51
T-52 | C-52 | L-52
T-53 | C-53 | L-53
T-54 | C-54 | L-54
T-55 | C-55 | L-55
T-56 | C-56 | L-56
T-57 | C-57 | L-57
T-58 | C-58 | L-58
T-59 | C-59 | L-59
T-60 | C-60 | L-60
T-61 | C-61 | L-61
T-62 | C-62 | L-62
T-63 | C-63 | L-63
T-64 | C-64 | L-64
T-65 | C-65 | L-65
T-66 | C-66 | L-66
T-67 | C-67 | L-67
T-68 | C-68 | L-68
T-69 | C-69 | L-69
T-70 | C-70 | L-70
T-71 | C-71 | L-71
T-72 | C-72 | L-72
T-73 | C-73 | L-73
T-74 | C-74 | L-74
T-75 | C-75 | L-75
T-76 | C-76 | L-76
T-77 | C-77 | L-77
T-78 | C-78 | L-78
T-79 | C-79 | L-79
T-80 | C-80 | L-80
T-81 | C-81 | L-81
T-82 | C-82 | L-82
T-83 | C-83 | L-83
T-84 | C-84 | L-84
T-85 | C-85 | L-85
T-86 | C-86 | L-86
T-87 | C-87 | L-87
T-88 | C-88 | L-88
T-89 | C-89 | L-89
T-90 | C-90 | L-90
T-91 | C-91 | L-91
T-92 | C-92 | L-92
T-93 | C-93 | L-93
T-94 | C-94 | L-94
T-95 | C-95 | L-95
T-96 | C-96 | L-96
T-97 | C-97 | L-97
T-98 | C-98 | L-98
T-99 | C-99 | L-99
T-100 | C-100 | L-100