## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 1630-P200-SYM-QAC-ITP-0012 Earthworks Type A REV01 | itp |  |  |  | Yes | 1630-P200-SYM-QAC-ITP-0012 Earthworks Type A REV01 | 7c815c14-dd38-4c3e-885f-4d0e050c79e6
section | 1.0 Pre-start activities
checkpoint | 1.2 - Site excavation and Material classification and supply (Site only)
label | Ref docs - VR Clause 204.06 (c) 204.04 (b)
label | Acceptance criteria - For site-won material: Prior to commencing excavation in any area and during excavation work, the Surveillance Officer and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04. Material classified as silt prior to compaction shall not be used as Type A material without stabilisation to the satisfaction of the Surveillance Officer.
button | Has all of the above been completed and approved? | Yes, No
label | Freq - Each Lot
label | Key - H
label | Resp - SE
label | SI Key - H
button | Remarks/record - Compliance Certificates/ Test Reports | Yes, No
button | NATA Test Reports: CBR, Swell, Permeability, Grading, PI | Yes, No
date | Inspection Date:
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 Set out
checkpoint | 2.1 - Set out and survey land appropriately for intended works.
label | Ref docs - VR Clause 204.03 (a)
label | Acceptance criteria - Set out pegs in place and clearly mark out limits of works as per design IFC drawings.
button | Has all of the above been completed and approved? | Yes, No
label | Freq - Each lot
label | Key - R
label | Resp - SE
date | Inspection Date:
section | 3.0 Placement of Type A Material
checkpoint | 3.1 - Underlying Layer Conformance
label | Ref docs - VR Clause 204.10(b) 204.06
label | Acceptance criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor. Any unstable areas detected by test rolling shall be rectified. Where ground water or seepage is encountered the Contractor shall notify the Superintendent and submit the proposed action to be taken to the Superintendent for review. The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater. The Contractor shall not commence playing any fill on the prepared areas until the area has been reviewed by the Superintendent.
button | Approval to proceed granted? | Yes, No
label | Freq - Each lot
label | Key - H
label | Resp - SE
label | SI Key - H
date | Inspection Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Placing of Geotextiles (If applicable)
label | Ref docs - VR Clause 210.05 IFC Drawing
label | Acceptance criteria - The placement of geotextile is not permitted without the written approval from the relevant Surveillance Officer. Geotextile shall be placed to the limits as shown on IFC Drawings without punctures or tears. If these occur, they shall be rectified, or the entire roll of geotextile replaced prior to covering. Geotextiles in subsurface drains shall be placed to conform to the approximate shape of the excavation and fully envelop the drainage material. All joints shall be overlapped or sewn in accordance with the Geotextile Record. Geotextiles shall be covered by filling within 48 hours of placement.
button | Has all of the above been completed per standard and approved? | Yes, No
label | Freq - Each lot
label | Key - H
label | Resp - SE
label | SI Key - H
date | Inspection Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Placing of Fill
label | Ref docs - VR Clause 204.10(d)
label | Acceptance criteria - Spread and compact in uniform layers not exceeding a compacted thickness of 200 mm. Visual Inspection for maximum particle dimension Where a fill is to be constructed on steep sideling ground or against an existing embankment with side slope steeper than 4H:1V, benches shall be progressively cut over the full area to be covered by new fill. The width of each bench shall be not less than 1 m.
button | Has all of the above been completed per standard and approved? | Yes, No
label | Freq - Each lot
label | Key - R
label | Resp - SE
button | Remarks/record - Verification Records: Layer Thickness at least every three layers | Yes, No
date | Inspection Date:
checkpoint | 3.4 - Keyed Fill Layers
label | Ref docs - VR Clause 204.10(d) Construction Work Pack
label | Acceptance criteria - Placement surface textured to ensure layers keyed into each other.
button | Has all of the above been completed per standard and approved? | Yes, No
label | Freq - Each lot
label | Key - R
label | Resp - SE
date | Inspection Date:
checkpoint | 3.5 - Test Roll of Type A fill layer.
label | Ref docs - VR Clause 204.12 173.03 Construction Work Pack (Test roll procedure in specification 173.03)
label | Acceptance criteria - Each layer should be test rolled immediately following completion of compaction but if test rolling is carried out at a later time the surface of the layer shall be watered and given a minimum of three passes with the test roller prior to commencement of test rolling. Surface shall withstand test rolling without visible deformation or springing.
button | Has all of the above been completed per standard and approved by relevant authorities? | Yes, No
label | Freq - Each lot
label | Key - H
label | Resp - SE
label | SI Key - H
date | Inspection Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 - Fill at Structures (if applicable)
label | Ref docs - VR Clause 204.11 (b) Table 204.111 Construction Work Pack
label | Acceptance criteria - No Fill to be placed within 3 m of structure until the foundation is reviewed by the relevant Surveillance Officer. Culverts with an opening height greater than 1200 mm, shall be material of at least Type A material quality.
button | Has all of the above been completed per standard and approved? | Yes, No
label | Freq - Each Lot
label | Key - H
label | Resp - SE
label | SI Key - H
date | Inspection Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7 - Fill within 300mm of structures
label | Ref docs - VR Clause 204.11 Construction Work Pack
label | Acceptance criteria - Use of geo-composite drainage material or Permeable Fill in accordance with 204.04(f). Compaction plant shall not be operated within the minimum distances from structures shown in Table 204.111. The difference in level of any fill being placed on opposite sides of a structure or structural component shall not exceed H/4 or 500 mm, whichever is the lesser, where H is the height of the structure.
button | Has all of the above been completed per standard and approved? | Yes, No
label | Freq - Each Lot
label | Key - R
label | Resp - SE
date | Inspection Date:
checkpoint | 3.8 - Fill Material against Concrete Structures
label | Ref docs - VR Clause 204.11 Construction Work Pack
label | Acceptance criteria - No material shall be placed against concrete within 14 days of casting.
button | Has all of the above been completed per standard? | Yes, No
label | Freq - Each Lot
label | Key - R
label | Resp - SE
label | Remarks/record - Concrete Pour Recorded
label | NATA Test Reports: Compressive Strength
date | Inspection Date:
checkpoint | 3.9 - Treatment of Unsuitable Material
label | Ref docs - VR Clause 204.07
label | Acceptance criteria - Where unsuitable material is encountered the Contractor shall submit the proposed in situ treatment or extent of excavation to the Superintendent for review.
label | Freq - Each Lot
label | Key - H
label | Resp - SE
label | SI Key - H
date | Inspection Date:
holdpoint | AUTHORITY HOLDPOINT
section | 4.0 Geotechnical Testing
checkpoint | 4.1 - CBR / Swell
label | Ref docs - VR Clause Table 204.041 204.141 Table PS3020.051
label | Acceptance criteria - Unless otherwise specified: CBR: ≥ 6%, Swell: ≤ 1.5% (1.0% for Verge Material). Initial testing frequency: 1 Lot test to determine Assigned CBR and swell.
button | Have the ideal results been achieved? | Yes, No
label | Freq - Each Lot
label | Key - R
label | Resp - SE
button | Remarks/record - NATA Test Report: CBR, Swell | Yes, No
date | Inspection Date:
checkpoint | 4.2 - Post Compaction Grading
label | Ref docs - VR Clause Table 204.041
label | Acceptance criteria - Sieve 75.0 mm – 100% passing by mass, Sieve 4.75 mm – 40 - 80% passing by mass, Sieve 0.075 mm – 10 - 40% passing by mass. Initial testing frequency: 1 test for each lot tested for compaction until 3 consecutive lots achieve specified requirements.
button | Have the ideal results been achieved? | Yes, No
label | Freq - Each Lot
label | Key - R
label | Resp - SE
button | Remarks/record - NATA Test Report: Grading | Yes, No
button | Visual Inspections for Maximum Particle Dimension | Yes, No
date | Inspection Date:
checkpoint | 4.3 - Plasticity Index
label | Ref docs - VR Clause Table 204.041
label | Acceptance criteria - PI: 6 - 25, PI x % Passing 0.425mm: 1000 Max. Initial testing frequency: 1 test per 2 lots until 3 consecutive lots achieve specified requirements.
button | Have the ideal results been achieved? | Yes, No
label | Freq - Each Lot
label | Key - R
label | Resp - SE
button | Remarks/record - NATA Test Report: Atterberg Limits | Yes, No
date | Inspection Date:
checkpoint | 4.4 - Permeability (Capping & Verge Material only)
label | Ref docs - VR Clause Table 204.041
label | Acceptance criteria - Permeability: 5E-9 m/s Initial testing frequency: 1 test per 2 lots until 3 consecutive lots achieve specified requirements.
button | Have the ideal results been achieved? | Yes, No
label | Freq - Each Lot
label | Key - R
label | Resp - SE
button | Remarks/record - NATA Test Report: Permeability | Yes, No
date | Inspection Date:
checkpoint | 4.5 - Compaction Testing
label | Ref docs - VR Clause Table 204.131 173.04(d)
label | Acceptance criteria - Minimum Characteristic Value of Density Ratio: 99% (Scale A), 98% (Scale B). For small areas (<500 m2): Mean value of density ratio: 101% (Scale A), 100% (Scale B). Initial testing frequency: Each lot until 3 consecutive lots meet compaction requirements.
button | Have the ideal results been achieved? | Yes, No
label | Freq - Each Lot
label | Key - R
label | Resp - SE
button | Remarks/record - NATA Test Report: Compaction and Moisture Content | Yes, No
date | Inspection Date:
checkpoint | 4.6 - Reduced Frequency of Testing
label | Ref docs - VR Clause 204.14 – Table 204.141
label | Acceptance criteria - Unless otherwise specified: Material properties (Scale A): Test at the initial testing frequency, if compliant, seek approval from Surveillance Officer for minimum testing frequency. Material Properties (Scale A): CBR/Swell: 1 test every 2 lots. Grading: 1 Test for every 2nd lot PI: 1 test every 4 lots Permeability: 1 test every 4 lots Material properties (Scale B): Test initial lot and no further testing required until changes in physical property/material source are observed. Compaction / Moisture Content: Reduced frequency: Test every 2nd lot.
button | Have the ideal results been achieved? | Yes, No
label | Freq - Each Lot
label | Key - R
label | Resp - SE
label | SI Key - R
button | Remarks/record - NATA Test Reports: CBR / Swell Grading PI (Atterberg Limits) Permeability Compaction | Yes, No
date | Inspection Date:
section | 5.0 Completion
checkpoint | 5.1 - Conformity with Drawings
label | Ref docs - VR Clause 204.03 Table 204.031
label | Acceptance criteria - Earthworks shall be finished to conform to the levels, lines, grades and cross-sectional specified or shown on the drawings with the following requirements. · Scale A: mean +5 / -15 mm Max S 12 mm. · Scale B: mean +5 / -25 mm Max S 15 mm. · Alignment: ±50 mm. Scale C - random levelling not required, no point > +10 / -30 mm.
button | Does the final product conform to the above criteria? | Yes, No
label | Freq - Each Lot
label | Key - R
label | Resp - SE
date | Inspection Date:
checkpoint | 5.2 - Preparation of Final Surface. (For Underside of Pavement Layers and the surface of the Cut Floor).
label | Ref docs - VR Clause 204.15
label | Acceptance criteria - Surface is Smooth, Hard, Tightly Bound and Free from Depressions Capable of Holding Water. Material within 150 mm of subgrade shall be maintained such that its moisture content is not less than 70% of OMC prior to the placement of any pavement layers.
button | Does the final product conform to the above criteria? | Yes, No
label | Freq - Each Lot
label | Key - R
label | Resp - SE
date | Inspection Date:
section | 6.0 Work Lot Close Out
checkpoint | 6.1 - Test Reports
label | Ref docs - VicRoads Specifications
label | Acceptance criteria - All Test reports received and Reviewed
label | Freq - Each Lot
label | Key - R
label | Resp - SE
button | Remarks/record - NATA Endorsed Test Reports | Yes, No, N/A
date | Inspection Date:
checkpoint | 6.2 - Product Non-Conformance
label | Ref docs - CQMP
label | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
label | Freq - Each Lot
label | Key - R
label | Resp - SE
label | Remarks/record - NCR reports
date | Inspection Date:
checkpoint | 6.3 - Quality Representative to check the above criteria and records to confirm
label | Ref docs - CQMP Lot Records
label | Acceptance criteria - All above criteria met, and records identified attached.
label | Freq - Each Lot
label | Key - R
label | Resp - SE
button | Remarks/record - Completed Checklist (if applicable) and reports and other compliance records attached. | Yes, No, N/A
date | Inspection Date: