## Sheet1
Form 087 Quality Assurance Form - Inspection and Test Plan
Work Order Number:
Product Description:
Date of Manufacture:
W: Witness H: Hold Point where work does not proceed unless approved R: Review S: Surveillance or Monitoring X: Self inspection by performer of work
ITEM | Description of Activity | Specification/Control Documents | Acceptance Criteria | Verifying Documents | Control Point | Inspection By | Inspection By | Inspection By
[6 empty] | Supervisor | Leading Hand | Quality Control
Preliminary Activities
1 | Review Work Instruction | Scope of works | All work instruction documents and drawings to be reviewed. Due date to be confirmed. | Work Instruction | REVIEW |  |  | N/A
|  | Customer order |  | Drawings
Client supplied drawings
Precast shop drawings
Lifting design drawings
2 | Certification of lifting points/ cast in items | AS/NZS 4671 | All materials to be new and free of defects. All materials to have manufacturer/supplier test certificates supplied. | Lifting Drawing certified by Ancon | REVIEW |  |  | N/A
AS 3679
AS 3850
AS 4680
3 | Concrete mix design | AS 3600 | Concrete Mix design meets requirement | Mix design | REVIEW |  |  | N/A
Historical records
Materials
4 | Assemble reinforcing cage | MJB Production Drawing | Drawings are available, bars placed as shown on MJB Production Drawing. | MJB Production Drawing | HOLD POINT |  |  | N/A
Pre-Pour
5 | Set up formwork/moulds | AS 1597 | Formwork is suitable for surface finish. | MJB Production Drawing | HOLD POINT |  |  | N/A
|  | AS 3610 | Dimensions checked in accordance with MJB production drawings.
6 | Apply form release | AS 1597 | Applied prior to pouring |  | HOLD POINT |  |  | N/A
AS 3600
AS 3850
7 | Installation of reinforcing | AS 1597 | Cover and location of reinforcement checked. | MJB Production Drawing | HOLD POINT |  |  | N/A
AS 3600
AS 3850
8 | Installation of cast-in items (Lifting Pins, Ferrules etc) | AS 1597 | Cover and location of cast-in items checked. | MJB Production Drawing | HOLD POINT |  |  | N/A
AS 3600
AS 3850
Batching Concrete
9 | Concrete testing | AS 1379 | Compressive strength test. Minimum 28 day compressive strength for S50 is 58 MPa | Every 20m3 concrete batch. | HOLD POINT |  |  | N/A
|  | AS 1012 | Slump and. Slump 120mm +- 20mm | Every 20m3 concrete batch.
Concrete Placement, Handling & Finishing
10 | Pour concrete | AS 3600 | Correct concrete supplied | Concrete delivery docket | HOLD POINT |  |  | N/A
Concrete temperature between 10-32 degrees Celsius at discharge. Freefall distance less than 2m
11 | Finishing | AS 1597 | Finish level to be trowelled as per AS 3610 |  | WITNESS |  |  | N/A
AS 3600
AS 3610
Post Pour
12 | Remove from mould | AS 1597 | Dimensions, lifting points and visual appearance are correct and within tolerance |  | HOLD POINT
AS 3600
13 | Curing | AS 3799 | All precast concrete cured by Master Builders Solutions Masterkure CC 100WB |  | WITNESS |  |  | N/A
Repairs (if required) and storage of product
14 | Identify and repair defects | AS 3610 | Identify defects, complete repairs with the correct method. |  | HOLD POINT
AS 1597
15 | Final inspection and storage of items |  | All items inspected, approved product have quality tick, moved to storage area prior to despatch. | Quality Tick on product. | HOLD POINT