## res2
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | Culvert Checklist | itp |  |  |  |  | Culvert Checklist
section | Preliminary Activities
checkpoint | 1 - Review Work Instruction
label | Specification/Control Documents - Scope of works, Customer order, Client supplied drawings, Precast shop drawings, Lifting design drawings
label | Acceptance Criteria - All work instruction documents and drawings to be reviewed. Due date to be confirmed.
label | Verifying Documents - Work Instruction, Drawings
label | Control Point - REVIEW
checkpoint | 2 - Certification of lifting points/ cast in items
label | Specification/Control Documents - AS/NZS 4671, AS 3679, AS 3850, AS 4680
label | Acceptance Criteria - All materials to be new and free of defects. All materials to have manufacturer/supplier test certificates supplied.
label | Verifying Documents - Lifting Drawing certified by Ancon
label | Control Point - REVIEW
checkpoint | 3 - Concrete mix design
label | Specification/Control Documents - AS 3600
label | Acceptance Criteria - Concrete Mix design meets requirement
label | Verifying Documents - Mix design, Historical records
label | Control Point - REVIEW
section | Materials
checkpoint | 4 - Assemble reinforcing cage
label | Specification/Control Documents - MJB Production Drawing
label | Acceptance Criteria - Drawings are available, bars placed as shown on MJB Production Drawing.
label | Verifying Documents - MJB Production Drawing
label | Control Point - HOLD POINT
holdpoint | HOLD POINT
section | Pre-Pour
checkpoint | 5 - Set up formwork/moulds
label | Specification/Control Documents - AS 1597, AS 3610
label | Acceptance Criteria - Formwork is suitable for surface finish. Dimensions checked in accordance with MJB production drawings.
label | Verifying Documents - MJB Production Drawing
label | Control Point - HOLD POINT
holdpoint | HOLD POINT
checkpoint | 6 - Apply form release
label | Specification/Control Documents - AS 1597, AS 3600, AS 3850
label | Acceptance Criteria - Applied prior to pouring
label | Control Point - HOLD POINT
holdpoint | HOLD POINT
checkpoint | 7 - Installation of reinforcing
label | Specification/Control Documents - AS 1597, AS 3600, AS 3850
label | Acceptance Criteria - Cover and location of reinforcement checked.
label | Verifying Documents - MJB Production Drawing
label | Control Point - HOLD POINT
holdpoint | HOLD POINT
checkpoint | 8 - Installation of cast-in items (Lifting Pins, Ferrules etc)
label | Specification/Control Documents - AS 1597, AS 3600, AS 3850
label | Acceptance Criteria - Cover and location of cast-in items checked.
label | Verifying Documents - MJB Production Drawing
label | Control Point - HOLD POINT
holdpoint | HOLD POINT
section | Batching Concrete
checkpoint | 9 - Concrete testing
label | Specification/Control Documents - AS 1379, AS 1012
label | Acceptance Criteria - Compressive strength test. Minimum 28 day compressive strength for S50 is 58 MPa, Slump and. Slump 120mm +- 20mm
label | Verifying Documents - Every 20m3 concrete batch. Every 20m3 concrete batch.
label | Control Point - HOLD POINT
holdpoint | HOLD POINT
section | Concrete Placement, Handling & Finishing
checkpoint | 10 - Pour concrete
label | Specification/Control Documents - AS 3600
label | Acceptance Criteria - Correct concrete supplied, Concrete temperature between 10-32 degrees Celsius at discharge. Freefall distance less than 2m
label | Verifying Documents - Concrete delivery docket
label | Control Point - HOLD POINT
holdpoint | HOLD POINT
checkpoint | 11 - Finishing
label | Specification/Control Documents - AS 1597, AS 3600, AS 3610
label | Acceptance Criteria - Finish level to be trowelled as per AS 3610
label | Control Point - WITNESS
section | Post Pour
checkpoint | 12 - Remove from mould
label | Specification/Control Documents - AS 1597, AS 3600
label | Acceptance Criteria - Dimensions, lifting points and visual appearance are correct and within tolerance
label | Control Point - HOLD POINT
holdpoint | HOLD POINT
checkpoint | 13 - Curing
label | Specification/Control Documents - AS 3799
label | Acceptance Criteria - All precast concrete cured by Master Builders Solutions Masterkure CC 100WB
label | Control Point - WITNESS
holdpoint | HOLD POINT
section | Repairs (if required) and storage of product
checkpoint | 14 - Identify and repair defects
label | Specification/Control Documents - AS 3610, AS 1597
label | Acceptance Criteria - Identify defects, complete repairs with the correct method.
label | Control Point - HOLD POINT
holdpoint | HOLD POINT
checkpoint | 15 - Final inspection and storage of items
label | Acceptance Criteria - All items inspected, approved product have quality tick, moved to storage area prior to despatch.
label | Verifying Documents - Quality Tick on product.
label | Control Point - HOLD POINT
holdpoint | HOLD POINT