## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
e9b5b6dc-6e2a-53e1-b54a-87ab33b9cde0 | checklist | Installation of FSMH | itp | Installation of FSMH
2ac8716a-63b3-52cf-b624-07c24c0cd6c9 | section | SECTION 3 - RECEIVING INSPECTIONS
2d6469ff-22e7-5477-8cef-d23cbae25acd | checkpoint | 3.1 - Material Delivery
806abcb6-a4fb-5349-9283-a2536c8bc7cc | note | Inspection Point: Quality Control Activity - Inspect for damage and wear, Confirm items are correct as per drawings and Specifications
8669d3f7-b6d6-5939-90d9-c12c0b0b1805 | note | Acceptance Criteria - Items are approved as per contract specification
084674f2-8ece-5416-b6b2-a6bd25b79931 | note | ○ DCC approved
8496239c-b7dc-5ab1-a142-bf9b50bc09ed | note | Verifying Document - Photos, delivery docket
6ec60bff-375a-55c9-9471-852b0e2d9cf1 | note | Frequency - On Delivery
33b800ec-d486-54ad-b320-c81e2e03e6c0 | note | Inspection Type (Visual, other) - Visual
beb6820b-eadd-5301-b91e-1fc9f3ba0aae | note | Inspection: Key - C
85e1e50b-119a-54bf-b55b-4ab7a294adeb | note | Inspection: By (Role Key) - SP/QE
8f6dbf2f-9f4d-514f-ae80-57151c1d03ae | checkpoint | 3.2 - Set out
239bdc79-e281-5263-be7a-c007f446e2f2 | note | Inspection Point: Quality Control Activity - Set out completed by an approved surveyor marked allignment
4789a771-1312-53e1-bfbc-913c4e8e9f34 | note | Acceptance Criteria - Allignment set out matches drawing C4400 or aggreed with the Engineer
1cc5fe31-66bd-5642-9ed2-1174cadd9bb7 | note | Verifying Document - Survey marks, photos
7ef3b481-1d15-540f-a3b7-fc41d9528d2b | note | Frequency - Prior to commencement of works
445bd94e-354d-51f7-a3fa-83abdb0c8278 | note | Inspection Type (Visual, other) - Survey
d2630a7c-41e0-5a4d-8b79-1849e680b9d9 | note | Inspection: Key - H
fdbc06bb-29e7-5dbe-bb16-30c52a361fad | note | Inspection: By (Role Key) - SV/SP/QE
57e25cdc-0d38-5a66-a6ee-bd14e8463cf5 | signoff | HOLD POINT
b75df167-953c-56c0-85ad-84e77b53dabd | checkpoint | 3.3 - Backfill / Bedding Material
04555d56-2a87-5bd2-b3a4-c63fd90661f0 | note | Inspection Point: Quality Control Activity - Approved Material, AP20 as per DCC code of subdivision 10329.
6ffc00f4-a4b5-50e2-8ed8-cf4bb471fa66 | note | Acceptance Criteria - As per DCC code of subdiviison 10329
08b60273-975b-59d9-991e-db2d5f154800 | note | Verifying Document - Delivery dockets, photos
4d5669ff-3a40-564a-b367-1229d5b29869 | note | Frequency - On Delivery
f4c1bc6f-a6b9-5282-b3c2-9ee0ec888446 | note | Inspection Type (Visual, other) - Visual
8849bef0-2894-5b1f-aa47-ab272fe6b3e0 | note | Inspection: Key - C
2d348209-830a-533c-b2cb-33a9176baef1 | note | Inspection: By (Role Key) - SP/QE
1d1078e0-1bb1-56f7-948a-752012ad998c | section | SECTION 4 - IN-PROCESS INSPECTIONS
c5f206b2-b8d9-55e2-a96f-c1168acbd237 | checkpoint | 4.1 - Trench Excavation
18e9a7a2-b731-5832-b156-742c33b5f4b0 | note | Inspection Point: Quality Control Activity - Excavate to required depth to invert as per C4400
5fea94fd-37d8-58d9-adcc-4b0960a0f2a4 | note | ○ Trench width to allow for 300mm seperation between springline of the pipe and trench wall or an adjacent pipe
7f43a1f4-eced-585a-9848-277a5413e3f8 | note | ○ Floor of Trench to be even across width and length
7dac419b-a2c1-5061-8eb3-8e2fe0f69030 | note | Acceptance Criteria - As per 561467-TW-04-DRW-02
3baf211e-25b2-5839-95a8-e35a0bcee911 | note | Verifying Document - Photos, measurement checks
d78f00b3-2675-51ff-9e82-dcc18b43a443 | note | Frequency - During Installation
656f4ca1-bf71-5ceb-a2ee-a47a43478424 | note | Inspection Type (Visual, other) - Visual
709665d1-1aa0-5554-8850-81d901359ae9 | note | Inspection: Key - V
39450a6a-1d07-5a05-bfce-094a739c248d | note | Inspection: By (Role Key) - SP/QE
5f723e23-2a78-544e-8477-4ca06f9af449 | checkpoint | 4.2 - Foundation
7a0456fa-aeea-5401-9aa3-1c17816e1e58 | note | Inspection Point: Quality Control Activity - Scala tests on base of trench
920e8675-2abc-55fa-8cca-11f1aed26ce4 | note | Acceptance Criteria - Minimum of 2 blows per 100mm
8e48f1fd-c1de-5185-bc84-70d2c5a3db1a | note | Verifying Document - Test results
1953cef0-a40e-57f9-890e-b357ef9b6583 | note | Frequency - During installation, per 20m
e22adcef-e4cf-53c3-99d9-6a420799ecf0 | note | Inspection Type (Visual, other) - Visual, On site test
98ae311a-245f-57e1-9fad-1b8e8892ad56 | note | Inspection: Key - H
e97f1f00-2966-5efb-ae0c-9922fc4b2702 | note | Inspection: By (Role Key) - SP/QE
a2836e07-5fe4-5bc6-a345-bf727e1f1bd5 | signoff | HOLD POINT
69cbeeac-442a-5a07-adc1-321b4887edcb | checkpoint | 4.3 - Bedding
78ed13b0-8a03-5ee3-8997-781459559776 | note | Inspection Point: Quality Control Activity - Bedding minimum 150mm compacted material
6d649f94-08f9-5be0-aae1-c24bd7d10a6f | note | Acceptance Criteria - Bedding to comply with requirements
437508f5-7db2-5df2-b967-ab7a7b5911cc | note | Verifying Document - Photo
591a1b3d-ba00-5677-a48d-cc67323c7135 | note | Frequency - During installation
65c94e26-7882-5acb-b501-ff35a8beac81 | note | Inspection Type (Visual, other) - Visual, Measurement Check
a808f533-8169-5d4d-848c-37053220432e | note | Inspection: Key - C
f7b3c87b-e466-57a0-9aeb-6595fae363bd | note | Inspection: By (Role Key) - QE/SP
35261bbe-78b4-50aa-ad09-d138991c4ad8 | checkpoint | 4.4 - MH Installation
c9a4cad1-f83d-5de0-a1bb-6f12bd0511f3 | note | Inspection Point: Quality Control Activity - MHs to be installed true to the design level
332d8a9c-647e-5a81-ab6a-3730b0c64c7e | note | Acceptance Criteria - Final levels are in accordance with the C4400 or within tolerance and agreed with the Engineer
0b230306-490b-5f77-a62e-ae7640a5da13 | note | Verifying Document - Photos, As-built
dbf55a3e-102b-5a1f-a5c3-b5a2ab8bcaed | note | Frequency - During installation
8f0f9f10-3d98-5f69-8152-c9645eccac27 | note | Inspection Type (Visual, other) - Survey
fe0ba045-d981-561d-bc8e-08fe2b5543ac | note | Inspection: Key - H
939ac9c7-32fe-53a7-ac5e-e793731a72bb | note | Inspection: By (Role Key) - SP/QE
5772216d-2908-5503-859b-cb8ca012cb8f | signoff | HOLD POINT
e02454ad-8697-5547-b422-8a0a33a7dfde | checkpoint | 4.5 - Benching
4790fff2-db43-59c7-a38d-41ee5396ecba | note | Inspection Point: Quality Control Activity - Benching concrete shall have a crushing strength of 20MPa at 28 days.
4955340a-15fb-506b-8eba-865e7f8fa33c | note | ○ Benching shape to have smooth transitions at bends and junctions
0ee5c2bd-cc2f-516a-9e2a-0a7711bb7917 | note | Acceptance Criteria - Benching built up to the specifications
ad316f58-4c66-5233-8bfd-fb82efe1f5de | note | Verifying Document - Photos
f9c8dc7f-a2b1-5f24-a55d-661207c48279 | note | Frequency - During benching contruction
8a4b059a-2f36-50b8-894d-b677f6684b9c | note | Inspection Type (Visual, other) - Visual, Test Results
efc5144c-0215-5565-87e1-b8c3dc5a8ce2 | note | Inspection: Key - H
506e0f61-82db-50e5-8dc3-96132d1fb8c9 | note | Inspection: By (Role Key) - SP/QE
78088795-c1e3-5e84-b7f5-e199fcd7b105 | signoff | HOLD POINT
9fb81e22-7beb-5512-a018-7c24aa9f22ca | checkpoint | 4.6 - Backfill and Compact
ddff2752-76d7-5533-ac35-92ff0d581551 | note | Inspection Point: Quality Control Activity - Backfill in 200mm layers of compacted material
f5a055c0-29a5-55e2-ae7b-c249238206c5 | note | ○ Compaction testing one test every two layers as required
8566b8f9-00b8-5641-9d03-1e99cea4b1cf | note | Acceptance Criteria - 95% MDD in roads, paths, and pavements
13201b33-ba4e-57e6-905c-279fc74ff298 | note | Verifying Document - Photos, Compaction test results
87f5eddc-01fa-5da9-9b24-56561ecac1ee | note | Frequency - During Installation
f65b7fd7-4f7a-53a0-bfce-8e9708847b2b | note | Inspection Type (Visual, other) - Visual, On Site test
5acf7857-6691-5b91-8a24-1f549c56f0cf | note | Inspection: Key - H
9d6c98ca-ef73-5c98-b50c-07dfd8224d13 | note | Inspection: By (Role Key) - SP/QE
3f6febb8-dc3a-59a7-9805-82407b0ba2e3 | signoff | HOLD POINT
26b44d4a-841a-50a8-b965-36c95addc184 | section | SECTION 5 - FINAL INSPECTION AND HANDOVER
52bc42b8-0dbe-5952-a95d-0b42df33e7e8 | checkpoint | 5.2 - Red pen markups
eee18487-5694-52f0-aa6e-e837caa7b0dd | note | Inspection Point: Quality Control Activity - Complete mark up of any changes from project drawings
2a89bca2-b19f-5b5d-9bb4-652fa178e835 | note | Acceptance Criteria - Signed ITP
6635c531-831b-5fce-9f78-37e20c29636a | note | Verifying Document - Red pen markup drawings
99eef058-390a-528a-a588-71d1b784d1bf | note | Frequency - After installation of FSMH
736baeb7-d8e6-5c5c-a6e3-e6fd6697687e | note | Inspection Type (Visual, other) - Document
8af5d5ba-4f8e-5ff0-8612-c2ba6ceb4ca1 | note | Inspection: Key - H
b7578470-37a7-50d1-b577-b49b5b6ac24b | note | Inspection: By (Role Key) - SP/QE/CM
6468b959-7075-58a9-aa05-3b68d9a54856 | signoff | HOLD POINT
7976dd77-c82f-5fdb-b4ee-c06df388d026 | checklist | Installation of SW Manhole Zone 2 | itp | Installation of SW Manhole Zone 2
2ac8716a-63b3-52cf-b624-07c24c0cd6c9 | section | SECTION 3 - RECEIVING INSPECTIONS
2d6469ff-22e7-5477-8cef-d23cbae25acd | checkpoint | 3.1 - Material Delivery
a29fa978-018e-5910-9fd9-c2abe424bd81 | note | Inspection Point: Quality Control Activity - Inspect for damage and wear, Confirm items are correct as per drawings and Specifications
44efb122-50da-5184-83a1-6644b0832b49 | note | Acceptance Criteria - Items are approved as per contract specification
a124ccac-63a5-5037-856e-82e28b828765 | note | ○ DCC approved
47495e5a-2e59-5328-bee0-afa8c2600cb2 | note | Verifying Document - Photos, delivery docket
f46f0672-2f07-5b75-9e4f-b19280511cf4 | note | Frequency - On Delivery
e5b649a2-bb85-505a-b168-29565677b11b | note | Inspection Type (Visual, other) - Visual
93724b38-b58b-5e0a-8907-3d27aaaf3bff | note | Inspection: Key - C
44e7eb58-f566-5b26-8f65-382bc031671b | note | Inspection: By (Role Key) - SP/QE
8f6dbf2f-9f4d-514f-ae80-57151c1d03ae | checkpoint | 3.2 - Set out
cde0254e-3d81-5145-a5f5-b167f165675d | note | Inspection Point: Quality Control Activity - Set out completed by an approved surveyor marked allignment
8ac22761-b102-5445-b4e5-d748803ce00a | note | Acceptance Criteria - Allignment set out matches drawing C4200 or aggreed with the Engineer
a38188ae-cf50-5764-9c9e-8928dc9f70b4 | note | Verifying Document - Survey marks, photos
cbeb97b3-d914-54ee-be83-a43349a2644e | note | Frequency - Prior to commencement of works
b195fc0e-79d6-5601-8369-29a7d84dd517 | note | Inspection Type (Visual, other) - Survey
8c2190d1-61d2-5c28-bc53-b0d2d35cd974 | note | Inspection: Key - H
21bf25ec-ef39-58c5-936c-ebe802f410d1 | note | Inspection: By (Role Key) - SV/SP/QE
57e25cdc-0d38-5a66-a6ee-bd14e8463cf5 | signoff | HOLD POINT
b75df167-953c-56c0-85ad-84e77b53dabd | checkpoint | 3.3 - Backfill / Bedding Material
4fdeb654-361b-550a-bd23-2c1a788a000a | note | Inspection Point: Quality Control Activity - Approved Material, AP20 as per DCC code of subdivision 10329.
2f6223a9-cd8d-5f0f-9586-4e5cd6477c22 | note | Acceptance Criteria - As per DCC code of subdiviison 10329
d36f3eb0-8591-59b9-8412-9ae07635780f | note | Verifying Document - Delivery dockets, photos
0b7a5cbb-1b66-56c9-b022-2292d4ec06e6 | note | Frequency - On Delivery
b3a71a87-9b26-5e89-acce-e66e7be47dde | note | Inspection Type (Visual, other) - Visual
45aefde4-eae5-5f28-b5f3-61c88fa056b3 | note | Inspection: Key - C
318833e9-18d3-53b9-862e-6bb7ae53ee4b | note | Inspection: By (Role Key) - SP/QE
1d1078e0-1bb1-56f7-948a-752012ad998c | section | SECTION 4 - IN-PROCESS INSPECTIONS
c5f206b2-b8d9-55e2-a96f-c1168acbd237 | checkpoint | 4.1 - Trench Excavation
85810065-8af2-5887-a763-6cbdc24251ee | note | Inspection Point: Quality Control Activity - Excavate to required depth to invert as per C4200
75bce559-fa6a-5b26-b9e3-c23642b9f6ee | note | ○ Trench width to allow for 300mm seperation between springline of the pipe and trench wall or an adjacent pipe
b7573bb5-9bb8-5b52-9332-16e014daedbb | note | ○ Floor of Trench to be even across width and length
4afa819a-40f1-5da1-b982-f49d4a0dcb1f | note | Acceptance Criteria - As per 561467-TW-04-DRW-002
b909a50e-3378-5033-994a-7778c9763473 | note | Verifying Document - Photos, measurement checks
44f14b9b-54f8-50d8-81f1-cd5d78cecea8 | note | Frequency - During Installation
ec891f0e-557c-5255-866d-4714aedf5957 | note | Inspection Type (Visual, other) - Visual
ea5c0f7e-b252-5353-9309-777a291c8ac7 | note | Inspection: Key - V
0fd76793-a9c3-5f0a-83e9-e11ad583b2fe | note | Inspection: By (Role Key) - SP/QE
5f723e23-2a78-544e-8477-4ca06f9af449 | checkpoint | 4.2 - Foundation
3e20161c-8141-576b-b480-8c2a015ca0da | note | Inspection Point: Quality Control Activity - Scala tests on base of trench
a21b6503-1a26-5dd7-b8f3-edbe7e271855 | note | Acceptance Criteria - Minimum of 2 blows per 100mm
96bf97eb-b433-5abe-878a-0518dec5b47a | note | Verifying Document - Test results
40b0f187-926a-59b0-82a0-178400a6f9d7 | note | Frequency - During installation, per 20m
416d7c62-2c7d-5f7a-9cd6-6a441a862892 | note | Inspection Type (Visual, other) - Visual, On site test
92dcf30b-7722-5237-8101-585ecc864b8c | note | Inspection: Key - H
a438f15f-858b-56d5-8ff1-704c4dda68f4 | note | Inspection: By (Role Key) - SP/QE
a2836e07-5fe4-5bc6-a345-bf727e1f1bd5 | signoff | HOLD POINT
69cbeeac-442a-5a07-adc1-321b4887edcb | checkpoint | 4.3 - Bedding
e314dd11-5ac5-5869-8fa0-50ae611dedae | note | Inspection Point: Quality Control Activity - Bedding minimum 150mm compacted material
e8e97747-7eff-534b-888b-60b7d89951f0 | note | Acceptance Criteria - Bedding to comply with requirements
94216d61-6a6e-5818-bb12-5f2a7fd2480b | note | Verifying Document - Photo
73cea6ff-8e6d-5440-abf2-9076e94302de | note | Frequency - During installation
fb62cdfa-bb79-5fef-8ce6-18b77a02d1f8 | note | Inspection Type (Visual, other) - Visual, Measurement Check
0cf46c90-ef08-5ebf-a70a-ea532642c4ae | note | Inspection: Key - C
76949fd5-e485-5834-8f36-7af1c69eede4 | note | Inspection: By (Role Key) - QE/SP
35261bbe-78b4-50aa-ad09-d138991c4ad8 | checkpoint | 4.4 - MH Installation
1043390d-4d96-5ba3-a3e8-5d91e2d79668 | note | Inspection Point: Quality Control Activity - MHs to be installed true to the design level
917349a0-72bb-51b7-a8ad-2407d4fb5cf9 | note | Acceptance Criteria - Final levels are in accordance with the C4200 or within tolerance and agreed with the Engineer
5a3b78e5-3f8a-5935-bc1f-5e27c15bf893 | note | Verifying Document - Photos, As-built
79551e70-7982-580a-a212-202f0c9d78c0 | note | Frequency - During installation
16d4994a-ae8c-58d6-b7ec-03d55d4e8ded | note | Inspection Type (Visual, other) - Survey
9a5a94f0-a19c-5050-9200-9e5145dbdd23 | note | Inspection: Key - H
56b7bcf5-daaa-5436-a5c4-e1ff0672ec68 | note | Inspection: By (Role Key) - SP/QE
5772216d-2908-5503-859b-cb8ca012cb8f | signoff | HOLD POINT
e02454ad-8697-5547-b422-8a0a33a7dfde | checkpoint | 4.5 - Benching
bdb5e955-ee00-5aea-a87e-f51af8efac94 | note | Inspection Point: Quality Control Activity - Benching concrete shall have a crushing strength of 20MPa at 28 days.
b7f1fe5d-8830-58d5-ad3b-4d87a6381f01 | note | ○ Benching shape to have smooth transitions at bends and junctions
56b7b1c6-79d9-5246-b6eb-bd62ce32fec8 | note | Acceptance Criteria - Benching built up to the specifications
a81ffc2a-a985-5824-a556-df665fcaeb0c | note | Verifying Document - Photos
a1cc689c-ebad-540b-ae7a-b7bb52abdc8e | note | Frequency - During benching contruction
94caab6a-0498-56a5-81c6-182cb6991e77 | note | Inspection Type (Visual, other) - Visual, Test Results
fbfdf55e-d05d-5b82-8499-8043d8ed3ab8 | note | Inspection: Key - H
50ac113d-709a-557e-a000-5ac0326d796b | note | Inspection: By (Role Key) - SP/QE
78088795-c1e3-5e84-b7f5-e199fcd7b105 | signoff | HOLD POINT
9fb81e22-7beb-5512-a018-7c24aa9f22ca | checkpoint | 4.6 - Backfill and Compact
321614b0-d678-5730-b64b-c2cb6c96f595 | note | Inspection Point: Quality Control Activity - Backfill in 200mm layers of compacted material
9f30fc69-192a-5107-9db8-85030d994a69 | note | ○ Compaction testing one test every two layers as required
580fb56a-7cd2-5978-bbd8-41558b175288 | note | Acceptance Criteria - 95% MDD in roads, paths, and pavements
5c48bacb-fa13-5ca5-9e42-f34caad1a86d | note | Verifying Document - Photos, Compaction test results
6dd2cb8d-5da2-57c9-8c62-9e589ff9d48a | note | Frequency - During Installation
a9206fb2-cd51-5a53-972a-89814436f002 | note | Inspection Type (Visual, other) - Visual, On Site test
a721cf59-d417-51e5-918d-bf63d99a5298 | note | Inspection: Key - H
98c15240-9448-5f0f-ae49-13f210498d57 | note | Inspection: By (Role Key) - SP/QE
3f6febb8-dc3a-59a7-9805-82407b0ba2e3 | signoff | HOLD POINT
26b44d4a-841a-50a8-b965-36c95addc184 | section | SECTION 5 - FINAL INSPECTION AND HANDOVER
52bc42b8-0dbe-5952-a95d-0b42df33e7e8 | checkpoint | 5.2 - Red pen markups
492c3ef5-ac79-5405-bbaf-d7c78682dc05 | note | Inspection Point: Quality Control Activity - Complete mark up of any changes from project drawings
8b4571f3-25ce-5633-bd22-8a1331c7671b | note | Acceptance Criteria - Signed ITP
c6a1071d-f5c0-5d7a-b09a-886c254c49f6 | note | Verifying Document - Red pen markup drawings
636e8c50-b853-5ae2-a93a-71449df33dcf | note | Frequency - After installation of FSMH
014f1139-c4b0-53ca-85e7-7332eae7669f | note | Inspection Type (Visual, other) - Document
b73a7f1e-c135-56f5-bdb4-62f11bea8078 | note | Inspection: Key - H
6a8c3dbe-52c9-5996-a92d-fdd1e16dadad | note | Inspection: By (Role Key) - SP/QE/CM
6468b959-7075-58a9-aa05-3b68d9a54856 | signoff | HOLD POINT
f52e22ee-141f-5f82-9ed5-924b0ace4c99 | checklist | Installation of SW Manhole Zone 5 | itp | Installation of SW Manhole Zone 5
2ac8716a-63b3-52cf-b624-07c24c0cd6c9 | section | SECTION 3 - RECEIVING INSPECTIONS
2d6469ff-22e7-5477-8cef-d23cbae25acd | checkpoint | 3.1 - Material Delivery
ed48456d-38dc-53e2-a8dd-4094c1c77905 | note | Inspection Point: Quality Control Activity - Inspect for damage and wear, Confirm items are correct as per drawings and Specifications
940d6822-78c1-54a1-b072-b45abc31ef0e | note | Acceptance Criteria - Items are approved as per contract specification
48e1bf1d-9157-518b-bcaf-0f4165da3672 | note | ○ DCC approved
81333b7f-873e-5540-ad8e-190bcc21ca64 | note | Verifying Document - Photos, delivery docket
54538da7-bbb2-52a6-af6f-1af4cbdeaf38 | note | Frequency - On Delivery
06200a2b-b312-5b2d-84b8-8ddc5010df73 | note | Inspection Type (Visual, other) - Visual
92089b0f-4845-54de-b429-30298e2c4e75 | note | Inspection: Key - C
69451d80-0f1b-508b-8e34-c0c64827545f | note | Inspection: By (Role Key) - SP/QE
8f6dbf2f-9f4d-514f-ae80-57151c1d03ae | checkpoint | 3.2 - Set out
8d5aea69-e70f-5e40-9ed9-0890911f45f4 | note | Inspection Point: Quality Control Activity - Set out completed by an approved surveyor marked allignment
1f893f9e-fde9-5f3d-9647-d7c33b05dc37 | note | Acceptance Criteria - Allignment set out matches drawing C4300 or aggreed with the Engineer
4bea244c-8ffb-54f7-8933-2b4ae4f0838c | note | Verifying Document - Survey marks, photos
7cb5e75b-8216-5240-9a3b-d21a00d6e012 | note | Frequency - Prior to commencement of works
3c104ae4-1c1d-5a8c-8d12-7deb5249e0e2 | note | Inspection Type (Visual, other) - Survey
cc1add3c-020c-5ec7-8282-37a531bbc22c | note | Inspection: Key - H
1678b6c5-57a1-546e-8872-d3ad6ffa4456 | note | Inspection: By (Role Key) - SV/SP/QE
57e25cdc-0d38-5a66-a6ee-bd14e8463cf5 | signoff | HOLD POINT
b75df167-953c-56c0-85ad-84e77b53dabd | checkpoint | 3.3 - Backfill / Bedding Material
f3b0d134-b8c7-58c3-a6da-1c12ca276411 | note | Inspection Point: Quality Control Activity - Approved Material, AP20 as per DCC code of subdivision 10329.
4c6de11c-2e6a-5d80-b8c6-552fd47a4797 | note | Acceptance Criteria - As per DCC code of subdiviison 10329
4d0ef22a-52c6-52df-a9db-8b285dcf4098 | note | Verifying Document - Delivery dockets, photos
7bbf9e74-26d5-5de7-acb4-3e2540a00ef0 | note | Frequency - On Delivery
eb239277-f7a2-5140-9f65-5907b5defc82 | note | Inspection Type (Visual, other) - Visual
68c5559d-57c5-5a03-afd6-d3a5db61df25 | note | Inspection: Key - C
e0e933a0-60ac-5e00-8d6d-4bf04ea05abb | note | Inspection: By (Role Key) - SP/QE
1d1078e0-1bb1-56f7-948a-752012ad998c | section | SECTION 4 - IN-PROCESS INSPECTIONS
c5f206b2-b8d9-55e2-a96f-c1168acbd237 | checkpoint | 4.1 - Trench Excavation
8c537452-2139-5018-8d3e-8716c5fb1ebc | note | Inspection Point: Quality Control Activity - Excavate to required depth to invert as per C4300
8c021eae-6672-5070-ba44-8cb0ce2670f9 | note | ○ Trench width to allow for 300mm seperation between springline of the pipe and trench wall or an adjacent pipe
a2508ce8-8a02-5b8b-9ad2-2e510313918f | note | ○ Floor of Trench to be even across width and length
ba7ec9ba-e82b-5057-b13a-0e35ccc2b0d6 | note | Acceptance Criteria - As per 561467-TW-04-DRW-002
6dc3d543-ea24-5f79-8aa7-543853943ebc | note | Verifying Document - Photos, measurement checks
e5430870-d58f-5ee6-ad76-b56c45763918 | note | Frequency - During Installation
71c8d5d0-4d95-5db0-8209-3e7d9efd0a39 | note | Inspection Type (Visual, other) - Visual
86b3fd0b-c273-5bd6-84e4-5ab8a80e2d62 | note | Inspection: Key - V
ff35bc3a-e1fc-5cfd-ac96-4bcbbc8b5c00 | note | Inspection: By (Role Key) - SP/QE
5f723e23-2a78-544e-8477-4ca06f9af449 | checkpoint | 4.2 - Foundation
e6569354-8ad1-58d0-8634-3c90d90112fd | note | Inspection Point: Quality Control Activity - Scala tests on base of trench
d7c4c73c-fb74-5dc0-bc51-3893c0cce08e | note | Acceptance Criteria - Minimum of 2 blows per 100mm
7dac7bb5-615a-5797-925d-732bc9e1fcad | note | Verifying Document - Test results
42d183cf-3cea-51f1-a638-9c825b0b166d | note | Frequency - During installation, per 20m
168a7e5e-aef1-525e-8ccc-28befb765c2a | note | Inspection Type (Visual, other) - Visual, On site test
52c7e5e0-3afd-5a95-8a34-b791a43972e3 | note | Inspection: Key - H
3211b1a6-d126-5ed3-9aa3-ad8f6daa76ac | note | Inspection: By (Role Key) - SP/QE
a2836e07-5fe4-5bc6-a345-bf727e1f1bd5 | signoff | HOLD POINT
69cbeeac-442a-5a07-adc1-321b4887edcb | checkpoint | 4.3 - Bedding
3b371ec9-d0bc-57e7-abd7-82cfd80d15a7 | note | Inspection Point: Quality Control Activity - Bedding minimum 150mm compacted material
2dba87ba-e387-584a-a564-a627bc16821b | note | Acceptance Criteria - Bedding to comply with requirements
223534c4-e7a7-557d-985f-4609ffe26a9e | note | Verifying Document - Photo
2e991094-ff11-57c3-910c-b6e3af232e90 | note | Frequency - During installation
fd860daf-ba5c-5521-9d86-c640f887f7df | note | Inspection Type (Visual, other) - Visual, Measurement Check
407baf7c-7a67-5aa0-80fc-5b45a9b9e8f2 | note | Inspection: Key - C
97d64a4c-1c20-5681-903b-1c6f81706802 | note | Inspection: By (Role Key) - QE/SP
35261bbe-78b4-50aa-ad09-d138991c4ad8 | checkpoint | 4.4 - MH Installation
f0fa5038-0455-5d94-be60-5b6d914bee57 | note | Inspection Point: Quality Control Activity - MHs to be installed true to the design level
61227a69-9080-5a93-82ea-4f7fa4b79db6 | note | Acceptance Criteria - Final levels are in accordance with the C4300 or within tolerance and agreed with the Engineer
10ee9b99-dfb2-5e3c-b674-be146a75f287 | note | Verifying Document - Photos, As-built
9f0aed31-b3d0-583c-a64e-4fb7dd397bd5 | note | Frequency - During installation
ad0e7df7-25c0-5cf8-9608-fae46736342b | note | Inspection Type (Visual, other) - Survey
1e6dcba3-5ceb-5b3e-b248-0eec6c1b52b7 | note | Inspection: Key - H
439831af-1bf4-5ff1-b37c-3540270470fa | note | Inspection: By (Role Key) - SP/QE
5772216d-2908-5503-859b-cb8ca012cb8f | signoff | HOLD POINT
e02454ad-8697-5547-b422-8a0a33a7dfde | checkpoint | 4.5 - Benching
6932a6a3-de5c-5834-ae16-4c426800e72d | note | Inspection Point: Quality Control Activity - Benching concrete shall have a crushing strength of 20MPa at 28 days.
ed25f9fc-3649-595f-a96c-eed3eec03db0 | note | ○ Benching shape to have smooth transitions at bends and junctions
ab7f8f5c-a323-5e1d-8410-b19893986134 | note | Acceptance Criteria - Benching built up to the specifications
bca6b58e-6a47-5f1d-bf34-cfc86cbee1fd | note | Verifying Document - Photos
9340d5bf-e9aa-5bee-a610-6bff54e8b32c | note | Frequency - During benching contruction
b741d3fd-d2cd-5598-ab85-00ccdaaa5f77 | note | Inspection Type (Visual, other) - Visual, Test Results
786d8327-f5e6-50a9-b284-5f34e63661f9 | note | Inspection: Key - H
a31b2973-433d-5355-8ed3-148a46341116 | note | Inspection: By (Role Key) - SP/QE
78088795-c1e3-5e84-b7f5-e199fcd7b105 | signoff | HOLD POINT
9fb81e22-7beb-5512-a018-7c24aa9f22ca | checkpoint | 4.6 - Backfill and Compact
c61ecf00-3e11-5596-97cf-845bad86bef4 | note | Inspection Point: Quality Control Activity - Backfill in 200mm layers of compacted material
80b60513-67e0-5a0a-af66-20eeef941d7e | note | ○ Compaction testing one test every two layers as required
e9241055-4c50-5231-97b3-6c448fe50ebb | note | Acceptance Criteria - 95% MDD in roads, paths, and pavements
a2177977-2e33-5d08-84d6-1f7438b20e4c | note | Verifying Document - Photos, Compaction test results
37978736-88a0-5c3c-bc2f-6a6f1f0bebd4 | note | Frequency - During Installation
946e4f80-994f-5b7d-a083-6f16c152f507 | note | Inspection Type (Visual, other) - Visual, On Site test
e4ea17e0-fe34-5626-ae8a-37581cba4c8f | note | Inspection: Key - H
d2c96eb6-5cd7-5c6e-be19-518dc03addeb | note | Inspection: By (Role Key) - SP/QE
3f6febb8-dc3a-59a7-9805-82407b0ba2e3 | signoff | HOLD POINT
26b44d4a-841a-50a8-b965-36c95addc184 | section | SECTION 5 - FINAL INSPECTION AND HANDOVER
52bc42b8-0dbe-5952-a95d-0b42df33e7e8 | checkpoint | 5.2 - Red pen markups
6ed2c482-71f7-592d-92c7-697f90303735 | note | Inspection Point: Quality Control Activity - Complete mark up of any changes from project drawings
e3cd0e18-db98-5139-a859-2b1af7c48a01 | note | Acceptance Criteria - Signed ITP
c360fa1f-3f2e-50ee-b109-8534b4b9f5f2 | note | Verifying Document - Red pen markup drawings
4e6158ff-dcd6-5c55-b75b-e121f2a1ee77 | note | Frequency - After installation of FSMH
161d3515-e1d8-542c-98c9-175b6b287715 | note | Inspection Type (Visual, other) - Document
346718c5-98b6-5799-88fb-deb5cb8e425f | note | Inspection: Key - H
0a8ccab2-b39d-50c7-bcfd-166efe1420d3 | note | Inspection: By (Role Key) - SP/QE/CM
6468b959-7075-58a9-aa05-3b68d9a54856 | signoff | HOLD POINT
5854a1ff-d026-5f0d-a306-b5237f8a5679 | checklist | ITP-1001 - Installation of Manhole - FSMH-A2 | itp | ITP-1001 - Installation of Manhole - FSMH-A2
2ac8716a-63b3-52cf-b624-07c24c0cd6c9 | section | SECTION 3 - RECEIVING INSPECTIONS
2d6469ff-22e7-5477-8cef-d23cbae25acd | checkpoint | 3.1 - Material Delivery
306c0cad-f080-5f4a-8125-bc0a08f3554b | note | Inspection Point: Quality Control Activity - Inspect for damage and wear, Confirm items are correct as per drawings and Specifications
5e5e9327-26c9-59f7-a0c4-99b8a67431c4 | note | Acceptance Criteria - Items are approved as per contract specification
64b73fde-4c6b-5dd9-bf71-c782eac57bc2 | note | ○ DCC approved
9c04f967-2974-5f90-b62d-1ea3b2dfa74c | note | Verifying Document - Photos, delivery docket
5ae2f52f-cf55-51e5-9ce9-595d53c893ba | note | Frequency - On Delivery
1ff3afcb-8a71-5ff8-8164-44363543c4cd | note | Inspection Type (Visual, other) - Visual
d5560565-7f1f-50d6-92ec-1b0164d0f3d9 | note | Inspection: Key - C
28f1a379-17f5-55bd-94fa-db9f689ee862 | note | Inspection: By (Role Key) - SP/QE
8f6dbf2f-9f4d-514f-ae80-57151c1d03ae | checkpoint | 3.2 - Set out
634560bd-2d69-5708-846d-83e4824de234 | note | Inspection Point: Quality Control Activity - Set out completed by an approved surveyor marked allignment
36af7152-0ebc-54aa-9fff-72c3aed35f65 | note | Acceptance Criteria - Allignment set out matches drawing C4400-2 or aggreed with the Engineer
536e8ebd-9bc6-5f46-aea4-f58bff2e201f | note | Verifying Document - Survey marks, photos
210f9cfa-cdb2-55d0-997c-d217bb5208aa | note | Frequency - Prior to commencement of works
f173228a-2625-5da9-8dc3-0f4fe40a5c96 | note | Inspection Type (Visual, other) - Survey
d4dd6ac5-9fe5-5ef8-a262-2019cd8785cc | note | Inspection: Key - H
3489559f-2cce-5044-ac1d-68336808ea4c | note | Inspection: By (Role Key) - SV/SP/QE
57e25cdc-0d38-5a66-a6ee-bd14e8463cf5 | signoff | HOLD POINT
b75df167-953c-56c0-85ad-84e77b53dabd | checkpoint | 3.3 - Backfill / Bedding Material
7d95440b-01a4-5e4c-8197-de8bbd98e036 | note | Inspection Point: Quality Control Activity - Approved Material, AP20 as per DCC code of subdivision 10329.
8976d22d-ab0c-5693-bc0a-d9731cd1c680 | note | Acceptance Criteria - As per DCC code of subdiviison 10329
3aaa88cc-82cb-5438-b429-bbe50ab25bce | note | Verifying Document - Delivery dockets, photos
da20e9a3-da29-5395-924b-b0a749585fa1 | note | Frequency - On Delivery
15be0528-629c-5f25-bc78-2861d180a933 | note | Inspection Type (Visual, other) - Visual
dbce0e37-a39c-58db-9199-89fb0acd70c5 | note | Inspection: Key - C
0a7fed2c-e9e2-566d-bcdd-6eee1bd88e1f | note | Inspection: By (Role Key) - SP/QE
1d1078e0-1bb1-56f7-948a-752012ad998c | section | SECTION 4 - IN-PROCESS INSPECTIONS
c5f206b2-b8d9-55e2-a96f-c1168acbd237 | checkpoint | 4.1 - Trench Excavation
13443767-b171-52bb-9b22-bd26e7ed259f | note | Inspection Point: Quality Control Activity - Excavate to required depth to invert as per C4400
ad0181d3-28d9-5570-98a6-0d95f6e8e56c | note | ○ Trench width to allow for 300mm seperation between springline of the pipe and trench wall or an adjacent pipe
4d541dba-2310-534f-991b-bb46d777fdb3 | note | ○ Floor of Trench to be even across width and length
b3273e85-f3a5-5135-848a-f9eccb508a4f | note | Acceptance Criteria - As per 561467-TW-04-DRW-001
0ab334c8-7193-5835-8747-29e28b6275ce | note | Verifying Document - Photos, measurement checks
f085aa79-2a42-57ae-9a27-e886937a35bf | note | Frequency - During Installation
df162fd0-006e-58a2-8d74-19c37c03037c | note | Inspection Type (Visual, other) - Visual
696eaf74-89b8-5bc2-8526-6312d48fc711 | note | Inspection: Key - V
4fc783ba-64f4-56bc-bb18-f18dc704004e | note | Inspection: By (Role Key) - SP/QE
5f723e23-2a78-544e-8477-4ca06f9af449 | checkpoint | 4.2 - Foundation
f6777232-5b7b-5e2d-8491-8fbe2d80d2c1 | note | Inspection Point: Quality Control Activity - Scala tests on base of trench
0c0f24e6-4d36-56f1-8819-85d1e0140505 | note | Acceptance Criteria - Minimum of 2 blows per 100mm
e1f3da71-b730-5e29-8117-8c70b079c7d8 | note | Verifying Document - Test results
49bdc67e-ab4f-5eb7-90fc-6ad8de95fc69 | note | Frequency - During installation, per 20m
d19e9046-4dcf-5b07-a0a5-7f421d037602 | note | Inspection Type (Visual, other) - Visual, On site test
1e37798f-bf41-58d2-9cdd-f54902bea504 | note | Inspection: Key - H
3d0248ad-d4c1-528c-a2e8-7c12a761c22c | note | Inspection: By (Role Key) - SP/QE
a2836e07-5fe4-5bc6-a345-bf727e1f1bd5 | signoff | HOLD POINT
69cbeeac-442a-5a07-adc1-321b4887edcb | checkpoint | 4.3 - Bedding
c9d10ab0-acb0-5f97-bd7f-f97d7ca9a448 | note | Inspection Point: Quality Control Activity - Bedding minimum 150mm compacted material
082d6c91-7e63-548e-a219-6421e0150690 | note | Acceptance Criteria - Bedding to comply with requirements
a4d1cd79-c590-55d1-9c74-b49b624a8f63 | note | Verifying Document - Photo
91821764-9bc8-5643-a7ba-9b166aeed9e9 | note | Frequency - During installation
52b29eea-0222-5f98-b5f6-140ee01632b0 | note | Inspection Type (Visual, other) - Visual, Measurement Check
3beafa43-a480-5e66-9f66-3762362904d0 | note | Inspection: Key - C
9ed966d4-c1d6-5720-bbcc-2acd909bd7e9 | note | Inspection: By (Role Key) - QE/SP
35261bbe-78b4-50aa-ad09-d138991c4ad8 | checkpoint | 4.4 - MH Installation
1a71b3f4-87ff-5889-8dc7-5fbbc4810e6d | note | Inspection Point: Quality Control Activity - MHs to be installed true to the design level
517f37f2-80ad-56ca-8279-3debc8ff5fbb | note | Acceptance Criteria - Final levels are in accordance with the C4400 or within tolerance and agreed with the Engineer
bedb719e-fd92-5c4f-962a-cdc24008f4f8 | note | Verifying Document - Photos, As-built
38547d56-e31a-5647-ab1d-05a003ba8501 | note | Frequency - During installation
51beda81-7f79-5608-a8f8-bafffa0b86ee | note | Inspection Type (Visual, other) - Survey
59618335-5b2b-5d04-8b6e-117819aee945 | note | Inspection: Key - H
81f1c5e4-c3e9-53a3-b559-9b502929dd54 | note | Inspection: By (Role Key) - SP/QE
5772216d-2908-5503-859b-cb8ca012cb8f | signoff | HOLD POINT
e02454ad-8697-5547-b422-8a0a33a7dfde | checkpoint | 4.5 - Benching
b3219cf7-d612-574b-971d-53e13f88b152 | note | Inspection Point: Quality Control Activity - Benching concrete shall have a crushing strength of 20MPa at 28 days.
2dba3673-76bc-5e74-ba92-c79e40b173e3 | note | ○ Benching shape to have smooth transitions at bends and junctions
f94713f1-7653-5a86-aff6-00f68488e81a | note | Acceptance Criteria - Benching built up to the specifications
a15c7bdc-75ff-5482-88c8-28918969046e | note | Verifying Document - Photos
701a26fc-74d5-58c5-80c3-68d493129a9e | note | Frequency - During benching contruction
78af94fa-ff65-556d-9996-995449ae6c45 | note | Inspection Type (Visual, other) - Visual, Test Results
beca31e4-8016-555e-a78d-9d83c98d9a9f | note | Inspection: Key - H
935600ea-3c11-5abf-9089-a67f9fac0cc3 | note | Inspection: By (Role Key) - SP/QE
78088795-c1e3-5e84-b7f5-e199fcd7b105 | signoff | HOLD POINT
9fb81e22-7beb-5512-a018-7c24aa9f22ca | checkpoint | 4.6 - Backfill and Compact
434b4f16-15f1-5e7c-8dc1-58874eb8ef09 | note | Inspection Point: Quality Control Activity - Backfill in 200mm layers of compacted material
c0bc7eda-6fc4-54ea-aa2d-88dc4577719b | note | ○ Compaction testing one test every two layers as required
f807d6cf-c23d-589b-a263-63eeefcc169e | note | Acceptance Criteria - 95% MDD in roads, paths, and pavements
a83baf94-efe2-52e7-9fa3-6f237ee77588 | note | Verifying Document - Photos, Compaction test results
12fec790-3c6b-562e-a35d-89a3dba9f20a | note | Frequency - During Installation
76534213-d26e-5cad-830d-4f9797e48734 | note | Inspection Type (Visual, other) - Visual, On Site test
1d68ec6b-9664-573d-bab2-ff657674e3c1 | note | Inspection: Key - H
c1380e7b-92fc-555b-8249-479f03d650aa | note | Inspection: By (Role Key) - SP/QE
3f6febb8-dc3a-59a7-9805-82407b0ba2e3 | signoff | HOLD POINT
26b44d4a-841a-50a8-b965-36c95addc184 | section | SECTION 5 - FINAL INSPECTION AND HANDOVER
52bc42b8-0dbe-5952-a95d-0b42df33e7e8 | checkpoint | 5.2 - Red pen markups
d9233c77-7620-509c-8c4f-1f065171d6de | note | Inspection Point: Quality Control Activity - Complete mark up of any changes from project drawings
872447f6-1d4d-5ee4-8faa-18daf6729fdd | note | Acceptance Criteria - Signed ITP
54a0857b-d6bc-5c16-93a8-19b5a3bcfc0a | note | Verifying Document - Red pen markup drawings
e8f25ae1-573f-5de9-9e24-2d614e57d495 | note | Frequency - After installation of FSMH
4a407ac5-1fbf-59df-8133-d74aa41d0afe | note | Inspection Type (Visual, other) - Document
4995ff0f-38f6-54d0-b90a-c90a2e1f44a2 | note | Inspection: Key - H
703d6adf-1136-569e-93bc-253dc285dbad | note | Inspection: By (Role Key) - SP/QE/CM
6468b959-7075-58a9-aa05-3b68d9a54856 | signoff | HOLD POINT
ce4c6a5e-549a-5776-a50b-b4aeb4bf90f1 | checklist | ITP-1004 - Installation of Manhole - WCMH-2B | itp | ITP-1004 - Installation of Manhole - WCMH-2B
2ac8716a-63b3-52cf-b624-07c24c0cd6c9 | section | SECTION 3 - RECEIVING INSPECTIONS
2d6469ff-22e7-5477-8cef-d23cbae25acd | checkpoint | 3.1 - Material Delivery
8fa440c1-35c5-5acd-a51d-7b63cb6819ad | note | Inspection Point: Quality Control Activity - Inspect for damage and wear, Confirm items are correct as per drawings and Specifications
b0775011-5c47-5478-a743-050b5e4e124f | note | Acceptance Criteria - Items are approved as per contract specification
1916c62f-0d2c-5946-a3c3-4f4e0ecce308 | note | ○ DCC approved
e22c4cf7-ba3b-530d-8827-d51d3fc91e53 | note | Verifying Document - Photos, delivery docket
7f7d3831-7829-581b-84bd-bb78b0212d8c | note | Frequency - On Delivery
edf2c7d9-ab72-5b5b-9799-c53ef40817b4 | note | Inspection Type (Visual, other) - Visual
d27a6a00-b74f-51bf-a1c9-ad9e267ac8ba | note | Inspection: Key - C
9316ddb4-9b6e-5563-9ef8-d03b6230b399 | note | Inspection: By (Role Key) - SP/QE
8f6dbf2f-9f4d-514f-ae80-57151c1d03ae | checkpoint | 3.2 - Set out
f81aa168-e5a8-5538-a502-81dc091b0694 | note | Inspection Point: Quality Control Activity - Set out completed by an approved surveyor marked allignment
b0a97d3e-4763-5a4b-94a9-64472d2198bb | note | Acceptance Criteria - Allignment set out matches drawing C4200-2 or aggreed with the Engineer
640f6956-0a9b-58cc-b4d8-9c1a0b867556 | note | Verifying Document - Survey marks, photos
dd42f976-425b-5c35-b376-c8b63ce81413 | note | Frequency - Prior to commencement of works
acb47ab2-3426-5196-a9c1-47ed2769912e | note | Inspection Type (Visual, other) - Survey
06ca9a3d-c73f-54f2-96f6-b088047b106f | note | Inspection: Key - H
f4651f5a-5a50-564f-be63-4ed2f6f66d38 | note | Inspection: By (Role Key) - SV/SP/QE
57e25cdc-0d38-5a66-a6ee-bd14e8463cf5 | signoff | HOLD POINT
b75df167-953c-56c0-85ad-84e77b53dabd | checkpoint | 3.3 - Backfill / Bedding Material
0a7d577b-71ef-53c0-ab91-cc85d898547d | note | Inspection Point: Quality Control Activity - Approved Material, AP20 as per DCC code of subdivision 10329.
c93739d4-5f81-5b46-a260-ecf26f4749b7 | note | Acceptance Criteria - As per DCC code of subdiviison 10329
0bbcab58-544d-50fb-a6c9-f534c56b42a3 | note | Verifying Document - Delivery dockets, photos
f1737fed-8057-5afa-ac20-e3a058349865 | note | Frequency - On Delivery
4d83e778-7f4f-5ea2-a72b-1fa535b38664 | note | Inspection Type (Visual, other) - Visual
f57f05df-bf6d-5793-a67e-d73780c58490 | note | Inspection: Key - C
ec227945-d25b-5ee2-93b8-9a3af819e859 | note | Inspection: By (Role Key) - SP/QE
1d1078e0-1bb1-56f7-948a-752012ad998c | section | SECTION 4 - IN-PROCESS INSPECTIONS
c5f206b2-b8d9-55e2-a96f-c1168acbd237 | checkpoint | 4.1 - Trench Excavation
0d3ee789-6114-5abe-96aa-1888cdb5ec60 | note | Inspection Point: Quality Control Activity - Excavate to required depth to invert as per C4200
7df35265-64d1-52bd-bf58-0c9c79c1ed70 | note | ○ Trench width to allow for 300mm seperation between springline of the pipe and trench wall or an adjacent pipe
4057deb7-13bb-5ee4-90b6-5c658f603d88 | note | ○ Floor of Trench to be even across width and length
c95c216c-dfdf-55a2-baba-7748a0a7068f | note | Acceptance Criteria - As per 561467-TW-04-DRW-001
abf5e034-9e42-5edb-8f4d-e40c9f91913f | note | Verifying Document - Photos, measurement checks
4cc64e1d-a805-5f2c-8520-c3129fee6143 | note | Frequency - During Installation
361e2426-2cca-5b2a-b138-7cfbdfc5ee6d | note | Inspection Type (Visual, other) - Visual
82c31f58-1382-5655-b00b-9e244d20d00f | note | Inspection: Key - V
8ce679d4-7b2e-56cc-bbe5-6aba815c4380 | note | Inspection: By (Role Key) - SP/QE
5f723e23-2a78-544e-8477-4ca06f9af449 | checkpoint | 4.2 - Foundation
db1349e0-c37c-562a-984b-8dd83a107885 | note | Inspection Point: Quality Control Activity - Scala tests on base of trench
ebb09bc1-86a4-5db0-9b72-80fa8d68a632 | note | Acceptance Criteria - Minimum of 2 blows per 100mm
49e613a2-9fe9-5bfd-bf85-7de44bde68a6 | note | Verifying Document - Test results
4cc02fab-c9d2-51a2-a782-ad30e38613c1 | note | Frequency - During installation, per 20m
43eed011-7105-52b0-bf4e-8d04815e680c | note | Inspection Type (Visual, other) - Visual, On site test
c08e0479-5b0e-59f6-9983-09693d4ffc63 | note | Inspection: Key - H
be471dab-2f27-5298-89cb-ff668bd7f56f | note | Inspection: By (Role Key) - SP/QE
a2836e07-5fe4-5bc6-a345-bf727e1f1bd5 | signoff | HOLD POINT
69cbeeac-442a-5a07-adc1-321b4887edcb | checkpoint | 4.3 - Bedding
10dcd092-9a4e-52f1-bcca-7afc901a024b | note | Inspection Point: Quality Control Activity - Bedding minimum 150mm compacted material
b67b94dc-fc4f-5956-ba16-122048ad9dbb | note | Acceptance Criteria - Bedding to comply with requirements
bf01b1e9-1d9e-5f5f-8a13-71af8770afde | note | Verifying Document - Photo
31afb6b1-51c8-55dd-a565-5447ebf59d88 | note | Frequency - During installation
6f291ce0-4ff6-5068-8754-4c877f260982 | note | Inspection Type (Visual, other) - Visual, Measurement Check
c3d2eb8e-0b93-534c-9877-1e74125bb723 | note | Inspection: Key - C
bf6a94f4-628b-5d30-a36c-39a8f6342935 | note | Inspection: By (Role Key) - QE/SP
35261bbe-78b4-50aa-ad09-d138991c4ad8 | checkpoint | 4.4 - MH Installation
9b0db491-a9cb-564c-8c2d-2bad3e0c19d3 | note | Inspection Point: Quality Control Activity - MHs to be installed true to the design level
5bd7b6ef-bd55-53ec-b535-acade7c8379f | note | Acceptance Criteria - Final levels are in accordance with the C4200 or within tolerance and agreed with the Engineer
00337b51-e286-5684-a097-2c725edf0514 | note | Verifying Document - Photos, As-built
1eadbb7f-3c41-5b2a-ac18-c20fb712da9d | note | Frequency - During installation
ade83643-63f3-5c98-b684-cb78a024ca39 | note | Inspection Type (Visual, other) - Survey
e3812b53-945b-5e99-92b3-d17ac162bb87 | note | Inspection: Key - H
96885560-ae96-5855-b777-211d31919e2c | note | Inspection: By (Role Key) - SP/QE
5772216d-2908-5503-859b-cb8ca012cb8f | signoff | HOLD POINT
e02454ad-8697-5547-b422-8a0a33a7dfde | checkpoint | 4.5 - Benching
1c6445ad-3259-545e-a1c5-1c527ea49e75 | note | Inspection Point: Quality Control Activity - Benching concrete shall have a crushing strength of 20MPa at 28 days.
a418cdcc-d4c9-5bca-8796-8560a5aef0c5 | note | ○ Benching shape to have smooth transitions at bends and junctions
1b2e754b-1695-52e9-98e8-b0b7d9f85a51 | note | Acceptance Criteria - Benching built up to the specifications
46f57886-66cc-5359-9f92-ac62bb8d0a75 | note | Verifying Document - Photos
81571416-ec56-5f97-a5ba-fef7a53ed24a | note | Frequency - During benching contruction
c0ce49fb-7d55-5d85-ad19-55d04d72dffe | note | Inspection Type (Visual, other) - Visual, Test Results
2899b8cb-27b9-595a-a5ee-a452d8c3f2c3 | note | Inspection: Key - H
247e67d6-4254-580b-b23f-7fb864f0559d | note | Inspection: By (Role Key) - SP/QE
78088795-c1e3-5e84-b7f5-e199fcd7b105 | signoff | HOLD POINT
9fb81e22-7beb-5512-a018-7c24aa9f22ca | checkpoint | 4.6 - Backfill and Compact
50cbb4d8-92ca-54cb-922d-2eefa1d3c222 | note | Inspection Point: Quality Control Activity - Backfill in 200mm layers of compacted material
208d99fe-2c94-5475-bca4-f36e9144381f | note | ○ Compaction testing one test every two layers as required
ff634880-7be7-52a4-93b1-c4ddb5e0996f | note | Acceptance Criteria - 95% MDD in roads, paths, and pavements
db3078c3-787d-5ec5-bb09-64bb4f014f96 | note | Verifying Document - Photos, Compaction test results
83c16760-a499-53e7-97a7-d468e6ce33b6 | note | Frequency - During Installation
f1f5d583-8224-50b5-88c7-d2972cdfade0 | note | Inspection Type (Visual, other) - Visual, On Site test
7af48950-7658-5d3a-8156-fdbbdda1d11f | note | Inspection: Key - H
70fcba41-5093-5bc7-9eae-4661563cfa7a | note | Inspection: By (Role Key) - SP/QE
3f6febb8-dc3a-59a7-9805-82407b0ba2e3 | signoff | HOLD POINT
26b44d4a-841a-50a8-b965-36c95addc184 | section | SECTION 5 - FINAL INSPECTION AND HANDOVER
52bc42b8-0dbe-5952-a95d-0b42df33e7e8 | checkpoint | 5.2 - Red pen markups
11e93153-0a59-56e2-8bf2-b48e861a1cce | note | Inspection Point: Quality Control Activity - Complete mark up of any changes from project drawings
8f489c22-9c6e-5a4a-96df-e96cb8ad05b4 | note | Acceptance Criteria - Signed ITP
4f80bbb7-24c7-5cab-a479-a612224c6f59 | note | Verifying Document - Red pen markup drawings
9e7dcbc8-9a00-589f-a41e-ce5a854e2d34 | note | Frequency - After installation of FSMH
dbef015b-f651-5642-8e52-97cc808e1371 | note | Inspection Type (Visual, other) - Document
9ab3b63a-07ed-51f1-93f5-1476d8da1168 | note | Inspection: Key - H
e1186783-7db3-58a0-b527-b39f5242c16b | note | Inspection: By (Role Key) - SP/QE/CM
6468b959-7075-58a9-aa05-3b68d9a54856 | signoff | HOLD POINT
0d3d5d49-b06a-53d5-be10-85ae059fcc07 | checklist | ITP-1006 - Installation of Manhole - WCMH-2A | itp | ITP-1006 - Installation of Manhole - WCMH-2A
2ac8716a-63b3-52cf-b624-07c24c0cd6c9 | section | SECTION 3 - RECEIVING INSPECTIONS
2d6469ff-22e7-5477-8cef-d23cbae25acd | checkpoint | 3.1 - Material Delivery
2129be25-4552-50bf-bf84-67903ce8518f | note | Inspection Point: Quality Control Activity - Inspect for damage and wear, Confirm items are correct as per drawings and Specifications
c69bf63f-e8ae-5377-900c-e0cab33759d3 | note | Acceptance Criteria - Items are approved as per contract specification
616155bd-b974-584d-8f39-6ff02ec2af4a | note | ○ DCC approved
ee46d58e-4bee-5255-a55c-e6bf3a3846c0 | note | Verifying Document - Photos, delivery docket
ca16054e-2d0a-589d-adc2-2c7ccd97a27b | note | Frequency - On Delivery
f037fd79-3d3c-5205-baae-055bb6bd93c4 | note | Inspection Type (Visual, other) - Visual
d6b29b04-e9f7-558b-8ffb-392dd7acd207 | note | Inspection: Key - C
2630dc7e-7500-5338-bbdb-6519ad3e2d49 | note | Inspection: By (Role Key) - SP/QE
8f6dbf2f-9f4d-514f-ae80-57151c1d03ae | checkpoint | 3.2 - Set out
47fd9c63-6dbf-5f05-86ac-53d84be70473 | note | Inspection Point: Quality Control Activity - Set out completed by an approved surveyor marked allignment
60bbb8b6-f4b9-5529-8702-b1a0ac50d2c0 | note | Acceptance Criteria - Allignment set out matches drawing C4200-2 or aggreed with the Engineer
89398a54-d73d-5fd8-aa56-518b9012f526 | note | Verifying Document - Survey marks, photos
c90998c3-eed4-58eb-aab1-d8cfd05e854a | note | Frequency - Prior to commencement of works
bcde56a5-0f06-55ba-a453-9421dc3b2eba | note | Inspection Type (Visual, other) - Survey
53be4673-323c-55ed-a331-abad99c4ce23 | note | Inspection: Key - H
b32dada6-5d30-5647-b0d0-72df20139663 | note | Inspection: By (Role Key) - SV/SP/QE
57e25cdc-0d38-5a66-a6ee-bd14e8463cf5 | signoff | HOLD POINT
b75df167-953c-56c0-85ad-84e77b53dabd | checkpoint | 3.3 - Backfill / Bedding Material
1c120b7b-82e8-58ac-8c42-d2966432c1f3 | note | Inspection Point: Quality Control Activity - Approved Material, AP20 as per DCC code of subdivision 10329.
1e5e4fae-1a33-5481-a1dd-ee4cb906808b | note | Acceptance Criteria - As per DCC code of subdiviison 10329
fa4741c4-f48d-556e-93ee-cdc486a6ccea | note | Verifying Document - Delivery dockets, photos
afad5a3b-5975-5bf8-84a5-1632c1b4b30e | note | Frequency - On Delivery
ad435216-b5e1-5bb0-984f-a27f2f72dbb3 | note | Inspection Type (Visual, other) - Visual
4e227693-62da-5ab2-bd22-be08bab21229 | note | Inspection: Key - C
525d03ee-8a09-5eae-8c52-7e0c09cfc422 | note | Inspection: By (Role Key) - SP/QE
1d1078e0-1bb1-56f7-948a-752012ad998c | section | SECTION 4 - IN-PROCESS INSPECTIONS
c5f206b2-b8d9-55e2-a96f-c1168acbd237 | checkpoint | 4.1 - Trench Excavation
4f113d00-5196-559a-9ef9-5cc5dae96d33 | note | Inspection Point: Quality Control Activity - Excavate to required depth to invert as per C4200
fdb825c1-2343-5415-a8e0-4cb20f62e1fb | note | ○ Trench width to allow for 300mm seperation between springline of the pipe and trench wall or an adjacent pipe
9a1dca0f-5d16-5e81-b25e-34bf470ee7f6 | note | ○ Floor of Trench to be even across width and length
3d32c05c-4376-58b7-bd23-0ec0f275812f | note | Acceptance Criteria - As per 561467-TW-04-DRW-001
f2fde9ba-e16f-53a7-8079-c6063b74b2bc | note | Verifying Document - Photos, measurement checks
bd32687e-0444-5f6c-9205-6dff35a52800 | note | Frequency - During Installation
fd4ba671-13cf-5023-be13-c8e6bfc1d5e0 | note | Inspection Type (Visual, other) - Visual
65a4eeae-5d90-5ae1-ba0f-7e76fba2fd4d | note | Inspection: Key - V
fd427284-92c4-5b4f-b414-f0a9fd929a96 | note | Inspection: By (Role Key) - SP/QE
5f723e23-2a78-544e-8477-4ca06f9af449 | checkpoint | 4.2 - Foundation
3640a966-b0cf-5803-a410-6d9379711ad4 | note | Inspection Point: Quality Control Activity - Scala tests on base of trench
3ab7c92a-3c86-523d-a20e-9b2369430c00 | note | Acceptance Criteria - Minimum of 2 blows per 100mm
cd7412c4-369c-5714-9e1b-af03c2e39f3c | note | Verifying Document - Test results
8e06f3b4-26b0-56f7-aa0c-6076e7c95082 | note | Frequency - During installation, per 20m
1f75e2bb-e452-5772-9582-206ddd4dd3cd | note | Inspection Type (Visual, other) - Visual, On site test
d2d497ed-d5d8-57e2-93cf-680d77300851 | note | Inspection: Key - H
e5090e8c-30ad-5211-a742-1c906bd8fcaa | note | Inspection: By (Role Key) - SP/QE
a2836e07-5fe4-5bc6-a345-bf727e1f1bd5 | signoff | HOLD POINT
69cbeeac-442a-5a07-adc1-321b4887edcb | checkpoint | 4.3 - Bedding
92cb3224-3812-5f50-9e16-39933d5c59f5 | note | Inspection Point: Quality Control Activity - Bedding minimum 150mm compacted material
79c6b6d4-3d60-5c6f-b346-a4290f646112 | note | Acceptance Criteria - Bedding to comply with requirements
6f1cd2d6-82a2-5cf6-be7f-aa7d8bc3497d | note | Verifying Document - Photo
d12dbf11-927a-5bdd-9c2d-74e1d2325e80 | note | Frequency - During installation
25879f01-96b8-5238-a290-358c44a88044 | note | Inspection Type (Visual, other) - Visual, Measurement Check
6bafc9aa-b9ea-5003-8e85-7803896fa8ef | note | Inspection: Key - C
2b1788bd-4cbb-5d89-8276-84879530448b | note | Inspection: By (Role Key) - QE/SP
35261bbe-78b4-50aa-ad09-d138991c4ad8 | checkpoint | 4.4 - MH Installation
894a0a03-2ee3-5401-a453-de584f9d0c37 | note | Inspection Point: Quality Control Activity - MHs to be installed true to the design level
ecd4aea4-b1fa-5944-ae9c-42c9e6f85917 | note | Acceptance Criteria - Final levels are in accordance with the C4200 or within tolerance and agreed with the Engineer
51b3c559-a273-5376-bc3a-b8919df9796b | note | Verifying Document - Photos, As-built
45844737-9223-5e25-bdb1-3062ebb67b84 | note | Frequency - During installation
19013682-480b-5280-b917-8eb98b65e16f | note | Inspection Type (Visual, other) - Survey
cc97f992-d495-5f16-aa15-6ef8897de957 | note | Inspection: Key - H
53e4c8c9-6efd-5972-a4fa-74395ebc5ac4 | note | Inspection: By (Role Key) - SP/QE
5772216d-2908-5503-859b-cb8ca012cb8f | signoff | HOLD POINT
e02454ad-8697-5547-b422-8a0a33a7dfde | checkpoint | 4.5 - Benching
2e7a56d3-6f2e-56aa-a563-38e2d5e57785 | note | Inspection Point: Quality Control Activity - Benching concrete shall have a crushing strength of 20MPa at 28 days.
13efd17e-a901-5a46-a036-546af4e33734 | note | ○ Benching shape to have smooth transitions at bends and junctions
c63ab44d-2829-52c0-8adc-ef671f75dc8d | note | Acceptance Criteria - Benching built up to the specifications
e2baa901-d655-5495-b741-bc9dab50cc5d | note | Verifying Document - Photos
4f582598-267d-5ea6-b77c-f68771805ffd | note | Frequency - During benching contruction
65c7fa76-6c6a-521d-b657-0093f48b0e47 | note | Inspection Type (Visual, other) - Visual, Test Results
677a5413-5663-5f4c-910d-2218ea14546f | note | Inspection: Key - H
78793769-c239-5d72-9ce9-ec94d82814a8 | note | Inspection: By (Role Key) - SP/QE
78088795-c1e3-5e84-b7f5-e199fcd7b105 | signoff | HOLD POINT
9fb81e22-7beb-5512-a018-7c24aa9f22ca | checkpoint | 4.6 - Backfill and Compact
cb53435c-3bd7-58d5-b086-1731c0ebc628 | note | Inspection Point: Quality Control Activity - Backfill in 200mm layers of compacted material
eafc30db-0b3e-56db-b0cd-923f99b26976 | note | ○ Compaction testing one test every two layers as required
d57c009b-a9b3-5806-b381-c0e3682a57bc | note | Acceptance Criteria - 95% MDD in roads, paths, and pavements
1024d49f-3cef-5a43-ab42-8a61dc98c7ff | note | Verifying Document - Photos, Compaction test results
47791464-f279-56c3-88ab-08e03dbc6303 | note | Frequency - During Installation
5bb5eb5f-9adc-53f6-82da-0f93625ccd1e | note | Inspection Type (Visual, other) - Visual, On Site test
9cacae21-08a7-5ed1-bed3-2d838fec2af9 | note | Inspection: Key - H
b853e219-829d-5237-a6dd-e57a9a4a4df5 | note | Inspection: By (Role Key) - SP/QE
3f6febb8-dc3a-59a7-9805-82407b0ba2e3 | signoff | HOLD POINT
26b44d4a-841a-50a8-b965-36c95addc184 | section | SECTION 5 - FINAL INSPECTION AND HANDOVER
52bc42b8-0dbe-5952-a95d-0b42df33e7e8 | checkpoint | 5.2 - Red pen markups
e8a97ddd-77a4-5c4c-979c-4b062488616e | note | Inspection Point: Quality Control Activity - Complete mark up of any changes from project drawings
13e4645f-df8d-5910-baf2-c0b82ebfd420 | note | Acceptance Criteria - Signed ITP
ef451ab7-c771-5ef8-9c6c-e68622b53e13 | note | Verifying Document - Red pen markup drawings
02ee9c30-1ef9-537e-a7e0-f941a7a74a7f | note | Frequency - After installation of FSMH
ec02aa85-a5ca-599c-8032-35fae5ed0a51 | note | Inspection Type (Visual, other) - Document
144d11e1-c35d-501c-8054-4edfbef2e178 | note | Inspection: Key - H
0d93a497-5140-52ef-92af-e464fb7aea49 | note | Inspection: By (Role Key) - SP/QE/CM
6468b959-7075-58a9-aa05-3b68d9a54856 | signoff | HOLD POINT
f9cf019b-7e50-57a7-a4da-f5d9e53185c2 | checklist | ITP-1007 - Installation of Manhole - FSMH-A1 | itp | ITP-1007 - Installation of Manhole - FSMH-A1
2ac8716a-63b3-52cf-b624-07c24c0cd6c9 | section | SECTION 3 - RECEIVING INSPECTIONS
2d6469ff-22e7-5477-8cef-d23cbae25acd | checkpoint | 3.1 - Material Delivery
9c944456-aaa8-570c-afbd-83041f113b0d | note | Inspection Point: Quality Control Activity - Inspect for damage and wear, Confirm items are correct as per drawings and Specifications
c6ebbd4c-0297-5055-a3eb-7924a73ce439 | note | Acceptance Criteria - Items are approved as per contract specification
3e9335c5-4ded-55ce-96a7-96f1167b96e8 | note | ○ DCC approved
e402b958-12d5-5840-a813-702b4fb20a53 | note | Verifying Document - Photos, delivery docket
156f23b8-e638-5d98-ae0e-922d43de3e28 | note | Frequency - On Delivery
9f009fe1-0381-57c1-849f-e3f635b08faf | note | Inspection Type (Visual, other) - Visual
988644a3-b067-563f-9ad8-4e55699d86a9 | note | Inspection: Key - C
53120ce5-6838-573a-9adb-fe5a6c210451 | note | Inspection: By (Role Key) - SP/QE
8f6dbf2f-9f4d-514f-ae80-57151c1d03ae | checkpoint | 3.2 - Set out
cc3edff8-d4c8-5017-8777-dd6eafc55626 | note | Inspection Point: Quality Control Activity - Set out completed by an approved surveyor marked allignment
eca05494-0818-5482-bd75-dd93bc902e9e | note | Acceptance Criteria - Allignment set out matches drawing C4400-2 or aggreed with the Engineer
a37fe102-149a-50e2-bef9-61b67bce901f | note | Verifying Document - Survey marks, photos
86213202-f372-51a9-bcc8-25927764da5f | note | Frequency - Prior to commencement of works
f8e2225c-b5e3-5a96-86d8-386192c87b20 | note | Inspection Type (Visual, other) - Survey
9666c49e-409e-5e80-a063-836d58eaa914 | note | Inspection: Key - H
d66e82fe-b168-5cdf-8a64-56abdb5e21cd | note | Inspection: By (Role Key) - SV/SP/QE
57e25cdc-0d38-5a66-a6ee-bd14e8463cf5 | signoff | HOLD POINT
b75df167-953c-56c0-85ad-84e77b53dabd | checkpoint | 3.3 - Backfill / Bedding Material
ca74c357-4db9-5d64-ac08-07271c460100 | note | Inspection Point: Quality Control Activity - Approved Material, AP20 as per DCC code of subdivision 10329.
21d395e6-7db6-58ef-8121-960d33196ae2 | note | Acceptance Criteria - As per DCC code of subdiviison 10329
8e0b4de2-5a38-5c20-87e9-386d3f3e87d0 | note | Verifying Document - Delivery dockets, photos
ea6fb9c5-e728-5b7e-b13f-f79bd66e3d93 | note | Frequency - On Delivery
ebc0da6a-803e-5da8-8d7d-7abbbdc1d1ad | note | Inspection Type (Visual, other) - Visual
142ef0a9-305b-55d8-8f2b-19f50bb1c487 | note | Inspection: Key - C
5f8c380d-99e2-5ed4-948f-dd2cc9bf2be9 | note | Inspection: By (Role Key) - SP/QE
1d1078e0-1bb1-56f7-948a-752012ad998c | section | SECTION 4 - IN-PROCESS INSPECTIONS
c5f206b2-b8d9-55e2-a96f-c1168acbd237 | checkpoint | 4.1 - Trench Excavation
00942766-1d14-5d66-93b5-31ddfcb351c5 | note | Inspection Point: Quality Control Activity - Excavate to required depth to invert as per C4400
f988e3ca-b55d-52d0-a2ed-e748ba961db2 | note | ○ Trench width to allow for 300mm seperation between springline of the pipe and trench wall or an adjacent pipe
3c8146fc-1c3c-5f7e-9962-fa659f5c9db6 | note | ○ Floor of Trench to be even across width and length
ef19da8b-b82c-5699-870d-8d4246063218 | note | Acceptance Criteria - As per 561467-TW-04-DRW-001
766ced10-59b6-500a-bd59-2ab91717eae6 | note | Verifying Document - Photos, measurement checks
76add296-34f1-54fd-8007-c3d99b0042b9 | note | Frequency - During Installation
efa07efd-49ae-5760-9872-b95d8eacb97e | note | Inspection Type (Visual, other) - Visual
69635b0c-5daa-5a4d-a111-56085607e195 | note | Inspection: Key - V
f76eb922-e8f8-57a7-ad03-5ad53ce4d7f6 | note | Inspection: By (Role Key) - SP/QE
5f723e23-2a78-544e-8477-4ca06f9af449 | checkpoint | 4.2 - Foundation
8c839496-38a2-55ee-a946-94b4df250110 | note | Inspection Point: Quality Control Activity - Scala tests on base of trench
be32d594-a994-58f6-94c9-a5290345d245 | note | Acceptance Criteria - Minimum of 2 blows per 100mm
ff316229-4259-5cdd-a585-52ac1d68fb8f | note | Verifying Document - Test results
93e97bc4-a41a-599c-9402-7b0b47a6c4b5 | note | Frequency - During installation, per 20m
2a309cf1-690b-58f7-b044-92d6bb173195 | note | Inspection Type (Visual, other) - Visual, On site test
a7a84084-fbe6-50e6-92bf-b8c185229b48 | note | Inspection: Key - H
ea651c0a-c31f-5a28-8a7c-872696fc6e6b | note | Inspection: By (Role Key) - SP/QE
a2836e07-5fe4-5bc6-a345-bf727e1f1bd5 | signoff | HOLD POINT
69cbeeac-442a-5a07-adc1-321b4887edcb | checkpoint | 4.3 - Bedding
8401336f-d25f-5dd6-bbbc-4d681ee3697c | note | Inspection Point: Quality Control Activity - Bedding minimum 150mm compacted material
960e79f6-3215-56bc-8844-371e489f411f | note | Acceptance Criteria - Bedding to comply with requirements
32da611d-8ead-5126-bb89-5c2ae2538ba1 | note | Verifying Document - Photo
28d58762-ba10-5818-b9ba-206dd13868a5 | note | Frequency - During installation
52f34e24-f0fb-5ed5-a70c-c2f9cfaeeac2 | note | Inspection Type (Visual, other) - Visual, Measurement Check
375dc0d5-7d5b-51a8-802b-6649a5f59a53 | note | Inspection: Key - C
c919c74c-aed8-5c81-b9e4-52b28149e082 | note | Inspection: By (Role Key) - QE/SP
35261bbe-78b4-50aa-ad09-d138991c4ad8 | checkpoint | 4.4 - MH Installation
0d5c0eab-c3b1-5d92-9a13-984815af7f67 | note | Inspection Point: Quality Control Activity - MHs to be installed true to the design level
a3de11cc-2d22-51d9-b336-6999c04d787f | note | Acceptance Criteria - Final levels are in accordance with the C4400 or within tolerance and agreed with the Engineer
f3211e54-16ba-58fd-b958-5abbcf5cf902 | note | Verifying Document - Photos, As-built
1e165e38-8284-59da-ae21-d1b90fa66e08 | note | Frequency - During installation
eab72def-6d2a-53b0-8eb4-85e82082d0a5 | note | Inspection Type (Visual, other) - Survey
0c2534d9-3a76-5562-8607-f67a9acfc900 | note | Inspection: Key - H
f21f59e6-d4ad-5e34-b898-1ba7ebd79e26 | note | Inspection: By (Role Key) - SP/QE
5772216d-2908-5503-859b-cb8ca012cb8f | signoff | HOLD POINT
e02454ad-8697-5547-b422-8a0a33a7dfde | checkpoint | 4.5 - Benching
051c3272-cfad-59ad-ae90-790b61514e59 | note | Inspection Point: Quality Control Activity - Benching concrete shall have a crushing strength of 20MPa at 28 days.
11484d81-5f63-5420-93e4-b5c39927ae5a | note | ○ Benching shape to have smooth transitions at bends and junctions
4201a6d0-6557-5047-a172-56939822d0bb | note | Acceptance Criteria - Benching built up to the specifications
229a9782-619c-5b14-87a3-48709f78db89 | note | Verifying Document - Photos
81a392af-5b9d-52cd-85f3-546d80c60c5c | note | Frequency - During benching contruction
0746f08d-4f6d-59ec-bf65-e9269b837e86 | note | Inspection Type (Visual, other) - Visual, Test Results
0895683c-59ce-5dfb-b142-6b83c6af50ff | note | Inspection: Key - H
5f070747-8a2d-5bd9-b48d-3a7ca34bd449 | note | Inspection: By (Role Key) - SP/QE
78088795-c1e3-5e84-b7f5-e199fcd7b105 | signoff | HOLD POINT
9fb81e22-7beb-5512-a018-7c24aa9f22ca | checkpoint | 4.6 - Backfill and Compact
962f9774-4d33-5bfd-833d-f5e3c6d4a54c | note | Inspection Point: Quality Control Activity - Backfill in 200mm layers of compacted material
cf8ef5ce-fd60-5653-9703-0876db6fd5ce | note | ○ Compaction testing one test every two layers as required
0f708920-4193-5d34-9824-eceec8ceefea | note | Acceptance Criteria - 95% MDD in roads, paths, and pavements
b54d469e-fe1f-586a-b4d7-314e7025b3e4 | note | Verifying Document - Photos, Compaction test results
b8e8611f-a82d-572a-99e3-fbfddf404edd | note | Frequency - During Installation
52751212-2ed9-5ccf-996a-a4bc80ae5309 | note | Inspection Type (Visual, other) - Visual, On Site test
7e3e4e85-d427-5e06-a73a-cb5f8faa6bc2 | note | Inspection: Key - H
fc4d8c1f-0bfc-5116-a9fb-bb6473e2d005 | note | Inspection: By (Role Key) - SP/QE
3f6febb8-dc3a-59a7-9805-82407b0ba2e3 | signoff | HOLD POINT
26b44d4a-841a-50a8-b965-36c95addc184 | section | SECTION 5 - FINAL INSPECTION AND HANDOVER
52bc42b8-0dbe-5952-a95d-0b42df33e7e8 | checkpoint | 5.2 - Red pen markups
2ab6b4e8-8df5-54b5-88d0-b8aa1fd0ee03 | note | Inspection Point: Quality Control Activity - Complete mark up of any changes from project drawings
ed5dc7b3-8416-572a-8c03-20d3c0da2821 | note | Acceptance Criteria - Signed ITP
bbfedd29-485c-5f0a-979d-accdb925ff52 | note | Verifying Document - Red pen markup drawings
54f648cd-498e-5dd1-be98-714bfafdc594 | note | Frequency - After installation of FSMH
b9a6ffc2-deae-5e1b-af83-08bfd62ce41e | note | Inspection Type (Visual, other) - Document
e40004ef-bc3f-50e7-967f-f8f7866c85ea | note | Inspection: Key - H
bd7731ce-94e7-5dfe-aef1-ad2fd78298b5 | note | Inspection: By (Role Key) - SP/QE/CM
6468b959-7075-58a9-aa05-3b68d9a54856 | signoff | HOLD POINT
3687e6c3-ffcb-54ff-b7fc-a0cc31c2f9a8 | checklist | ITP-1009 - Installation of Manhole - WCMH-1 | itp | ITP-1009 - Installation of Manhole - WCMH-1
2ac8716a-63b3-52cf-b624-07c24c0cd6c9 | section | SECTION 3 - RECEIVING INSPECTIONS
2d6469ff-22e7-5477-8cef-d23cbae25acd | checkpoint | 3.1 - Material Delivery
4bba8f0c-bedb-5fb0-8969-0c980dc0215b | note | Inspection Point: Quality Control Activity - Inspect for damage and wear, Confirm items are correct as per drawings and Specifications
ee0dd9d0-6654-59b7-b028-36af54ee93b5 | note | Acceptance Criteria - Items are approved as per contract specification
f9de903e-253b-58b2-9df4-f35504fe6cd8 | note | ○ DCC approved
c8083818-2d19-5401-817c-0e41c8a0f59e | note | Verifying Document - Photos, delivery docket
b5dc0145-6899-5802-8337-27f1860c5544 | note | Frequency - On Delivery
30219fde-0c78-54ea-a456-4a9334dca039 | note | Inspection Type (Visual, other) - Visual
11435c04-3962-5adb-97cb-9d6223beaadd | note | Inspection: Key - C
d1423c98-6dc6-5e86-9efa-71de3953a734 | note | Inspection: By (Role Key) - SP/QE
8f6dbf2f-9f4d-514f-ae80-57151c1d03ae | checkpoint | 3.2 - Set out
e7156165-aee1-56d0-baef-820d7de568ac | note | Inspection Point: Quality Control Activity - Set out completed by an approved surveyor marked allignment
35089c78-f9e4-5412-8d1e-1947d0ff0f39 | note | Acceptance Criteria - Allignment set out matches drawing C4200-2 or aggreed with the Engineer
dd5fccc5-a1d3-58bf-8c6d-fafc6d627548 | note | Verifying Document - Survey marks, photos
582da6db-b956-5bcd-98f9-d97a74d28827 | note | Frequency - Prior to commencement of works
40dd9e6f-881d-54f1-900d-f407820d604c | note | Inspection Type (Visual, other) - Survey
65604cd3-4381-587f-8dc8-f8e655c4eaa6 | note | Inspection: Key - H
d2220e04-ea6e-5c89-bd1e-0fb73c14b440 | note | Inspection: By (Role Key) - SV/SP/QE
57e25cdc-0d38-5a66-a6ee-bd14e8463cf5 | signoff | HOLD POINT
b75df167-953c-56c0-85ad-84e77b53dabd | checkpoint | 3.3 - Backfill / Bedding Material
c3553c7b-e239-52b5-8f8f-6dab93cf91d0 | note | Inspection Point: Quality Control Activity - Approved Material, AP20 as per DCC code of subdivision 10329.
c1cbe52a-7ba7-5e0e-8864-2bf8a6298f74 | note | Acceptance Criteria - As per DCC code of subdiviison 10329
c4843dee-9ffb-53cb-b2c3-1156f96b6434 | note | Verifying Document - Delivery dockets, photos
d6c5a021-73e2-5da8-a5ae-6e433ee02942 | note | Frequency - On Delivery
34f5a313-cb40-562f-bdbe-7edecde82e3d | note | Inspection Type (Visual, other) - Visual
930626e8-eaa0-566b-a064-b867591ec4ba | note | Inspection: Key - C
dfaacdfe-de84-5e22-8892-c1a560eedbb4 | note | Inspection: By (Role Key) - SP/QE
1d1078e0-1bb1-56f7-948a-752012ad998c | section | SECTION 4 - IN-PROCESS INSPECTIONS
c5f206b2-b8d9-55e2-a96f-c1168acbd237 | checkpoint | 4.1 - Trench Excavation
b2ccea4c-a642-533c-9959-b69b08169a73 | note | Inspection Point: Quality Control Activity - Excavate to required depth to invert as per C4200
45e6a967-ac20-527f-83d4-ad2decdd29ea | note | ○ Trench width to allow for 300mm seperation between springline of the pipe and trench wall or an adjacent pipe
41c70a73-3c1d-59bb-955b-94be1d0648a0 | note | ○ Floor of Trench to be even across width and length
5675a2b2-064e-543e-a8fb-f18c49476165 | note | Acceptance Criteria - As per 561467-TW-04-DRW-001
6460381c-725e-5df9-8d3a-d622be4b69b5 | note | Verifying Document - Photos, measurement checks
5f9241db-4e59-582d-961f-2554d5c2645b | note | Frequency - During Installation
dc7e6ecf-3b09-59c1-9c0b-6cb4e257b20e | note | Inspection Type (Visual, other) - Visual
9bba54ba-de83-5239-8e35-85a873c59ab8 | note | Inspection: Key - V
d39c4d9d-872a-5f24-95e9-2d6cd80572f4 | note | Inspection: By (Role Key) - SP/QE
5f723e23-2a78-544e-8477-4ca06f9af449 | checkpoint | 4.2 - Foundation
66cc17a0-1741-54ec-9037-12708146e48c | note | Inspection Point: Quality Control Activity - Scala tests on base of trench
6f48e733-4c7d-5504-ab50-96604e26a06d | note | Acceptance Criteria - Minimum of 2 blows per 100mm
048742b5-e420-505f-a0b4-b79e6b0e5c81 | note | Verifying Document - Test results
c5c1b880-1138-5801-9ae3-397cccf1d3d4 | note | Frequency - During installation, per 20m
10caefc7-24f2-5020-8a6f-022f90ccc2f4 | note | Inspection Type (Visual, other) - Visual, On site test
990e78e0-ca6a-5bd9-a5e8-a2cda578ca3c | note | Inspection: Key - H
b7c253da-4966-514d-9a99-b6bbea3a0c80 | note | Inspection: By (Role Key) - SP/QE
a2836e07-5fe4-5bc6-a345-bf727e1f1bd5 | signoff | HOLD POINT
69cbeeac-442a-5a07-adc1-321b4887edcb | checkpoint | 4.3 - Bedding
cdf17202-8724-5cd5-a3fa-e53ae564f944 | note | Inspection Point: Quality Control Activity - Bedding minimum 150mm compacted material
57ca8dd9-eb73-5f7e-a201-f4cb8819058d | note | Acceptance Criteria - Bedding to comply with requirements
1e3ac7ec-b384-54e1-909a-d02f3fbcbff3 | note | Verifying Document - Photo
2113429f-4cf7-547d-8614-e1f0af0e4b74 | note | Frequency - During installation
19832ed9-691e-55ea-a268-e8d62d4e7f70 | note | Inspection Type (Visual, other) - Visual, Measurement Check
82388996-cd26-58d9-b7e2-294fce67c929 | note | Inspection: Key - C
b9e70f09-12ba-554b-852f-f124f3791a10 | note | Inspection: By (Role Key) - QE/SP
35261bbe-78b4-50aa-ad09-d138991c4ad8 | checkpoint | 4.4 - MH Installation
d942c43c-b7ca-5eb7-9db5-99379fbe2c2d | note | Inspection Point: Quality Control Activity - MHs to be installed true to the design level
44238abf-a60a-54ff-ad49-6dde4bb8a678 | note | Acceptance Criteria - Final levels are in accordance with the C4200 or within tolerance and agreed with the Engineer
3566d868-c896-55eb-b2d6-2a2938b54a80 | note | Verifying Document - Photos, As-built
3e25e488-b705-5971-a5a1-abf024b0fb26 | note | Frequency - During installation
449fc9df-2809-5163-bdef-354d88e3a99f | note | Inspection Type (Visual, other) - Survey
d6c97684-c881-59f0-a9f3-ec5bb97e5e00 | note | Inspection: Key - H
42f0a032-2f6b-575d-a3b8-5d9d64ec5b57 | note | Inspection: By (Role Key) - SP/QE
5772216d-2908-5503-859b-cb8ca012cb8f | signoff | HOLD POINT
e02454ad-8697-5547-b422-8a0a33a7dfde | checkpoint | 4.5 - Benching
167c5266-3770-508a-ae0b-89b6c82f6443 | note | Inspection Point: Quality Control Activity - Benching concrete shall have a crushing strength of 20MPa at 28 days.
1abdff5a-1b61-57b0-b5bc-06449d170f13 | note | ○ Benching shape to have smooth transitions at bends and junctions
822edcdc-e161-57f1-b85a-6bf53c4b92b0 | note | Acceptance Criteria - Benching built up to the specifications
e58acd2d-fa29-509e-ba17-804e6f463446 | note | Verifying Document - Photos
a8c3f034-2c26-5e91-804a-d84a2d4552fa | note | Frequency - During benching contruction
f048d018-1558-56ae-a0ae-d7614f451ddb | note | Inspection Type (Visual, other) - Visual, Test Results
a8f609ef-45da-57ef-956f-53760fc18c23 | note | Inspection: Key - H
4380f189-3dfb-541e-8eff-1e37c5edcd07 | note | Inspection: By (Role Key) - SP/QE
78088795-c1e3-5e84-b7f5-e199fcd7b105 | signoff | HOLD POINT
9fb81e22-7beb-5512-a018-7c24aa9f22ca | checkpoint | 4.6 - Backfill and Compact
2d959c0f-236b-5fcb-a06c-b15ed1c6282e | note | Inspection Point: Quality Control Activity - Backfill in 200mm layers of compacted material
4dc6ed87-34f7-5dab-887b-96492ba55425 | note | ○ Compaction testing one test every two layers as required
23befd66-83b5-57f0-9389-63a3b4c79118 | note | Acceptance Criteria - 95% MDD in roads, paths, and pavements
3876fd68-f718-57df-bb19-3f2f48734dc6 | note | Verifying Document - Photos, Compaction test results
0ba0c3a8-0ed5-58ca-9648-e6db15e37f01 | note | Frequency - During Installation
e34f44ce-9b1b-5007-90bc-180195489e62 | note | Inspection Type (Visual, other) - Visual, On Site test
367ed3c8-06b6-5a6b-8865-9b7decf42b81 | note | Inspection: Key - H
8c4229f9-c268-5b3b-80f0-a3a01cc705c2 | note | Inspection: By (Role Key) - SP/QE
3f6febb8-dc3a-59a7-9805-82407b0ba2e3 | signoff | HOLD POINT
26b44d4a-841a-50a8-b965-36c95addc184 | section | SECTION 5 - FINAL INSPECTION AND HANDOVER
52bc42b8-0dbe-5952-a95d-0b42df33e7e8 | checkpoint | 5.2 - Red pen markups
222a2907-4622-55d9-87a8-bf6dd5c5f67f | note | Inspection Point: Quality Control Activity - Complete mark up of any changes from project drawings
0fcc88b2-3ab8-5015-b305-b1b55e43b262 | note | Acceptance Criteria - Signed ITP
ee0759fc-cbcf-5ecf-a72e-a47c3648acfb | note | Verifying Document - Red pen markup drawings
a8b08e99-a452-5b7f-b374-28485b3dffc2 | note | Frequency - After installation of FSMH
5dd8d99f-f3d4-584e-9758-37824a076a72 | note | Inspection Type (Visual, other) - Document
4a1b0c21-d0e5-596c-91f1-738d3e84e129 | note | Inspection: Key - H
503e0ce5-25c4-5f75-93a2-9e60397cc53b | note | Inspection: By (Role Key) - SP/QE/CM
6468b959-7075-58a9-aa05-3b68d9a54856 | signoff | HOLD POINT
c84058aa-512d-52ad-9658-d71c45f77b32 | checklist | ITP-4002 - WCMH-5 | itp | ITP-4002 - WCMH-5
2ac8716a-63b3-52cf-b624-07c24c0cd6c9 | section | SECTION 3 - RECEIVING INSPECTIONS
2d6469ff-22e7-5477-8cef-d23cbae25acd | checkpoint | 3.1 - Material Delivery
38603c8f-a73c-5d3d-82f1-28b95910bac8 | note | Inspection Point: Quality Control Activity - Inspect for damage and wear, Confirm items are correct as per drawings and Specifications
9c267aa9-0cf7-5ce5-84c5-061a05ab0636 | note | Acceptance Criteria - Items are approved as per contract specification
07635d10-95b8-5590-8a3b-78d90300b01c | note | ○ DCC approved
68703632-508d-5e5d-954d-ce925de00a15 | note | Verifying Document - Photos, delivery docket, MDD results for backfill materials
e79ca831-2d9d-5c32-95f2-e0cc09660e08 | note | Frequency - On Delivery
f65e4f50-fbc7-5114-b934-12ba70cc876c | note | Inspection Type (Visual, other) - Visual
e03b5b46-05ea-57a1-abb6-130c5cbfcccb | note | Inspection: Key - C
65de8343-ad37-5854-9247-8f0f72e39085 | note | Inspection: By (Role Key) - SP/QE
8f6dbf2f-9f4d-514f-ae80-57151c1d03ae | checkpoint | 3.2 - Set out
bfc82637-aaf4-5433-8c1a-408b5acaf4bd | note | Inspection Point: Quality Control Activity - Set out completed by an approved surveyor marked allignment
89ac8ef3-7f5a-5e88-8bf9-a3f875988828 | note | Acceptance Criteria - Allignment set out matches drawings or aggreed with the Engineer
e5a14dd7-3629-55b7-b396-dda6dac09c4b | note | Verifying Document - Survey marks, photos
8d03c984-cae6-545e-81f9-c5fd949e1c9b | note | Frequency - Prior to commencement of works
a97224c6-c592-5809-a764-70600471ae60 | note | Inspection Type (Visual, other) - Visual, Instrumental
da82f296-0062-59fd-b461-65eab2d4bc44 | note | Inspection: Key - H
3c3c0e11-54bf-5a9d-bd5b-18b3487a3c57 | note | Inspection: By (Role Key) - SV/SP/QE/PE
57e25cdc-0d38-5a66-a6ee-bd14e8463cf5 | signoff | HOLD POINT
1d1078e0-1bb1-56f7-948a-752012ad998c | section | SECTION 4 - IN-PROCESS INSPECTIONS
c5f206b2-b8d9-55e2-a96f-c1168acbd237 | checkpoint | 4.1 - Trench Excavation
8261be8e-3b86-5fe8-9e6b-db454c71faaf | note | Inspection Point: Quality Control Activity - Excavate to required depth to invert as per C4200
994c45d7-2f1b-5ef6-8094-e9598e4e6bc2 | note | ○ Trench width to allow for 300mm seperation between springline of the pipe and trench wall or an adjacent pipe
4b9898c5-242a-59f1-a4b2-c3afaa7455a3 | note | ○ Floor of Trench to be even across width and length
0e3b8cb1-8106-5f6e-b1e2-95bd2c6c778b | note | Verifying Document - Photos, measurement checks
6a299a39-c994-5c6b-bbda-5e01b757a357 | note | Frequency - During Installation
dbb2364c-9356-5d6a-ba4a-9de963d3bac6 | note | Inspection Type (Visual, other) - Visual
1f515b94-1bc0-50b4-800b-acd76aed6fbe | note | Inspection: Key - V
4639a0bc-8afe-5e70-b44d-2c89026711b8 | note | Inspection: By (Role Key) - SP/QE/PE
5f723e23-2a78-544e-8477-4ca06f9af449 | checkpoint | 4.2 - Foundation
bedd57af-f748-5622-ab50-bc09b56e7f26 | note | Inspection Point: Quality Control Activity - Scala tests on base
a5a9c327-6b92-5386-9837-7d85367045ca | note | Acceptance Criteria - minimum of 2 blows per 100mm
5daf8c44-62c9-5d5d-af5e-597f07cb2f48 | note | Verifying Document - test results
1bdac60f-976c-5d3a-8f8e-b85af7a0a9da | note | Frequency - One off
031b4f8e-d70b-558c-9fe3-0e2beaebe73d | note | Inspection Type (Visual, other) - Visual, On site test
85d9d35b-aa6a-516e-97ae-79ff198602d6 | note | Inspection: Key - C
ce6a87c3-bea1-51eb-aa81-a8e80422a68f | note | Inspection: By (Role Key) - SP/QE
69cbeeac-442a-5a07-adc1-321b4887edcb | checkpoint | 4.3 - Bedding
9b7be36a-4d29-5381-b326-3ae29434cf20 | note | Inspection Point: Quality Control Activity - Bedding minimum 75mm compacted material
9b117924-f2fc-5dec-8892-8369b9c6f17b | note | Acceptance Criteria - Bedding to comply with requirements
d1fa6168-e255-52d7-bf49-6cea3eb08aa3 | note | Verifying Document - Photo
5778ed11-0cce-56c3-9d8a-7204219c1b49 | note | Frequency - During installation
ad94ef2e-1f9f-5aa2-9c15-ac75da3dbd35 | note | Inspection Type (Visual, other) - Visual, Measurement Check
1c643703-4893-5e4b-8924-1438ac282e91 | note | Inspection: Key - C
29b35aa2-e61d-5d02-b15d-535273317b10 | note | Inspection: By (Role Key) - QE/SP
45ae2b77-c14d-5585-9f34-e620eebab318 | checkpoint | 4.4 - Chamber Installation
8fa3e48e-fcea-5e18-886f-6da1c9b22b6f | note | Inspection Point: Quality Control Activity - Chambers installed true to the design level
8e7e29a8-d04e-5c66-bdde-cdcfa0202099 | note | Acceptance Criteria - Final levels are in accordance with the drawings or within tolerance and agreed with the Engineer
49e59276-ffec-5798-a96f-f90e3827b361 | note | Verifying Document - Photos
005763f4-aba0-56b3-a823-bf70212a06bf | note | Frequency - During installation
30da20b8-85ab-5e07-a4b2-9bf402e9e1d3 | note | Inspection Type (Visual, other) - Visual, instrumental
d9651a06-241a-5264-ab38-76add105648f | note | Inspection: Key - C
2a0a209f-be3f-55f6-af65-c6dc81a5bf16 | note | Inspection: By (Role Key) - SP/QE
e02454ad-8697-5547-b422-8a0a33a7dfde | checkpoint | 4.5 - Benching
5004ff03-0b46-5519-90ec-18dfd4bc3858 | note | Inspection Point: Quality Control Activity - Benching concrete shall have a crushing strength of 20MPa at 28 days. All benching and sloping surfaces on manhole floor shall be rendered in 20mm thick 1:3 mortar
b76e848b-6fc8-53fe-bcec-d3782e58347c | note | ○ Benching shape to have smooth transitions at bends and junctions
4860b592-5293-5da4-89df-6e9e0441aa52 | note | Acceptance Criteria - Benching built up to the specifications
d9e719b5-8a10-5050-80be-c503d0085b3d | note | Verifying Document - Photos
98c10eea-6d73-520e-8b13-c92526597efc | note | Frequency - During benching contruction
7ffb771d-3810-5af2-9c03-8af3e7babc23 | note | Inspection Type (Visual, other) - Visual, measurement check
c1344bc6-bc2b-57b8-a74b-682bdc3b19c4 | note | Inspection: Key - H
5308cc01-12e1-5a76-ac3f-8b34b0dec9c0 | note | Inspection: By (Role Key) - SP/QE/CR
78088795-c1e3-5e84-b7f5-e199fcd7b105 | signoff | HOLD POINT
9fb81e22-7beb-5512-a018-7c24aa9f22ca | checkpoint | 4.6 - Backfill and Compact
ffb18f72-2e7e-5229-bca1-ccac49a0e930 | note | Inspection Point: Quality Control Activity - Backfill in 200mm layers of compacted material
61b74aea-25a8-528e-8edb-dd8b128c052b | note | ○ Compaction testing one test every two layers as required
855cf8a1-5bac-59dd-a8b6-c89df0dab385 | note | Acceptance Criteria - 95% MDD in roads, paths, and pavements
d609b4d9-4a9b-5bcb-8c39-5497aa3d0669 | note | Verifying Document - Photos, Compaction test results
90518fb7-7b58-5a35-8957-c77127c90408 | note | Frequency - During Installation
7317b953-c5df-509e-a83c-abb29536cd4c | note | Inspection Type (Visual, other) - Visual, On Site test
1561bf6a-ce61-5c95-82cc-e72f9bf8526b | note | Inspection: Key - H
f69cb71b-3f9e-5b17-81f0-ec5d5b8ebfa3 | note | Inspection: By (Role Key) - SP/QE
3f6febb8-dc3a-59a7-9805-82407b0ba2e3 | signoff | HOLD POINT
26b44d4a-841a-50a8-b965-36c95addc184 | section | SECTION 5 - FINAL INSPECTION AND HANDOVER
a8639c4d-8eb4-5709-aaf3-da9bea54048a | checkpoint | 5.2 - As built
0d089f0a-1f73-554b-8f41-6abc17237ee8 | note | Acceptance Criteria - Engineer Approval
924fa07a-a0d7-5c8c-8d10-a3ab51d55132 | note | Verifying Document - QA records
b1045636-68e5-5afa-8560-f907829ad853 | note | Frequency - at completion
282d2a98-a19f-52ba-b676-62f80d90217b | note | Inspection Type (Visual, other) - Asbuilt drawings
5e8866e2-f29d-5476-ac1e-55fdbc99ce68 | note | Inspection: Key - H
c63bbce1-2a68-52e1-b8dd-26f7d75f1068 | note | Inspection: By (Role Key) - PE/PM/SV
5f37c66d-bc12-5377-9961-e04e7b6ed987 | signoff | HOLD POINT