## CON
|  | ROBINSON CONTRACTORS Ltd |  | INSPECTION AND TEST PLAN |  |  |  |  | Project Number - DN1203
|  |  |  | Project: NZTA 5363 CIP SH30 Te Ngae Road Corridor-Iles Rd to Coulter Rd |  |  |  |  | Date submitted: 10 March 2024
|  |  |  | Construction Process: Concrete Works - Motion Culvert Retaining Wall |  |  |  |  | Prepared By: Downer New Zealand
Client: NZTA |  | Head Contractor Subcontractor |  | Specification: 600 - Structural concrete |  |  |  |  | Approved By:
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents | Responsibility | Comments | Checked by
|  | Detail of Activity | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) | Inspection / Test method |  |  |  |  | Engineer | Contractor | Date
1 | Setout, Materials and Preparation
1.1 | Survey Set Out | GPS Setout of the Retaining wall as per the construction drawings. | W | Length of the retaining wall | Visual Inspection | Survey Report | Contractor's site diary and/or photos | Contractor | Setout location prior to commencing works.
1.2 | Materials Approvals | Submit testing data fir the following materials: - GAP 40 - GAP 20 - GAP 65 - Hardfill - Rip Rap (dump rock) | H | Once for each material | Quarry Testing Data | Engineer's Acceptance | InEight Records | Contractor
2 | Construction and Finishing
2.1 | Bases, Footings and/or Toes | Raft Construction (GAP65) | M | Every 5m section | Visual Inspection | As per drawing | QC Sheets | Contractor | RAFT SHALL CONSIST OF A 0.9m-DEEP UNDERCUT. A LAYER OF GEOTEXTILE BIDIM A29 OR AN APPROVED EQUIVALENT SHOULD BE LAID ON THE EXPOSED SUBGRADE. LAY AND COMPACT GRANULAR MATERIAL (GAP65). COMPACTED TO 95% OF THE MDD.
2.2. |  | Raft Reinforcement | H | Whole length | Visual Inspection | As per drawing | QC Sheets | Contractor | THE RAFT SHALL BE REINFORCED WITH GEOGRID (DURAFORCE 40/40 OR APPROVED EQUIVALENT) PLACED AT THE DEPTHS OF 0.3m AND 0.6m AND 0.9 WITHIN THE UNDERCUT.
2.3. |  | Reinforcing WSP INSPECTION | M H | Length of Wall | Visual Inspection | ALL REINFORCING BARS SHALL BE OF GRADE 500E MILD STEEL. MINIMUM REINFORCING LAP LENGTHS SHALL BE 550mm FOR HD12 BARS AND 800mm FOR HD16 BARS UNLESS NOTED OTHERWISE ON THE DRAWINGS. | QC Sheets | Contractor/ Engineer
2.4. |  | Formwork | H | Length of Wall | Visual Inspection | As per drawing | QC Sheets | Contractor | FORMWORK SUPPLIED BY DOKA
2.5. |  | Concrete | H | All concrete orders | Concrete Dockets | Concrete strength 25MPa at 28 days Mix design to be approved by the Engineer Minimum cover to reinforcing for walls and footings 75mm unless noted otherwise | Concrete Dockets | Contractor | ALL CONCRETE USED SHALL ATTAIN 25MPa COMPRESSIVE STRENGTH AT 28 DAYS CURE. ALL CONCRETE USED SHALL COMPLY WITH THE REQUIREMENTS FOR EXPOSURE CLASS XA2. THE CONTRACTOR SHALL PROVIDE THE CONCRETE MIX DESIGN FOR THE APPROVAL OF THE ENGINEER PRIOR TO THE COMMENCEMENT OF ANY CONCRETE WORKS
2.6. |  | Self Compacting concrete | M | Void filler between existing culverts and new precast culvert | Concrete Dockets | As per Detail A on drawing C01 | Concrete Dockets/ QC Sheets | Contractor
2.7. | Walls | Reinforcing WSP INSPECTION | M H | Length of Wall | Visual Inspection | ALL REINFORCING BARS SHALL BE OF GRADE 500E MILD STEEL. MINIMUM REINFORCING LAP LENGTHS SHALL BE 550mm FOR HD12 BARS AND 800mm FOR HD16 BARS UNLESS NOTED OTHERWISE ON THE DRAWINGS. MINIMUM REINFORCING LAP LENGTHS SHALL BE 550mm FOR HD12 BARS AND 800mm FOR HD16 BARS UNLESS NOTED OTHERWISE ON THE DRAWINGS. | QC Sheets | Contractor/ Engineer | Scabble or green cut interface in accordance with Type B construction joint to NZS 3109 For joints, the surface of the concrete may be prepared by green cutting (using high velocity air/water jets or vigorous wire brush) to remove all laitance and inferior surface concrete after the concrete has hardened sufficiently to prevent loosening of any aggregate which is not removed.
2.8. |  | Formwork | H | Every 5m | Visual Inspection | As per drawing | QC Sheets | Contractor
2.9. |  | Dowels | M | Every 300mm centres | Visual Inspection | R20 DOWEL 450 LONG AT 300 CENTRES CONTROL JOINTS SHALL BE KEY JOINTS SPACED AT MAXIMUM 6.1m INTERVALS OR A SUITABLE LESSER LENGTH IF REQUIRED | QC Sheets | Contractor
2.10. |  | Finish / Joints | W | All areas | Visual Inspection | Smooth, off shutter finish. Cut joints as appropriate. | QC Sheets | Contractor
2.11. |  | Concrete | H | All concrete orders | Concrete Dockets | Concrete strength 25MPa at 28 days Mix design to be approved by the Engineer Minimum cover to reinforcing for walls and footings 75mm unless noted otherwise | Concrete Dockets | Contractor | ALL CONCRETE USED SHALL ATTAIN 25MPa COMPRESSIVE STRENGTH AT 28 DAYS CURE. ALL CONCRETE USED SHALL COMPLY WITH THE REQUIREMENTS FOR EXPOSURE CLASS XA2.
2.12. | Backfill | Backfill behind wall - GAP40 | W | Length of wall | Visual Inspection | As per drawing | QC Sheets | Contractor | Backfill behind wall with Hardfill
2.13. | Drainage | Installation of subsoil drain | H | Length of wall | Visual Inspection | As per drawing | QC Sheets/ Site Records | Contractor | 100Ø PERFORATED SUBSOIL DRAIN WITH 40/20 DRAINAGE AGGREGATE WRAPPED IN GEOTEXTILE OF STRENGTH CLASS B AND FILTRATION CLASS 2
2.14. | RIP RAP | Rip Rap construction at outfall | W | Whole length | Visual Inspection | As per drawing | QC Sheets | Contractor | THE RIP RAP SHALL BE CONSTRUCTED MINIMUM 250MM THICK ON GEOTEXTILE - BIDIM 29 OR SIMILAR
2.15. | Stainless Steel Connector Plates | Connect new precast culvert to existing culvert | W | Per Plate | Visual Inspection | As per drawing | Site Records | Contractor | Connect new precast culvert to existing culvert using 400mm x 150mm x 6mm thick stainless steel plates with 4 x M20 Stainless Steel Bolts
3 | Close Out
3.1 | Collate above documentation | Document review | H | Each ITP | Review | All above documentation is shown as attached to this work pack. | Review | Contractor
3.2 | As-built drawings | Survey | H | At completion of construction | Asbuilts to be submitted at the completion of construction, information to be captured | Asbuilts reviewed and submitted | In Eight record | Contractor
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
BBO Engineers Rep Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.
Note on G14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Spec says 1500mm deep
Note on G15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Grade 500E Mild Steel
Note on G17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Missing Engineer approval of concrete mix Missing minimum cover
Note on G19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Grade 500E Mild Steel
Note on J19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: <Missing the requirement to scabble the interface between the base and the stem with Type B construction Joint to NZS3109
Note on G21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Spacing is inconsistent with formwork length (6m)
Note on G23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Missing Engineer approval of concrete mix Missing minimum cover
Note on G26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Spec says 1500mm deep